INCREASED HOUSEHOLD INCOME THROUGH POULTRY KEEPING BY AGAPE GROUP MEMBERS IN MBEZI, DAR ES SALAAM

BARAKA DEUS SEKAGOMA

A DISSERTATION SUBMITTED IN PARTIAL FULFILLMENT OF THE REQUIREMENT FOR THE DEGREE OF MASTER IN COMMUNITY ECONOMIC DEVELOPMENT IN THE OPEN UNIVERSITY OF TANZANIA

2015

# CERTIFICATION

The undersigned certifies that he has read and hereby recommends for the acceptance by the Open University of Tanzania a project entitled, Increased Household Income through Poultry keeping by Agape group Members in Mbezi, Dar es Salaam in partial fulfillment for the requirements of the degree of Master of Community Economic Development of the Open University of Tanzania.

______________________

Dr. Hamidu Shungu)

(Signature)

______________________

Date

# COPYRIGHT

All rights are reserved.   No part of this Dissertation may be reproduced and stored in any retrival system or transmitted in any form or by any means of eletronic, mechanical, photocopying  or Otherwise, without prior written permission of the Author or the Open University of Tanzania on behalf of.

# DECLARATION

I, Baraka Deus Sekagoma do hereby declare that this CED project report is my own original work and that it has not been submitted or presented and will not be presented to any other university for similar or any other degree award

______________________

Signature

______________________

Date

# DEDICATION

This work is dedicated to my lovely parents Mr Sylvester Sekagoma and Mrs. Doreka Sekagoma for the encouragement, emphasises and the supports I received from them during my studies in Master in Community Economic Development. My special thanks to my lovely wife Mary Swai for her tolerance and supports I received from her during my studies in order to pursue Master in Community Economic Development.

# ACKNOWLEDGEMENTS

May I take my sincerely acknowledgement to my Almighty God for giving me a chance to pursue my Master in Community Economic Development. It was not easy to pursue the course but I managed to achieve due to God being with me. I also appreciate the supports from my Lecturers Prof.Deus Ngaruko, Dr.Hamidu Shungu and other teaching staff of the Open University of Tanzania especially Centre for Community Economic Development.Speciall thanks to my family, Mr and Mrs.Sekagoma for their supports and courage.My lovely wife Mary Swai for her supports and tolerance during my time of study.My fellow students Mr.Syabus Kikungwe, Miss Wumi Mbogo, Mrs.Renata Yalengeko, that we pursued Master in Community Economic Development.

# ABSTRACT

This dissertation is an outcome of the research study that was conducted at Mbezi ward and the project identified being implemented in the same ward. The study and project implementation covers the period from September 2014 to July 2015.The study conducted by using participatory methods. Community needs assessment was conducted at Mbezi by using participatory methods such as Focus Group Discussion, Interview, the use of questionnaire for primary data collection methods and for secondary data collection there was the use of journals, books, internet and reports. The study found different needs and these needs were ranked by the use of Pair wise ranking in order to determine the potential project. The first ranked potential project was Poultry keeping project. Poultry keeping project was ranked by the community as the number one project to be implemented as their income generating project. The study revealed that poultry keeping project will be sustainable as they identified themselves and they implement with efficiency, not too expensive to establish and the demand of the products increases as days increase. Also time frame for the chicks to mature and become ready for sale also is too short as it can take four to six weeks depending on the feeds used. The study recommends that community members can organize themselves and manage the income generating projects in order to increase their incomes. Through trainings, community members can achieve their planned project goal and the project becomes sustainable and reduces income poverty to community members

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENTS	vi

ABSTRACT	vii

TABLE OF CONTENTS	viii

LIST OF TABLES	xiii

LIST OF FIGURES	xiv

LIST OF ABBREVIATION	xv

CHAPTER ONE	1

1.0 PARTICIPATORY NEEDS ASSESSMENT	1

1.1 Introduction	1

1.2   Community Profile	2

1.2.1 Population	2

1.2.2 Health services	3

1.2.3 Education Services	3

1.2.4 Economic Activities	3

1.2.5   Financial Services	3

1.3   Community Needs Assessment	4

1.3.1 Objectives of Community Needs Assessments	5

1.3.1.1 Overall Objective	5

1.3.1.2  Specific Objective	5

1.3.2  Research/Community Needs Assessment questions	5

1.3.3   Research Methodology	6

1.3.3.1   Research design	6

1.3.3.2   Sampling techniques	7

1.3.3.3   Data collection methods	7

1.3.3.3.1   Secondary data	7

1.3.3.3.2  Primary data	7

1.3.3.3.3   Questionnaires	8

1.3.3.3.4   Interview Method	8

1.3.3.3.5   Focus Group Discussion	8

1.3.3.4   Data analysis methods	9

1.4   Community Assessments Needs Findings	9

1.4.1   Respondent’s sex	9

1.5   Community Needs Prioritization/levelling of needs	20

1.6   Chapter Conclusion	23

CHAPTER TWO	24

2.0   PROBLEM IDENTIFICATION	24

2.1  Background to Research Problem	24

2.2  Problem Statement	25

2.3 Project description	26

2.3.1 Target Community	26

2.3.2 Stakeholders	26

2.3.3 Project Goals in CED terms	27

2.3.4 Project Objectives	27

2.2.4.1 General Object	27

2.3.4.2 Specific objectives	27

2.4  Host Organisation/CBO profile	27

2.4.1 Mission	28

2.4.2 Vision	28

2.4.3 Activities	28

Figure 2: Organization structure of Host organization	28

2.4.4 The role of CED Student in the Project	30

2.4.5 Role of CBO in the Project	30

CHAPTER THREE	31

3.0   LITERATURE REVIEW	31

3.1 Introduction	31

3.2 Theoretical Literature	31

3.3 Empirical Literature	34

3.4 Policy Review	39

3.5  Literature review summary	46

CHAPTER FOUR	48

4.0   PROJECT IMPLEMENTATION	48

4.1 Introduction	48

4.2 Project outputs	48

4.3 Project planning	52

4.3.1. Project Implementation Plan	52

4.4 Inputs	64

4.5 Staffing Pattern	69

4.6 Project Budget	69

4.7 Actual Project Implementation	74

4.8 Project Implementation Report	74

4.9 Project Implementation Gantt chart	83

5.0   PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	88

5.1 Introduction	88

5.2 Participatory monitoring	90

5.2.1 Monitoring Information System	93

5.2.2 Participatory Monitoring Methods	98

5.2.2.1. Documentation	98

5.1.2.2. Participant Observation	98

5.2.2.5. Group Interview	99

5.2.3 Participatory Monitoring Plan	99

5.3 Project Participatory Evaluation Summary	104

5.3.2 Participatory Evaluation Methods	110

5.3.3 Project Performance Indicator	111

Table 25: Project Performance Indicators	112

5.4 Project sustainability	115

CHAPTER SIX	118

6.0   CONCLUSION AND RECOMMENDATION	118

6.1 Introduction	118

6.2 Conclusion	119

6.3 Recommendation	123

REFERENCES	125

APPENDICES	127

APPENDIX – 3 INTERVIEW GUIDE TO GOVERNMENT OFFICIALS	131

# LIST OF TABLES

Table 1   :    Sex of respondents	10

Table 2   :    Respondent’s age	10

Table 3   :    Occupations of Respondents	11

Table 4   :    potential income generating project	12

Table 5   :   	Education levels of Respondents	13

Table 6   :    	Economic Activities	14

Table  7   :    Impact of Poultry keeping to Community Members	16

Table 8   :  	Decrease of Dependency	16

Table 9   :    Creation of Employment	17

Table 10   :   Project Risks/cChallenges	18

Table 11   :   Supports from Government	19

Table 12   :   Technical Skill on Poultry Keeping	19

Table 13   :   Community Needs Pair wise Ranking	22

Table 14   :   SWOT Analysis Table	29

Table 15   :   Project Objective and Output	49

Table 16   :   Project Implementation plan	54

Table 17   :   Project Logical Framework	60

Table 18   :   Project Inputs	65

Table 19   :   Project Budget	70

Table 20   :   Actual Project Implementation Summary	80

Table 21   :   Project Implementation Gantt chart	84

Table 22   :   Project Monitoring Information System	96

Table 23   :   Participatory Monitoring Plan	101

Table 24   :   Participatory Evaluation Summary	106

# LIST OF FIGURES

Figure 1  	:  	Viable Economic Activities	15

Figure 2   	:  	Tanzania Vicoba Sustainable Development Agency Organogram	28

Figure 3  	:  	One day workshop on Poultry Keeping	76

Figure 4 	:	Clarification during one day Workshop on Poultry Keeping	76

Figure 5  	: 	Some trainees who attended Workshop	77

Figure  6	:   Building for Poultry Keeping.	77

Figure 7  	:	Chicks in a Building	78

Figure 8   	: 	Chicks in Place	78

Figure 9   	:   	Vaccination and Feeding of Chicks	79

Figure 10   :  	Feeding of Chicks	79

# LIST OF ABBREVIATION

AD		Annual Domical

ADB                African Development Bank

ADRI              Animal Disease Research Institute

OUT		The Open University of Tanzania

CED		Community Economic Development

NGO		Non Governmental Organization

VEO		Village Executive Officer

WEO		Ward Executive Officer

DCB                Dar es Salaam Community Bank

DEO		Division Executive Officer

CBO		Community Based Organization

FBO		Faith Based Organization

IP                    Influential People

BP                   Business People

VE                  Veterinanry Expert

WAT-HST     WAT-Human Settlements Trust

VICOBA	Village Community Bank

FAO		Food and Agricultural Organization

BC                  Before Christ

NRPC		National Rural Poultry Centre

DANIDA       Danish International Development Agency

IFAD             International Fund for Agricultural Development

GDP                Gross Domestic Product

NSGRP           National Strategy for Growth and Reduction of Poverty

OIE		Office international des epizotie

WTO		World Trade organization

SPSS                Statistical Packages for Social Science

CVL                Central Veterinary Laboratory

VIC                 Veterinary Investigation Centers

SUA		Sokoine University of Agriculture

TAWIRI          Tanzania Wildlife Research Institute

TCCIA            Tanzania Chamber of Commerce, Industry and Agriculture

TCAL             Tanzania Chamber of Agricultural Council and Livestock

CTI                 Confederation of Tanzania Industries

PRA		Participatory Rural Appraisal

# CHAPTER ONE

# 1.0 PARTICIPATORY NEEDS ASSESSMENT

# 1.1 Introduction

Participatory needs assessment is a way of understanding the needs of a local population including needs relating to Health, Food, Housing, Security, Employment and Education. Professionals and local people form a partnership to identify community needs, set priorities and develop a way forward (an action plan). The overall aim of the participatory needs assessment is to understand the needs of the community from their own perspective rather than from the provider/donor or external’s view point. In Participatory Needs Assessment, there are different methods of information collection and these methods are; Informal or Formal voluntary discussions with community groups, Focused Group Discussion, Interview with Key Informants and service users, Household Surveys, Relevant local documents about the community, Observations, Community Mapping and others.

Participatory needs assessment was conducted to Mbezi Ward Residents in order to assess the level of income poverty to community members and determine the best intervention in order to make a positive change which is to find the ways on how community members can increase the level of incomes to their households in order to reduce income poverty.

Poverty is defined relative to the standards of living in a society at a specific time. People live in poverty when they are denied an income sufficient for their material needs and when these circumstances exclude them from taking part in activities which are an accepted part of daily life in that society.

Reducing poverty has become an international concern, yet there is no international consensus on guidelines for measuring poverty. Income poverty is when a family's income fails to meet a federally established threshold that differs across countries. Typically it is measured with respect to families and not the individual, and is adjusted for the number of persons in a family. Economists often seek to identify the families whose economic position (defined as command over resources) falls below some minimally acceptance level, similarly, the international standard of extreme poverty is set to the possession of less than 1$ a day. In order to reduce income poverty there is a need to have an intervention that will lead to increased income to households to the people of Mbezi Ward.

# 1.2   Community Profile

# 1.2.1 Population

Agape group is a group of people who identified and organized themselves with the help from CED Student. These group members have different ages, sex and occupations. Some are food vendor, some, saloonists, some operate Groceries and Bars. Some are Teachers, Farmers, Petty traders and Tailoring. These people are residing within Mbezi Ward which is found in Kinondoni District in Dar es Salaam. Mbezi ward has a population of 73,414 people of which males are 35,637 and females are 37,777(according to 2012 census).

# 1.2.2 Health services

Residents of Mbezi ward have access to health services. Mbezi ward has health services by having three dispensaries which are Mbezi Dispensary, Msumi Dispensary and Mpiji dispensary.

# 1.2.3 Education Services

Mbezi ward has education services, these educational services are accessed by ward’s residents. Education services are provided through the presence of primary and secondary school. There are two secondary schools which are Mbezi Inn Secondary School and Mpiji Secondary School while Primary Schools are nine and their names are Mbezi Primary school, Upendo primary school, Makabe primary school, Mshikamano primary school, Msumi Primary school, Iddrisa Abdulwakil primary school, Makamba primary school, Kibesa primary school and Mbezi Luis primary school.

# 1.2.4 Economic Activities

Mbezi ward residents do perform livestock keeping, farming and business. They keep goats and cows, they farm tomatoes and other vegetables and others are business people.

# 1.2.5   Financial Services

There are financial services like having outlets of DCB Bank, Mkombozi Bank and having VICOBA. Apart from that, they also get financial services through the use of M-Pesa, Tigo Pesa and Airtel Money.

# 1.3   Community Needs Assessment

A Community Needs Assessment is a combination of information gathering, community engagement and focused action with the goal of community improvement. A community needs assessment identifies the strength and weaknesses (needs) within a community. A community needs assessment is also unique and specific to the needs within a community and is usually an extension of a community’s strategic planning process. Community needs assessments are generally executed in four steps which are planning and organizing, data collection, coding and summarizing the needs assessment results, and sharing the results with the community to facilitate action planning.

The exact methodology to implement a community needs assessment  is partially determined by the type of assessment that is being performed though generally the proposed are the use of focus group discussion, creating a needs assessment survey, collecting and analyzing data, community public forums, producing a final report and planning action committees. In order to implement community needs assessment one has to select the community and people who will structure the community needs assessment and these people needs to have a degree of commonality.

The community needs assessment study was conducted in order to know the economic income gap (income poverty) to community members and find a potential intervention to solve the situation. The potential intervention will be to find a suitable income generating project that will be owned by community members. The income generating projects if sustainable will help community members to increase the level of income at household levels hence decrease of income poverty to community members.  The study had different people who were selected for community needs assessment and these people were local politicians, professionals, youth and adults residing within the community and influential people.

# 1.3.1 Objectives of Community Needs Assessments

Research objective aimed on collecting the information and analysing the data collected in order to identify community economic gap (household income gap) and identify the possible suitable intervention to overcome the constraints.

# 1.3.1.1 Overall Objective

Overall Objective is to determine important information required to implement a poultry keeping for sales project to increase household income levels within Agape group members.

# 1.3.1.2  Specific Objective

- To determine the economic activities that are undertaken by Agape group members by September 2015

- To examine the possibility of establishing the income generating project in the Agape group by September 2015

- To assess if the identified income generating project will have an impact on household and Agape group member’s economic status by September 2015.

# 1.3.2  Research/Community Needs Assessment questions

The study had some questions and these questions were;

- What are economic activities carried by Agape group members?

- Are the economic activities carried out throughout the year?

- What is the average income of Agape group members?

- What can be a potential income generating project that will increase the income to Agape group members?

- What types of resources are available in Agape group members that can be used for project execution?

- Will the income generating project have an impact to Agape group members?

- Will the potential income generating project decrease the level of dependence in Agape group members?

- Will the potential income generating project create job opportunities? If yes, how many opportunities?

- What will be the risks/challenges facing the potential income generating project?

- Does the Government give any support in the potential income generating project?

- Do Agape group members have technical skills on the potential income generating project?

# 1.3.3   Research Methodology

# 1.3.3.1   Research design

The research done was descriptive in nature, in this descriptive study, both qualitative and quantitative methods for data collection were used. Quantitative approach involves collection of quantifiable data which are normally in terms of quantities (numbers) and qualitative data were also collected such as sex of respondents. These qualitative data and quantitative data collected from the study were represented in form of tables.

# 1.3.3.2   Sampling techniques

Both purposive and random sampling techniques were used to get the sample size required. Purposive sampling was used to collect secondary information data in most cases and some primary data from professionals. Random sampling technique was used for sampling Agape group members who were providing details on their community.

# 1.3.3.3   Data collection methods

Data were collected through primary sources and secondary sources. Both secondary and primary data were collected through various methods and these methods were;

# 1.3.3.3.1   Secondary data

Secondary data were taken from available data or information that were in documentations in various offices. These data collected were taken through documentary review method, in which, the abstract from different reports, pamphlets, books, event reports and Journals.

# 1.3.3.3.2  Primary data

These are the data collected by the researcher directly from the respondents that were selected through the determined sampling procedures. Interviews, Focus Group Discussions and other methods were used by the researcher. The following are methods and tools used in the exercise;

# 1.3.3.3.3   Questionnaires

Data were collected through the use of questionnaires. Questionnaires were distributed to sixty respondents but only forty respondents returned the questionnaires. The respondents had ability to read and write. The questionnaire helped in collecting general information about the interviewee such as age, sex, level of education, respondents’ income, respondents’ occupation, community economic activities.

# 1.3.3.3.4   Interview Method

Interview method was used in primary data collection. The researcher collected information/data from the respective respondents by using interview method by using structured and unstructured questions as a main tool. Questionnaires used had some questions that were used to interview the respondents.

# 1.3.3.3.5   Focus Group Discussion

Focus Group Discussion method was very useful in collecting data or Information from the community or respondents by using two groups of participants or respondents. Community members had a Focus Group Discussion on various issues like income generating activities existing within their community and the potential projects that would increase households’ income. Focus Group Discussion apart from being used as data collection method, it was also bringing capacity building to group members when participating in answering some questions.

# 1.3.3.4   Data analysis methods

Data collected from the study were manually analysed and then changed to variables coded in order to be entered into SPSS for data analysis. Data processed and analysed using Descriptive statistics methods, mainly frequency tables. Qualitative data were collected through the use of Focus Group Discussion that was conducted during the study. During the study some were given questionnaires, some were interviewed and some were collected or gathered for Focus Group Discussion in order to collect data. Community members had a Focus Group Discussion on various issues like income generating activities existing within their community and the potential projects that would increase households’ income. So, during the study both qualitative and quantitative data were collected.

# 1.4   Community Assessments Needs Findings

# 1.4.1   Respondent’s sex

The findings from the Community Needs Assessment done at Mbezi Ward basing on the methods of data collection used, it was found that the respondents’ sex was 27.5% male and 72.5% female and this data was taken from the forty respondents out of sixty planned sample of respondents. Findings were derived through the use of different data collection methods which included the Questionnaires, Focus Group Discussion, Observations, interviews  (key informants), and secondary data were taken from Ward Office and Kinondoni Municipal Council.

Table 1   :    Sex of respondents

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Male | 11 | 27.5 | 27.5 | 27.5 |
|  | Female | 29 | 72.5 | 72.5 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

Female constitute 72.5% of the respondents, in community-based or led projects, women do take parts and seem to be trustful in execution of the projects and also for the projects’ sustainability as the women are in most cases not supporting the zeal for embezzlement of the project’s fund and by being trustful and manage well the funds, then the project becomes sustainable.

Table 2   :    Respondent’s age

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | 18-25 | 9 | 22.5 | 22.5 | 22.5 |
|  | 26-33 | 10 | 25.0 | 25.0 | 47.5 |
|  | 34-41 | 14 | 35.0 | 35.0 | 82.5 |
|  | 41-48 | 4 | 10.0 | 10.0 | 92.5 |
|  | 48-55 | 3 | 7.5 | 7.5 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

Findings shows that out of forty respondents 22.5% had age ranging between 18-25 years, 25% had an age ranging from 26-33 years, 35% had an age ranging from 34-41 years,10% had the ages between 41-48 years and 7.5% had an age ranging from 48-55 years. This finding shows that most of the respondents were youth which is a man power and this can be used for the development of their community and Country at large. Although youth are sought not to be serious with project’s management, in this project youth will be useful as there are other members who are older to them and these matured or older people will help to manage the youth in order to make them focus for the sustainability of the project and by the project becoming sustainable the individuals and households level of income will increase. By increasing the level of incomes to youth participating in the project this will also decrease the number of dependency in the community and this increases the effective utilization of youth as manpower and also youth will be of a help for the transfer of the knowledge concerning project to the next generation.

Table 3   :    Occupations of Respondents

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Farmer | 3 | 7.5 | 7.5 | 7.5 |
|  | Business | 25 | 62.5 | 62.5 | 70.0 |
|  | Saloons | 3 | 7.5 | 7.5 | 77.5 |
|  | Teachers | 1 | 2.5 | 2.5 | 80.0 |
|  | Bar Maid | 2 | 5.0 | 5.0 | 85.0 |
|  | Petty Trader | 1 | 2.5 | 2.5 | 87.5 |
|  | Tailor | 5 | 12.5 | 12.5 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

The findings show that this community had many occupations and the respondents had different occupations as 7.5% are Farmers,62.5% are Business men and female,7.5% were saloonists,2.5% were Teachers,5.0% were Bar maids,2.5% were petty traders and 12.5% were Tailors. Findings show that each respondent had an occupation as it is being categorized in the Table 1.3.3.Most of the Agape members are business men and women, having people with knowledge and experiences in business will easy the search for the markets for the project products and also will help in the financial management of the project because they have the experience of managing money for the business hence making the right decision at right time for fund utilization.

Table 4   :    potential income generating project

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Hot culture | 6 | 15.0 | 15.0 | 15.0 |
|  | Bricks Making | 3 | 7.5 | 7.5 | 22.5 |
|  | Cow Keeping | 1 | 2.5 | 2.5 | 25.0 |
|  | Poultry Keeping Project | 30 | 75.0 | 75.0 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

The findings show that 15% proposed that the potential income generating project to be formulated is Hot culture while 7.5% proposed a project of Bricks Making, 2.5% proposed Cow Keeping, 75% proposed Poultry Keeping Project. Data collected show that frequency of 30 ( 30 respondents ) which constitutes 75% of the total respondents are proposing Poultry keeping project to be formulated and implemented and it is their assumption that this project if executed will be sustainable in their community and will increase the level of income in their households and community at whole. Poultry keeping project will be sustainable due to the fact that the project is not too cost full, easy to manage and needs few time for the chicks to mature and become ready for sale. Poultry can take four to six weeks in order to become mature for sale and also the return on sale is the double of the cost of the project. Group members will have the income through selling of unslaughtered chicken, slaughtered chicken, feathers also members will benefit from getting the manure for agricultural purposes.

Table 5   :   Education levels of Respondents

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Primary | 8 | 20.0 | 20.0 | 20.0 |
|  | Secondary | 9 | 22.5 | 22.5 | 42.5 |
|  | Certificate | 6 | 15.0 | 15.0 | 57.5 |
|  | Diploma | 11 | 27.5 | 27.5 | 85.0 |
|  | Graduate | 5 | 12.5 | 12.5 | 97.5 |
|  | Post Graduate | 1 | 2.5 | 2.5 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

Respondents had different levels of education and this has been presented in the Table number 5.Respondents who had Primary School Education level had 20%, Secondary School Education Level had 22.5%, Certificate had 15%, Respondents with Diploma comprised 27.5%, Graduates comprised of 12.5% and Post Graduate were 2.5%.The findings show that this Community had no people without formal education and the majority of the respondents had Diploma Education Level. This is a community of literates’ people. Due to the different education levels, there will be an easy in project management.

Table 6   :    Economic Activities

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Saloon | 4 | 10.0 | 10.0 | 10.0 |
|  | Food Cafe | 5 | 12.5 | 12.5 | 22.5 |
|  | Hotculture | 2 | 5.0 | 5.0 | 27.5 |
|  | Tailoring | 5 | 12.5 | 12.5 | 40.0 |
|  | Bar | 6 | 15.0 | 15.0 | 55.0 |
|  | Groceries | 10 | 25.0 | 25.0 | 80.0 |
|  | Food Vendors | 8 | 20.0 | 20.0 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

Respondents had different economic activities that they perform in order to get earning and 10% were dealing with activities of operating saloons, 12.5% were operating Food Cafes, 5% were doing with hot culture, 12.5% were doing Tailoring, 15% had bar operation, 25% were doing business of operating groceries and 20% were dealing with Food Vending. Most of the respondents were dealing with selling of food and drinks.

Figure 1  :  Viable Economic Activities

Respondents had different views on which project would be viable in their community. Some respondents who formed 5% proposed that Bricks Making would be viable, some respondents who formed 67.5% proposed that Poultry Keeping will be viable, 20% proposed that hot culture would be viable while 7.5 proposed that Tailoring project would be viable. As the majority proposed that Poultry Keeping would be viable so this can be the right projects for this community.

Table  7   :    Impact of Poultry keeping to Community Members

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | First Class | 28 | 70.0 | 70.0 | 70.0 |
|  | Second Class | 11 | 27.5 | 27.5 | 97.5 |
|  | Third Class | 1 | 2.5 | 2.5 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

The finding show that the project of Poultry Keeping will bring an impact of 70% in the economic status or income status of the community members at household level to the community level at large.27.5% of the respondents said that the project will have an economic impact while a third class was comprised with2.5% who said that the project will have an impact though low impact.

Table 8   :  Decrease of Dependency

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Maximum | 33 | 82.5 | 82.5 | 82.5 |
|  | Minimum | 7 | 17.5 | 17.5 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

The findings show that the project will decrease the level of dependence and most of the respondents said that it will decrease the level of dependency at maximum (82.5% respondents accepted that it will decrease at maximum). 17.5% said that the project will decrease the level of dependency at minimum. So the project will have a positive impact on decreasing the dependency level. This community seems to have a big number of dependants and having a big number of dependants in one or another can be regarded as households having low incomes as the expenses seem to be high in households compare to few people who have earnings for the survival of households. By implementing this project, many people will have an employment and earn incomes, by earning incomes this will increase the level of incomes to households hence the households will be able to meet its obligations for instance purchase of households’ food, clothes, paying for the housing or shelter and also making payments for the school fees for their children. By knowing the importance of the project, the community will be serious on the implementation and managing well the project to become sustainable.

Table 9   :    Creation of Employment

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | 20-40 | 4 | 10.0 | 10.0 | 10.0 |
|  | 40-60 | 12 | 30.0 | 30.0 | 40.0 |
|  | 60-80 | 14 | 35.0 | 35.0 | 75.0 |
|  | 80-100 | 10 | 25.0 | 25.0 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

The findings show that the project will create employment of people ranging from 60-80 employment opportunities. Majority of respondents(35%) said that the project will create 60-80 employment opportunities,30% respondents said that the project will create 40-60 job opportunities,25% said that the project will create 80-100 employment opportunities while 10% said that the project will create 20-40 employment opportunities. The project will create some employments to community members themselves and also to the external people and this number of 60-80 is the number of direct employment and by employing 60-80 directly then we can assume the project will create more than hundred jobs by creating more or about twenty employments indirectly. Because community members have seen the impact or benefit of the project in perspective of employment creation, then they will do the best in order to implement the project and maintain it to become sustainable in order for them to get employment and increase their incomes.

Table 10   :   Project Risks/cChallenges

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Inadequate Of Skills | 24 | 60.0 | 60.0 | 60.0 |
|  | Diseases | 14 | 35.0 | 35.0 | 95.0 |
|  | Un Reriable Markets | 2 | 5.0 | 5.0 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

The findings show that the 60% respondents had inadequate skills concerning the project hence the need to train them so that the project to become sustainable.35% respondents pointed that Disease is a risk for the project to become sustainable and 5% said that un-reliable markets is a risk for the project. So, if the community members are trained then the project will be suitable as when they have knowledge/skills then they can control disease and also search for the markets.

Table 11   :    Supports from Government

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Training | 3 | 7.5 | 7.5 | 7.5 |
|  | No Any Support | 37 | 92.5 | 92.5 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

The findings show that the Government do give support to the citizens in a form of training as it was said by 7.5% respondents and 92.5% respondents said that the Government does not give any support to the citizens. As the Government does not give sufficient support, there is a need for other stakeholders to support the community members especially in community-led projects in order to increase the community households’ income. By increasing the household income then poverty will obviously be reduced at household level and at national level too. NGOs and other private sectors can give support in terms of training community members on how to manage the projects, vaccination, how to construct housing for the chickens as the project to be implemented is poultry keeping hence a need for housing for them.

Table 12   :   Technical Skill on Poultry Keeping

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Highly Needed | 16 | 40.0 | 40.0 | 40.0 |
|  | Medium Needed | 20 | 50.0 | 50.0 | 90.0 |
|  | Low Needed | 4 | 10.0 | 10.0 | 100.0 |
|  | Total | 40 | 100.0 | 100.0 |  |

Findings show that 40% respondents are in highly need of training on technical skills on Poultry keeping.50% respondents said that there was a medium need of training while 10% said that there was a low need for the training on technical skills on Poultry keeping. Generally the findings show that there should be a training to the community members in order to have enough knowledge on how they can feed, vaccinate, identify the chicks or chicken with diseases, how to do cleanliness in order to prevent the chicken from diseases and project management in order for the project to become sustainable. If training is not done then there will be no project sustainability hence the community’s income does not change hence the living status of community members remain the same. As the project intends to be implemented for the aim of increasing individual and household’s income then there is a need for the Government and other stakeholders to give support on technical skills on poultry keeping and this will lead to project sustainability hence increase in incomes to individuals and households which will also reflect in the reduction of poverty at indivual concern or at households.

The study planned sixty respondents but the responded respondents were forty respondents of which eleven were males and twenty nine were females. Respondents were from different categories like professions, occupation and organizations. Some of the respondents were VEO, WEO, DEO, CBO, FBO, IP, BP, VE and entire community. This was done in order to get information of the potential income generating project.

# 1.5   Community Needs Prioritization/levelling of needs

Poultry keeping project was identified by the Agape group members through focus group discussion. Focus group discussion was used to identify potential project to be executed. Potential projects were identified and Pair wise Ranking method was used to rank the identified potential projects in order to determine the first and best project to be executed. By Pair wise ranking, Poultry keeping project was given a first priority to be executed because it got more scores. Potential identified projects were: the project to make bricks for sale, cows keeping, food vending, hot culture, tailoring and other businesses. By ranking all those potential projects, groups members ranked them in order to determine the project that will be viable, less cost and that can be sustainable and achieve their planned goal and have economic impact by increasing household incomes that will turn them having positive improvements in their economic status. Group members participated in the identification and ranking the potential projects and came up   Poultry keeping project as the project to be executed for income generation in order to reduce income poverty hence affordability of their needs or meeting their family obligations.

Table 13   :    Community Needs Pair wise Ranking

|  | Hot culture | .Business | Bricks Making. | Cow keeping | Hot culture | Tailor | Poultry keeping | Food vendors | SCORE | RANKING |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hot culture |  | Business | Bricks Making | Hot culture | Hot culture | Tailor | Poultry keeping | Food vendors | 3 | 5 |
| Business | Business |  | Bricks Making | Business | Agriculture | Tailor | Poultry keeping | Food vendors | 3 | 5 |
| Bricks Making. | Bricks Making | Bricks Making |  | Bricks Making | Bricks Making | Bricks Making | Poultry keeping | Bricks Making | 7 | 2 |
| Cow keeping | Cow keeping | Business | Bricks Making |  | Agriculture | Tailor | Poultry keeping | Food vendors | 2 | 6 |
| Hot culture | Hot culture | Business | Agriculture | Agriculture |  | Tailor | Poultry keeping | Food vendors | 3 | 5 |
| Tailor | Hot culture | Tailor | Tailor | Tailor | Tailor |  | Poultry keeping | Tailor | 6 | 3 |
| Poultry keeping | Poultry keeping | Poultry keeping | Poultry keeping | Poultry keeping | Poultry keeping | Poultry keeping |  | Poultry keeping | 8 | 1 |

# 1.6   Chapter Conclusion

Chapter one has dealt with the Participatory Needs Assessments and this has involved community members in the identification of the community needs and wants and ranking them in order to prioritize their community needs and wants in order to find the possible interventions or ways to solve them. Participatory Needs Assessments done at Agape Vicoba Group at Mbezi Ward show that they can reduce the dependency level by increasing household income through formulation and implementation of income generating project which is Poultry keeping project which was declared by community members that this project will be viable and sustainable.

# CHAPTER TWO

# 2.0   PROBLEM IDENTIFICATION

# 2.1  Background to Research Problem

WAT-Human Settlements Trust is a Non Governmental Organization that facilitates affordable housing and securing Tenure for the low and middle income earners in Tanzania. Currently WAT-HST is operating in Dar es Salaam.WAT-HST as it facilitates affordable housing through the provision of house loans to low and middle income earners who are residents of Dar es Salaam.WAT-HST has ten project sites of which five project sites are at Kisarawe Two Ward in Temeke Municipal and other five project sites are at Mabwepande and Mbezi Msumi at Kinondoni Municipal. These low and middle income earners are to be in groups of not less than five people and each group member makes choice of the house of which he or she can afford to pay for and these houses do differ in terms of loan amount because they differ in plot sizes and the house size( number of the rooms).

One of the groups that have benefited from the house loans from WAT-HST is Agape Group. Agape group members have benefited from house loans though they face a challenge on the repayments of their loans. Agape group members are doing economic activities like operating Saloons, Food cafes, Tailoring, Bar and Groceries. These businesses are characterised with unstable sales volumes hence fluctuations in sales volumes of which affects the expected profits which would be used for housing loan repayments. Most of Agape group members are facing this challenge of consistence in repayments due to the inconsistence in repayments. This inconsistence in repayments have led them follow in arrears and by falling in arrears exposes them to re-possession and by doing re-possession means losing the house.

Income poverty has become a challenge to most of Tanzanians for both living in rural and living in urban areas. Many families live under income poverty, they live under 1 US $ per day. These people cannot afford some basic needs like having their own modern houses for their families hence depending on renting from landlords of which they face challenges like not being allowed to do any farming or livestock keeping on the premises. If these people can access more incomes they can afford to either buy or construct their own modern houses on which they can do urban agriculture in order to increase the household income through selling of surplus food products, increase of household nutrients and also they decorate the household premises.

In order for the Agape group members to access and afford housing loan repayments for the whole loan period, there is a need of establishing income generating project that will increase their level of income hence consistence in loan repayments. As having other source of income through establishment of income generating project, these Agape group members will also get surplus of which increases the household income and household improvements.

# 2.2  Problem Statement

Agape group members are in need of the modern houses for their families. The majority cannot afford to construct or buy a house with cash. These group members cannot afford having their own modern houses for their families hence depending on renting from landlords They opted for the housing loan from WAT-HST and they have to repay consistencely.Due to Income poverty among the members has caused them to have inconsistences in housing loan repayments. Therefore Agape Group members need to access more sources of incomes in order to meet their obligations and also improve their household status. Therefore then Agape group members have to establish poultry keeping project as a faster income generating project in order to meet their obligations.

# 2.3 Project description

Poultry keeping for sales is the project to be implemented by Agape VICOBA group members. These members prioritized this project as there is an increase in demand of chicken meat especially in urban areas. They will rent a building for poultry centre, buying of batch of chicks, buying of chicks’ feeds, vaccination and some equipments.These chicks are fed to grow till the time for selling them.

# 2.3.1 Target Community

Target community for the project are people with low incomes. With the study done, Agape VICOBA group members were taken as a model for low income earners. Low income earners to the study carried are the people living under 1 US $ per day and those living above 1 US $ but cannot afford basic needs.

# 2.3.2 Stakeholders

Stakeholders for this project will be WAT-Human Settlements Trust, Mbezi Ward Local Government Leader, Extension workers, Influential people at Mbezi, Mbezi residents.

# 2.3.3 Project Goals in CED terms

Project goal is to increase the income level to the low income earners through poultry keeping for sale project.

# 2.3.4 Project Objectives

# 2.2.4.1 General Object

General objective of the project is to increase the income level to low income earners through poultry keeping for sale.

# 2.3.4.2 Specific objectives

Project intends to;

- Training 20 group members on poultry keeping by Jan 2015

- Acquiring an office and a building for poultry keeping by April 2015

- Undertake production of the first batch of seven days old chicks by Jun 2015

- To sale 400 live chicken to at least two reliable markets by  July 2015

- To register the business officially by Sept 2015

# 2.4  Host Organisation/CBO profile

Host organisation is VICOBA.VICOBA Makazi is found at Mbezi in Kinondoni District in Dar es Salaam. VICOBA has members from different parts of Dar es Salaam and comprises of men and women and the aim of VICOBA is to improve the incomes of their members through capacity building and provisional of loans to its members. Apart from providing loans to its members, members are also the market for the members' produced products.

# 2.4.1 Mission

Self-determination within group members, self-empowerment through entrepreneurship and financial access.

# 2.4.2 Vision

To empower ourselves through Trainings, entrepreneurship and access to finance .

# 2.4.3 Activities

Activities are collecting savings from members, issuing loans to members and becoming market to members’ produced products. Training for entrepreneurship and access to Finance.

Figure 2   :  Tanzania Vicoba Sustainable Development Agency Organogram

Figure 2: Organization structure of Host organization

Table 14   :    SWOT Analysis Table

| Strength | Weakness | Opportunities | Threats |
| --- | --- | --- | --- |
| Strong and committed leadership | Insufficient funds for the project | Availability of market for project products | Diseases |
| Group has an access to Financial Institutions | Inadequate knowledge in Poultry keeping | Availability of extension workers within the ward | Theft due to lack of watchman |
| Group has strong unity | Distance between the Poultry building and the office | Members volunteering for the the project |  |
|  | Lack of basic accounting knowledge | Availability of feeds nearby |  |
|  | Lack of own building leading to rent expenses |  |  |

# 2.4.4 The role of CED Student in the Project

The roles of the CED Student in the Project is to make sure the plans are executed as they are planned in order the group members achieve the goal. The roles are listed here below:

- To facilitate identification of potential trainees for poultry keeping project.

- Facilitating Training of 20 trainees in Poultry keeping.

- To assist Agape group members in search for buildings for an Office and building for Poultry keeping.

- To assist in Agape group members in purchase of poultry equipments, feeds and chicks.

- Assisting in lobbying and advocacy for Poultry keeping project.

- Advising the group members on how to search for market of their product.

- Facilitate in capacity building to group leaders for monitoring and evaluation of the project.

# 2.4.5 Role of CBO in the Project

- Assist in fund raising for the project

- Facilitate in training for Poultry keeping project

- Assist in identification of trainees

- Assist in robbing and advocacy for Poultry keeping project

# CHAPTER THREE

# 3.0   LITERATURE REVIEW

# 3.1 Introduction

This chapter review the literature related to the local community economic development. It helps a researcher to get the relevant information through different data sources which are either in primary source or in secondary source of data. Data are being found in different sources such as from the policy relating to the project to be executed, from different books, journals, reports and respondents. According to Patton (2003), Literature review is important as it provides knowledge of the problem are, clearly identifies the need for the proposed study and it identifies the gaps and strengths in previously scholarly studies. The chapter provides the Theoretical literature, Empirical Literature, Policy Review and Literature review summary.

# 3.2 Theoretical Literature

Poultry keeping is done by both rural and urban dwellers as poultry contributes for household incomes which leads for the families to meet their social obligations, increasing food supply and nutrition to household members by either eating the meat or eggs from poultry. According to Kiman, (2006) and FAO, (2007), the term ‘’ chicken keeping’’ refers to poultry, irrespective of the genotype, that are kept in small numbers in an urban or peri-urban setting for commercial or social purposes. The birds could be layers, broilers or indigenous chicken, ducks, turkey, geese, quail or guinea fowls. They may be kept in enclosed or in a free range but are housed indoors at night. The number of birds may range from as few as six to as many as hundred or more, either as one type or in mixed flocks. The birds are kept in specially built houses, sometimes in cages, and are provided with feeds and water in a controlled way. There are also semi-intensive systems which combine both feeding and scavenging within an enclosure.

The poultry production systems in Africa are mainly based on scavenging indigenous chickens and most of these chicken are found in virtually all villages and households in rural Africa. (Aichi, 2003: Kazi, 1998).These systems are characterized by low output per bird. However, over seventy percent of the poultry products and twenty percent of animals’ protein intake in most African countries come from this sector (Aichi, 2003).Poultry production systems in Africa are distinguished by the fact that chickens are indigenous and integral part of farming system, with short life cycles and quick turn over; low input production system with outputs accessible at both inter households and intra household levels. The free range systems convert low quality feeds into high quality protein. In most African countries, the chicken have no regular health control programme, may or may not have shelter and scavenge for most of their nutritional needs(Van veluw,1987;Yongolo,1996).

Chicken productions in Bangladesh have improved the status of landless women through access to more food, income and labour as well as increased social status in the rural community (Saleque and Mustafa, 1996). Further, accessing village woman with chicken encourage their involvement in rural development, particularly where technology transfer include their participation of end users (Ngongi, 1996; Alders, 1997). Local chicken are known to be able to survive under various types of shelters including make shift chicken houses, kitchen and even roosting in trees (Adrew,1990; Host,1990; Mustafa,1990; Yongolo,1996).

Chicken housing in modern poultry keeping is an important input and has to be a major component of the initial capital investment (Weaver, 1996; Baghwat, 1996).Surveys have shown cases where no housing/shelter provided in rural poultry system

(Huchzermeyer, 1973; Kuit, Traore and Wilson, 1986; Antubi and Sonaiya, 1994; Yongolo, 1996).

Reports suggest that where housing is provided to village chickens, the houses are made of the locally available materials such as wood,mud,bricks,sugarcane stems, bamboo and cereal stovers(Antubi and Sonaiya,1994;Huchzermeyer,1973;Yongolo,1990).

Commercially poultry production systems are said to be unstable especially when there is hunger and thus deficit in grain sources. In such circumstances, rural local chickens were to be the main source of animal protein (Suleiman, 1989).The shortage of maize which is the staple food for Tanzanians, affects production of commercial poultry feeds as maize is the major source of ingredients. The free-ranging local chicken sector can therefore provide a sustainable means of provisional of much need animal protein at a minimum cost (Msofe et al, 2002).

Although poultry keeping is beneficial as it increases income, nutrition and is environmental friend, the production faces constraints like diseases and parasites, poor feeds supply, limited to financial credit access, high prices in inputs, insufficient of marketing strategies, low management skills. All these contribute to low productivity.

# 3.3 Empirical Literature

Empirical literature review was done in order to find if there are related studies done in order to capture what others have done in order to know the gap or use their findings as inputs to the current study. This was done by the use of research questions of the study. The empirical study based or focused on the assessment of the commercial poultry keeping in order to find if the poultry keeping for commercial purposes will lead to an increase of incomes to households, individuals and national through its contribution in the Gross Domestic Product.

Poultry keeping has its history and this can be traced back to probably eight thousand years ago. The history of chickens (Gallus domesticus) is a bit of puzzle and they were first domesticated from a wild form called red jungle fowl (Gallus Gallus),a bird that still runs wild in most of southeast Asia, likely hybridized with the grey jungle fowl(G.Sonneratii).That occurred probably about eight thousand years ago. Recent research suggests there may have been multiple origins in distinct areas of South and Southeast Asia, including North and South China, Thailand, Burma and India.

Since the wild progenitor of chickens is still among us, comparisons of behaviour and other changes that exist are available to us.Behaviorally, domesticated chickens are less active, have fewer social interactions, are less aggressive to would-be predators, and are less likely to go looking for foreign food sources than their wild ancestors. Other changes include increased adult body weight and simplified plumage; egg production starts earlier, is more frequent and produces larger eggs.

Genetic studies suggest multiple origins of domestication. The first archaeological evidence to date is from China about 5400 BC, in geographically widespread sites such as Cishan (Heibei province, a 5300 BC), Beixin (Shandong province,ca 5000 BC),and Xian (Shaanxi province,ca 4300 BC).Domesticated chickens appear at Mohenjo-Daro in the Indus Valley by about 2000 BC and, from there the chicken spread into Europe and Africa. The earliest firm evidence for chickens in East Africa are illustrations from several sites in New Kingdom Egypt.

Chickens arrived in western Africa at Iron Age sites such as Jenne-Jeno in Mali,Kirikongo in Burkina Faso and Daboya in Ghana by the mid-first millenium AD.In Americas,it is believed that chickens were brought to the Polynesian islands from Southeast Asia with the Lapita expansion, about 3300 years ago. While it was assumed that they had been brought to the Americas with the Spanish conquistadors, presumably pre-Columbian chickens have been identified at several sites throughout the Americas, most notably at the site of El Arenall in Chile,ca 1350 AD.

Since then chickens have been kept in different countries, these chickens are kept due to their importances like being the source of food, nutrition, income, eggs, poultry manure for use as organic manure, source of foreign exchange to the country through exports of poultry products. Chickens keeping is done in different countries like Malawi, Tanzania, Bangladesh and others. In Malawi village poultry keeping forms an integral part of rural life in Malawi. Most villagers own chickens even an impoverished widow and this helps to improve the living status of villagers. In Malawi there is an opportunity of keeping chicken as there are control for diseases, better housing, better nutrition, better breeding, better management. In each of these aspects there are gaps and constraints where dedicated input can achieve real progress, real benefits.

In Malawi there is a focused attention to the village poultry sector in order to improve the productions. The National Rural Poultry Centre (NRPC) was formed in early 2013 as an affiliate of the International Rural Poultry Centre, a subsidiary of the KYEEMA Foundation based in Brisbane, Australia. The NRPC exists to promote the needs of smallholder poultry farmers to raise livelihoods and contribute to improved nutrition in rural areas of Malawi.NRPC aims on fostering widespread Government and Community commitment to village poultry, promote advocacy for the smallholder poultry, Improve disease control and other sources of loss, serve as a focus for a network of individuals and institutions who are involved in with village poultry, serve as a small but significant local centre of excellence on the village poultry sector. Others are to promote measures to improve the health of rural poultry genetic resources, promote training and education at all levels, in smallholder poultry and related subjects, undertaking some basic field research on health, production and marketing of village poultry and finally evaluate and optimise the potential of rural poultry.

In Malawi, about 86 percent of the population lives in rural areas, where most people practice smallholder subsistence farming(NSO,2000).The majority of the people are resource poor, and over 60 percent are food insecure (NEC,1999).These farmers grow different crops and are the custodians of more than 80 percent of the total national livestock population(GO,1998).Their annual per capita income could be as low as the equivalent of US$74(Gondwe et al,1999),mainly derived from crop production. In Malawi poultry are named in Chichewa and most of the names were descriptive and based on phenotype; feather plumage, legs, tail feathers, head and other features or simply colour. Poultry keeping in some countries, are kept under the approach of the community-based project. Community-based project is designed to promote diverse breeding of poultry species in rural areas while at the same time putting necessary intervention measures in place to deal with identified constraints. Unlike other projects related to poultry, such as the Bangladesh (Jansen, 2000) and Egyptian models (Kolstand and Abdou, 2000).This project concentrates on indigenous poultry species of chicken in order improve meat and egg production and sustain diversification within flocks utilizing the existing free-range system. All management decision under community-based projects, are taken and implemented by the community and accompanying research is based on full farmer participation.

In Bangladesh’s experiences, women are the ones operating and managing technical enterprises like; broiler farming, layer farms and duck farms efficiently with a high economic return on the investment(Riise et al,2004).Rural women in either male-headed or female headed households of North-West Amhara,were more responsible for chicken rearing, while the men were responsible for crop cultivation and other off-farm activities(Halima,2007).According to Mcainsh et al(2004) and Gueye (1998);approximately 80% of the chicken flocks in a number of African countries were owned and largely controlled by rural women.

In Bangladesh, over two million poor women have involved themselves in poultry production and this has been valued as a tool for poverty alleviation through increasing of household income by selling of chicken. Poultry production can be a tool for improving the immediate welfare in household, especially for women and children, (Alam, 1996 and 1997).Quisumbing et al (1995 and 1998), argue that considerable attention is needed to adapt the poultry model to the cultural, technical, economic, and institutional situation in the target country. Over the years many donord including DANIDA, IFAD, WFD and ADB have supported the poultry projects in Bangladesh with funding and technical assistance.

In Ethiopia, poultry production systems show a clear distinction between traditional low input systems and modern production system using relatively advanced technology. There is also a third emerging small-scale intensive system as an urban and peri urban small-scale commercial system(Alemu and Tadelle,1997).In Ethiopia, smallholder rural poultry production is characterised by the small flocks, nil or minimal inputs with low output and periodic devastation of the flock by disease(Tadelle and Ogle,1996).

In Tanzania, poultry keeping forms an integral part of household activities providing food and generating additional family income. Poultry keeping makes an important contribution to the livelihoods of the most vulnerable rural households. In Tanzania, poultry is now being transformed to sub sector into an industry that will cater for the needs of poor households. Chicken production also improves household’s nutrition standards and helps meet family and social obligations. Poultry production in Tanzania is being contributed by the growing of demand of poultry products.

The poultry industry in Tanzania is divided into traditional poultry production and commercial poultry production. Traditional poultry sector is the largest contribution of about 70% of the flock and supplying 100% of poultry meat and eggs consumed in rural and 20% in urban areas. Poultry production in Tanzania is being carried out under two major systems which are small scale village or backyard poultry system which is the dominant one and the small scale extensive traditional systems in rural areas.

Chicken are kept in Tanzania because of the benefits derived and these benefits are sources of animal protein for the population of Tanzania, source of income to the farmers, sources of foreign exchange to the country through exports of poultry products, feathers and continuous supply of eggs and also manure for use as organic manure. Though poultry in Tanzania brings some benefits, the industry is being faced with some challenges which are lack of marketing skills, lack of organization among producers, inadequate regulatory framework in the poultry farming, inadequate technical support services and low genetic potential of the local breeds, Hatcheries and breeding farms are limited, lack of motivation by the local population to engage and invest in poultry farming, poor health control, poor housing and inadequate feeding, lack of adequate capacity to control diseases like Newcastle disease that attack poultry, low productivity per producer and poor nutrition and husbandry management.

# 3.4 Policy Review

Tanzania is endowed with natural resources which include land, forage and a large livestock resource base. Livestocks kept in Tanzania are for instance 18.5 million Cattle, 13.1 million Goats, 3.6 million Sheeps, 1.2 million Pigs, 30 million indigenous poultry and other species (MWLD, Statistical Year Book, 2005) .The livestock industry in Tanzania is being categorized into two major production systems which are extensive and intensive. In order for livestock industry to develop and achieve its goals, the industry requires a comprehensive livestock policy to guide all stakeholders.

Since 1980s, Tanzanian economy has been undergoing gradual and fundamental transformations in order for the industry to achieve its goals. Different livestock policies have been formulated, the first policy document was formulated and launched in 1983 with the aim of stimulating livestock development in the centralized economy and the emphasis was on large-scale parastatal institutions for production, processing and marketing. The second policy (Agricultural and Livestock Policy of 1997) was in line with the ongoing reforms and redefined roles of public and private sectors. During the implementation of second policy, other reforms emerged thus demanding for a review and formulation of a new policy.

The new policy which is the third policy seeks to address specific key issues which include animal identification, registration and traceability, animal welfare, indigenous technical knowledge, biotechnology and bio-safety, organic livestock farming, food safety, emerging diseases, livestock products regulatory institutions, professional regulatory institutions, animal genetic resource conservation, livestock stocking, veterinary laboratory system, livestock related disasters and pet animals. The policy aims at stimulating development in the livestock industry in order to increase rural and national income, improve food security and environmental conservation. The policy endeavors to increase national well-being of all stakeholders involved in the livestock industry.

In 2005, the Agricultural Sector contributed to the Gross Domestic Product (GDP) at 45.6% of which Livestock contributed 5.9%. About 40% of the livestock GDP originated from beef production, 30% from dairy products and about 30% from Poultry and small stock production. Livestock played an important substitution role in supply of food products thus contribute to food security, source of income and employment mostly in the rural economy and used to fulfill roles in the communities. Though livestock contributes to GDP, Livestock development in Tanzania faces some challenges like lack of proper arrangement to allocate land and give ownership of grazing areas according to traditional or legal procedures, frequent changes of livestock grazing areas into crop cultivation, game reserves and the migration of livestock farmers that limit them to develop their areas, Livestock diseases, inadequate infrastructure for processing and marketing of livestock and livestock products, knowledge and skills of livestock keeping and unavailability of credit facilities.

There are opportunities for livestock development in Tanzania and these opportunities will increase the poultry’s contribution to the national economy. These opportunities are like a large herd and diverse livestock resources, land resources, diverse and favorable climate and agro-ecological zones, potential domestic and export markets, availability of trainable manpower and relatively low cost labour, wide range of indigenous technical knowledge in livestock and favorable macro-economic policies.

The rationale for the national livestock policy is to commercialize the industry and stimulate its development while conserving the environment. The aim is to support the livelihoods of livestock farmers through increased incomes and self-sufficiency in food of animal origin and thus addressing the goals set in the National Strategy for Growth and Reduction of Poverty (NSGRP) of 2004.Tanzanian population is expected to increase to 55.2 million by the year 2025 thereby significantly increasing demands for livestock products; therefore a need for special emphasis on improvements of livestock productivity.

‘’The livestock industry has a clear development vision, based on the Tanzanian development Vision 2025 that states; By year 2025, there should be a livestock sector, which to a large extent shall be commercially run, modern and sustainable, using improved and highly productive livestock to ensure food security, improved income for the household and the nation while conserving the environment’’ (Tanzanian livestock policy, chapter 2.1)

The policy also has a mission which states;

‘’ To ensure that livestock resource is developed and managed sustainably for economic growth and improved human livelihood’’. (Tanzanian livestock policy, chapter 2.2)

Policy has an overall objective and specific objectives. An overall objective of is to develop a competitive and more efficient livestock industry that contributes to the improvement of the well-being of the people whose principal occupation and livelihood is based on livestock. Specific objectives are for instance to contribute towards national food security through increased production, processing and marketing of livestock products to meet national nutritional requirements, improve standards of living of people engaged in the livestock industry through increased income generation from livestock, increase the quantity and quality of livestock and livestock products as raw materials for local industry and export, promote integrated and sustainable use and management of natural resources related to livestock production in order to achieve environmental sustainability, strengthen technical support services and develop and disseminate new technologies and to develop human resources including livestock farmers.

The poultry industry in Tanzania is divided into traditional and commercial production systems and traditional system is the largest contributing over 70% of the flock and supplies most of the meat and eggs consumed in rural and about 20% in urban areas. The main indigenous breed sub-types include Kuchi, Kishingo, Sukuma, Kinyafuzi and Kiduchu.Commercial poultry production is mostly practiced in urban and peri-urban areas. The common commercial breeds and their crosses include White Leghorns, Rhode Island Red, Light Sussex and Plymouth Rock and some hybrids such as Hi sex, hybro, Shavers and Arbo Acres. Both commercial and traditional systems are constrained by diseases, poor quality feeds, and inadequate technical support services, low genetic potential of the local breeds and weak farmers’ organizations and there is inadequate regulatory framework in hatcheries and breeding farms.

As the policy aims to increase the quantity and improve the quality of poultry and its products to satisfy domestic demand, increase export and promote sustainable poultry production, the Government of Tanzania has to support and strengthen technical support services and use of appropriate technologies in poultry production, promote inventorisation, characterization, evaluation and selection of the indigenous poultry breeds. The Government has to undertake promotion for investment in poultry production, processing and marketin.Others are to encourage establishment of quality breeding farms and hatchery facilities and to sensitise,encourage and promote establishment of poultry producers and traders associations.( Tanzania Livestock Policy,Pg 9).

For veterinary services, the policy states that there should be veterinary services that comply with World Organization for Animal Health (Office Internationale des Epizooties-OIE) standards, recommendations on animal health and guidelines for international animal diseases control and trade.Livestocks and livestock’s products are guided by World Trade Organization (WTO) Sanitary and Physanitary (SPS) Agreements. The government has established veterinary laboratory system that comprises national laboratory and zonal laboratories that are strategically located and these include Animal Disease Research Institute(ADRI-Temeke) functioning as Central Veterinary Laboratory (CVL),Veterinary Investigation Centers (VICs) at Mpwapwa, Iringa, Arusha, Mwanza, Mtwara, Temeke and Tabora. These laboratories do provide technical support for disease surveillance, diagnosis, quality control and supervision of field vaccination campaigns. There are other laboratories like that of Sokoine University of Agriculture (SUA), Tanzania Wildlife Research Institute (TAWIRI) and other private owned laboratories.

The Government has declared in the policy that the veterinary medicines will be provided by ensuring adequate supply, accessibility and affordability of safe, quality and efficacious veterinary medicines. The policy states that the Government will encourage and support manufacturing, importation and distribution of quality veterinary medicines and will also strengthen technical support services in veterinary service. The Government has also declared in the policy that livestock inputs like feed resources, germ-plasm materials, farm machinery, and equipment used for veterinary practice and livestock facilitated by working in collaboration with stakeholders in order to promote investment in production and distribution of these livestock inputs and the Government will also strengthen technical services in livestock inputs.

Local Government Authority has been given greater responsibility and authority to develop and implement their plans in livestock production, facilitation and maintenance of law and order, while private sector is tasked to respond to a new set of opportunities and challenges. Some of the reforms have been made in the Local Government Authorities in order to enable them implement the policy, strategies and programmes and this has been done hand in hand with the livestock extension staffs being transferred from central Government to Local Government Authorities in order to increase their efficiency, effectiveness and accountability.

Non-Governmental Organizations (NGOs) and Community Based Organizations (CBOs) also play a role in livestock development, particularly in the provision of knowledge, information, capacity building and mobilization of resources at the grass-root level and the Government will provide an enabling environment for the NGOs/CBOs to provide the necessary interventions. Apart from NGOs/CBOs, there are associations supporting the industry and these are like Tanzania Chamber of Commerce, Industry and Agriculture (TCCIA), Tanzania Chamber of Agricultural Council and Livestock (TCAL) and the Confederation of Tanzania Industries (CTI).

So, the National Livestock Policy will be used as a guide towards achieving the vision and mission of the livestock industry. The objective is to attain food security, poverty reduction and increasing of in household and National income from livestock industry.

# 3.5  Literature review summary

The study found literatures concerning Poultry Keeping project. Different poultry keeping projects are implemented in the world. Some Poultry keeping projects were found in Tanzania, Malawi and other countries. In Tanzania, the Government has formulated the Policy in order to support the Poultry keeping as Poultry keeping brings income to households through the selling of the products such as meat, feathers and manure. Poultry keeping in Tanzania seems to be carried out at most

Household’s levels. Most rural families keep Poultry as the poultry in rural areas are less costing as the chicken search for feeds themselves. This makes many families to keep them.

The Government has supported the poultry keeping projects by formulating the policy and the implementation of the policy helps the people with poultry keeping projects get support. The Government has shown the interest of support by implementing the policy by employing extension workers in order to support the poultry keepers within the country. Apart from employing extension workers, the Government has established livestock/poultry research centres to ensure healthy of the livestock or poulty.Government has given private sector the approval to support livestock and poultry sector development by allowing them to open research centres, veterinary medicine centres, vaccination centres and other supports in order to ensure poultry sector grows and helps households to increase their income and fight against income poverty. It is expected that Poultry keeping project that was established by Agape group members will be sustainable and increase the incomes to households of community members and other community members indirectly hence reducing poverty at household levels.

# CHAPTER FOUR

# 4.0   PROJECT IMPLEMENTATION

# 4.1 Introduction

This chapter is very important as it links with previous chapter one and two. Chapter four is the execution of the identified project. As it links chapter one which is the needs identified and chapter two which is problem identification. After identification of the project to be implemented, we implement in chapter four. Chapter four deals with the project implementation and this implementation carries sub-titles which are Project output, Project planning, Project Implementation Plan, Project Inputs, Staffing Pattern, Project Implementation Budget and Actual Implementation Report.

# 4.2 Project outputs

- 20 group members were trained on Poultry keeping

- Office has been rented

- Building for Poultry keeping was rented

- Purchase of chicks, Feeds and Equipments was done

- Robbing and Advocacy was done

- Registration is on progress

Table 15   :   Project Objective and Output

| Objectives | Outputs | Activities |
| --- | --- | --- |
| 1.Training 20 group members on poultry keeping by Jan 2015 | 1.1 : 20 group members were trained on Poultry keeping | Identification of trainees |
|  |  | Conducting one day workshop on poultry keeping |
| 2. Acquiring an office and a building for poultry keeping by April 2015 | 2.1. office rented | 2.1.1 Fund raising for finding fund for office rent |
|  |  | 2.1.2 Contract signing for office rent |
|  | 2.2. Poultry building rented with seven square meter | 2.2.1 Solicit fund for renting a Building for poultry keeping |
|  |  | 2.2.2 Contract signing for renting a building for poultry keeping |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1 To identify good quality chicks |
|  |  | 3.1.2 Purchase of chicks |
|  | 3.2. Twenty bags of Chicks’Feedswere bought | 3.2.1 To identity the Feeds with required nutrients for the chicks |
|  |  | 3.2.2 To purchase twenty bags of chicken feeds |
|  | 3.3 Poultry brooders,heaters,feeders and troughs equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments |
|  |  | 3.3.2 To purchase the equipments |
|  | 3.4 One vaccination done to four hundred chicks | 3.4.1 To identity the veterinary expert for vaccination |
|  |  | 3.4.2 Doing vaccination activity |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1 Two buyers identified | 4.1.1 Robbing and Advocacy for Marketing |
|  |  | 4.1.2 Transport of live chicken |
| 5. To register the business officially by Sept 2015 | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making. |
|  |  | 5.1.2 Signing and approval of the constitution |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the bank |
|  |  | 5.2.2 Selecting signatories and opening the account |
|  | 5.3 Certificate of Registration acquired | 5.3.1 Facilitation of registration process |
|  |  | 5.3.2 Paying for registration |

The project identified to be implemented focuses on different expected outputs. Project to be implemented has five objectives which are Training of twenty group members on poultry keeping by Jan 2015, Acquiring an office and a building for poultry keeping by April 2015, Undertaking production of the first batch of seven days old chicks by Jun 2015, to sale four hundred live chicken to at least two reliable markets by July 2015 and to register the business officially by September 2015.These objectives leads the project to have outputs and the outputs are explained below;

Output number one was training of twenty group members on the poultry keeping. Group members were trained in order to have sufficient knowledge on the management of the project in order to make the project sustainable. Before training, trainees were selected or identified from the group members and they were accepted and approved by the majority in the group. One day workshop on poultry keeping was conducted in order for the group members to have knowledge on the best selection of the quality chicks, purchase of the equipments for the project, vaccination of the chicks, identifying the quality feeds for the chicks, feeding and knowing the maturity of the chicken.

Other outputs are to rent an office and building for the poultry. This output was achieved by soliciting fund and signing of the contracts for renting. After having a poultry building, one batch of four hundred chicks were bought and twenty bags of chicks’ feeds bought. Also purchase of the equipments like poultry brooders, heaters, feeders and troughs to support the project. Purchase of the chicks goes hand on hand with vaccination in order for the chicks not to be affected by diseases. While feeding continues, identification of the at least two buyers will be done in order to have a reliable market for the chicks when mature. A group expects to have a constitution, Bank account and certificate of registration to become a business entity.

# 4.3 Project planning

Project planning is a procedural step in project management, where required documentation is created to ensure successful project completion. Documentation includes all actions required to define, prepare, integrate and coordinate additional plans. The project plan clearly defines how the project is executed, monitored, controlled and closed. This project planning requires an in-depth analysis and structuring of the setting project goals, identifying project deliverables, creating project schedules and creating supporting plans. Schedules such as Gantt Charts are used to plan and and subsequently report the progress within the project environment.

The project goal is defined and the appropriate methods or activities are planned in order to execute the project. The necessary activities and duration are planned into a work breakdown structure. The project planning also organises different areas of the project for instance project plans, workloads and the management of teams and individuals, funding or budgeting and materials. Usually project planning is being done before the project is actually started.

# 4.3.1. Project Implementation Plan

Project implementation plan is a technical document that provides a high level view of the overall structure of the project. This is the execution of the plan in order to achieve project overall goal, objectives and output. It describes how the activities will be carried out in order to achieve outputs. Time to be spent, resources to be used and responsible person. In order to achieve the overall goal of the Poultry keeping project, there are some activities to be carried and these activities are the identification of the community, conducting a one day workshop on poultry keeping, fundraising for finding funds for poultry building centre and office rent, identification and purchase of chicks, purchase of equipments and chicks’ feeds and marketing and selling of the poultry after maturity. Resources needed are community members and poultry expert for human resources and funds as financial resource and some stationery.

For the project to be implemented, time frame was planned for each activity to be carried out. For the month of January 2015, the month was planned for the Community Needs Assessment followed by identification of the Host organization, identification of Trainees and Project identification. February was planned for preparation of material for workshop and conducting workshop. March the activity planned was for the community to identify the potential project and fund raising for the project. For the month of April was planned for search of an Office and project building. For the month of May, planned activities were to identify and purchase of equipments for the project. On June plan was project itself in place and its management. Sales of project products are expected to be done in July followed by project evaluation. In August it was planned for fumigation/cleanliness for preparation of the second phase if evaluation will give a positive impact of the project to community. September will be the month for the start of second phase if first phase will approve successfully. August, September and October will be the time for facilitation of registration of the group in order to get Registration. By  November  and  December  it  was  planned  for  the  group or  community to make

payments for registration and Registration Certificate to be in place.

| Objective | Output | Activity | Project Implementation month | Resource Needed | Responsible person |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1 20 group members were trained on Poultry keeping | Identification of trainees |  |  |  |  |  |  |  |  |  |  |  |  | * | VICOBA,CED Student |
|  |  | Conducting one day workshop on poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  | Meeting venue | Facilitator,CED Student, VICOBA Members |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Facilitator’s Fee |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Pens 20 pcs |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Notebooks 20 pcs |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Flip Chart 1pc |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Marker pen 1pc |  |
| Acquiring an office and a building for poultry keeping by April 2015 | 2.1 Office rented | 2.2.1. Fund raising for finding fund for Office rent |  |  |  |  |  |  |  |  |  |  |  |  | Soft Drinks | VICOBA Members, Agape members,CED Student |
|  |  | 2.2.2. Contract signing for office rent |  |  |  |  |  |  |  |  |  |  |  |  | LGA | VICOBA |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Funds |  |
|  | 2.2.Poutry building rented with seven square meters | 2.2.1. Solicit fund for renting a Building for poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  | Soft Drinks | VICOBA Members, Agape members,CEDStudent |
|  |  | 2.2.2. Contract signing for renting a Building for poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  | LGA | VICOBA |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1. To identify good quality chicks |  |  |  |  |  |  |  |  |  |  |  |  | Poultry expert | Extension Officer, Agape Members,CED Student |
|  |  | 3.1.2. Purchase of chicks |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Agape members,CED Student |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1. To identify the feeds with required nutrients for the chicks |  |  |  |  |  |  |  |  |  |  |  |  | Poultry expert | Extension Officer, Agape Members,CED Student |
|  |  | 3.2.2. To purchase twenty bags of chicken feeds |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Extension Officer,Agape members,CED Student |
|  | 3.3. Poultry brooders,heaters,feeders and troughs equipments for poultry keeping were purchased | 3.3.1. To identify the needed suitable equipments |  |  |  |  |  |  |  |  |  |  |  |  | Poultry expert | Extension Officer,Agape members,CED Student |
|  |  | 3.3.2.To purchase the equipments |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Agape group members, Extension Officer |
|  | 3.4.One vaccination done to four hundred chicks | 3.4.1. To identify the veterinary expert for vaccination |  |  |  |  |  |  |  |  |  |  |  |  | Veterinary expert | Agape group members,CED Student |
|  |  | 3.4.2. Doing vaccination activity |  |  |  |  |  |  |  |  |  |  |  |  | Veterinary expert | Extension Officer,Agape members,CED Student |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1. Two buyers identified | 4.1.1 Robbing and Advocacy for Marketing |  |  |  |  |  |  |  |  |  |  |  |  | Funds for transportation | Agape group members |
|  |  | 4.1.2 Transport of live chicken |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Agape group members |
| 5. To register the business officially by Sept 2015 | 5.1. Constitution prepared | 5.1.1 Agape group members meeting for constitution making. |  |  |  |  |  |  |  |  |  |  |  |  | Transport | 5.To register the business officially by Sept 2015 |
|  |  | 5.1.2. Signing and approval of the constitution |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Agape group members |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the Bank |  |  |  |  |  |  |  |  |  |  |  |  | Fund for soft drinks | Agape group members |
|  |  | 5.2.2 Selecting signatories and opening the account |  |  |  |  |  |  |  |  |  |  |  |  | Fund | Agape group members |
|  | 5.3 Certificate of Registration acquired | 5.3.1 Facilitation of registration process |  |  |  |  |  |  |  |  |  |  |  |  | Fund, Transport | Agape group members,CED Student |
|  |  | 5.3.2 Paying for registration |  |  |  |  |  |  |  |  |  |  |  |  | Fund | Agape group members |

Table 17   :   Project Logical Framework

| Hierarchy of Objectives | Objectively Verifiable Indicators (OVIs) | Means of verification (MOV) | Assumptions |
| --- | --- | --- | --- |
| Goal (Impact): Reducing Income Poverty | Increased income and improved standards of living the community | Survey and audited monthly and annual reports | Willingness of community members to disclose their economic status. |
| Objective 1: Training 20 group members on poultry keeping by Jan 2015 |
| Output 1.1: 20 Group members were trained on Poultry keeping | 20 group members were trained on Poultry keeping | Progressive report | Community members become aware about the project |
| Activities |
| 1.1.1.Identification of trainees | 20 trainees identified | List of trainees | Group members are aware for training on poultry keeping |
| 1.1.2.Conducting one day workshop on poultry keeping | 20 Group members attended the Workshop | Attendance list | Community members become aware about the project |
| Objective 2: Acquiring an office and a building for poultry keeping by April 2015 |
| Output 2.1 office rented | Signed contract | Contract documents | Group members can access office building |
| Activities |
| 2.2.1.Fund raising for finding fund for Office rent | Amount collected | Amount collected | Payment done and group members occupy an office |
| 2.2.2.Contract signing for office rent | Signed contract | Contract documents | Occupying an Office |
| Output 2.2: Poultry building rented with seven square meters | Signed contract and receipt for payments | Contract documents | Poultry occupying the building |
| Activities. |
| 2.2.1.Solicit fund for renting a Building for poultry keeping | Amount collected | Amount collected | Payment receipts |
| . 2.2.2. Signing for renting a Building for poultry keeping | Signed contract | Contract documents | Contract documents |
| Objective 3: Undertake production of the first batch of seven days old chicks by Jun 2015 |
| Output 3.1: One batch of four hundred chicks were bought | Receipt for payments | Chicks in the poultry building centre | Chicks in the poultry building centre |
| Activities |  |
| 3.1.1.To identify good quality chicks | Quality of Chicks bought | Physical appearance of the bought chicks | Physical appearance of the chicks |
| 3.1.2. Purchase of chicks | Receipt showing purchase payments done | Receipts and chicks in chicks building | Receipt of payment and presence of the chicks in poultry keeping building/centre |
| Output 3.2. Twenty bags of Chicks’ Feeds were bought | Feeds in the project area | Presence of feeds to the project area | Receipt for payment and presence of feeds at project area. |
| Activities |  |
| 3.2.1. To identify the Feeds with required nutrients for the chicks | Labels showing the type of feeds and their contents | Labels showing the type of feeds and their contents | Physical healthy of the chicks |
| 3.2.2. To purchase twenty bags of Chicks’ Feeds | Receipt for payments and quantity of feeds bought | Receipt for payments and feeds available | Availability of chicken feeds |
| Output 3.3. Poultry brooders,heaters,feeders and troughs equipments for poultry keeping were purchased | Equipments in place | Receipt for payments and availability of equipments | Equipments in place |
| Activities |  |
| 3.3.1. To identify the needed suitable equipments | Equipments were identified | Quality of equipments bought | Labels showing quality of equipments |
| 3.3.2. To purchase the equipments | Receipt for payments and quantity of equipments bought in place | Quality of equipments bought | Equipments in place |
| Output 3.4. One vaccination done to four hundred chicks | Number of chicks vaccinated | Progressive report | Visit done by Veterinary officer |
| Activities |  |
| 3.4.1. To identity the veterinary expert for vaccination | Veterinary officer was identified | Progressive report | Poultry were vaccinated |
| 3.4.2. Doing vaccination activity | Number of chicks vaccinated | Physical health of chicks | Payment receipt for vaccination |
| Output 4.1. To sale four hundred live chicken to at least two reliable markets by July 2015 | Number of poultry sold | Increase of income through sales | Sales report |
| Activities |  |
| 4.1.1. Two buyers identified | Sensitization for poultry | List of sensitized people | Readiness of community members to support the project |
| 4.1.2 Transport of live chicken | Chicken loaded in a truck | Truck with loaded live chicken | Chicken are ready for sale |
| Objective 5. To register the business officially by Sept 2015 |  |
| Output 5.1 Constitution prepared | Minutes of the meeting for constitution making | Constitution in place | Agape group members adhere to constitution |
| Output 5.2 Bank account opened | Account number | Check book | Readiness of group members to use Bank account |
| Output 5.3. Received Certificate of Registration | Receipt for registration fees’ payments | Certificate of Registration in place | Community members are aware of the project |
| Activities |  |
| 5.1.1 Agape group members meeting for constitution making | Group members contribute to formulate constitution | Constitution manuscript | Stakeholders become aware on project |
| 5.1.2 Signing and approval of the constitution | Group members accepted to formulated constitution | Attendance list of the meetings | Stakeholders become aware on project |
| 5.2.1 Meeting to select the Bank | Group members attendance on the meeting | Attendance list | Agape group members are aware on the importance of the use of Bank account |
| 5.2.2 Selecting signatories and opening the account | Minutes of the meeting held for account opening | Names of signatories | Agape group members are aware on the importance of the use of Bank account |
| 5.3.1. Facilitation of registration process | Key members making follow ups on registration process | Application letter for certificate of registration | Group members are aware for the project |
| 5.3.2. Paying for registration | Amount of payment | Receipt for payment | Sustainability of the project |

# 4.4 Inputs

During project implementation, some inputs were used in order to implement the poultry keeping project. Some of the inputs that were used during implementation of the project were human resources inputs, materials inputs and financial inputs. Human resources inputs were the use of human beings as project manpower and also as project management team. For the material resource, some material were used for the execution of the project and also financial resources was used as input for the project. Financial resource used was the use of funds/money for the payment of an Office rent, payment of a rent for poultry keeping building, purchase for poultry keeping equipments, payment for extension worker, purchase of chicks, purchase of Feeds, purchasing vaccination medicines and other payments done for the execution of the project.

Table 18   :    Project Inputs

| Objectives | Outputs | Activities | Required Inputs |
| --- | --- | --- | --- |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1 : 20 group members were trained on Poultry keeping | Identification of trainees | * |
|  |  | Conducting one day workshop on poultry keeping | Meeting venue |
|  |  |  | Facilitator’s Fee |
|  |  |  | Pens 20 Pcs |
|  |  |  | Notebooks 20 Pcs |
|  |  |  | Flip chart 1 Pc |
|  |  |  | Marker Pen 1 Pc |
| 2. Acquiring an office and a building for poultry keeping by April 2015 | 2.1. Office rented | 2.1.1 Fund raising for finding fund for Office rent | Soft drinks |
|  |  | 2.1.2 Contract signing for office rent | Local Authority Personnel |
|  |  |  | Fund |
|  | 2.2. Poutry building rented with seven square meters | 2.2.1 Solicit fund for renting a Building for poultry keeping | Soft drinks |
|  |  | 2.2.2 Contract signing for renting a Building for poultry keeping | Local Authority Personnel |
|  |  |  | Funds |
| Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1 To identify good quality chicks | Poultry expert |
|  |  | 3.1.2 Purchase of chicks | Funds |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1 To identity the Feeds with required nutrients for the chicks | Poultry Expert |
|  |  | 3.2.2 To purchase chicken feeds | Funds |
|  | 3.3 Poultry brooders,heaters,feeders and troughs equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Poultry Expert |
|  |  | 3.3.2 To purchase the equipments | Funds |
|  | 3.4 One vaccination done to four hundred chicks | 3.4.1 To identity the veterinary expert for vaccination | Veterinary Expert |
|  |  | 3.4.2 Doing vaccination activity | Veterinary Expert |
|  |  |  | Funds |
| To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1 Two buyers identified | 4.1.1 Robbing and Advocacy for Marketing | Funds for transportation |
|  |  | 4.1.2 Transport of live chicken | Funds |
| 5. To register the business officially by Sept 2015 | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making. | Transport |
|  |  | 5.1.2 Signing and approval of the constitution | Funds |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the bank | Fund for soft drinks |
|  |  | 5.2.2 Selecting signatories and opening the account | Fund |
|  | 5.3 Received Certificate of Registration | 5.3.1 Facilitation of registration process | Transport |
|  |  | 5.3.2 Paying for registration | Funds |

Project needs some inputs for its implementation and those inputs were identified. The identified project inputs are directly linked to the project activities, outputs and ojectives.In order for the project to be sustainable there was a need for training twenty group members on the poultry keeping and in order to achieve training some inputs were identified and those inputs are meeting venue, facilitator’s fee or allowance, pens, note books, flip chart and marker pens. In order for the fund to be raised for renting an office and poultry building, the required inputs identified was some funds for buying soft drinks also the need for an allowance for local authority personnel. In order to undertake production of the first batch of seven days old chicks by June 2015, some inputs like hiring an expert who will assist in the identification of the good quality chicks and also assist during purchase of the equipments for the project such as poultry brooders,heaters,feeders and troughs, vaccination and  assisting during the identification of the feeds with required nutrients for the chicks and also funds that will be used for purchases and paying an allowance for the expert.

For achieving objective four which is the sale of the four hundred live chicken to at least two reliable markets, the required identified inputs were funds for hiring mode of transport that will transport live chicken from the production area to the market and in order to register the business officially the inputs identified were the need for the funds that will be used to facilitate transportation, buying of soft drinks that will be used during the meeting for constitution making.

# 4.5 Staffing Pattern

Poultry keeping project’s execution will be carried by group members themselves with the support from external people who are poultry experts. Group members divided duties and responsibilities to each members in order to have equal participation in the execution of the project. Some were given activities of supervision of the project, some were given the task of cleaning and fumigating the building in order for the poultry to be free from pests, insects, parasites that would affect the poultry’s health. Others were given a role of feeding the chicks and others were given the sales and marketing role to play. Each group member was given a task to perform in order to enhance participatory.Supervitory people were also given the task of keeping documents and reports for the project that would be used for monitoring and evaluation purposes.

# 4.6 Project Budget

For the project to be implemented, there should be a budget for the project. Project implementation Budget was planned by the Agape group members and they raised fund for the project. The budget is well planned and will enable planned activities to be carried out in order for the project to achieve its goal of increasing household incomes to the low income earners who are Agape group members. Inputs for each planned activity were allocated with the amount of fund that would be spent to fulfil the planned activity. Below is the Table showing project implementation budget with the allocated amount of fund.

Table 19   :    Project Budget

| Objectives | Outputs | Activities | Resource needed | Quantity | Price/Unit | Total Tsh |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1 : 20 group members were trained on Poultry keeping | 1.1.1.Identification of trainees | * | * | * | * |
|  |  | Conducting one day workshop on poultry keeping | Facilitator( Veterinary) | 1 | 80,000 | 80,000 |
|  |  |  | Stationeries | Pens 20 | 200 | 4,000 |
|  |  |  |  | Notebook 20 | 1,000 | 20,000 |
|  |  |  |  | Flip Chart 1 | 10,000 | 10,000 |
|  |  |  |  | Marker pens 1 box | 6,000 | 6,000 |
| 2. Acquiring an office and a building for poultry keeping by April 2015 | 2.1. Office rented | 2.1.1 Fund raising for finding fund for Office rent | Soft drinks | 30 | 1,000 | 30,000 |
|  |  | 2.1.2 Contract signing for office rent | Local Government Authority | 1 | 20,000 | 20,000 |
|  |  |  | Fund | Months 12 | 40,000 | 480,000 |
|  | 2.2. Poultry building rented with seven square meters | 2.2.1 Solicit fund for renting a Building for poultry keeping | Soft drinks | 30 | 1,000 | 30,000 |
|  |  | 2.2.2 Contract signing for renting a Building for poultry keeping | Local Government Authority | 1 | 20,000 | 20,000 |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1 To identify good quality chicks | Poultry expert | 1 | 20,000 | 20,000 |
|  |  | 3.1.2 Purchase of chicks | Fund | 400 | 1300 | 520,000 |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1 To identity the Feeds with required nutrients for the chicks | Poultry expert | 1 | 20,000 | 20,000 |
|  |  | 3.2.2 To purchase chicken feeds | Fund | Bags 20 | 50,000 | 1,000,000 |
|  | 3.3. Poultry brooders, heaters, feeders and troughs equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Poultry expert | 1 | 20,000 | 20,000 |
|  |  | 3.3.2 To purchase the equipments | Poultry brooders and heaters | 5 | 15,000 | 75,000 |
|  |  |  | Poultry feeders and troughs | 5 | 15,000 | 75,000 |
|  | 3.4 One vaccination done to four hundred chicks | 3.4.1 To identity the veterinary expert for vaccination | Veterinary | 1 | 20,000 | 20,000 |
|  |  | 3.4.2 Doing vaccination activity | Veterinary | 1 | 30,000 | 30,000 |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1 Two buyers identified | 4.1.1 Robbing and Advocacy for Marketing | Transport | 4 | 10,000 | 40,000 |
|  |  | 4.1.2 Transport of live chicken | Funds | 4 | 10,000 | 40,000 |
| 5. To register the business officially by Sept 2015 | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making | Transport | 2 | 10,000 | 20,000 |
|  |  | 5.1.2 Signing and approval of the constitution | Funds | 3 | 20,000 | 60,000 |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the Bank | Fund for soft drinks | 30 | 1,000 | 30,000 |
|  |  | 5.2.2 Selecting signatories and opening the account | Fund | 3 | 10,000 | 10,000 |
|  | 5.3 Receive Certificate of Registration | 5.3.1 Facilitation of registration process | Transport | 2 | 20,000 | 40,000 |
|  |  | 5.3.2 Paying for registration | Funds | 1 | 40,000 | 40,000 |
| Grand Total | 2,760,000 |

Project budget was prepared in order for each objective to be achieved as planned. Each objective has its outputs and activities that will be carried out in order to achieve the objective concern. Each activity has been linked with the resources needed, quantity, price per unit and total cost in order to make the activities be done as planned. For objective number one was to train twenty group members on poultry keeping by Jan 2015.The output for this objective is twenty group members being trained and the planned activities are identifying the trainees and conducting one day workshop on poultry keeping. In order to train twenty group members resources needed are the facilitator and stationaries like pens,notebooks,flip chart, marker pens and each resource has been allocated the quantity and total costs to be incurred by the project.

Acquiring the building for an office and for poultry was planned to have two main activities which are fund raising and contracts signing and the resources needed are funds that will be used for payments for rents and buying of soft drinks and paying for the allowance for local government personnel who stands as a witness of the contracts. For the project to undertake production of the first batch of seven days old chicks, activities identified were to identify good quality chicks, identifying the feeds required for the chicks, purchase of chicks, identifying the needed suitable equipments for the project and purchasing them, identifying the veterinary expert for vaccination and doing vaccination activity. These activities will need some resources which are hiring an expert in poultry and funds that will be used for payment of the required resources.

Project will need to sale four hundred live chicken to at least two reliable markets. Resources needed to support sales will be funds that will be used for facilitating the activity and finally the last objective of the project is to register the business officially. In order to register the business officially, there will be needs for constitution, bank account and certificate of registration. These outputs will be achieved by carrying out activities like having meeting for constitution making, signing and approving the constitution, meeting to select signatories and opening bank account. These activities will need some funds to facilitate them. Each objective has been planned with activities to be carried out and each activity has been budgeted for in order for the project to achieve its goal.

# 4.7 Actual Project Implementation

This part describes the actual project implementation. It described how the project was executed step by step. Shows how the activities were executed and the resources utilized in order for the activities to be implemented. Activities executed are those that were planned in the project design. Project implementation requires a coordination of a wide range of activities, the overseeing the team, the management of the budget, communication and other issues associated with the project. Project implementation is the phase where visions and plans become reality.

# 4.8 Project Implementation Report

Project implementation was done and planned activities were carried out as planned. The following activities have been conducted and some are accomplished while others are still on progress. Project design and planning was done and identification of trainees was done. Twenty members were identified for training and one day workshop on Poultry keeping was conducted in order to have group members with a capacity that will manage the project to become sustainable. There was a need for the group to search for the funds in order to pay for the rent of an Office and building for poultry keeping. Funds were raised and building for poultry keeping was rented and also the Office for the project was rented hence an office in place. After fund raising for the payment of rent of the building for poultry and an office, group members signed the renting contracts in the presence of Local Government Authority as their witness.

With the help from veterinary or poultry expert, the equipments for the poultry keeping were purchased, Feeds were purchased and healthy chicks were purchased. Some activities were done like identifying the quality needed equipments, needed and recommended feeds with the quality nutrients and thereafter the chicks were purchased and being kept in their rented poultry building. Feeding of the chicks proceeded and vaccination was done to make the chicks healthy by being free from diseases attack. Supervision for feeding and records keeping went hand on hand in order for the project team to observe the maturity of the chick.Robbying and advocacy for markets was done and the facilitation for the group to be registered still in progress. Facilitation for registration has been done to some extent and still on progress and payment for registration has not been done because it is still on progress.

The table below shows a summary of the project implementation.

Figure 3  :  One day workshop on Poultry Keeping

Figure two above shows CED Student clarifying about the project to the Agape community during the one day workshop conducted for poultry keeping project.

Figure 4  : Clarification during one day Workshop on Poultry Keeping

Figure 5  : Some trainees who attended Workshop

After one day workshop, group members decided to find a building for poultry keeping. They searched for a place with a building that could be suitable for poultry keeping.

Figure  6   :   Building for Poultry Keeping.

After poultry building in place, group members purchased first batch of four hundred chicks in order to start production of the project.

Figure 7  : Chicks in a Building

Figure 8   : Chicks in Place

After purchase of chicks, feeding started.

Figure 9   :   Vaccination and Feeding of Chicks

Figure 10   :  Feeding of Chicks

Table 20   :    Actual Project Implementation Summary

| Objectives | Outputs | Activities | Actual Implementation |
| --- | --- | --- | --- |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1 : 20 group members were trained on Poultry keeping | Identification of trainees | 20 group members were identified for training |
|  |  | Conducting one day workshop on poultry keeping | One day workshop on Poultry keeping was conducted |
| 2. Acquiring an office and a building for poultry keeping by April 2015 | 2.1. Office rented | 2.1.1 Fund raising for finding fund for Office rent | Fund was raised for Office rent |
|  |  | 2.1.2 Contract signing for office rent | Contract for an Office rent was signed and Agape group members have an Office in place |
|  | 2.2. Poultry building rented with seven square meter | 2.2.1 Solicit fund for renting a Building for poultry keeping | Funds were raised for the purpose of renting a building for poultry keeping |
|  |  | 2.2.2 Contract signing for renting a Building for poultry keeping | Contract for poultry keeping building rent to be signed in April 2015 and Agape group members have a building in place |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1 To identify good quality chicks | Healthy Chicks were identified in May 2015 |
|  |  | 3.1.2 Purchase of chicks | Healthy chicks were purchased in June 2015 |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1 To identity the Feeds with require Nutrients for the chicks | Feeds with required nutrients for the chicks were identified in May 2015 |
|  |  | 3.2.2 To purchase chicken feeds | Feeds with required nutrients for the chicks were purchased in May 2015 |
|  | 3.3 Poultry brooders,heaters,feeders and troughs equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Equipments to support poultry keeping were identified |
|  |  | 3.3.2 To purchase the equipments | Equipments with high quality that support poultry keeping were purchased in May 2015 |
|  | 3.4 One vaccination done to four hundred chicks | 3.4.1 To identity the veterinary expert for vaccination | Veterinary expert for vaccination was identified |
|  |  | 3.4.2 Doing vaccination activity | Vaccination was done in June,2015 for the chicks to become healthy |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1 Two buyers identified | 4.1.1 Robbing and Advocacy for Marketing | Robbing and advocacy for marketing will be conducted in July,2015 |
|  |  | 4.1.2 Transport of live chicken | To be done in July 2015 |
| 5. To register the business officially by Sept 2015 | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making. | To be done by Jun 2015 |
|  |  | 5.1.2 Signing and approval of the constitution | To be done by Jun 2015 |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the bank | To be done by Jun 2015 |
|  |  | 5.2.2 Selecting signatories and opening the account | To be done by Jun 2015 |
|  | 5.3 Received Certificate of Registration | 5.3.1 Facilitation of registration process | Will be conducted before end of September 2015 |
|  |  | 5.3.2 Paying for registration | Will be done by Sept 2015 |

# 4.9 Project Implementation Gantt chart

Gantt charts are tools used for analyzing and planning complex projects. They help in planning out the tasks that need to be completed, they give a basis for scheduling when these tasks will be carried out, and they assist in allocation of the resources needed to complete the project and also helps to work out the critical path for the project in terms of date of project completion. When a project is under way, Gantt charts help to monitor whether the project is on schedule.

Table 21   :   Project Implementation Gantt chart

| Objective | Output | Activity | Activity Implementation Monthly |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1. 20 group members were trained on Poultry keeping | Identification of trainees |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conducting one day workshop on poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  |
| Acquiring an office and a building for poultry keeping by April 2015 | 2.1. Office rented . | 2.2.1. Fund raising for finding fund for Office rent |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.2.2. Contract signing for office rent |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2. Poultry building rented with seven square meters | 2.2.1. Solicit fund for renting a Building for poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.2.2. Contract signing for renting a Building for poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1. To identify good quality chicks |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.2. Purchase of chicks |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1. To identity the Feeds with required Nutrients for the chicks |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.2.2. To purchase chicken feeds |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.3. Poultrybrooders,heaters,feeders and troughs equipments for poultry keeping were purchased | 3.3.1. To identify the needed suitable equipments |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.3.2. To purchase the equipments |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4. One vaccination done to four hundred chicks | 3.4.1. To identity the veterinary expert for vaccination |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.4.2. Doing vaccination activity |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1. Two buyers identified | 4.1.1 Robbing and Advocacy for Marketing |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 4.1.2 Transport of live chicken |  |  |  |  |  |  |  |  |  |  |  |  |

| 5. To register the business officially by Sept 2015 | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 5.1.2 Signing and approval of the constitution |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the bank |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 5.2.2 Selecting signatories and opening the account |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.3. Received Certificate or Registration | 5.3.1. Facilitation of registration process |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 5.3.2. Paying for registration |  |  |  |  |  |  |  |  |  |  |  |  |

Project implementation Gantt chart shows the implementation of the project. It shows time of which each activity will be implemented as planned. Identification of the trainees will be done in Jan 2015 while conducting one day workshop will be conducted on February. Fund raising in order to find funds for office renting and building for poultry will be done on march followed by contracts signing for rent on April 2015.After having office and building in place, the identification of feeds with nutrients needed for chicks, identification of the good quality chicks, identifying veterinary expert, purchase of equipments for the project.

In June there will be purchase of chicken feeds, chicken, vaccination. By July to September activities that will be carried out will be robbing and advocacy for marketing, transport of live chicken, meeting to make constitution, signing and approval of constitution, meeting to select the Bank in order to open an account, selection of the signatories, facilitation of registration process and paying for registration of the business officially.

CHAPTER FIVE

# 5.0   PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

# 5.1 Introduction

Chapter five describes how the project participatory monitoring and evaluation will be carried out for the project to become sustainable. In order for the project to become sustainable there should be effective and efficient project monitoring and evaluation. Project monitoring will show if the project activities are executed as planned and the resources planned are utilized as it was planned hence gives a direction of the project so as the project team can determine if they are moving towards the planned direction in order to achieve the project objective hence achievement of the project overall goal. Evaluation has to be done and this will help to get the right information that will help the team to know if the project will either be sustainable or not to become sustainable.

According to World Bank web, Participatory monitoring and evaluation refers to a process through which stakeholders at various levels engage in Monitoring and Evaluation of a particular project. It entails sharing the responsibilities for evaluation planning, implementation and reporting by involving stakeholders in defining the evaluation questions, collecting and analyzing data and drafting and reviewing the report. So, the needs for participation according to the World Bank is the sharing of the responsibilities by each stakeholder for each stage of the project during project life.

Participatory monitoring is the systematic recording and periodic analysis of information that has been chosen and recorded by stakeholders (insiders) of the project with the help of outsiders (experts).The main purpose of participatory monitoring is that it provides information during the life of the project, so that adjustments and/or modifications can be made if necessary. Participatory monitoring provides an ongoing picture that allows the community to determine whether the activities are progressing as planned and it also shows when activities are not leading to objectives, so that early adjustments can be made.

Participatory evaluation is an opportunity for both insiders (community members) and outsider (expert) to stop and reflect on the past in order to make decisions about the future. Insiders are encouraged and supported by outsiders to take responsibilities and control of planning, evaluation and analysis of the information and presenting evaluation results. Participatory evaluation is not taken as a final judgement on whether the project activities are successful or unsuccessful. The information should encourage changes and adjustments either during the life span of the activities for future phases of the activities or for future new activities.

The chapter describes project participatory monitoring, evaluation and sustainability of the Poultry Keeping project. The information has been collected and analysed for the purpose of monitoring the project, evaluating the project and see if the project will be sustainable. Monitoring and evaluation was done in order to ensure that the planned activities for Poultry keeping project are performed as planned, resources planned are well utilized, stakeholders participation if fully done. Agape group members participated in project planning and participated in planning on how monitoring and evaluation will take place. Agape group members participated in monitoring and evaluation for instance some of them volunteered in cleanliness of the Poultry building, during cleaning the building, they see everything that is happening at the project site. Participation during vaccination also is a part of monitoring on how Poultry are vaccinated and also monitors the number of the poultry that were vaccinated and the medicine used for vaccination. By participating on vaccination helps them to know the medicine and costs used for purchase of the medicine and by doing so they are evaluating the vaccination activities. Some of the group members are Supervisors or Leaders for the project, being leader of the project means participation in the management of the project and by doing so, becomes the part of monitoring and evaluation of the project. As long as many group members participate in the project stages the expectation of the project to become sustainable becomes high.

# 5.2 Participatory monitoring

Participatory monitoring is the systematic recording and periodic analysis of information that has been chosen and recorded by insiders with the help of outsiders. Participatory monitoring provides information during the life of the project, so that adjustments and/or modifications can be made if necessary and by doing so, it helps to measure the progress of the project. Participatory monitoring helps to keep track of activities by recording information on a daily,weekly,monthly or seasonal basis and taking the time to stop and analyze the information monitored can provide important immediate feedback and can be used in the future for participatory evaluations. Keeping of tracks gives an information for decision making.

Participatory monitoring does not only keep records but also giving a room for people to add up, discuss, integrate the information. The time to stop and analyze vary according to the nature and/or seasonality of activities. In order for community members to participate in monitoring there should be an agreement on why they are making monitoring and everyone should be informed on the progress towards planned objectives and activities. These members should be given an opportunity for trainings in order to have the ability to combine qualitative (descriptive) information with qualitative (number) information, providing a more complete analysis. By having an ability to track qualitatively and quantitatively, community members become able to track the progress towards objectives and activities.

We do participatory monitoring due to the reasons that it gives a room for knowing an ongoing picture that allows a community to determine whether activities are progressing as planned. Also it shows if the activities are not leading to objectives so that early adjustments can be made. Monitoring provides an early warning which identifies problems at an early stage hence solutions can be sought before the problems get out of hand. By doing monitoring, good standards are maintained. Continuous feedback throughout the life of the activities ensures that the quality of the activities is sufficient to provide good results. Participatory monitoring shows the required resources that are required to produce a certain effect or how necessary resources can be distributed differently to get a better effect. Participatory monitoring ensures the equally representation in decision making and equally distribution of costs and benefits.

In this project, community members have participated fully at each stage. On project identification, group members joined together voluntarily and participated in the stage of identification of which project will be executed that will generate income in order for the group members to benefit from incomes that will be derived from the selling of the project products. Group members came from different occupations which were food vendors, tailoring, saloon, horticulture and bar and groceries. Participation was done fully and they organized themselves and made an agreement on the project to be executed. They all participated in identification by using scoring ranking method of the thought projects and came up with the establishment of the poultry keeping project as they became aware that this will be viable and it is not too expensive to start and manage the project.

In project planning, each group member participated by giving his or her views concerning the project. Project planning needed their consent as it is the ones who are the owners of the project and are the ones that will have to implement the project. By implementing the project, they have to make monitoring and controlling of the project during project executions in order to control the resources to be used in order to manage the project planned budget. Implementation of the project will be done by group members. Group members have volunteered to perform some tasks in order to reduce the project management costs and also it is a part of learning to the group members. The members have volunteered to perform cleanliness, assist in vaccination activities, doing feeding of the poultry and also they volunteered in searching for the markets in order to be sure of the selling of the project products.

Participatory monitoring will be done in collaboration with the group members, this has been planned and it was organised by themselves. This aims to empower the group members for future project sustainability. This participatory monitoring will empower them as they will either establish new projects or increase the size of the project in order to increase the sales of their project products hence the increase of their incomes. Evaluation of the project will be done by the project evaluation expert in collaboration with the group members. Fully participation of the group members in project evaluation will empower the group members in order for them to perform evaluation of their projects for their future projects. Group members will be trained on how evaluation of the project is being done and they will learn by doing the evaluation activities during evaluation of the current project.

# 5.2.1 Monitoring Information System

Monitoring information system is the system that has been designed to collect and report information on a project and project activities that enable a project manager to plan, monitor and evaluate the operations and performance of the project. According to IFAD (2000), monitoring system is defined as an observation system for the project managers to verify whether the project activities are happening according to planning and whether means are used in a correct and efficient manner. In order for the monitoring of the project to be effective, monitoring information systems planned should be of timely, relevance and trustworthy in order to give an information that can be used to assess if the planned or desired changes are taking place. The system should also be considered in terms of cost, scope and scale of the information to be collected for monitoring, time and expertise during planning or selecting the system that should be used for monitoring.

Monitoring information systems can be of the quantitative in nature or qualitative in nature. During planning or selection of the information system to be used, planning teams should consider that the quantitative are often more costly in terms of the equipments, people and time while qualitative requires special skills which means the need for skilled people to be specified that are the ones to conduct the monitoring activities for the project. So, there is a need to think before you plan what type of monitoring information system should be used for monitoring.

The monitoring information system that were developed should be appropriately managed. Monitoring system will need resources and management support to ensure that it is carried out effectively and in a way that it should contribute to the overall success of the project. If it is poorly managed then the reputation among stakeholders will be harmed. Poorly managing of the information system will leed to failing to collect information on time, poor quality monitoring work, overspending the budget, limited capabilities. In order for the project monitoring systems to work well then there should be a positive consideration on the people to be trained in order to promote effective monitoring support, systems that will integrate the information into a management structure and ensure data storage, processing and retrieval, and which can clarify formats for reports and timing, Time for monitoring activities to take place, Financial resources and use of monitoring information.

As the information is the fuel that drives the project monitoring system, without information, it is not possible to know what has happened and what has to be done in order to rectify the changes occurred. A well-functioning project monitoring system will enable to collect appropriate information on the work and on the project’s context in a way that will feed into timely and relevant decision-making, reporting and learning on changes happened. Information system has to be carefully managed to ensure that the necessary information is collected at the right time, and to ensure that you do not receive more information than you can analyse and that you need as a basis for action. This will help to collect the information that is needed rather than collecting information that is irrelevant. It also gives a room to oversee the quality of the information received so that the analysis and subsequent actions are not spoiled by the poor quality of the information available for the project.

In this project, monitoring information system was designed in order for the project monitoring team to be able to monitor the project. Monitoring information system was designed by Agape group members with collaboration with the CED Student. The system planned will assist the members to monitor if the activities are carried out as planned, costs and expenditures, records to keep, who collects reports, who makes decision on the reports, time planned and time spent and other resources used.

Table 22   :   Project Monitoring Information System

| Categories of information | What to Monitor | What Record to Keep | Who Collects Data | Who Uses Data | How to use Information | What Decisions can be made |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Work plan Activities | Time spent Activities performed Resources spent | Resources’ Utilization record | CBO team. CED Student. Agape group members. | CBO team CED student Agape group members | Ensure planned activities are performed as planned through making reference to work plan. | Reschedule of activities if needed. |
| 2. Cost and Expenditure | Resources spent Equipments purchased Time management Operating within Budget | Purchasing records Inventory Time management Payment records | CBO team. CED Student. Agape group members. | CBO team CED student Agape group members | Compliance with Financial plan agreed by group members. | Determine needs for other funding sources. Budget review |
| 3. Volunteers | Performance of group members volunteering | Performance progress report | Agape group members. CED Student | Agape group members. CED Student | Information will determine if the poultry building is of hygiene or not | Either volunteers to proceed or be removed. |
| 4.Equipments and Feeds | Quality of equipments purchased. Quality of Feeds purchased. | Feeding reports. Purchasing receipts and reports. | Agape group members. CED Student | Agape group members. CED Student | Ensuring purchased Equipments and Feeds followed quality planned. | Feeds purchased to feed the chicks or purchasing other Feeds. |
| 5.Marketing and Sales | Marketing activities done. Cost of marketing and costs associated with Sales. Number of poultry sold | Sales and Marketing reports | Agape group members. CED Student | Agape group members. CED Student | Sales report to be used to determine if the project gets profit or loss. | Reschedule marketing activities. Re-pricing if the project does not make profit |
| 6.Project sustainability | Resources’ utilization. Project sustainability | Performance progress reports | Agape group members. CED Student | CBO team CED student Agape group members | Comparing work plan and Actual in order to determine if the project is on the right track. | Reschedule activities if not on the right track. Search for other funding sources if funds are insufficient. |

# 5.2.2 Participatory Monitoring Methods

Participatory Monitoring Method used was Participatory Rural Appraisal (PRA).It promoted the use of the methods in a participatory manner, allowing group members to be involved in deciding which the methods are appropriate, designing them, and collecting the information. By involving the group members in analysing the information for significant changes, there is a greater likelihood that project stakeholders as well as project staff will learn from the experience. Monitoring methods used were;

# 5.2.2.1. Documentation

Documentation method was used in collecting daily, weekly reports for monitoring progress of the project. Reports were collected from group members, extension worker and host organization and information that were collected were documented in various offices. .Data taken helped the project team in monitoring of the poultry keeping project and sustainability.

# 5.1.2.2. Participant Observation

Agape group members and other project stakeholders used the participants’ observation for monitoring activities being carried for the project in order for the monitoring of the project. Monitoring is an ongoing activity and can be done by observing what is being done, relevance of what was done in relation to the project’s activities planned. Each participant is given a room to participate in monitoring activity in order to determine if the project is smoothly moving towards the plan.

# 5.2.2.5. Group Interview

Group interview tool/method was used to gather information that was used for the monitoring purposes. Group interviews give information about the experience and perspectives of the group concerning the progress of the project. All members were given a chance to express their view and experience concerning the project.

# 5.2.3 Participatory Monitoring Plan

Participatory Monitoring Plan refers to a detailed proposal for doing monitoring, it is a plan of action, it is deciding on and making arrangements for participatory monitoring in advance. Monitoring plan should be created after the planning phase and before the design phase of a project or intervention. The Participatory monitoring plan should include information on how the stakeholders of the project or intervention will participate in monitoring and how the project will be examined and assessed. The plan should underlay assumptions on which the achievement of the project goal depend. The anticipated relationships between activities, outputs and outcomes.

Members of the project beneficiaries participated in the planning of how monitoring activities will be carried out. They discussed and prioritized their developmental needs and external actors (experts) used the information to plan their project and programmes. In participatory planning, local community members were given power in planning and were involved in decision –making on what they thought to be able for them to achieve. It is a plan that involved group members who are the owner of the project in measuring, recording, collecting, processing and communicating information to assist local development project extension workers and local group members in the decision making.

In this project, participatory monitoring plan was planned by Agape group members who are project owner with the help of external experts and they were able to set the project objectives, project outputs, project activities, indicators, data sources, method/tools for data collection person responsible and allocated time frame for each activity to be carried out. The table shows a summary of the participatory monitoring plan for the Poultry keeping project. Each member of Agape group participated in monitoring planning and each was given a task of which she or he will have to perform for monitoring of the project.

Table 23   :   Participatory Monitoring Plan

| Objectives | Outputs | Activities | Indicators | Data Source | Method/Tools | Person Responsible | Time Frame |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1 : 20 group members were trained on Poultry keeping | Identification of trainees | List of Participants | Progressive report | Meeting | VICOBA,CED Student | Jan,2015 |
|  |  | Conducting one day workshop on poultry keeping | Training report | Progressive report | Lecture, Group discussion | Facilitator, CED Student, VICOBA Members | Feb,2015 |
| 2. Acquiring an office and a building for poultry keeping by April 2015 | 2.1. Office rented | 2.1.1 Fund raising for finding fund for Office rent | Fund raised | Progressive report | Meeting | VICOBA Members, Agape members, CED Student | March,2015 |
|  |  | 2.1.2 Contract signing for office rent | Contract in place | Progressive report | Meeting | VICOBA | Apr,2015 |
|  | 2.2. Poultry building rented with seven square meters | 2.2.1 Solicit fund for renting a Building for poultry keeping | Funds raised | Progressive report | Meeting | VICOBA Members, Agape members, CED Student | March,2015 |
|  |  | 2.2.2 Contract signing for renting a Building for poultry keeping | Contract in place | Progress report | Meeting | VICOBA | Apr,2015 |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1 To identify good quality chicks | Chicks in place | Analytical Report | Screening of chicks | Extension Officer, Agape Members, CED Student | May,2015 |
|  |  | 3.1.2 Purchase of chicks | Purchasing report, Chicks in place | Delivery Note, Goods receivable note | Purchasing | Agape members, CED Student | June,2015 |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chicks | Feeds in place | Analytical report | Identification report | Extension Officer, Agape members, CED Student | May,2015 |
|  |  | 3.2.2 To purchase chicken feeds | Feeds in place | Purchasing report | Payment receipt | Extension Officer, Agape members, CED Student | Jun 2015 |
|  | 3.3 Poultry brooders, heaters, feeders and troughs equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Identification report | Identification Report | Purchasing analysis report | Extension Officer, Agape members, CED Student | May 2015 |
|  |  | 3.3.2 To purchase the equipments | Equipments in place | Goods receivable note | Inventory | Agape group members, Extension Officer | May 2015 |
|  | 3.4 One vaccination done to four hundred chicks | 3.4.1 To identity the veterinary expert for vaccination | Identified Extension Officer | Identification/Progressive report | Screening report | Agape group members, CED Student | May 2015 |
|  |  | 3.4.2 Doing vaccination activity | Chicks vaccinated | Vaccination report | Injection | Extension Officer, Agape members, CED Student | June 2015 |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1 Two buyers identified | 4.1.1 Robbying and Advocacy for Marketing | Displayed advertisements done | Progressive report | Advertisements | Agape group members | June-July,2015 |
|  |  | Transport of live chicken | Live chicken loaded in a truck ready for transportation | Receipt for transport payment | Hired Truck | Agape group members | Jun-Jul 2015 |
| 5. To register the business officially by Sept 2015 | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making. | Constitution manuscript in place | Minutes of the meeting | Meeting | Agape group members | July-Sept 2015 |
|  |  | 5.1.2 Signing and approval of the constitution | Approved constitution in place | Minutes of the meeting Approved Constitution copies | Meeting | Agape group members | July-Sept 2015 |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the bank | Minutes of the meeting | Minutes of the meeting | Meeting | Agape group members | July-Sept 2015 |
|  |  | 5.2.2 Selecting signatories and opening the account | Names of signatories selected | Minutes of the meeting | Meeting | Agape group members | July-Sept 2015 |
|  | 5.3 Received Certificate or Registration | 5.3.1 Facilitation of registration process | Certificate of Registration | Progressive report | Filling of Registration Forms | Agape group members, CED Student | Sept,2015 |
|  |  | 5.3.2 Paying for registration | Receipt for payment | Progressive report | Bank deposit | Agape group members | Sept,2015 |

# 5.3 Project Participatory Evaluation Summary

This part gives a summary of participatory evaluation. Evaluation is the tool or approach that is used to ensure that implementation of the different planned activities for the project are well implemented for the achievement of the set project goal. Project evaluation shows to what extent has the project goal, objective, effectiveness, efficiency, impact and sustainability has been achieved. Participatory evaluation gives a partnership approach to project stakeholders in planning and executing evaluation activities at every stage of project implementation.

Evaluation gives a periodic assessment of the relevance and performance of the project. It gives a feedback to the project team on what it can do differently to accomplish its objectives. Evaluation also assesses projects’ impact and sustainability of the project. Evaluation for the project was planned by project stakeholders in collaboration with some experts. Participatory evaluation is still an ongoing activity for the poultry keeping project that has been designed, planned and executed by Agape group members. Project Participatory Evaluation as it gives a room where Professional evaluators, project staff, project beneficiaries or participants and other community members all become colleagues in an effort to improve the community’s quality of life. Participatory evaluation should think of Process, Implementation and Outcomes. Process of a project includes the planning and logistical activities needed to set up and run it.Implementation is the actual work of running the projct.Outcomes are results of the project’s existence. Group members participated in evaluation of the project in order to be sure if the planned goal was achieved, if the resources planned were utilized as planned and the impact of the project itself to the beneficiaries. Agape group members participated in evaluating if all planned activities were fully done, costs that the group inquired, quality of chick purchased, quality of feeds purchased, equipments purchased, contracts signing for renting an Office and Poultry building and also they evaluated if the sales attained brought profit or loss to the project

Table 24   :   Participatory Evaluation Summary

| Objectives | Outputs | Activities | Performance Indicators | Expected Outcome | Actual Outcome |
| --- | --- | --- | --- | --- | --- |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1 : 20 group members were trained on Poultry keeping | Identification of trainees | List of Trainees identified | Identified Trainees | 20 Agape group members identified for Training |
|  |  | Conducting one day workshop on poultry keeping | Progressive report | 20 Agape group members to be trained on Poultry keeping | 20 Agape group members Trained on Poultry keeping Project |
| 2. Acquiring an office and a building for poultry keeping by April 2015 | 2.1. Office rented | 2.1.1 Fund raising for finding fund for Office rent | Contract signed, Receipt of Payment | Fund to be raised | Fund was raised |
|  |  | 2.1.2 Contract signing for office rent | Signed contract | Contract to be signed and members to have an Office | Office in Place |
|  | 2.2. Poultry building rented with seven square meter | 2.2.1 Solicit fund for renting a Building for poultry keeping | Funds raised | Fund to be raised | Fund was raised |
|  |  | 2.2.2 Contract signing for renting a Building for poultry keeping | Signed Contract | Contract to be signed and members to have Poultry building in place | Building for Poultry in place |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1 To identify good quality chicks | Chicks identified | Chicks to be identified | Chicks were identified |
|  |  | 3.1.2 Purchase of chicks | Chicks purchased | Chicks to be purchased | Chicks in place |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chicks | Feeds Identified | Feeds to be identified | Feeds with required nutrients were identified |
|  |  | 3.2.2 To purchase chicken feeds | Purchased Feeds, Payment receipts | Feeds to be purchased | Feeds in place/Feeds purchased |
|  | 3.3 Poultry brooders, heaters, feeders and troughs equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Identified equipments | Equipments to be identified | Suitable Equipments were identified |
|  |  | 3.3.2 To purchase the equipments | Equipments purchased in place | Equipments to be purchased | Purchased Equipments in place |
|  | 3.4 One vaccination done to four hundred chicks | 3.4.1 To identity the veterinary expert for vaccination | Identified Extension Officer | Veterinary expert to be identified and chicks to be vaccinated | Veterinary expert was identified |
|  |  | 3.4.2 Doing vaccination activity | Chicks’ healthy | Chicks to be vaccinated | Chicks were vaccinated |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1 Two buyers identified | 4.1.1 Robbying and Advocacy for Marketing | Sales Report | Market for chicken | Chicken were sold |
|  |  | 4.1.2 Transport of live chicken | Number of chicken reached the market for Sales | Increase in Agape group members income | Agape group members increased their incomes |
| 5. To register the business officially by Sept 2015 | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making. | Constitution manuscript in place | Good Governance of the project. Accountability | Good Governance from July-Sept 2015 |
|  |  | 5.1.2 Signing and approval of the constitution | Approved constitution in place | Accountability | Good Governance to be done from July-Sept 2015 |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the bank | Minutes of the meeting | Good management of Project Fund | Good Governance to be done from July-Sept 2015 |
|  |  | 5.2.2 Selecting signatories and opening the account | Names of signatories selected | Good management of Project Fund | Good Governance To be done from July-Sept 2015 |
|  | 5.3 Received Certificate or Registration | 5.3.1 Facilitation of registration process | Certificate of Registration | Group to be registered | Agape group members got Registration |
|  |  | 5.3.2 Paying for registration | Certificate of Registration | Certificate of Registration | Certificate of Registration |

# 5.3.2 Participatory Evaluation Methods

Participatory Evaluation Method used was Participatory Rural Appraisal (PRA).It promoted the use of the methods in a participatory manner, allowing group members to be involved in deciding which the methods are appropriate, designing them, and collecting the information. By involving the group members in analysing the information for significant changes, there is a greater likelihood that project stakeholders as well as project staff will learn from the experience. In participatory evaluation, people learn more about the things that will have worked well and also learn on how and why they worked well. They also learn on things that have not worked well and why they did not work well.

In a participatory evaluation, the overall and immediate objectives, their continued relevance and the effectiveness of the activities are all taken into account. Much of the information from Participatory Assessment, Participatory Baseline and Participatory Monitoring can be used in participatory evaluation. Information from participatory monitoring will give progress trends and total amounts. By examining the activities individually and relative to objectives, give stakeholders relevant and useful information that will help them decide whether the objectives and/or activities should stay the same or change. Participatory rural appraisal was used to facilitate the use of Questionnaire, Focus Goup Discussion and Key informants Interview methods were planned to be used during evaluation of the project.

# 5.3.3 Project Performance Indicator

In order for the project to be achieved and sustainable, there should be performance indicators planned in order to assess the achievement of the project. Performance indicators refer to variables that show the extent of change that resulted from the project. They help to measure quantities, quality and timeliness of what was planned. They measure the status of progress in achieving outputs and outcomes. The project indicators do show relevance, performance and effectiveness of the project as well as progress towards meeting its outputs and outcomes.

# Table 25: Project Performance Indicators

| Objectives | Outputs | Activities | Resources Needed | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. Training 20 group members on poultry keeping by Jan 2015 | 1.1 : 20 group members were trained on Poultry keeping | Identification of trainees | * | List of Trainees identified |
|  |  | Conducting one day workshop on poultry keeping | Facilitator, Stationary, Allowance | List of trainees participated |
| 2. Acquiring an office and a building for poultry keeping by April 2015 | 2.1. Office rented | 2.1.1 Fund raising for finding fund for Office rent | Funds | Contract signed, Receipt of Payment |
|  |  | 2.1.2 Contract signing for office rent | Signatories | Signed contract |
|  | 2.2. Poultry building rented with seven square meter | 2.2.1 Solicit fund for renting a Building for poultry keeping | Funds | Funds raised |
|  |  | 2.2.2 Contract signing for renting a Building for poultry keeping | Signatories | Signed Contract |
| 3. Undertake production of the first batch of seven days old chicks by Jun 2015 | 3.1. One batch of four hundred chicks were bought | 3.1.1 To identify good quality chicks | Extension Officer | Chicks identified |
|  |  | 3.1.2 Purchase of chicks | Funds, Extension Officer | Chicks purchased |
|  | 3.2. Twenty bags of Chicks’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chicks | Extension Officer, Funds | Feeds Identified |
|  |  | 3.2.2 To purchase chicken feeds | Extension Officer, Group members, Funds | Purchased Feeds, Payment receipts |
|  | 3.3 Poultry brooders, heaters, feeders and troughs equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Extension Officer | Identified equipments |
|  |  | 3.3.2 To purchase the equipments | Extension Officer, Agape group members, Fund | Equipments purchased in place |
|  | 3.4 One vaccination done to four hundred chicks | 3.4.1 To identity the veterinary expert for vaccination | CV of Extension Officer | Identified extension Officer |
|  |  | 3.4.2 Doing vaccination activity | Extention Officer, Funds, Agape group members | Chicks’ healthy |
| 4. To sale four hundred live chicken to at least two reliable markets by July 2015 | 4.1 Markets were found | 4.1.1 Robbying and Advocacy for Marketing | Agape group members, CED Student | Sales Report |
|  |  | 4.1.2 Transport of live chicken | Funds | Number of live chicken reached market place |
| 5. Registration of the business | 5.1 Constitution prepared | 5.1.1 Agape group members meeting for constitution making. | Funds | Constitution draft in place |
|  |  | 5.1.2 Signing and approval of the constitution | Fund | Constitution in place |
|  | 5.2 Bank account opened | 5.2.1 Meeting to select the Bank | Fund for soft drinks | Bank selected |
|  |  | 5.2.2 Selecting signatories and opening the account | Fund | Members selected as signatories |
|  | 5.3 Received Certificate or Registration | 5.3.1 Facilitation of registration process | Funds | Certificate of Registration |
|  |  | 5.3.2 Paying for registration | Funds | Certificate of Registration |

# 5.4 Project sustainability

Project sustainability is defined as a requirement of our generation to manage the resource base such that the average quality of life that we ensure ourselves can potentially be shared by all future generations…Development is sustainable if it involves a non-decreasing average quality of life (Geir B. Asheim, ’’Sustainability,’’ The World Bank,1994).In order for the project to become sustainable there should be better utilization of resources and opportunities, understanding the interconnections among economy, society and environment and also living or utilizing resources within the limit. A project becomes sustainable when its resources are managed and utilized in the way that ensures successful project completion. For the project to become sustainable there are some principles to be followed and these principles are use limited resources, never exceed available resources and allocate resources strategically.

Use limited resources, the project can be accomplished only if resources are available and enough Agape group members assessed the required amount of resources and compared it to the existing resources base and this will help the Agape group members manage the project in a sustainable manner. The principle states that never exceed available resources. The efforts to achieve effective management will be successful if the use of available resources never exceed the amount of resources necessary for the project completion. You should plan resource consumption in advance and minimize resource wastage. Allocate resources strategically. Agape group members recognized the importance of allocating project resources to only prioritized directions according to the strategy Resources allocation activities should be planned for the long-term perspective and utilized considering stakeholders’ expectation.

Planning sustainability. In order to plan sustainability you need to think of conceptualization of the project, organizing the project team, incorporate standards, minimize waste and communicate project. Conceptualize project, the concept of project has to reflect the probability of successful project accomplishment. If the concept is unrealizable, then the project is likely to be unsuccessful. In order for this project to become sustainable, Agape group members carefully managed the process of project conceptualization to develop a concept that is coherent to available project resources, meets stakeholder’s expectations and fits into their strategy. Organize project team, Project team will be a major project resource. Agape group members identified themselves and organized themselves in order to become the project resource for the aim of the project to become sustainable. Minimizing waste, project beneficiaries planned the use of resources in order to avoid wastage of resources. Incorporate standards and communicate project, group members incorporated their standards in order to fit their expectations and these were all communicated to the project team.

Project sustainability plan, group members prepared a document that described how the project management was going to respond to certain changes, events, emergencies or other factors which would challenge viability and relevance of their project. The plan also was strictly emphasising on the resources to be used. For this project, the resources needed are easily to be attained as Poultry Feeds are many sold at different places in Dar es Salaam, Vaccination medicines are available.

With these steps being taken, it is the hope of the project beneficiaries that their project will be sustainable and the incomes that will be derived from the selling of the project products will increase the households’ income and help to improve the economic and living standards of the project beneficiaries. The project will be sustainable as the market for poultry increases as days go on. The increase in demand gives a room for the project to be sustainable.

Institutional sustainability, due to the fully participation of project stakeholders from project identification, designing, implementation, monitoring and evaluation, this brings the sense of project ownership. Because they feel being the owner of the project they will have strategies to make the project sustainable. They had planned to register their group in order to be legally enforced and become a business entity that keeps poultry for sales. Another plan is to open a Bank account in which the profits will be saved for the future expansion of the project.

Financial sustainability will be achieved due to the reason that the group members planned to volunteer in performing some activities in order to minimize running costs for the project. Some of the project profit derived from sales will be deposited to the Bank account and any withdrawal shall be approved with some group members. This has been done in order to avoid embezzlement of their money. They have planned to have some months without distributing the profits to themselves in order to increase the money for future expansions of the project.

# CHAPTER SIX

# 6.0   CONCLUSION AND RECOMMENDATION

# 6.1 Introduction

This Chapter six gives a summary of all previous Chapters. It explains what was done in the all previous chapters. The chapters gives a brief explanation on how Community Needs Assessment was carried out, Problem Identification, Literature review, Project Implementation, Participatory Monitoring and Evaluation and finally Project Sustainability. Participatory needs assessment was conducted to Mbezi Ward Residents in order to assess the level of income poverty to community members and determine the best intervention in order to make a positive change which is to find the ways on how community members can increase the level of incomes to their households in order to reduce income poverty. Mbezi ward residents do perform livestock keeping such as keeping of Cows, Goats and they do farming like farming tomatoes and other vegetables and some of the residents are doing business. The community needs assessment study was conducted in order to know the economic income gap (income poverty) to community members and find a potential intervention to solve the situation.

Problem identification was done during Community Needs Assessment as many residents of Mbezi who were respondents to the study revealed that they are low income earners hence failure to afford some basic needs like constructing their own Houses or repay for the houses that they got from WAT-HST through Housing Microfinance Loan. Due to low incomes and in affordability of some basic needs, the study with participation of those respondents came up by identifying that the problem was income poverty facing them. After knowing the problem, members ranked potential projects that would generate incomes for them and they came up with Poultry keeping project. Literature review was done in order to get information that would support the project to be viable and sustainable. After Literature review, it was found that Poultry keeping project will be sustainable as there are many information supporting the project like Government support through policy and employing extension staff that support the project. Apart from the Government, the project has been implemented in other countries and became sustainable. Project planning and Implementation was done in order for the group members to achieve their goal which is to increase the incomes to individuals and households level. During planning, monitoring and evaluation was planned and will be carried in order to know if the project will be sustainable and if there are changes to be adjusted in order for the project to achieve its goal. Generally, this chapter six explains briefly on what was done in the previous chapters.

Apart from giving a briefly explanation of what was done in the previous chapters, this chapter also explains on the conclusions and recommendations basing on the project in order to give a room for others who will need to undertake a study like this in the future.

# 6.2 Conclusion

The study was carried effectively at each stage, steps were followed at each stage in order for the project to be identified to be a real project that community members have selected through Pair wise ranking and the project to be executed to become sustainable and attain the planned goal of the community. By carefully conducting of Community Needs Assessment, Problem identification, Literature review and Project Implementation were well planned and executed. Monitoring and Evaluation will also be carried in order for the project team and community to assess if their project will be sustainable in order to start second phase of the project.

The findings from the Participatory Needs Assessment conducted at Mbezi Ward basing on the methods of data collection used, it was found that the respondents’ sex was 27.5% male and 72.5% Female of which 22.5% had age ranging between 18-25 years, 25% had an age ranging from 26-33 years, 35% had an age ranging from 34-41 years, 10% had the ages between 41-48 years and 7.5% had an age ranging from 48-55 years. This finding shows that most of the respondents were youth which is a man power and this can be used for the development of their community and Country at large. The findings show that this community had many occupations and the respondents had different occupations as 7.5% are Farmers, 62.5% are Business men and female, 7.5% were saloonists, 2.5% were Teachers, 5.0% were Bar maids, 2.5% were petty traders and 12.5% were Tailors. Although the community members had occupations, their incomes were low hence income poverty. This data was taken from the forty respondents out of sixty planned sample of respondents. Education level of the community ranges from primary school to University and they revealed the project will be viable and sustainable due to the increase in demand and this will decrease dependency by creating new direct and indirect jobs due to the presence of the project. The study found that the community needs to be trained on skills and knowledge for the project in order to avoid risks.

The study found that poultry keeping is being done at different places like in rural and urban, and at different countries. Poultry keeping is done by both rural and urban dwellers as poultry contributes for household incomes which leads for the families to meet their social obligations, increasing food supply and nutrition to household members by either eating the meat or eggs from poultry. According to Kiman, (2006) and FAO, (2007). Chickens are kept due to their importance like being the source of food, nutrition, income, eggs, poultry manure for use as organic manure, source of foreign exchange to the country through exports of poultry products. Chickens keeping is done in different countries like Malawi, Tanzania, Bangladesh and others. Although poultry keeping is beneficial as it increases income, nutrition and is environmental friend, the production faces constraints like diseases and parasites, poor feeds supply, limited to financial credit access, high prices in inputs, insufficient of marketing strategies, low management skills. All these contribute to low productivity and in order to increase productivity there is a need for stakeholder to give support on the mentioned issues.

The reason for the Poultry keeping project to be selected was due to the reasons that Agape group members had ranked their potential projects and this became the project with more scores which means it was the first and selected to be executed. Second, the project is easy to establish as it is not more expensive as it does not need more capital for investment. Third, after the project becoming successful, Agape group members will have their own poultry building in place in order to avoid paying rent of which in future they will only be inquiring the costs for purchase of chicks, feeds and medicine which will obviously be cheaper compared to other ranked project.

The objectives like Capacity building was achieved as the identification of trainees was done and twenty trainees attended a one day workshop on Poultry keeping. Acquiring an Office and building for poultry keeping was achieved as funds were raised and the group achieved to rent an Office and building for poultry. Project Management objective was not achieved because the time for executions was not ready hence Batch of Chicks, Chicks’ Feeds, Equipments for the Poultry keeping will be purchased later and Vaccination and Supervision will also be done later. Other objectives like Collaboration with other partners and Registration of the business will also be conducted later.

Participatory monitoring, evaluation and sustainability plans were developed and used as was planned. Relevant matrixes against Objectives, Outputs and Activities were developed for Project Monitoring and Evaluation. Monitoring plan was also established and it shows Project Performance Indicators, Sources of Data, how and when the data will be collected and the responsible persons to collect the information. Foe evaluation, also performance indicators against the objectives, outputs and Activities were developed. Two Objectives were monitored and evaluated and were achieved at a hundred percent. Other objectives will be monitored and evaluated when their implementation time starts.

If the group members had their own funds to start the project, the project could be implemented before March and April could be the time for sales of the project produced products. As the members had no funds of their own, they had to make arrangements for fund raising to be done and fund raising consumed time that could be done for project executions. Also search for an office and a building for project consumed much time as project team wanted to get a place where security for the project would be high.

Outcomes that may be expected if the project will be  successfully completed are the Community to increase their incomes individually and at household level and by an increase in incomes they can afford basic needs like paying for their House loans and meet other family obligations like paying for children’s school fees, affording foods purchases and clothes. Second outcome is the impact of capacity building to the community. Agape group members will be able to manage poultry keeping projects and can also transfer the knowledge to the other communities. Third outcome is the Registration of their group to become a Business Entity, by becoming a Business entity they will be able to access sources of fund from Banks and other Financial Institutions rather than relying or depending on fund raising which there is no assurance to collect funds. So, in future it is expected that the group will be a Business entity with its members receiving middle or higher incomes.

# 6.3 Recommendation

Researcher recommends for those intending to do studies in this similar project to encourage community participation at every stage. Community participation has a significant or impact on learning. By participatory of each members at every stage gives a room for each participant to gain new knowledge and also transfer his or her knowledge to others. It my belief that each community member has a knowledge whether informal or formal and this knowledge can be of a support to others.

Capacity building has to be given a priority as this study revealed that most of the community members had insufficient knowledge on the project supervisor and management. There is a need for capacity buildings to be done to the communities that want to establish the project like this. Though poultry keeping is been done since previous years, many community members do not have sufficient knowledge on the project. So, empower the communities by doing Trainings, Workshops and Seminars to support them.

The needs for Community Participation, Transparency and Accountability are inevitable for the sustainability of the projects. Give a room for members to participate fully, allow and encourage Transparency in every stage from project identification to implementation and Monitoring and Evaluation. Also insist each person to be accountable for the project. Take measures for the people who make things in a wrong way.

In order for the projects to be effectively and efficiently, project design should be done systematically and each component needed should been accounted for. No any room to exclude things that are supposed to be included because by excluding things you will find difficulties during project implementation. You need to have detailed plan that shows the overall objective, specific objectives, output and activities to be carried out. Show who will do what, when and how and the location and the costs to be incurred.

Researcher recommends for the Literature review to be done effectively by gathering information from many different data/document sources. There are different sources of information like documentaries, journals, books, internet, pamphlets and previous Dissertations. Find detailed information from different sources. With sufficient sources of information, planning will be easily and implementation hence sustainability.

# REFERENCES

Beutler,  A.  2007: Introduction to Poultry Production in Saskatchewan, University of Saskatchewan, Saskatoon, Saskatchewan, S7N5A8. http://www .agriculture. gov.sk.ca/ Introduction_Poultry_Production_Saskatchewan Accessed: November 18, 2009 Extension Poultry, from: http://www.mdchick.umd.edu

Jacob,  J. P., Butcher, G. D., and Mather, F. B. 1998. Vaccination of Small Poultry Flocks,

Kimani, C. W (2006); Improving farmyard poultry production in Africa. Socio-economics and Policy Research Working Paper 32. ILRI (International Livestock Research Institute), Nairobi, Kenya.

Minga, U. M., Katule, A., Yongolo, M., and Mwanjala, T. (1996); The rural chicken industry in Tanzania

Rhodes, J. L., J Timmons, Nottingham, J .R. and Musser, W.: 2008. Broiler Production  Management for Potential and Existing Growers, University of Maryland Cooperative

Sonaiya, E. B. (1990); toward sustainable poultry production in Africa. In: Paper presented at the FAO expert consultation on strategies for sustainable animal agriculture in developing countries, Rome, Italy.

Sonaiya, E.  B. 1993. Evaluation of non-conventional feed ingredients as supplements for scavenging chickens. In Proceedings, 7th World Conference on Animal Production, Edmonton, Alberta, Canada, p. 28–29.

Sonaiya,  E.  B. and  Swan, S. E. J. (2000); Small-scale poultry production, technical guide manual. FAO Animal Production and Health 1. Food and Agriculture Organization of the United Nations (FAO), Rome. University of Florida, Gainesville, 32611.

Yongolo, M.. G. S., Minga U.M., Katule A.M., Mtambo M.M.A. Mutayoba S.K.., Mdegela R.H and Lawrence P. (1998);Effect of Newcastle Disease on Population and Economic impact to scavenging village chicken in Msolwa Village in Morogoro Region Tanzania.

Yongolo, M..G..S. 1996. Epidemiology of Newcastle disease in village chickens in Tanzania. PhD dissertation, Sokoine University of Agriculture, Morogoro, United Republic of Tanzania

# APPENDICES

APPENDIX - 1   STRUCTURED QUESTIONNAIRE FOR COMMUNITY MEMBERS

Dear respondent, the questionnaire below intends to collect or gather some information from you. Please be free to give the required information and information provided will be kept confidential. Your views will be of great importance and hence contribute to community development.

Tick where appropriate and fill the information where required.

1.   Respondents Personnel Particulars

1.1   Sex:	a) Male     (     )        b) Female         (      )

1.2   Age:    a) 18-25    (     )        b) 26-35            (      )    c) 36-45   (    )

d) 46-55     (     )       e) 56-and above (     )

2. Respondent’s level of Education:

01) None                                                               (     )

02) Primary Education                                          (     )

03) Secondary Education                                      (     )

04)   University                                                     (     )

05) Above                                                            (     )

3. Occupation of respondent

01) Farmer                                                                  (     )

02) Teachers                                                                (     )

03) Local Leaders                                                       (     )

04) Business/Traders                                                  (     )

05) Technicians                                                         (     )

06) Doctors                                                                 (     )

07) Others …………………………………………………………………………

4.   What is an average or monthly income of the community members?

01) Tzs.  5000-10,000    (       )     02) Tzs. 15,000-30,000     (       )      03) Tzs.35, 000-50,000 (      )

04) Tzs.55000-100,000 (       )     05) Tzs. 200,000-500,000 (       )      06) 550,000-1,000,000   (      )

5. Economic Assessment

2. 1 what are the major economic activities in the community?

01) Food vendor       (    )	 02) Tailoring           (     )    	03) Hot culture              (    )

04) Food processing (    )        05) Boutique maker (     )	06) Animal husbandry   (    )

07) Pharmacy           (    )       08) Food cafe            (     )	09) Saloon/Barber shop (    )

6. What kind of project/business do you think is potentially, sustainable and economically viable?

01) Agricultural activities (     )    02) Animal Husbandry    (     )

03) Garbage collection      (     )

04) Saloon/Barbershop     (     )    5) Food processing      (     )   06) Food vendors     (     )

07) Food cafe                   (     ) 08) Tailoring                (      )    09) Poultry keeping  (     )

7. Can the business in number six (6) operate throughout the year?

01) Yes   (     ) 		02)  No   (       )

8. What will be the impact of that project?

Please, cycle the appropriate score using the following scale

1=First class     2=Second class   3=Third class

1. Increase in of individual income                   1              2            3

2. Decrease of dependence                               1              2            3

3. Creation of employment                               1              2            3

9. What challenges do you think you may face in implementing the proposed project?

01) Inadequate capital (    )        02) Unreliable Market (    )    03) Lack of technical skills

04) Disease                  (    )

10. Do you think the project will decrease dependency in the community?

i) Yes (    )          ii) No   (     )

11. How many people do you think the project will create a job for them?

a) 10-25     (    )    b) 25-50    (    )       c) 50-75    (     )      d) 75-100    (     )

12. Does the government/private institutions provide support to income generating activities in the community?

01) Yes (    )		 2) No (     ) 		03) I don’t know (     )

13. If yes what kind of support do they get?

01) Financial support        (    )   02) Entrepreneurship skills (     )

03) Tools and equipments (    )   04) No Support                   (    )

05) Other Support             (     )

APPENDIX – 2 INTERVIEW GUIDE FOR FOCUS GROUP DISCUSSIONS WITH CBO

Date of Interview     ___/___/___	Place of Interview ________________

Name of Moderator of Focus Group Discussion: ________________________________

Name of the CBO: _______________________________________________________

- How many members of VICOBA are male and female? a)Male_____ b)Female___

- When did VICOBA start? (Year)……………….

- Is the CBO registered?

- Who financed the CBO during the take-off?

- What is the overall goal?

- What are the income activities being undertaken?

- Are the income generating activities generate profit? i)Yes (   )  ii) No (   )

- Do you think the income from the established project will be beneficial to the members?.......................

- What are the other potential economic projects in the community?.........................

- What are the challenges facing the project?............................................................

- Have the CBO members received any training on business under takings or technical knowledge related to the group activities?..........................................

- How have the members benefited from the group income activities?..................................................

- What kind of support has CBO received from the Government/any other development institution?............................................................................................

- What should be done to improve the group economic performance?.............................................................................................................

APPENDIX – 3 INTERVIEW GUIDE TO GOVERNMENT OFFICIALS

Date of Interview _____/___/____ 		Place of Interview_______________

- Is there any program that support poultry keeping projects? .....................

- If yes, what kind of support? …………………………………………….

- How many CBO’s are dealing with income generating activities in this community?

- Does Government have any policy that support poultry keeping project?

- What challenges facing poultry keeping in the community?

- How does the Government support the project to be sustainable?

- Suggest measures to support the project to become sustainable

a)………………………………………………….

b)………………………………………………….

c)…………………………………………………

APPENDIX-4 APLICATION LETTER TO CBO

C/O The Open University of Tanzania,

P.O. Box 23409,

Dar es Salaam,

15/11/2014.

Mwenyekiti wa VICOBA Makazi

S. L P

Mbezi,

Dar es Salaam.

Salaam,

YAH: MAOMBI YA KUKUTANA NA WANACHAMA WA VICOBA MAKAZI

Mada ya hapo juu ya husika,

Kwa barua hii nawasilisha maombi rasmi ya kukutana na wanachama wote wa VICOBA Makazi.

Azimio la kukutana ni kupata fursa ya kujadiliana na kubadilishana mawazo katika suala zima la kuleta maendeleo ya kiuchumi miongoni mwa wanachama na jamii kwa ujumla.

Majadiliano yanatarajiwa kutumia muda wa saa moja na nusu na hii itategemea ushiriki wenu ikiwa ni pamoja na kujali muda.Majadiliano hayo yanatarajia kuleta matokeo ambayo yatasaidia kuimarisha au kuibua namna ya kupata ufumbuzi wa masuala ya kiuchumi na changamoto zinazojitokeza katika maisha ya wanachama.

Iwapo ombi langu litakubaliwa naomba kupangiwa siku, saa na mahali pa kukutania.

Natanguliza shukurani zangu za dhati

Baraka Deus Sekagoma

Mwanafunzi wa chuo kikuu Huria-Kituo cha Dar es Salaam Makao makuu

Kitivo cha uchumi na maendeleo ya Jamii.

APPENDIX- 5: REPLY OF LETTER FROM CBO

VICOBA Makazi,

S.L.P                 ,

Dar es Salaam,

21/11/2014.

Bw.Baraka Sekagoma,

K.K Chuo Kikuu Huria,

S. L P 23409,

Dar es Salaam.

Ndugu,

YAH: OMBI LAKO LA KUKUTANA NA WANACHAMA WA VICOBA MAKAZI

Mada ya hapo juuu ya husika,

Kwa barua hii napenda kukufahamisha kuwa maombi yako ya kukutana na wanachama wote wa VICOBA Makazi yamekubaliwa.

Kutokana na azimio uliloandika la kukutana kuwa ni kupata fursa ya kujadiliana na kubadilishana mawazo katika suala zima la kuleta maendeleo ya kiuchumi miongoni mwa wanachama na jamii kwa ujumla, Uongozi umeafiki kukupa nafasi ya kukutana na wanachama.

Unaombwa kufika ofisini uonane na Mratibu ili kupanga ratiba na jinsi ya kukutana mara upatapo barua hii. Natanguliza shukurani zangu za dhati na pia kwa niaba ya wanachama.

Mwadawa Said Selemani

Mratibu VICOBA Makazi

.

# Text boxes

CHAIRPERSON

SECRETARY

TREASURYTREASURER

DISCIPLINE

KEY HOLDER

CASHIER 1

CASHIER 2

Table 16   :   Project Implementation plan