IMPROVING LIVELIHOOD OF MALE YOUTH COMMUNITY THROUGH SAND HARVESTING PROJECT AT KIMARA B SUBWARD, SARANGA WARD IN UBUNGO DISTRICT

MOHAMED BESTA

A PROJECT REPORT SUBMITTED IN PARTIAL FULFILMENT OF THE REQUIREMENT FOR THE DEGREE OF MASTERS OF COMMUNITY ECONOMIC DEVELOPMENT OF THE OPEN UNIVERSITY OF TANZANIA

2017

# CERTIFICATION

The undersigned certifies that she has read and hereby recommends for acceptance by the Open University of Tanzania (OUT), a project entitled; “Improving Livelihood of Male Youth Community through Sand Harvesting at Kimara B Sub-ward, Saranga Ward in Ubungo District”, in partial fulfilment for the degree of Master in Community Economic Development degree of The Open University of Tanzania.

...........................................................

Dr. Harrieth G. Mtae

...................................................

Date

# COPYRIGHT

No part of this project report may be reproduced, stored in any retrieval system, or transmitted in any form by any means, electronic, mechanical, photocopying, recording or otherwise without prior written permission of the author or The Open University of Tanzania in that behalf.

# DECLARATION

I, Mohamed Besta, do hereby certify that this project report is my own original work, and that it has not been presented to any other institution and will not be presented to any other institution other than The Open University of Tanzania.

…………………………………….

Signature

............................................................

Date

# DEDICATION

With great affection I dedicate this achievement of completion of Master in Community Economic Development (MCED) to my late father, Mr. Besta Mohamed Besta and my mother, Mrs Halima Rajabu Besta for their righteous upbringing, love, and support I have had from them throughout my lifetime. My warmest thanks goes to my wife Mrs Abella Rutashobya Besta for steadfastly standing by me over the period when I have been excessively pre-occupied with the obligations of pursuing Master in Community Economic Development. Also, my special thanks goes to my wonderful children, Sekera, Junior and Karya who have been my inspiration to finalize this project report and being a reason for audacity to undertake academic life.

# ACKNOWLEDGEMENT

I would like to expressly extend my heartfelt appreciation to Dr. Harrieth Mtae for her tireless encouragement and immense guidance throughout the period of the course and whenever I needed her intervention for this project work and other related academic matters.   Her incessant mentorship in this endeavor has been enormously influential in realizing the milestones from course works during trimesters, face to face sessions to finalization of this project.  Furthermore, my earnest gratitude is also extended to Mr Timothy Lyanga and Dr. Hamidu Shungu for their expert advice to join and pursue Master of Community Economic Development (MCED).  It was a worthwhile excellent academic trail that was never before and has bequeathed upon me with vast opportunities and developed intimacy with colleagues and lecturers at the University alike.

I also express my sincere appreciation to Mr Allen Kalongola (Senior Community Development Officer) of Ubungo Municipality, Rose Mpeleta (Community Development Officer – Mbezi Louis) and the entire staff at Ubungo Municipal Council for their effective co-operation in conducting Community Needs Assessment and assistance in implementing the project. My sincere thanks goes also to Mrs Jane Haule Kinunda (Kimara B Subward Executive Officer - CCM) for her assistance and participating in engaging the target community group to work together to this end. I, am greatly indebted to all other stakeholders particularly the youth community at Kimara B for their willingness to be nucleus to this achievement.

# ABSTRACT

This project report culminates from the community-based research study that was conducted at Kimara B Subward (Mtaa), Saranga Ward in Ubungo Municipality, Dar es salaam region. The community needs assessment (CNA) commenced in May 2017 with a view to undertake a participatory action research based on CED principles.  During the needs assessment process, the research design was formulated and data collection methods were identified and implemented that befits the research objectives and related questions.   From the CNA, the researcher has established that the male youth community was desirous to be engaged in at least five economic activities with varying degree of community preference and needs.  Subsequently, a project was perceived by the researcher and various key and secondary stakeholders were also identified for necessary incorporation and implementation of activities on the basis of participatory action research. The necessary consultations with the stakeholders were key to ensuring that the Project Implementation Plans (PIP) and funding are conducted based on principles of sustainability for the identified male youth beneficiaries. It was concluded that the communities can sustainably exploit available natural resources for income generation if there is participatory implementation planning and consideration of the cross cutting issues of the development paradigms towards the project and thereby aiding in alleviating poverty and improving wellbeing of the community. From the foregoing, the researcher recommended that that bold inclusive actions must be taken by involving all stakeholders to ensure equitable use of resources and sustainable implementation of the community economic development project.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENT	vi

ABSTRACT	vii

TABLE OF CONTENTS	viii

LIST OF TABLES	xiii

LIST OF FIGURES	xiv

LIST OF ABBREVIATIONS AND ACRONYMS	xvi

CHAPTER ONE	1

1.0 PARTICIPATORY NEEDS ASSESSMENT	1

1.1 	Introduction	1

1.2		Community Profile	1

1.2.1 	Demographic Data	3

1.2.2 	Administrative Setting	3

1.2.3 	Social Economic Activities	4

1.2.5 	Urban Agriculture	4

1.2.4 	Health Services	5

1.3		Community Needs Assessment	6

1.3.1 	Objective of the Community Needs Assessment	8

1.3.1.1 	Overall Objective	8

1.3.1.1 	Specific Objectives	9

1.3.1.2 	Research Questions	9

1.3.3 	Research Methodology	10

1.3.3.1 	Research Design	10

1.3.3.2 	Sampling Techniques	10

1.3.3.3 	Data Collection Methods	11

1.4	CNA Findings	14

1.4.1 		Findings on Social and Demographic Elements	15

1.4.2 	Findings on Economic Needs and Sustainability Elements	21

1.4.2 	Findings from Qualitative Data Analysis	29

1.5		Community Need Prioritization	32

1.6		Conclusion	34

CHAPTER TWO	36

2.0 PROBLEM IDENTIFICATION	36

2.1 	Background of Research Problem	36

2.2 	Problem Statement	38

2.3 	Project Description	39

2.3.1 	Target Community	41

2.3.2 	Stakeholders	42

2.3.3 	Project Goals in CED Terms	44

2.3.3 	Project Objectives	44

2.4 	Host Organization Profile	45

2.4.1 	Host Organization Leadership	46

2.4.3 	Host Organization Mission	48

CHAPTER THREE	49

3.0 LITERATURE REVIEW	49

3.1 	Introduction	49

3.2 	Theoretical literature	49

3.2.1 	Definition of Sand	49

3.2.1 	Sand as Constituent Construction Material	50

3.2.2 	Sources of Sand as a natural Resource	52

3.2.3 	Sand Budget	52

3.3 	Empirical Literature	53

3.4 	Policy Review	56

3.5 	Literature Review Summary	59

CHAPTER FOUR	61

4.0 PROJECT IMPLEMENTATION	61

4.1 	Introduction	61

4.2		Products and Outputs	63

4.2.1 	Project Outputs	63

4.2.2		Project Products	65

4.3		Project Planning	65

4.3.1		Implementation Plan	66

4.3.2		Inputs	72

4.3.3		Staffing Pattern	74

4.3.4		Project budget	75

4.4		Project Implementation	79

4.4.1		Project Implementation Report	79

CHAPTER FIVE	86

5.0 PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	86

5.1	Introduction	86

5.2	Participatory Monitoring	86

5.2.1	Monitoring Information System	87

5.2.2	Participatory Monitoring Method	90

5.3	Participatory Evaluation	93

5.3.1	Performance Indicators	94

5.3.2	Participatory Evaluation Methods	97

5.3.3	Participatory Evaluation Summary	98

5.4	Project Sustainability	101

5.4.1	Links Between the Project and National or Regional Activities	101

5.4.2	Links Between the Project and Key Stakeholder Priorities	102

5.4.3	Financial and Economic Conditions of the Project	102

5.4.4	Choice of Technology for the Project	102

5.4.5	Participation and Local Ownership	103

5.4.6	Environmental Conservation and Climate Change Adaptation	103

5.4.7	Financial Factor for the Project	104

5.4.8	Political Factor for the Project	104

CHAPTER SIX	106

6.0 CONCLUSION AND RECOMMENDATIONS	106

6.1 Introduction	106

6.2	Conclusion	106

6.3	Recommendations	110

6.3.1	Recommendation on the Participatory Assessments	110

6.3.2	Recommendations on the Project Design and Implementation	111

6.3.3	Recommendations on the Literature Review	113

6.3.4	Recommendations on the Monitoring, Evaluation  and                              Sustainability	114

6.3.5	Recommendations on Policy-Making on Youth Economic                         Development	114

REFERENCES	116

APPENDICES	118

# LIST OF TABLES

Table 1.1: Health Services Facilities	5

Table 2.1: Stakeholders Participatory Analysis	43

Table 4.1: Planned Project Activities and Expected Outputs	64

Table 4.2: Project Implementation Plan	66

Table 4.3: Project Logical Framework for the Sand Harvesting at Kimara B	69

Table 4.4: Project Inputs	72

Table 4.5: Project Staffing Pattern	75

Table 4.6: Project Budget	76

Table 5.1: Project Monitoring Information System for Sand Mining and                  Harvesting Project	88

Table 5.2: Participatory Monitoring Plan	91

Table 5.3: Project Performance Indicators	95

Table 5.4: Participatory Evaluation Summary	98

Table 6.1: Intrinsic Project Attributes and Researcher’s Action for Project Implementation	111

# LIST OF FIGURES

Figure 1.1: Locality Map of Ubungo District and Wards 	2

Figure 1.2: Marital Status of the Respondents	16

Figure 1.3: Age of Respondents	17

Figure 1.4: Education Level of Respondents	18

Figure 1.5: Number of Dependants for the Respondents	19

Figure 1.6:  Monthly Incomes of Respondents	20

Figure 1.7:  Status of Employment	21

Figure 1.8:  Causes of Social Economic Problem in the community	22

Figure 1.9:  Causes of Social Economic Problem in the community	23

Figure 1.10:  Social Economic Impact on Exploitation of Natural Resources	24

Figure 1.11: Accessibility to Natural Resources for Economic Prosperity	25

Figure 1.12: Awareness on Environmental Protection Issues	26

Figure 1.13: Awareness on Occupational Health and Safety Issues	27

Figure 1.14: Commitment Towards Sustainable Exploitation of Natural                   Resources	28

Figure 1.15: Opinion of the Community on the Training Needs	29

Figure 2.1: Organisation Structure	47

Figure 4.1: Youth Leader Mr. Cyprian Kayombo Providing His View                           Among The Participant Community In Meeting Forum 1	83

Figure 4.2: Youth Leader Demonstrating Objectives for Their Project In                            Flip Chart	83

Figure 4.3: Change Agent and Youth Leader Taking Lead In Completion Of                     Question In Meeting Forum 1	83

Figure 4.4: A section of youth at identified location for sand harvesting	83

Figure 4.5: Youth Leader Mr Kayombo at site with the youth community	83

Figure 4.6:  A stockpile of Harvested Sand at site awaiting trucking services	83

Figure 4.7:  Youth Leader Offering Assistance for Completing	84

Figure 4.8:  Change Agent Discussion on the Progress for the Project Implementation During Meeting Forum 3	84

Figure 4.9: Change Agent, Youth Leader and Youth Community Discussing                      on Project Implementation during Meeting Forum 3	84

Figure 4.10: Project Implementation Gantt Chart	85

# LIST OF ABBREVIATIONS AND ACRONYMS

CDO		Community Development Officer

CED		Community Economic Development

CAN		Community Need Assessment

COP		Conference of Parties

DED		District Executive Director

EIS		Evaluation Information System

HSE		Health, Safety and Environment

MCDGC	Ministry of Community Development Gender and Children

MCED		Masters of Community Economic Development

MEO		Sub-ward (Mtaa) Executive Officer

MIS		Monitoring Information System

NYDP		National Youth Development Policy

NSGRP	National Strategy for Growth and Reduction of Poverty

OUT		Open University of Tanzania

PIP		Project Implementation Plan

PNA		Participatory Needs Assessment

PRA		Participatory Rural Appraisal

SDG		Sustainable Development Goals

SARAR  	Self-esteem, Associative strengths, Resourcefulness, Action planning, Responsibility

SPSS	Statistical Package of Social Science

TFNC	Tanzania Food and Nutrition Centre

TCDP	Tanzania Community Development Policy

TZS	Tanzania Shillings

UN		United Nations

USD		United State Dollar

WEO		Ward Executive officer

WADC	Ward Development Committee

WAO		Ward Agriculture officer,

WNRO	Ward Natural Resource officer

WHSEO	Ward Health, Safety and Environment Officer

WEO		Ward Executive Officer

# CHAPTER ONE

# 1.0 PARTICIPATORY NEEDS ASSESSMENT

# 1.1 Introduction

Kimara B is a locality in Ubungo District located in the Western side of the Dar es Salaam Region in the United Republic of Tanzania. The locality is characterized by a multitude of demographic and economic profiles ranging from families, individuals and groups of households engaged in informal sector and formal sector activities. According to the Saranga Ward local leaders, the Kimara B settlements resulted from a natural dynamics of city growths (i.e. spatial interaction and ethnographic influence) and increase in the need for housing and related economic activities and therefore the Temboni settlement area is a result to that dynamics in growing socio economic and demographic demands which was caused and mobilized by inadequate strategy by the government and local authorities for planned settlements and housing schemes to respond to population and economic growth.

In this project, focus is placed on the male youth community aged between 18 to 35 years of age residing at Kimara B, Ubungo District in  Dar es salaam. More importantly, the youth community was adequately positioned to take actions in adaptation with the principles environmental protection based on the existing regulatory framework and national policies on utilization of the natural resources.

  - Community Profile

Kimara B is a growing settlement for various income level communities at is situated Saranga Ward of the Ubungo Municipal Council in Dar es salaam being among  the  four  districts  in  the  Dar es salaam  Region  of  Tanzania. The Kimara B locality is situated at representative reference coordinates of S 6° 47′ S and E 39° 08′ E.   It covers an area of approximately 34 square km which is equivalent to 7% of total area of the Ubungo Municipal Council.  The recently established Ubungo District in Dar es salaam region has resulted in the formation of Ubungo Municipal Council administrative statute under the local government structure. (Ubungo Municipal Council, Council Profile Document, 2016)

# Figure 1.1: Locality Map of Ubungo District and Wards (Saranga Ward)

# 1.2.1 Demographic Data

Generally, according to geospacial data sourced from National Bureau of Statistics (2012), the Saranga Ward   is estimated to be inhabited by population of 104,127 (year 2012) people.  According to World Bank Group study, it is estimated that the annual population growth rate is estimated to be 3% which projects a population of 127,035 people by the end of year 2016. Figure 1.1 shows the statistical and graphical estimate of population growth in Tanzania by the National Bureau of Statistics and World Bank Group.

# 1.2.2 Administrative Setting

The Ubungo Municipal Council is divided into fourteen (14) wards, which in turn are sub divided into sub wards commonly known as “Mtaa” (singular) or “Mitaa” (plural). There are 91 Mitaa.  The Municipality also has 2 electoral constituencies namely: Ubungo and Kibamba. The Municipal governing body is the comprehensive  Council which comprises 14 Councilors who are elected Ward representatives, 2 are Members of Parliament elected constituencies representatives (MPs), while Members of Parliament(MPs) (women special seats) and  Presidential Appointees are not yet distributed.

The Municipality executes its administrative duties through:

- The Municipal Council,

- Ward Development Committees under the Chairmanship of the Councilor and

- Sub-Ward (Mitaa) Development Committees

These administrative responsibilities have resulted in identifying and establishing key high level administrative stakeholders who shall ensure participatory implementation and sustainability of project at the hand over phase to the Ward Development Committee and Department of Community Development and Social Welfare of the Ubungo Municipal Council.

# 1.2.3 Social Economic Activities

It was estimated that Ubungo District has a population of 1,031,349, among of those 701,317 are manpower while the remainders are elders and children estimated at a population of 20,626 and 309,404 respectively. In the manpower group, 61% are engaged in private sector, 35% are self employed and 4% are employed in public sector. The activities engaged are private companies, institutions, business, petty traders, fishing, livestock keeping and agricultural activities. The Kimara B locality is composed of the following demographic, ethnic and socio economy structure;

- the informal private sector businesses engaged in selling building materials, and transportation business dominated by Chaga societies,

- retail and wholesale shops dominated by various tribe mixes but largely Chaga communities and groceries and liquor stores and social places and

- formal sector employees working with various government and non-governmental organizations.

# 1.2.5 Urban Agriculture

It is estimated that about 1,850 (Ha) of land in the Municipality is potential for agricultural practices especially crop cultivation, though the estimate is rapidly decreasing due to rapid expansion of urban related activities. The land are under use for both cash crops and food crops is estimated 174.94(Ha); which is 9.45% of the total available area for agricultural practices. Small growers are engage in farming using inferior farming equipment and technology. Quite a few numbers of farmers use tractors and technologically advanced equipment. It is estimated that agricultural activities provides the Municipality with 1,007.54 tonnes of food crops, which is only 0.65% of the total annual food requirement of the population.

# 1.2.4 Health Services

The Ubungo district council is responsible for providing health services to its community in collaboration with private sector service providers. The Council currently has a total of 68 health facilities of which 17 are government owned, while the remaining 51 are owned by Private Organizations. The Sinza and BOCHI Hospitals are the only hospitals owned by the government and private organizations respectively for providing health services within the Municipal. This hospital is called a district hospital which is providing services for 1,000 to 1,500 in and out patients per day. All the health facilities provides cure, preventions of communicable and non communicable diseases.  A Table 1 below shows a list of health facilities available in Ubungo Municipal Council.

# Table 1.1: Health Services Facilities

| HEALTH FACILITY LEVEL | GOVERNMENT | PRIVATE | TOTAL |
| --- | --- | --- | --- |
| Hospital | 2 | 4 | 5 |
| Health Centres | 0 | 6 | 6 |
| Dispensaries | 16 | 41 | 57 |
| Total | 17 | 51 | 68 |

Source: researcher, 2017

  - Community Needs Assessment

Community Needs Assessment (CNA) is in principle a participatory action research (PAR) methodology. It is an approach to research in communities that emphasizes participation and action in solving community needs for improving livelihood. It seeks to understand the world by trying to change it, collaboratively and following reflection and contribution from the community in question. The CNA emphasizes collective inquiry and experimentation grounded in experience and social history. In general, a CNA is comprised of four key components including assessment, dissemination, implementation and monitoring and evaluation (Briard, 2013 and Finifter et al., 2005).

The general objective of a CNA is to identify population needs and to describe factors that should be addressed in order to improve the well-being of a given community or population. Information obtained from a CNA assists in gauging and assessing the needs of community members and population groups. In addition, in order to achieve a thorough understanding of the community, the CNA must be a participatory process that engages community members, stakeholders, professionals, and experts.

In the end, the CNA is concluded by drawing conclusion on findings and dissemination of the report and thereafter evaluate assessment’s merit and worth to the community. CNAs typically involve the gathering of pertinent information to draw conclusions, identify priority areas and determine future directions. According to Briard (2013), information should be obtained in the following areas; community description/identification, community weaknesses and areas of need, assessment and prioritization of community needs, community resources and strengths and specific areas of interest for programme development and implementation

This chapter elucidates the community needs assessment (CNA) which was conducted for the Kimara B male youth in relation to improving their economic wellbeing. The community needs assessment was conducted in May 2017 involving the unemployed section youth at Kimara B, Saranga Ward, Kimara B, Ubungo District in Dar es salaam region. In the course of drawing a meaningful CNA, it was generally agreed that the best approach to conducting a CNA is to make it multi-faceted, mixed, and dynamic in nature (Alberti et al., 2014, Finifter et al., 2005, Kazda et al., 2009, Murray and Graham, 1995, Wilkinson and Murray, 1998). There is no one method or technique that surpasses the other. Instead, multiple methods of assessment are used in order to gain the most possible comprehensive overview of community needs. It is best practice to use a mixture of both quantitative and qualitative methods to assess community needs (Murray and Graham, 1995).  According to Finites et al (2005), comprehensive needs assessment comprise of three steps as follows:

Step 1: Identification of gaps in economic opportunity and services and the development of potential strategies to address these gaps. This includes a literature review, collection and analysis of secondary data sources (i.e., census, archival data), surveys of community members and service providers, the conducting of focus groups, and the completion of case studies.

Step 2: Once the initial needs assessment is complete, a process of dissemination is established. This may include a conference to discuss preliminary findings, community forums, presentations and the development of a final report for continual implementation by the stakeholders involving beneficiary group, community based organizations (CBO’s) and hamlet leadership.

Step 3: The implementation of recommended participatory actions for community economic improvement. This step is the ultimate goal of any project to improve quality of life for community members based on their intrinsic needs and solutions.

From the foregoing, it can be described that the chief purpose of conducting the community needs assessment (CNA) is to identify, from participatory action approach, areas of socio economic concerns among the identified youth community and critical aspects of relevance which must be addressed in order to improve economic prosperity among the male youth community whilst taking cognizance of the environmental and regulatory challenges and other limitations. However, it was critically essential that community needs assessment was conducted whilst recognizing the need to understand the prevailing economic improvement and environmental needs of the community from their intrinsic perception of their situation rather than imposing preconceived external solutions onto them by the various agencies or external organizations.

# 1.3.1 Objective of the Community Needs Assessment

# 1.3.1.1 Overall Objective

The overall objective is to determine important community based participatory solutions required to improve increase productivity and household income levels whilst taking responsibility on the sustainable exploitation of natural resources among male youth community at Kimara subward, Saranga Ward, Ubungo Municipal Council.

# 1.3.1.1 Specific Objectives

The specific objective of this study is primarily focused on the following objectives:

- To identify means and ways for improving livelihood of the male youth community in Kimara B;

- To examine the major socio-economic opportunities, challenges and barriers confronted by the youth community;

- To assess the impact of participatory and empowerment strategies on the lives of the male youth at Kimara B.

# 1.3.1.2 Research Questions

In essence, the research questions have evolved in attempt to answer income generation and livelihood issues associated with various informal activities conducted by male youth at Kimara B. The questions are envisaging in obtaining sustainable solutions to social economic aspects of the community while recognizing social environment issues as well. The following are questions towards the identified challenges:

- What are the demographic features and location of Kimara B (Kimara B) community?

- Which means and ways should be explored and implemented for improving livelihood of the male youth community at Kimara B?

- How can the male youth community identify and deal with the major socio-economic opportunities, challenges and barriers in their livelihood?

- What is the impact of the participatory and empowerment strategies on the lives of the male youth at Kimara B?

# 1.3.3 Research Methodology

# 1.3.3.1 Research Design

Research design for this project was intended to facilitate the smooth running of the various research demands, thereby making research as efficient as possible yielding maximal information with minimal exploitation of resources such as time and funds (Research Methodology for Postgraduate Students - OUT Manual). For this project, descriptive research design was adopted which sought to provide accurate description of observations of a subject phenomena based on collected information on and from youth  at the Kimara B community  by using  questionnaires, direct observation and key informant interviews  to identify  possible means and ways of improving income and working environment youth whilst observing the requisite legal, administrative and sustainable exploitation of natural resources  in Ubungo Municipality.

# 1.3.3.2 Sampling Techniques

The sampling techniques involve taking a representative selection of the population and using the data collected for research purposes. In essence, a sample is a representative subgroup of a population which with or without bias can represent a whole array of population under the research processes. In this dissertation non-probabilistic sampling was utilized for the different intentions in achieving statistical inferential parameters, analytical tools and drawing descriptive findings from the study.  A purposive (judgemental) sampling technique has been utilized to obtain and delineate a spectrum of the population characteristics.

1.3.3.2.1 Purposive Sampling

In purposive sampling, the researcher has employed judgment about who to include in the sample frame.  Prior knowledge and research skill has been used in selecting the respondents and elements to be sampled.  It is characteristically non-randomly selected based on a particular feature such as various actors and factors as well. In principle, purposive sampling has been used to collect secondary information and data in most cases and primary data from targeted youth community, officials and organizational or Kimara B Mtaa leadership.

# 1.3.3.3 Data Collection Methods

In this research both secondary and primary data were collected from the relevant sources which are linked to the subject of the study. Distinction was drawn in data collection methods and tools in order to delineate the apparent difference between the two corresponding methods for data collection.

1.2.3.3.1 Secondary Data

Secondary data include information from the national census and other government information archives. One type of secondary data was used by researcher is administrative and regulatory data. This term refers to data that is collected routinely as part of the day-to-day operations of an organization, institution or agency. The secondary data available from Ubungo Municipal Council and its administrative arms at Ward and sub-ward levels was accessed to provide relevant information contributory to this project.

1.3.3.3.2 Primary Data

Primary data originated by the researcher through direct efforts, specifically for the purpose of addressing the research problem.  Primary data is generally a first hand or raw data. Primary data collection was evidenced to be quite expensive as it was sourced directly from the respondents selected through the adopted sampling procedures. Interviews through the guided questionnaires were used in securing and classifying primary data. The primary data collection methods such as questionnaires, direct observations and key informant interviews were extensively and cautiously employed in this project.

1.3.3.3.3 Questionnaire Method

Questionnaires are tools of data collection in which each respondent in this research dissertation were asked to respond to the same set of questions in a predetermined order linked to the specific objectives. The designed questionnaires were appropriately used in soliciting data and information as part of process to conduct the explanatory or descriptive research.

The solicited primary data were solicited through conducting structured questionnaires from the identified respondents who best suits the community for which the study is aimed at. In this method, questions were set and designed such that responses from participants were quantitative in nature and varied in responses. This subtype of questionnaire was useful in collecting primary data from the premeditated and purposively targeted group of  youth and to some extent a section of local authority officers at the Ubungo Municipal Council, Saranga Ward, and Kimara B sub-ward (Serikali ya mtaa) levels.

1.3.3.3.4 Non Participant Observation Methods

Non-participant observation is a typical research method in which case the researcher observes the spontaneous behavior or subject with their knowledge, but without taking an active part in the situation under inquiry. Through the non participant observation method, the primary data was collected by systematically observing behavior of the subject phenomena.  Observations were then systematically recorded, using an observation checklist. The various typical data was analyzed using both quantitative and qualitative data analysis methods.

1.3.3.3.5 Key Informant Interview

Key Informant Interviews involve interviewing people who have particularly informed perspectives on an aspect of the subject dissertation. Key informant interviews are qualitative, in-depth interviews involving respondents selected for their first-hand knowledge about a topic. The interviews were conducted in generally unstructured manner, relying on a list of pre-identified issues during the discussion. Key informant interviews were conducted in form of interactive conversation between the researcher on one hand and the various experts at the Ubungo Municipal Council and ward officers on the other, allowing a free flow of ideas and information either way. Choice of the key informants was made taking cognizance of the prior knowledge of the officers on the subject matter. During the process, the information gathered was carefully noted in a notebook, sifted and analyzed for their relevance in conformance with the study objectives.

1.3.3.4 Data Analysis Methods

The collected data from the sources was organized and coded prior for entering into SPSS 16/20 for analysis. Under the non-parametric analysis; the inferential descriptive statistics and frequencies was consequently derived. In addition, focus group discussion and observatory data methods was employed in creating triangulation for the purpose of validating accuracy and reliability of data collected from questionnaires.

  - CNA Findings

The findings from the CNA in Kimara B youth community are described on the basis on the method, type of data collection and precisely the research design. Through the questionnaire the researcher managed to get information on demographic particulars and general views on various issues regarding community needs, income and productivity related issues and other health, safety and environmental (HSE) related social issues.  In addition, from the focus group discussions with various stakeholders, key informant interviews and non-participant observation the researcher managed to establish a wider knowledge base on the subject matter for which accurate observations and conclusions on the community needs can be derived.

During the field survey, the researcher collated of information using the questionnaire whereby about 35 copies were prepared and only 30 were duly completed through interviewer guided sessions conducted at their various location at Kimara B junction, Temboni Matosa (Mkwajuni) and Matosa Primary School. A semi-structured questionnaire was prepared to purposively cover two main areas of interview which contains social and demographic elements and economic needs and sustainability elements. The content of the first area of the questionnaire is characterized by data on marital status, age, level of education, number of dependants; monthly income and occupational status.  Moreover, the second part of the questionnaire contained elements encompassing economic needs and related health, safety and environmental considerations for sustainable community economic development.

# 1.4.1 Findings on Social and Demographic Elements

The analysis of the survey data based on descriptive research method has resulted in deriving frequency tables, valid percentage values and cumulative distribution of the observed research phenomena.  In analyzing the data, valid percent values was used so that the missing data during the survey are excluded. The designed survey questionnaire has been designed to provide responses that are directly related to the research questions/gap and precisely the research objectives. In this context, the findings have been observed based on the questionnaire as designed in Appendix 1.

Based on the above explanation, the respondents were requested to reveal their marital status. In order to get the information from youth community the change agent solicited such vital information which helps in understanding level of social responsibility and dependence the respondent is assuming at the time of survey. The account of information indicates that 43% and 47% from among 30 respondents from the community are married and not married respectively. This can be interpreted that there is nearly equal proportion of the section of the male youth community who either are married or not married  have wives which would have invariably mean that those who are marred carry higher social responsibilities to provide for their spouses and progeny.  Figure 1.2 shows the descriptive data based on marital status of the respondents.

# Figure 1.2: Marital Status of the Respondents

In addition, respondent were inquired to reveal their age. Such information from the youth community was solicited by the change agent is indispensable delineating age groups which are comparatively highly active than the rest. The data analysis indicates that the greater proportion of youth fall in age group of between 30 to 35 years which exhibits 57% of the respondents. This can be conveniently interpreted that a relatively older age group male youth community dominates and with high degree possibility of having a spouse. On the other hand, about 20% to 23% of the male youth belong to age group 18 – 23 years and 24 – 29 years respectively.   Figure 1.3 shows the descriptive data based on age groups of the respondents.

# Figure 1.3: Age of Respondents

The change agent (researcher) has also endeavored in obtaining data on the distribution on the level of education among the respondents. As can be referred from Chart 3 below, the descriptive statistics indicate that 90% of respondents have only acquired primary education and have no other vocational training. A very small proportion of the respondents’ equivalent to 7% and 3% had achieved a higher secondary and no background of formal education at all respectively. No respondent have attended college or vocational training at all.

This gives a perspective that while creating awareness to community members, the change agent should exert more efforts to ensure that a section of semi illiterate and illiterate respondents are given a relatively wider chance to participate during the presentation and interactive discussion by using Information, Education and Communication (IEC) techniques through Training of programme implementers, community organizing, networking, establishing linkages among stakeholders and media-based promotion. Figure 1.4 illustrates level of education among the respondents

# Figure 1.4: Education Level of Respondents

In addition, the change agent also endeavored in obtaining data on the number of dependants they individually have in their households. As can be referred from Figure 1.5 below, the descriptive statistics indicate that about 43% of respondents had dependants between 3 and 4 followed by 27% of respondents who had dependants between 1 and 2. Further to that, 17% and 13% of the respondents have either greater that 5 or nil dependents respectively. Figure 1.5 below shows the descriptive data based on the number of dependants the respondents had at the period of the survey.

The statistical descriptive analysis was also conducted by the change agent on the estimated monthly income for each of the 30 respondents. As can be seen from Figure 1.5, the descriptive statistics indicate that 80%of the respondents range between 50,000 TZS - 100,000 TZS. This clearly indicates that almost 80% of the youth community earns very little on monthly basis (below 2 USD a day).

# Figure 1.5: Number of Dependants for the Respondents

In addition, a section of 17% of youth community earns between 101,000 TZS and 150,000 TZS per month. There was no youth who declared earning in excess of 300,000 TZS. This earning trend classifies the youth community in the income poverty situation which calls for concerted efforts for social mobilization towards adequate use of the community assets and skills to improve sustainable means of income generation. With such descriptive statistics, it can be justified that the needs of the community points towards the economic issues and therefore on the relatively highest priority hierarchy of needs. Figure 1.6 shows the descriptive data based on the monthly income of the respondents.

The descriptive statistical analysis on the status of employment for each of the respondents was also executed. It can be described from the statistics that 83% of the respondents declared to be apparently unemployed and depends on easily accessible means of livelihood. This clearly indicates that significant proportion of the youth community is virtually unemployed leading to poor earnings as attested in Figure 1.6 above. This explains the fact that the unemployment is one greater social ill and worsens poverty especially among individuals with spouses and progeny.

# Figure 1.6:  Monthly Incomes of Respondents

Besides, it is revealed from the descriptive statistics only about 10 % and 7% are casually employed by truck/block making business owners or self employed respectively. This explains to justify creation and sustenance of comparatively better community institutions, organizing and mobilization strategies to enable youth thrive economically through their self employment or casual employment status. To facilitate this, a holistic approach is requisite to assisting the youth in developing their emotional, mental, physical and spiritual prowess to achieving economic wellbeing through self employment and by sustainably utilizing the available natural resources. Figure 1.7 shows the status of employment

# Figure 1.7:  Status of Employment

# 1.4.2 Findings on Economic Needs and Sustainability Elements

The findings from the descriptive statistics were also derived through set questions to suit the information required among section of male youth community at Kimara B. The setting of questions were made to address the demographic factors and its delineation, research related questions especially regarding  youth  livelihood as well as  their various social needs  for achieving better livelihood among youth in a sustainable manner.

The statistical descriptive information indicate that a sizeable section of the youth community accounting for 63% of the sampled population  agreed that  absence of sources of income generation opportunities is the major causes on their  social insecurity whilst 13 % opined  that poor health quality have effects in their lives.  In addition about 10% and 7% have indicated poor water quality, educational services and environmental degradation have negative impact on their livelihood respectively. Based on the foregoing descriptive information it is apparent that absence of sources of income greatly affect their wish to live prosperous life and followed by far with poor health services in their community.  Figure 1.8 shows the respondents varied view on the major community problems faced by the youth.

# Figure 1.8:  Causes of Social Economic Problem in the community

Additionally, the statistical descriptive information indicate that a large section of the youth community accounting for 54% were of the view that sand harvesting activity is a preferred source of income followed by 20% who opined  that employment in motorcycle taxi services (bodaboda) can have better impact on their livelihood.  In addition about 13% and 10 % indicated vocational training for employment and mason technical auxiliary (Fundi ujenzi msaidizi) would generate better prosperity in lives respectively. Lastly, only 3% considered cultivation of vegetables would be a better means of income for their families. Based on the foregoing descriptive information it is apparent that sand harvesting would generate prosperous life followed by far motorcycling taxi services.  Figure 1.9 shows the respondents varied view on the occupational means for livelihood.

# Figure 1.9:  Causes of Social Economic Problem in the community

Also, further of statistical descriptive information indicate that a sizeable section accounting for 57% of the sampled population agree that exploitation of natural resources  have “high” impact on their economic wellbeing whilst 33% have asserted  that use of natural resources has “average” impact on the social economic wellbeing. On the other hand, about 7% and 3% on the surveyed population have indicated exploitation of natural resources activities have poor and very high impact on their livelihood respectively.

However, based on the foregoing descriptive information on monthly income of the community it can be deduced that those who have opined that use of natural resources have “very high” impact on their social wellbeing probably said so due to inevitable dependence of the accessible natural resources, community assets and resources and may not have alternative economic options at their disposal. Figure 1.10 shows the opinion of the community on the social economic impact (value) on exploitation of natural resources for their livelihood.

# Figure 1.10:  Social Economic Impact on Exploitation of Natural Resources

Further to that, an extensive community participatory research was devoted to establishing the degree and means of accessibility of the available natural resources among the youth communities. The results from the descriptive statistics indicate that 53% of the respondents are considering that accessibility to the natural resource is least favourable which is indicative of apparent concern among the youth on accessibility of the natural resources for income generation needs.

Besides, a proportion of 33% of the community have opined that conditions and environment for accessibility of the natural resources are unfavourable which calls for participatory action to address this situation by creating an enabling environment for accessing the natural resource sites. However, about 7% of the respondents indicated the accessibility is either “favourable” or “fairly favourable” which is seemingly an outlier results based on the statistical distribution on this phenomenon. Figure 1.11 illustrates the opinion of the community on the accessibility to natural resources.

# Figure 1.11: Accessibility to Natural Resources for Economic Prosperity

The change agent also took great deal of impetus in revealing the degree of awareness of protection and protection of the environmental which is an integral factor for consideration when making exploitation of natural resources for economic ends. The results from the descriptive statistics indicate that 40% of the respondents are in possession of “average” knowledge and awareness on the principles and practices for environmental protection and protection.  In addition, a proportion of 33% of the community have opined that they possess relatively poor awareness on environmental issues as an integral element for their means for income generation and livelihood.

However, about 20% of the respondents have indicated to possess high awareness on the environmental protection as a cross-cutting subject. This is a clear indication the 20% section of the respondents can be used to provide “internal awareness” and have demonstrated good leadership in championing sustainable exploitation of natural resource, at community level. Nevertheless, it was observed that the 7% respondents who have poor awareness on environmental protection can be brought to knowledge level by instituting tailor-made training on sustainable use of resources. Figure 1.12 shows the opinion of the community on the environmental protection and protection.

# Figure 1.12: Awareness on Environmental Protection Issues

In the same vein, an aspect on occupational health and safety was consulted among the target community. This was executed in order to secure information on the inherent knowledge among the youth community on health and safety aspect as aspect of relevance associated with the exploitation of natural resources. The descriptive statistics indicate that 43% of the respondents are in possession of “poor” knowledge and awareness on the need for the occupational health and safety. In addition, a proportion of 30% of the community have opined that they possess average awareness on health and safety aspects as an integral element for their day to day livelihood.

However, about 20% of the respondents have indicated to possess high awareness on the environmental protection as a cross-cutting subject. This is a clear indication the 17% section of the respondents with “high” awareness can be used to provide basic awareness on the pertinent occupational health and safety and can also be exposed in championing its importance for longevity and general livelihood of the community. Nevertheless, it was observed that the 10% respondents who have poor awareness on occupational health and safety aspects mining industry can be brought to knowledge level by instituting relevant training and mentorship. Figure 1.13 shows the opinion of the community on the occupational health and safety issues.

# Figure 1.13: Awareness on Occupational Health and Safety Issues

Also, the descriptive statistics were generated and analyzed on the community commitment towards sustainable means for exploitation of natural resources. The descriptive statistics indicate that the majority 83% of the respondents strongly agree to commit themselves towards the concept of sustainable community economic development. In addition, a proportion of 10% of the community have opined that they “agree” that exploitation natural resources should be done based on sustainability principles. However, about 7% of the respondents were not sure probably due to lack of education on the subject matter. However, none of the respondents indicated disagreement with the commitment towards knowledge-based training Figure 1.14 shows the opinion of the community on the occupational health and safety issues.

# Figure 1.14: Commitment Towards Sustainable Exploitation of Natural Resources

In addition, the descriptive statistics were generated and analyzed on the community needs for a range of education and training area to facilitate their livelihood wish. This was executed in order to seek their view on the need to provide knowledge capital through participatory training to ensure sustainable use of scarce natural and diminishing resources. The descriptive statistics indicate that 40% of the respondents would prefer to undergo entrepreneurship training. In addition, a proportion of 23% of the community have opined that training in environmental protection would be ideal for their community. However, only 10% of the respondents preferred training in vocational training for employment and husbandry respectively. Figure 1.15 illustrates opinion of the community on their preferred training needs

# Figure 1.15: Opinion of the Community on the Training Needs

# 1.4.2 Findings from Qualitative Data Analysis

Based on the qualitative data analysis, the change agent conducted extensive bur rather cautious interviews with the various stakeholders and document review relevant to community needs assessment.  Among the tangible methods employed to achieve this included the focus group discussion with the target community, local community leadership and Ubungo Municipal Council who provided indispensable guidance and facilitation to conducting this research.

In collaboration with Kimara B Mtaa leadership the researcher conducted one forum discuss at Kimara B subward (Mtaa) Office located along Morogoro Road in the vicinity of Temboni Bus Station. The forum discussion was fruitful in providing the perception of the community leadership. During the discussion the researcher on several occasions indicated on the need for local Authority to adapt to environmental principles to community economic development especially those related to exploitation of natural resources.  The researcher also conducted interview at block making sites and discuss the challenges they confront when in need of sand as a constituent material for making blocks.

In one instance, on 12 June 2017, at Temboni Matosa area the researcher visited the site with a view to gather explanatory information from the block makers. Mr Muharami, a prominent block maker and supplier was disgruntled by the fact that he has to transport sand from far away sources from Dar es Salaam Region and at relatively exorbitant cost. He asserted that;

“in practice and as I understand from my experience, I have known and used sand transported from natural sources such as river and lakes since childhood and families have benefitted not only from sand mining but rock sites where we obtained aggregates and stones for construction of houses. My father’s house was built by using stones. Also, as a block maker (muuza matofali) and seasoned trader I now find it difficult to transport sand from far away in another region and we are always stranded in long queues of trucks and you may spend a whole day to transport sand far away from Temboni . This makes my business difficult sometimes, especially these days. I generally support the idea that use of natural sources be accepted and may be local leadership and NEMC can assist us on this”

From non-participant observation, the researcher gathered some information on the sociological pattern of the youth involved in sand mining and harvesting. The choice of this qualitative research method was made since the researcher is forming part of the community in question from the geographical point of view. In addition, covert observations have indicated that researcher the sand mining youth is inclined to such an activity as a response of desperate economic needs. By exercising covert observations the researcher managed to build trust and develop empathy with participants. The field notes taken during the visit at sand harvesting sites indicates that the youth community are somewhat semi-illiterate and are ready to resort to other income generation activities which needs menial work such as digging trenches, hauling of blocks, labourers at construction sites, employment as bodaboda riders and others.  However, they have indicated they willingness to comply with the bye-laws associated in order to earn income from the activity.

Furthermore, the researcher conducted asset mapping of the community at Kimara in its entirety in order to identify inherent resources within the study area. It was established that the demographic area possess assets including schools (Kimara B Primary School, Jitihada Primary School and Matosa Primary and Secondary Schools), private health centres and various formal and informal businesses as indicated earlier. However, the youth lack strong community based associations and assistance from non-profit organizations to advance their economic needs and strategizing in business development.

In concussion to the above and based on repeated participatory action  meetings with the  youth community, it is the standpoint of the researcher that the proportion of youth in the community are inclined to  sand harvesting  as means for income generation provided that adequate facilitation and assistance is appropriately made available.

  - Community Need Prioritization

The interactive meeting conducted between the change agent and the focus youth community provided a platform for determining the community priorities. Use of pair-wise prioritization method was adopted as it provides a systematic way to compare various options by comparing the options in pairs. A list of possible options was developed as indicated n Table 2 below. Each item was compared to the other items individually and then the number of times it was chosen was summed to determine its ranking and thereby deducing priorities perceived by the focus group.

It has been established the youth community need is on improved income through adequately facilitated and managed access to the mining sites. The researcher observes that this income generating activity must go hand in hand with indoctrination of the community on environment protection, protection and adaptation and training on occupational health and safety.

Table 1.2: Community Needs Prioritization

|  | Improving Income from Sand Mining and harvesting | Employment on Motorcycle Taxi (Bodaboda) Services | Mason Technical Auxiliary (Fundi Ujenzi) | Vocational Training for Employment | Vegetable (Crop) Husbandry | Score | Rank |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Improving Income from Sand Mining and harvesting |  | 8 | 8 | 4 | 8 | 28 | 1 |
| Employment on Motorcycle taxi (Bodaboda) Services | 0.1 |  | 4 | 1 | 4 | 9 | 2 |
| Mason Technical Auxiliary (Fundi Ujenzi) | 0.1 | 0.2 |  | 1 | 4 | 5.3 | 4 |
| Vocational Training for Employment | 0.2 | 1 | 1 |  | 4 | 6.2 | 3 |
| Vegetable (Crop) Husbandry | 0.1 | 0.2 | 0.2 | 0.2 |  | 0.7 | 5 |

Key

| Score | Description |
| --- | --- |
| 8 | Row is much more important than column |
| 4 | Row is more important than column |
| 1 | Row and column are equally important |
| 0.2 | Row is less important than column |
| 0.1 | Row is much less important than column |

  - Conclusion

The Community Needs Assessment was conducted using the purposive selection of the male youth group in sand mining and harvesting in May 2017. The researcher conducted the necessary data collection and analysis processes in order to determine sustainable and inclusive empowerment action to take in cooperation with the community. For the purpose of this dissertation, the researcher employed the both the primary and secondary data collection methods.

Also, the structured questionnaire was designed to solicit quantitative data collection and analysis whilst key informant interview, covert non-participant and unstructured interviews were conducted at various levels involving stakeholders. In addition, document review was made with the intention to identify the existing community assets that can support the local economy of community Kimara B level.   The researcher also took photographs during interactive meeting sessions and at the sand harvesting sites in order to objectively demonstrate the interaction that existed among the change agent, key beneficiaries and other stakeholders.

The findings from the quantitative and qualitative research indicated that male youth communities are constrained by accessibility of means for of sustainable income. Furthermore, the findings revealed the apparent dependence of the youth group towardssand harvesting from the perennial rivers at various identified locations in Kimara B and Temboni Matosa.  On the other hand, procurement of tools for excavating and harvesting and collecting sand was made by the youth community themselves and this does not involve excessive funding from elsewhere. However, awareness training on management practices, health and safety and environmental (HSE) protection were perceived as integral to the project.   It is anticipated community reflection that the resulting project shall survive and remain relevant for the community as it progresses, due to long term economic benefits.

# CHAPTER TWO

# 2.0 PROBLEM IDENTIFICATION

# 2.1 Background of Research Problem

A section of youth at Kimara B faces stringent means for access to the means of income generation and; it is from this situation that there is pressing need for devising meaningful empowerment strategies in addressing their circumstance through participatory action. The efforts towards this end should be devised whilst taking consideration of the youth community willful inclination to expressing their needs in a manner that gives them first hand, but guided, priority in identifying inherent challenges surrounding their economic wellbeing. If the youth community can expressly reveal their concerns, they can easily reveal, learn, build and exercise strong will from their own reflections on how they can take responsibility and sustained ownership in managing and overcome challenging economic situation in the context of available local assets or natural resources to reduce income poverty and thus achieve sustainable dignified livelihood.

Therefore, it cannot be overemphasized that participatory action with the local community is requisite to attainment of community-desired social economic change as advanced in the National Development Vision, 2025 (2000) and in particular within the  context of the Paris Council of Parties (COP21/22) 17 Sustainable Development Goals (SDGs – Agenda 2030)  which focus on achieving globally sustainable development of the people, planet, prosperity, peace and in partnership (the 5P’s) under the United Nation’s SDG motto “No Country is Left Behind”. In the UN COP21 declaration it was promulgated that conditions for sustainable, inclusive and sustained economic growth, shared prosperity and decent work for all should be attained to address youth income related challenges, among others several global issues.

In achieving this vital in goal, meaningful planning and implementation processes to involve local communities and youth on wealth creation must be propagated and promoted in line with the principles of community participatory action to ensure that communities participate in formulating and implementing collective and consensus-based strategies  to suppress income poverty.

In the same vein, the identification of social ills experienced by the Kimara B youth was executed by utilizing Participatory Needs Assessment approach whilst focusing on the aforementioned national and global goals.  The participatory action has been an indispensable tool which provided for identification of underlying social challenges and enabled execution of planning process for determining most impactful solutions affecting the youth who are demographically representing a wide variety of the Kimara B suburban, multi-ethnic and multi-religious community .

The research has revealed that the multitude of youth communities at Kimara B are engulfed in income poverty which is mobilized mainly by uncertain income sources from various identifiable informal economic platforms. In essence, the ensuing income poverty has constrained and sidelined the majority of the optimistic youth from realizing their dreams in contravention with the Goal 1 of the SDG Agenda on eradicating extreme poverty for all people everywhere globally. In a bid to overcome income poverty, the Kimara B communities have engaged themselves into various informal income generating activities at household level relating to small shop outlets, groceries, saloons, pharmacy, genges, and extracting and selling construction materials among others.

# 2.2 Problem Statement

Income poverty is a major problem among youth living at Kimara B.  Great majorities of youth are informally and insecurely employed or unemployed and rely on shoddy and often irregular day work from construction sites and other unreliable means of income generation.  It is evident that due to informal structure of employment in construction industry, the youth have been attracted to sand harvesting activities either stationing themselves at source or as hired hands in sand trading using trucks owned by the local businessmen or self employed to provide for would be customers. It cannot be overemphasized that sand harvesting for trading is one of the business and experiences direct and indirect interrelation between concepts of utilization of natural resources and environmental protection.

Besides, it is further revealed that a range of opportunities are inherent within the Kimara B community which includes, population growth giving rise to relative broadening of consumerism and domestic market of goods as well as exponential growth of housing needs as a catalyst to increasing demand for construction material to support facilities such as homes, schools and other community assets. Conversely, this trend has also given rise to the inability to access sand sources within short haul distances and consequently higher cost of the material and related regulatory hindrances which should be afforded by the sand harvesting youth community.

On the other hand, sand trading is confronted with certain regulatory barriers at different administrative levels. These barriers have continued to pose income insecurity among the youth as a result of stringent regulations and  penalties on individual unemployed youth. However, the most identical regulatory barrier is mainly at the local community level where civil police (polisi jamii) have been impounding trucks and; in worst case scenarios, arresting, prosecuting and possibly prison the youth at local police posts. This anomaly has largely contributed to the stifling of the youth’s efforts in sand harvesting and trading and exposes their income generating capacity in perpetual uncertainty.

In the final analysis, the youth lives in constant income insecurity and engender discord with the authorities at local and national levels. Eventually, the concerned authorities have the responsibility to bear in terms of conserving the environment and implementing oversight obligation relating to social environment requirements. In the same vein, the authorities are constrained to create an enabling environment for the youth to responsibly and sustainably exploit the sand sources as accessible and potential natural resources while at the same comply with the existing statutes.

# 2.3 Project Description

The project was based on enabling sand harvesting male youth community whose age range between 18 and 35 years old to establishing a reliable access to and from the sand harvesting sites, enhance their income generating means from trading of in-demand construction sand and create customer base whilst in adherence with the existing social, environmental and regulatory mechanism at local and national level.

In essence, the key aspect of the project was to improving community livelihood through improved access to the harvesting sites, increased production quantity of sand and resulting income generation for Kimara B youth within the predetermined age bracket at Saranga Ward in Ubungo District, Dar es Salaam region in the United Republic of Tanzania. It is a known fact that sand is an indispensable constituent material in the production of cement blocks, making of fresh concrete and in particular executing a range of masonry works. Therefore, sourcing of sand must be as convenient, easily accessible by the communities and as cost effective as possible within the jurisdiction of the existing land use and mining statutes. It is from this necessity that sand mining has been and; remain to be, among the major activities that provides employment, formal and informal, to all communities, Kimara B community being among of those.

In the same vein, it has been established that the majority of the youth at Kimara B are unemployed and have insecure means of income as a result of lack of employment in both formal and informal sectors of the economy. Therefore by streamlining community participatory action, the youth in sand harvesting economic activity can manage equitable access to mining sites, generate increased production sand quantities for Kimara B community and realize increased income of individual youth positioning themselves at sand harvesting sources and at point of trading of the commodity.

The project was executed by a small group of sand mining youth under the supervision of the ward leadership (Saranga Ward Executive Office) as the host organization. To ensure sustainability and efficiency the group elected its leadership which served as a link among them, the administrative organs and stakeholders. The project activities were planned to be executed between April and June 2017 and the host organization was beforehand consulted to ensure that draft Project Implementation Plan (PIP) was shared among the stakeholders and Project Activities were timely executed. Noteworthy, the Ubungo District Council administration as the core stakeholder signaled willingness to support the project by providing necessary facilitation such as training, advisory services and possible identification for candidate sites for exploitation of sand within economic haul distances in the Ubungo Municipality

# 2.3.1 Target Community

The target community of this project was male youth community with age spanning between 18 and 35 years and who are widely unemployed would need to engage themselves in any means to income generation through use of the natural resource at Kimara B and in the vicinities. The group was identified by the researcher as distinctively social group which has been involuntarily formed as a means to either self employment resulting from spatial interaction.

This community was regularly consulted and sensitized in attempt to establish the needs assessment, formulating the project from identified needs and ensure their readiness to active participation in closing the gaps and thus sustainability. In formulating the project, the researcher understands the potential conflicts that may arise between the economic needs against those relating to the environmental protection. In this regard, the researcher has provided a project design that takes into cognizance on the need for considering “trade-off” and overlapping considerations among competing needs.

The target group involves 30 male youth strategically stationed at the junction of Temboni and Morogoro road and Temboni – Matosa arterial roads. The group has been purposively selected and is the main beneficiaries of the project implementation. The secondary beneficiary of the project is the Saranga Ward Executive Officer, through its Ward Environmental Committee through equitable control and exploitation of the in demand sand resource.

# 2.3.2 Stakeholders

Based on the participatory action perspective, stakeholders play a leading and definitely beneficiary role in realizing the outcome of the proposed actions. Clearly this would involve both the primary and secondary targeted beneficiaries. However, consideration of how to make community-based developments feasible and sustainable has led to a growing appreciation that those with a “stake” in the outcome of any development initiative includes many groups other than the target groups themselves.

Feasibility in implementation and sustainability in the long run requires a degree of homogeneity in purpose among several parties to the project than the primary target beneficiaries. It is in this respect that the definitions of project stakeholders in community development have continued to evolve to broadly include all of those with an interest at some stage in the outcome of the actions being proposed. The intention of having a broad based stakeholder platform is to ensure a sustainable community economic development impact that would take into account multilateral interests towards the common goal. Table 2.1 shows stakeholders and their expected impact for the project.

# Table 2.1: Stakeholders Participatory Analysis

| No | Stakeholder | Roles of the stakeholder | Expected Participatory Impact |
| --- | --- | --- | --- |
| 1 | Male youth aged between 18 to 35 and their leadership | - Primary project beneficiaries | Actively participate in the project through implementation of the procedures for access of the mining sites |
| 2 | Kimara B subward Leadrship | - Identifying and mobilize the youth community to implement and own the project - Oversee the project implementation plan based on sustainable use of the sand harvesting sites | Implementing the Project Implementation Plan (PIP) in collaboration with the youth. |
| 3 | Saranga Ward Executive Officer (WEO) | - Sanctioning of the project and linking with other government organs - solicit funds for training and environmental awareness sensitization - Implementation of District environmental plan | - Linking the WEO, the target youth community and the Council Environmental - Management Officer and Land Use Officer - Provision of logistical, financial and management services |
| 4 | Change Agent | - Advisory services based on non-participant observations - Preparation of PIP and establishment of coordination and environment collaborative-decision making (i.e. facilitation) - Training needs assessment and follow up project funding sources | - Overseeing project implementation - To reinvigorate access and use of natural resources based on principles of environmental protection and adaptation |
| 5 | Ward Community Development officer | - Guidance for Implementation of development activities - Monitoring and evaluation | - Increased community participation - Project sustainability |
| 6 | Ward Natural Resource officer | - Identify and providing Ephemeral River location for periodic harvesting - Provision of technical services | - Project sustainability - Budgeted sand harvesting production |
| 7 | Ward Health and Safety Officer | - Providing guidance on health and safety practices - Provide training on Health | - Project sustainability - Budgeted sand harvesting production |

Source: researcher, 2017

# 2.3.3 Project Goals in CED Terms

The goal for the development and implementation of this project is to enhance accessibility of sand mining sites among identified youth group based on the principles of sustainable utilization of finite natural resource. This will culminate into creation of reliable means for reduction and elimination of income poverty as well as inculcating social responsibility among youth in sand mining and harvesting activities. This goal can only be attainable and sustainable only when the youth, community leadership, government authorities and institutions and other stakeholders have a mechanism to implement policies, plans and associated programmes aimed at improving income among the disadvantaged youth whilst in observance of the responsibility towards social environment. Therefore, shared responsibility shall remain in focus among the stakeholders to ensure sustainable exploitation of the natural resources and improved income among youth.

# 2.3.3 Project Objectives

Based on the observations from the qualitative data and their analysis, the project is designed to address the participatory community needs which are intended to achieve the following objectives:

- To sensitize and train  30 sand mining youth  on the process to establish and maintain access to the sand harvesting sites including best practices  for exploitation of the harvesting sites by July 2017 ;

- To establish access to and reliable markets of  harvested sand in compliance with the applicable regulatory framework by July 2017 and

- To indoctrinate the 30 youth and the local community on environmental protections/adaptation methods for sustainable economic exploitation  of the natural resource by July 2017

# 2.4 Host Organization Profile

The host organization is the Kimara B subward (Mtaa) which is subordinate to Saranga Ward Executive Office. The Ward carry out its responsibility through Ward Development Committee (WDC) which is responsible for all matters relating to the sustainable socio economic development of the Saranga Ward and in particular Kimara B locality. The Ward development committee meets regularly to deliberate and follow up implementation of the various multi-sectoral responsibilities including community development matters, promotion of trade, agriculture, education and health and environment among others emerging development challenges within their geographical confines.

In implementing the responsibilities pertaining to the social development the following pertinent issues take a centre stage at the levels of Saranga Ward and Kimara B Subward (Mtaa):

- Social awareness and identify opportunities and barriers to development in their areas.

- Provide for clarity and coordinating the implementation of the policy of the Ministry of Community Development Gender and Children.

- Facilitate the implementation of policies and programs for development projects in various sectors;

- Collecting and analyzing various social, economic and geographic data and distribute them to various stakeholders in the development of the community;

- Providing education for community leaders on leadership and good governance.

- Encouraging and educating the community on the utilization of local available natural resources in order to foster prosperity among the people

- Encouraging and educating the community about the protection and preservation of the environment and natural resources for sustainable development.

- Managing subscriptions and coordinate the activities of NGOs and CBO’s and lastly but least

- Educating the public on the role of gender equity and rights of children that shall contribute to their development.

# 2.4.1 Host Organization Leadership

The Kimara B subward is part of Saranga Ward Organization structure headed by the Ward Executive Officer (WEO) whose responsibility is to fully participate in the preparation of development plans as well as coordinating and integrating action plans from the Mtaa Executive officers and submit such plan to the Ubungo District Executive Director. In this regard, this responsibility is central to the recurring agenda during the Ward Development Committee (WDC) meetings. The WDC is characteristically a grass root structure that is obligated to attend to matters affecting livelihood and emerging and real security, social, economical and environmental interests at the community. It is structured to devise strategies on matters affecting business growth, land use and conflict resolution before they endanger the, agriculture, livestock keeping, trade and revenue collection within their confines. The WDC meets once every month to review the implementation status of development plans, monitor progress and identify new emerging development challenges at ward level. Based on the Ubungo District Council profile document, the organization structure at the Ward level is as shown in Figure 2.1.

# Figure 2.1: Organisation Structure

2.4.2 Host Organization Vision

The Kimara B subward at Saranga Ward upholds the vision propagated by Ubungo District Council which aims at creating and maintaining “a community which is motivated, dynamic, with socio economic development”. In this, the vision is in conformity with supporting and facilitating the various social groups.

# 2.4.3 Host Organization Mission

The Kimara B subward of the Saranga Ward espouses a mission aiming at provision of quality services to the community through effective and efficient use of resources; capacity building, good governance and rule of law and improved living standard of people. In this regard, the community focuses on the equitable use of resources and improved livelihood among the social group.

# CHAPTER THREE

# 3.0 LITERATURE REVIEW

# 3.1 Introduction

This chapter provides an account of information related to literature review pertaining to improving access and income prosperity of the youth community through production and supply of construction sand obtainable from the legally identified localities in Ubungo Municipality and neighboring districts. Extensive review of the journals, research papers and books was conducted to aid in providing validated data and information which can be used as referral material to enrich this research work as well understanding the responsibilities that must be exercised by youth towards adaptation to environmental protection.

Relevant information was collated from the various theoretical literatures including definition of sand as an construction material possessing economic value was provided. Besides, the review of empirical literature was also made in order to acquire insight and experience from existing factual information from other African countries and globally with a view to  analysis and identify gaps that need to be addressed in this study.

# 3.2 Theoretical literature

# 3.2.1 Definition of Sand

Sand is defined as “loose coarse particles of hard broken rock”. More restrictive definitions also exist which depend upon the frame of reference or academic discipline to which the meaning of sand is to be applied. For example, to a sedimentologist sand is an unconsolidated (loose), rounded to angular rock fragment or grain having a diameter in the range of 1/16 to 2 mm (0.0025 to 0.08 inches.). An engineer on the other hand may restrict the meaning of sand to include only rounded fragments having a diameter of 0.074 mm (retained on U.S. standard sieve no. 200) to 4.76 mm (passing U.S. standard sieve no. 4). Practically, sand may be considered to consist of small detrital fragments (rock or minteral particles liberated by mechanical disintegration of parent rock material), biogenic particles (shells or shell fragments) or chemical precipitates (evaporites or oolites) occurring in nature and distinguishable by the naked eye.

# 3.2.1 Sand as Constituent Construction Material

It is estimated that globally, between 47 and 59 billion tonnes of construction material is mined every year (Steinberger, Krausmann, and Eisenmenger, 2010) of which sand and gravel account for the largest share  ranging from 68% to 85% (Krausmann, et al., 2009). Unfortunately, there is no any reliable data on the quantity of sand mined globally or even at national levels. Only in recent years the developed countries started to collect and maintain such data for economic or environmental purposes. This makes the task of assessing the global demand or exploitation of sand as a natural resource or the different use to which they are put to or the environmental impact assessment very difficult and possibly inaccurate.

An indirect way of estimating the demand for sand is through the assessment of the product for which sand is a constituent material such as concrete. It is estimated that in year 2012, around 3.7 billion tonnes of cement was produced globally as reported by 150 countries. Cement is used for the production of concrete and on average cement and sand is combined in the ratio of 1:6 to 1:7. Thus globally 26 to 30 billion tonnes of sand was used for the year 2012 alone for concrete and masonry works—which is equivalent amount for mixing concrete sufficient to construct a wall of 27 meters high and 27 meters broad across the equator (Orr and Krumenacher, 2015).

Sand harvesting, transportation and other related work have increased employment and income to many households both in rural and urban areas. In addition, there are thousands of indirect employment opportunities generated through sand mining. As in the case of the quantity of sand mined reliable data regarding the income or employment generated through sand mining is readily available.  Sand mining and harvesting is not a recent activity unique to any particular region or country. However, historical account holds enough evidence to prove that sand was used in some way or other for different purposes relating to human development activities. From time immemorial sand was mined across the globe for various activities and will continue to be so for a long time ahead.

Source of harvesting sand is naturally mobilized through aquatic transportation and the sand deposits accumulates in the river banks and forms dunes in the vicinities of rivers or areas close coastal zones. Traditionally, scientific and environmental friendly methods of sand mining were followed. The sand thus mined was replaced in the rain that followed through aquatic activity. As the local demand for sand increased due the increased demand from the construction sector and employment, the sand mining is now undertaken indiscriminately by vendors and self employed people (Shaji and Anilkuar, 2014).

Sand mining as a traditional economic activity has been on the rise to keep pace with the ever increasing demand from the construction industry. There has been indiscriminate mining across the world especially in the developing countries in the past couple of decades. To predict the consequence of sand mining beyond the replenishment limit is not possible in a short period of time.  In other words, mining may continue for years without apparent effects upstream or downstream, only to have geomorphic effects manifest later during high flows. (Swer and Sing, 2004).

# 3.2.2 Sources of Sand as a natural Resource

It is estimated that 20% of the earth’s surface is occupied by sand in various form. The formation of sand and sand bed are associated with natural activates which takes place thousands of years. Sand is usually found at oceans shore, rivers, streams, flood plains, hills, mountains and deserts. Rivers and their floodplains are the most economic source of sand as there occurs regular natural replacement—limited to the natural replacement capacity (Kori and  Mathada, 2012).

# 3.2.3 Sand Budget

The difference in geographical features, the location of the sand bed, the climatic condition, the amount of rain the region get, the extent of water flows, the catmint area of the river determines the extent of sand one can mine from a particular sand bed. The sand budget, in simple terms denotes “the amount of sand that could be removed from the area without causing undue erosion or degradation, either at the site or a nearby location, upstream or downstream”.(Kumar and Sukumar, 2012).Topographic, hydrologic and hydraulic information are the pre-requisite to determine the sand budget. Interestingly, there are hardly any efforts taken to determine the sand budget of a mining region both by the authorities who issue the sanction and by the agencies involved in the mining.

# 3.3 Empirical Literature

Sand is an attractive natural resource of great socio-economic value. It has several varied social human livelihood uses, among them, as a constituent ingredient in manufacturing  concrete for building and construction industry, as an abrasive (sand paper, sand blast), as a source of silica for making sodium silicate, used in foundries for molding and other cultural uses. Thus, the importance of the resource cannot be over emphasized, and community development intensively depends on it.

Sand is one of the words most plentiful resource (20 % of the Earth‟s crust is sand) and has the ability to replenish itself. Natural resources are extensively available regardless, of whether or not communities are inclined to choose to use them to improve quality of their lives. They are “neutral stuff” that make up the world, but they become resources when we find utility in them (Hunker, 1964). Therefore river sand and various deposit sites are vital for human social economic well-being and for sustenance of rivers and earth.

The human species is part of nature and therefore heavily dependent to gain from it. Its existence depends on its ability to draw sustenance from finite natural resources whilst maintaining ability to abstain from devastation of the ecological systems that regenerate the world. Economic activity must account for the environmental costs of production which includes labour and entrepreneurship. The maintenance of livable global environment depends on the sustainable development of entire human family through the use of natural resource in the improvement of living conditions (Naveen, 2012).

Natural resources are the basic building blocks in the production system, they are raw materials. Keller (1992) observed that little of their value is derived from human input such as labor; they generally have a lower value per unit than other commodities. In few cases natural resources have high value in the ground, but in this instance it is the consumer that drives the price up, if the demand is greater than the amount of resource available (Cutter, 2004). Resources when well used can improve the living conditions of the users. Economists view the resources that we extract from nature as form of capital and just as classical capitalist, systems seek to accumulate and re-invest monetary capital, ecological economist argue that natural capital should be regenerated rather than depleted (Hawken et al., 1999).

Increased income for the community is crucial for the sustainability of families and improvement of their living conditions.  Social scientists attest that real development lies in the economic empowerment of people and especially at family level. It is believed that unemployment for people implies not only deterioration in their living standards but also an increase in their dependence on other people and loss of autonomy as well as security (Sen, 1989).

Globally, sand mining and harvesting is in great demand due to increased demand in the construction industry and should be of great economic benefit to the people who live in the area through accessing better education for their children. Though, as much as it has contributed to the improvement of the people‟s lives it has also led to the development of negative effect of sand including the permanent loss of sand in areas as well as habitat destruction (Naveen, 2012). It is in this contention that need for sustainable sand harvesting and mining to ensure that the natural resource is not depleted and cause irreparable damage to the environment.

A study by Borges et al., (1992) in Acero archipelago Portugal found out that sand harvesting impact social and economic growth of archipelago in 20th century particularly in last quarter of the century resulted to accelerated coastal development which included the construction of communication infrastructure and buildings all of which required large volume of sand .Given the local geological constraints, natural and suitable sand required for construction purposes is scarce and normally call for adequate regulatory measures to impose controls over its exploitation .

Sand harvesting like any other economic activity is able to help the people in a given area in affording their basic needs given that it raises their purchasing power. A study by Deller and Schreiber (2012) on Franc Sand harvesting and Community Economic Development found that communities that are more heavily dependent on harvesting for employment  can provide well-paying jobs leading to lower levels of poverty. A study by Binoy et al., (2002) in river pariyar Karela India found out that annual demand for sand for construction purpose in Karela is estimated at more than 3 million tonnes. Collecting sand from river and its distribution has become and industry giving job opportunities for thousands. According to estimates, sand mining provides direct employment opportunities to over 60,000 registered laborers in the state.

In Africa, the harvesting of sand and gravel in Togo has created job for youth. The revenue gained is used in most part to meet basic needs of the family including food, to pay tuition for children. They earn average 3,000 CFA francs per day and the revenues are used to meet basic needs food, rent, medical care and children schooling. The United Republic Tanzania experiencing a booming growth of its construction industry which contributes to overall economic growth, effective policies are required to manage sand mining which is an indispensable component in the construction process. Currently, the United Republic of Tanzania does not have a clear national policy framework and guidelines that set grounds for equitable exploitation of sand, as natural resources.

Conversely, there is regulatory vacuum and lack of institutional capacity that supports this economic activity in a sustainable manner. Unfortunately, the National Environmental Management Council (NEMC) is inclined towards on imposing stricter and punitive actions which have long term economic and unfortunately environmental disbenefits. On one hand, economic disbenefits arise as a result of unilateral regulatory measures which disenfranchise communities the economic opportunity to mine or harvest self-replenishing river sands. On the other hand, environmental disbenefits arising from lack of institutional capacity for exercising environmental enforcement obligations across the entire vast United Republic of Tanzania leading to uncontrolled and often unnoticed sand mining or harvesting in the country.

# 3.4 Policy Review

The welfare of communities is primarily dependent on exploitation of natural resources will be increasingly vulnerable if they do not adapt to environmental protection and this vulnerability will be increasingly aggravated by management decision that restricts access to the resource (such as sand in this research) in the short run, even if those restrictions are designed to increase long term sustainability of source of construction sand. It is arguably obvious that the communities struggling to maintain their quality of life are less likely to support protection measures that constrain access to resources that can transform their livelihood.

Therefore, review of policy affecting natural resource management can be very helpful in identifying policy gaps that could strike a balance between exploitation of resources for improving community livelihood and the adaptation to environmental protection. The Tanzania Community Development Policy 1996,  explicitly declare that there must be sustainable cooperation  between all authorities/institutions concerned with community development in planning and implementing development plans among other issues.

In addition, the policy seeks to mobilize the community to use available resources and assets in a sustainable manner through application of participatory action.  On the other hand, the Tanzania Development Vision 2025 was developed with a view to creating and maintain enabling environment essential for economic, social, political and cultural development. The Vision takes into account predictable changes and global trends in the economy. The implementation of the Vision enhances the need to deal with global and social challenges through hard work, initiative, skill development, as well as exploiting opportunities and the resources available in our country.

In the Vision 2025 policy document, it is emphasized that determination and disciplined planning and implementation is the key to disentangle the majority of Tanzanians from the abject poverty. Therefore, participation of the Ministries, government institutions, private sector, non-governmental organizations, civil society, co-operative societies, villages and all other social groupings is vitally important to achieving effective implementation of the envisioned objectives.

In the implementation of the Vision 2025, the government has devised Tanzania Five Year Development Plans in order to make gradual and systematic growth towards the long term vision. In the 2012 – 2016 five year development plan, five priorities have been identified to unleash Tanzania’s latent growth potentials which include;

- Infrastructure for energy, transport infrastructure (port, railway, roads, air transport), water and sanitation and ICT;

- Agriculture,

- Industrial development targeting industries that contribute towards growth of value chain economy i.e. linkage between agriculture and industry for value addition,

- Human capital and skills development, with an emphasis on science, technology and innovation; and

- Tourism, trade and financial services.

In the global context, recent international development policy-making has culminated into agreement on Council of Parties (COP-21) related to the ambitious 17 Sustainable Development Goals which are characterized by 169 targets. The SDGs seek to build on the Millennium Development Goals (MDGs) and complete what they did not achieve. They are integrated and indivisible and balance the three dimensions of sustainable development: the economic, social and environmental. For this project, the most interesting are SDG goals 1, 3, 8, 12 and 14 which are as follows:

- Goal 1 -  End poverty in all its forms everywhere

- Goal 3 -  Ensure healthy lives and promote well-being for all at all ages

- Goal 8 - Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all

- Goal 12 - Ensure sustainable consumption and production patterns

- Goal 14 - Conserve and sustainably use the oceans, seas and marine resources for sustainable development.

Holistically, the aforementioned goals seek to address inclusive approach towards sustainable development of people from all walks of life using the available community assets, principles and opportunities for dignified livelihood of communities whilst in adherence with protection of environment.

# 3.5 Literature Review Summary

Literature review from both theoretical and empirical sources has revealed that supply of construction sand is in demand natural resource both in the developed and developing nations whose exploitation is regulated under the mining and environmental regulatory framework specific for each State to ensure adequate sanctioning processes and sustainable use of the finite material. Interestingly, despite the ever rising need among youth communities to make livelihood out of exploitation of the natural resource other corresponding development government agencies have intervened to impose regulatory measures aimed at ensuring that sand sources can be exploited for economic purposes without causing irreversible environmental damage to the environment.

In addition, empirical literature has revealed that some emerging economies like India have recognized and sanctioned sand mining as an income generating economic activity for most low income communities which culminated into developing and implementation of guidelines on how communities can benefit from access and production of sand as a major supply to the booming construction industry. Case in point is the recently published and promulgated “Sustainable Sand Mining Guidelines” issued by Ministry Environment, Forests and Climate Change of India in year 2016.

Moreover, it has been learnt from the 5 – year Development Plan (2012 – 2016) that the primary goal of the country is to develop and maintain  Infrastructure for energy, transport infrastructure (port, railway, roads, air transport), water and sanitation and ICT. In this respect, need for identifying, accessing and production of construction material such as sand, aggregate and cement cannot be overemphasized. By increased access and production of the much need construction materials, the goal for developing and maintaining a robust transport and energy infrastructure, water and sanitation necessary for supporting the economy and communities at large can be achieved.

# CHAPTER FOUR

# 4.0 PROJECT IMPLEMENTATION

# 4.1 Introduction

This chapter contains details on the process for the planning of the project, how the project activities were determined, inputs identified and finally which outputs can be realized throughout the execution phase. During the project implementation phase, it is prerequisite that products, output from the project, activities, objectives, resources and time frame to accomplish the project are pre-determined and clearly forecast. The implementation plan also goes as far as projecting budgeted estimates for purchase of equipment, training and other associated operational costs.

The project planning and implementation must set firm basis for identifying and commitments of various stakeholders who are key contributory organs for the project. During the key informant interviews from Ubungo Municipal council, it was ascertained that they are ready to provide their support and facilitation in training and accessibility and oversight of sustainable exploitation of the sand sources.  Besides, a visit conducted at the NEMC offices at Regent Estates in Dar es salaam and an interview with Senior Environmental Officer (Ms Nancy Shushu) indicated their readiness to coordinate and participate with the local authorities in identification and sanctioning of process for environmental auditing and certifying of selected sand mining sources in Saranga ward and Kimara B Sub-Ward in particular.

The Saranga Ward Executive Officer is the primary owner who is obligated to ensure implementation of the project based on the available resources, providing support and facilitation from the Change agent. The chief responsibility of the change agent is to establish a guided roadmap and necessary advisory services to the WEO during the implementation process. As indicated earlier on, the main objective for the project idealization and implementation was to facilitate equitable access to the identifiable sand mining sites, improve productivity and thereof income generation and sensitize the youth on the social responsibilities regarding environmental adaptation.

The project initiation phase was realized from April 2017 where the sand mining youth were contacted through their representative (Mr Mwalami Saidi) and 30 of the youth participated in the guided interview and interactive consultation at Kimara B Primary School. This consultation phase enabled exchange of indispensable information between the youth and the change agent on fundamental issues such as level of youth knowledge on sustainable exploitation of natural resources for economic benefits, existing regulatory frameworks and inculcating responsible entrepreneurship skills.

It was planned that by July 2017 the project would accomplish its activities including the intermittent monitoring activities except evaluation and possible derivation of other projects that will be grown out this base project. The planned project product is the improvement in community livelihood opportunities through improved access and productivity at the sand harvesting sites (as a factor of production) whilst in adherence with principles of environmental protection and climate adaptation. However, the project product cannot be easily visible during the planning and implementation phase spanning from April to July 2017 which is normally laden with several activities unless a detailed evaluation is conducted at the end of July 2017, a delivery period. It is foreseen that the identified youth community group in sand harvesting at Kimara B will experience improvement in the quality of their livelihood in terms of ability to meet costs for the social amenities and possibly financial savings for meeting costs associated with education and health.

  - Products and Outputs

The principal project implementation planning and programming contained in this project is expected to achieve the following products and outputs based on the identified planned activities.

# 4.2.1 Project Outputs

The project is expected to accomplish the following outputs.

- 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017

- 30 sample youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017

- Identify locations for sand harvesting/mining and  establish and implement sustainable exploitation of natural resources by July 2017

- Indoctrinate  on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017

In an attempt to achieve the desired outputs and the goal of the project which is the establishment of mechanism and attaining improved access to the sand mining and sand harvesting sources among  male youth so that they can equitably meet their social needs and reduce  income poverty some activities were planned and successful  implemented.. The planned activities were as it is indicated in Table 4.1.

# Table 4.1: Planned Project Activities and Expected Outputs

| Objective | Output | Activity |
| --- | --- | --- |
| - 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017. | - Conduct one interactive sensitization seminar | 1.1.1 Consult the local authority leaders and youth community informal leadership |
|  |  | 1.1.2 Establish rapport with the youth community at their sites |
|  | - 20 sand mining youth attended the interactive seminar | 1.2.1 Prepare the subject matter agenda for presentation |
|  |  | 1.2.2 Conduct the seminar based on participatory approach |
| - 30 sample youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017 | - One training on sustainable exploitation of sand sources conducted | - Prepare budget for the training |
|  |  | - Identify location and develop programme for the training |
|  | - 15 youth in sand mining activities participated in the training | - Outsource for the experts from the industry |
|  |  | - Conduct training on best practice mining/harvesting procedures and principles on environmental protection |
| - Identify locations for sand harvesting and establish and implement sustainable exploitation of natural resources by July 2017 | - One meeting involving stakeholders conducted | - Identification of the stakeholders |
|  |  | - Organize stakeholders forum for discussion and consensual resolution |
|  | - Location for sand harvesting and mining identified | - Identify location for sand mining and harvesting |
|  |  | - Procure tools/equipment for small-scale sand mining equipment using appropriate technology principles |
|  |  | - Prepare and promulgate Guidelines for Sustainable Access and Trading of Sand |
| - Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 | - Disseminate the project through local public announcements, FM Radio and print media | - Prepare and fund for the media promotional services |
|  |  | - Identify and engage individuals/leaders for the media advocacy |
|  | - Approval/license/registration for sand mining/harvesting sources issued to 10 sand mining youth group; | - Solicit funds for approving/licensing the identified sand mining/harvesting sites for the youth community |
|  |  | - Conduct continuous environmental oversight obligations at local level |
|  | - 10 youth in sand mining/harvesting maintain legal access to the identified sand sites | - Inaugurate the sand mining/harvesting project |
|  |  | - Monitor and evaluate on the best practices for sand mining/harvesting among youth |

    - Project Products

The chief project product is the improved access of construction sand material sources as exploitable natural resource among the identified youth community which will culminate into improved and sustainable community livelihood and economic opportunities at Kimara B. This can be attained through responsible and observant access and income generation of the exploitable sand as a natural resource from the various sources within and in the vicinities of Kimara B geographical confines.

  - Project Planning

Project planning is an indispensable process in the life cycle of the project and overall project management. The planning process relates with the identifying activities, expected outputs, mobilizing resources and subsequently reporting progress within the project scope. In the project planning identifies the key stakeholders, defines roles and responsibilities and inputs required to achieve the desired objectives within the planned period of time.

The planning process in this project was conducted with the concept of participatory approach of the community and other stakeholders in order to ensure sustainability of the plan and actions. Table 4.2 indicated Project Implementation Plan (PIP)

    - Implementation Plan

# Table 4.2: Project Implementation Plan

| Objective | Output | Activity | Planned Implementation Time |  |  |  |  | Resource Required | Responsible person |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 |  |  |
| - 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017. | - Conduct one interactive sensitization seminar | - Consult the local authority leaders and youth community informal leadership |  |  |  |  |  | Human, financial Stationery | Human, financial Stationery WEO Youth Leadership |
|  |  | - Establish rapport with the youth community at their sites |  |  |  |  |  | Human, financial Stationery | Human, fund for fuel and hire of venue Youth Leadership |
|  | - 20 sand mining youth attended the interactive seminar | - Prepare the subject matter agenda for presentation |  |  |  |  |  | Human, financial Stationery | Stationery, human and fuel |
|  |  | - Conduct the seminar based on participatory approach |  |  |  |  |  | Human, financial Stationery | Hire of venue, human, WEO |
| - 30 youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017 | - One training on sustainable exploitation of sand sources conducted | - Prepare budget for the training |  |  |  |  |  | Human, financial Stationery | Subject matter expert, financial |
|  |  | - Identify location and develop programme for the training |  |  |  |  |  | Human, financial Stationery, subject matter experts | Human, stationery, reference material, financial |
|  | - 15 youth in sand mining activities participated in the training | - Outsource for the experts from the industry |  |  |  |  |  | Human, financial Stationery | Subject matter experts, financial |
|  |  | - Conduct training on best practice mining/harvesting procedures and principles on environmental protection |  |  |  |  |  | Human, financial Stationery, subject matter experts | Subject matter experts, financial, WEO, youth leadership |
| - Identify locations for sand harvesting and establish and implement sustainable exploitation of natural resources by July 2017 | - One meeting involving stakeholders conducted | - Identification of the stakeholders |  |  |  |  |  | Human, financial Stationery | Subject matter experts, financial, time |
|  |  | - Organize stakeholders forum for discussion and consensual resolution |  |  |  |  |  | Human, financial Stationery | Financial, WEO and District Environmental Officer |
|  | - Location for sand harvesting and mining identified | - Identify location for sand mining and harvesting |  |  |  |  |  | Human, financial Stationery | Subject matter experts, financial |
|  |  | - Procure tools/equipment for small-scale sand mining equipment using appropriate technology principles |  |  |  |  |  | Human, financial Stationery and subject matter experts | Youth leadership Financial resource, subject matter expert |
|  |  | - Prepare and promulgate Guidelines for Sustainable Harvesting of Sand |  |  |  |  |  | Human, financial Stationery, fuel | Subject matter expert |
| - Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 | - Disseminate the project through local public announcements, FM Radio and print media | - Prepare and fund for the media promotional services |  |  |  |  |  | Human, financial Stationery | WDC, Subward leadership |
|  |  | - Identify and engage individuals/leaders for the media advocacy |  |  |  |  |  | Human, financial Stationery | Financial resource Youth Leadership Change Agent Subward leadership |
|  | - Approval/license/registration for sand mining/harvesting sources issued to 10 sand mining youth group; | - Solicit funds for approving/licensing the identified sand mining/harvesting sites for the youth community |  |  |  |  |  | Human, financial Stationery | Financial resource Youth Leadership Change Agent Subward leadership |
|  |  | - Conduct continuous environmental oversight obligations at local level |  |  |  |  |  | Human, financial Stationery | Financial resource Youth Leadership Change Agent Subward leadership |
|  | - 10 youth in sand mining/harvesting maintain legal access to the identified sand sites | - Inaugurate the sand mining/harvesting project |  |  |  |  |  | Human, financial Stationery, fuel, venue, refreshments | Financial resource Youth Leadership Change Agent Subward leadership WDC |
|  |  | - Monitor and evaluate on the best practices for sand mining/harvesting among youth |  |  |  |  |  | Human, financial Stationery, fuel | Financial resource Youth Leadership Change Agent Subward leadership WDC |

# Table 4.3: Project Logical Framework for the Sand Harvesting at Kimara B

| Hierarchy of Objectives | Objectively Verifiable Indicators (OVIs) | Means of Verification (MOVs) | Assumptions |
| --- | --- | --- | --- |
| Goal: Improving income of the male youth community through sand harvesting at Kimara B | Increased income generation and better quality of life among youth community | Comparative analysis of the beneficiary’s income levels before and after winding up of the project | Accuracy of the management information system (MIS) for the project |
| Objective1: 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017 |  |  |  |
| Output 1.1 30 youth primary project beneficiaries’ for sand harvesting established | Available number of male youth in sand harvesting project | Project Archives | Participatory action and community inclusiveness campaign appropriately executed to engage sufficient number. |
| Activities |  |  |  |
| 1.1.1 Structured and rigorous interaction and communication among selected group of youth | Established procedure for effective communication and interaction | Communication Procedure | Project stakeholder’s participation |
| 1.1.2 Developing consensus among youth and develop project implementation plan | Number and register of applicants and Project Implementation Plan | Project Implementation Report | Effective participation among groups of youth |
| Objective 2: 30 youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017 |  |  |  |
| 2.1 30 male youth community undergo training in environmental protection, and vocational health and safety issues | Number of trained youth and the Guidelines | Project Implementation Report | Availability of subject matter experts and training material |
| Activities |  |  |  |
| 2.1.1 Identify venue for the Training sessions | Venue use timetable | Project Implementation Report | Effective coordination with the host organization and the target community |
| 2.1.2 Develop Guidelines on Sustainable Harvesting from Natural Sources | Draft Final Guidelines prepared (Appendix 2 of this Report) | Project Implementation Report | Stakeholders comments incorporated to facilitate promulgation of the Guidelines (Appendix 2) |
| 2.1.3 Conduct training on sustainable harvesting of sand from natural sources | 30 beneficiary youth members participated in the training. | Training Reports | Acceptance of the youth community to attend the training |
| Objective 3: Identify locations for sand harvesting and establish and implement sustainable exploitation of natural resources by July 2017 |  |  |  |
| Output 2.1 Location for sand harvesting identified | Endorsed Meeting Minutes | Visit sand mining areas | Availability of funds and consensus among stakeholders |
| Activities |  |  |  |
| 2.1.1 identify location for sand harvesting in association with representatives Ward Development Committee and Municipal Community Development Officer | Number of viable locations for sand harvesting | Project implementation Report | Effective Participation of project stakeholders and other peripheral organs |
| 2.1.2 Harvesting of Sand based on best practice | Two locations identified | Conducting site visits | General consensus among stakeholders reached and best practice in sustainable exploitation of natural resources |
| 2.1.3 Transporting of sand to various customers including block makers, ongoing housing project sites and contractors | Sand harvested and Transported | Dialogue businesspersons engaged in block making and housing sites | Truck owners willing to purchase the sand consignments from time to time |
| Objective 4: Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 |  |  |  |
| Output 4.1 30 male youth identified and notified for indoctrination session son environmental protection and adaptation | List of youth and leaders | Register of participation | Leaders and youth understanding on integrating of environmental concepts in the harvesting project |
| Activities |  |  |  |
| 4.1.1 Conduct two indoctrination sessions with the | 30 beneficiary youth members participated in the training | Project implementation reports | Free and fair election |
| 4.1.1 Prepare Project Implementation Reporting | Monitoring and evaluation reports | Project implementation reports | Effectiveness of Participatory Monitoring and Evaluation methods |

    - Inputs

For the purpose of ensuring smooth project implementation, various inputs were employed including human and material resources. These inputs have been indicated in Table 6. It included a range of human resources from the Municipal council officials, outsourced experts,   leadership among the sand mining and harvesting male youth, Saranga ward leaders, Kimara B subward (Mtaa) leaders and the change agent administering the project. The sources of material resources were Ubungo District Council (allocated fiscal budget in the community development, gender and children department) for obtaining tools and appropriate skills for mining and harvesting of sand, stationery and training cost. Also, Saranga ward took the responsibility of being a as Host organization which provided a forum, logistical and core management accountabilities for the project execution.  Table 4.4 illustrates the planned project inputs necessary for the execution of the project.

# Table 4.4: Project Inputs

| Objective | Output | Activity | Resource Allocation |  |
| --- | --- | --- | --- | --- |
|  |  |  | Human | Non-Human |
| - 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017. | - Conduct one interactive sensitization seminar | - Consult the local authority leaders and youth community informal leadership | Stationery Change Agent Participants Project manager | Venue Fuel Stationery |
|  |  | - Establish rapport with the youth community at their sites | Project Manager Project coordinator Change Agent | Venue Fuel Stationery |
|  | - 20 sand mining youth attended the interactive seminar | - Prepare the subject matter agenda for presentation | Change Agent Subject matter experts | Refreshments |
|  |  | - Conduct the seminar based on participatory approach | Facilitator Change Agent | Stationery Venue Fuel |
| - 30 youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017 | - One training on sustainable exploitation of sand sources conducted | - Prepare budget for the training | Change Agent Treasurer | Stationery |
|  |  | - Identify location and develop programme for the training | Change Agent Experts | Stationery |
|  | - 15 youth in sand mining activities participated in the training | - Outsource for the experts from the industry | Facilitator Experts Participants (target group) | Stationery |
|  |  | - Conduct training on best practice mining/harvesting procedures and principles on environmental protection | Change Agent Experts Participants (target group) | Stationery Refreshments Venue Fuel |
| - Identify locations for sand harvesting and establish and implement sustainable exploitation of natural resources by July 2017 | - One meeting involving stakeholders conducted | - Identification of the stakeholders | Change Agent Project Manager Project coordinator | Fuel |
|  |  | - Organize stakeholders forum for discussion and consensual resolution | Change Agent Experts Participants | Stationery Refreshments Venue Fuel |
|  | - Location for sand harvesting and mining identified | - Identify location for sand mining and harvesting | Change Agent Experts Participants | Refreshments Venue Fuel |
|  |  | - Procure tools/equipment for small-scale sand mining equipment using appropriate technology principles | Change Agent Project Manager Project coordinator Treasurer | Spades Crowbars Shovels Wheelbarrows |
|  |  | - Prepare and promulgate Guidelines for Sustainable Harvesting of Sand | Change Agent Project Environmental Expert | Stationery Fuel Honoraria |
| - Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 | - Disseminate the project through local public announcements, FM Radio and print media | - Prepare and fund for the media promotional services | WEO/WDC Treasurer Change Agent Participants | Advert costs Sitting Allowances Fuel |
|  |  | - Identify and engage individuals/leaders for the media advocacy | WEO WDC Change Agent | Advert costs Sitting Allowances Change Agent Fuel Stationery |
|  | - Approval/license/registration for sand mining/harvesting sources issued to 10 sand mining youth group; | - Solicit funds for approving/licensing the identified sand mining/harvesting sites for the youth community | Change Agent WEO Youth Leadership | Honoraria Change Agent Fuel |
|  |  | - Conduct continuous environmental oversight obligations at local level | Youth Change Agent Project Environmental Experts | Fuel Allowances Refreshments Stationery |
|  | - 10 youth in sand mining/harvesting maintain legal access to the identified sand sites | - Inaugurate the sand mining/harvesting project | WDC Treasurer Change Agent Youth Leadership | Fuel Venue Refreshments |
|  |  | - Monitor and evaluate on the best practices for sand mining/harvesting among youth | Change Agent Youth Leadership | Stationery Refreshments Allowances |

    - Staffing Pattern

The project is managed by the Subward (Mtaa) Executive Office under the coordination and active participation of Ward (Kata) development committee and the representation of the youth community in the sand mining and harvesting activities. The premises are located within Kimara B so the guardian is Ward Executive committee and the sub-ward development who both anticipate reimbursement of allocated funds from the Ubungo Municipal Council fiscal budgets targeting community development components. However, the implementation to a great extent was aided by the Ward Executive Officer, change agent  and with the high level guidance and incorporation of the Municipal Community Development officer and Municipal Health and Environment Officer. These administrative personnel assumed and continue to assume different roles in the implementation of the project. Inclusion of the cross cutting issues was considered pivotal in order to ensure sustainability on the project and developing other projects in the future.

# Table 4.5: Project Staffing Pattern

| S/N | Title | Project Roles and Responsibilities |
| --- | --- | --- |
| 1 | Saranga Ward Executive Secretary | Project Manager |
| 2 | Municipal Community Development Officer | Project Coordination |
| 3 | Municipal Health and Environment Officer | Project Environmental Protection and Health Expert |
| 4 | Sub-ward Executive Secretary | Secretary and Treasurer |

In ensuring that these roles are adequately implemented, the Ward Development Committee included agenda on improving access to sand mining and harvesting sites as an agenda in its meetings and provides necessary secretariat and financial management directives.

    - Project budget

The budget and expenditure was as presented in Table 10 below which indicates the various cost elements covered for the project. The main source of funding was the Ubungo Municipal Council obtains from its fiscal allocation under the various budget department sub votes especially the Department of Community Development and Department of Health and Environment.

# Table 4.6: Project Budget

| Objective | Output | Activity | Resources Required | Unit | Quantity | Price (TZS) |
| --- | --- | --- | --- | --- | --- | --- |
| - 30 youth at Kimara B engaged in sand mining and sand harvesting sensitized by July 2017. | - Conduct one interactive sensitization seminar | - Consult the local authority leaders and youth community leadership | Stationery Change Agent Participants Venue Fuel | LS | Item | 75,000 |
|  |  | - Establish rapport with the youth community at their sites | Facilitator Change Agent Venue Fuel | LS | Item | 75,000 |
|  | - 20 sand mining youth attended the interactive seminar | - Prepare the subject matter agenda for presentation | Change Agent Refreshments | LS | Item | 30,000 |
|  |  | - Conduct the seminar | Stationery Facilitator | LS | Item | 30,000 |
| - 30 sample youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand based on principles of adherence to the existing regulatory frameworks by July 2017 | - One training on sustainable exploitation of sand sources conducted | - Prepare budget for the training | Change Agent Stationery | LS | Item | 30,00 |
|  |  | - Identify location and develop programme for the training | Stationery Change Agent Experts | LS | Item | 0 |
|  | - 15 youth participated in the training | - Outsource for the experts from the industry | Facilitator Experts Participants | LS | Item | 300,000 |
|  |  | - Conduct training on best practice mining/harvesting procedures and principles on environmental protection | Change Agent Experts Participants | LS |  | 260,000 |
| - Establish and implement sustainable access, exploitation and reliable markets of construction sand by July 2017 | - One meeting involving stakeholders conducted | - Identification of the stakeholders | Facilitator | LS | Item | 100,000 |
|  |  | - Organize stakeholders forum for discussion and consensual resolution | Change Agent Experts Participants | LS | Item | 100,00 |
|  | - A sum of 3,5 million shillings allocative funds collected from Ubungo Municipality | - Identify and promulgate mechanism for preparing local bye-laws and procedures in line with the national regulatory frameworks | Change Agent Experts Participants | LS | Item | 30,000 |
|  |  | - Procure tools/equipment for small-scale sand mining using appropriate technology principles | Spade Crowbar Shovels Wheelbarrow | LS | Item | 660,000 |
|  |  | - Prepare and promulgate Guidelines for Sustainable Exploitation of Sand | Stationery Change Agent Fuel | LS | Item | 50,000 |
| - Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 | - Disseminate the project through local public announcements, FM Radio and print media | - Prepare and fund for the media promotional services | WDC Change Agent Participants | LS | Item | 250,000 |
|  |  | - Identify and engage individuals/leaders/ for the media advocacy | WEO WDC Change Agent | LS | Item | 200.000 |
|  | - Approval/license/registration for sand mining/harvesting sources issued to 10 sand mining youth group; | - Solicit funds for approving/licensing the identified sand mining/harvesting sites for the youth community | WDC | LS | Item | 50,000 |
|  |  | - Conduct continuous environmental oversight | Change Agent Youth Leadership | LS | Item | 150,000 |
|  | - 10 youth engaged in sand mining/harvesting maintain legal access to the identified sand sites | - Inaugurate the sand mining/harvesting project | Youth Change Agent WEO | LS | Item | 125,000 |
|  |  | - Monitor and evaluate on the best practices for sand mining/harvesting among youth | WDC Change Agent Youth Leadership | LS | Item | 570,000 |
| TOTAL (TZS) |  |  |  |  |  | 2,885,000 |

Note: The budget was prepared on the basis of LUMPSUM project costs

Key: LS = Lumpsum

  - Project Implementation

    - Project Implementation Report

The implementation of the project was initiated in 17 May 2017 after securing a   research clearance letter from the OUT Vice Chancellor in conformance with the Community Needs Assessment (CNA) and its resultant findings which enables formulation of the project implementation planning process, development of the necessary information systems and monitoring and evaluation structures. Subsequently, the project activities, outputs, resources and expected impact were identified against the community needs and the available budget for execution of the project.

The level of accountabilities and responsibilities of stakeholders and individual were explicitly identified to ensure unobstructed implementation of the project. These stakeholders and individuals involved the change agent, host organization leadership at Saranga Ward Executive Office through its Ward Executive Committee, Kimara B subward (Mtaa) leadership and representative persons from the youth in sand monitoring/harvesting activities. It was noted this project is characterized by multifaceted attributes and therefore consultation with other extended stakeholders such as environment and occupational health was regularly conducted.

From the foregoing basic information, it is apparent the implementation of the project was premised on a participatory action approach (or in other words principle of exclusivity) which involved various key and extended stakeholders in order to ensure successful implements the project. In this regard, the participatory action process was implemented based on a principle of capacity building. In this principle, capacity building processes of the communities to identify their employment and income related challenges was given greater impetus. The second principle was  based on the change agent’s clear understanding  that the  sand mining/harvesting youth at Kimara B must stay organized in order to make consensual community decisions and carry out actions for their communities’ income and employment related benefits. In order to make community change sustainable, it was critical to build the capacity of youth group since it will create an enabling environment for building upon their own skills and experience to conduct and review assessment and identifying their emerging needs as the project progresses.

In addition, the project implementation was based on notion that the entire process is premised and driven by Kimara B youth. This means that the youth community decides what they want to do, how they want to do it, how they want to present the results, and how they want to use the results for community action. Community-driven interventions were central to ensure successful implementation of this community project. In this regard, development of the project implementation plan (PIP), programme and budgetary needs were made taking into consideration of youth current and emerging needs to realize income generation from sand harvesting trade.

In doing so, various steps of activities were identified by the community with the facilitation of the change agent. Identification of activities was pre-requisite to establishing and understanding the required inputs, expected outputs and impact such outputs would have on the livelihood of the youth community. It was also clearly understood that the activities, inputs and outputs must remain in focus with the project set objectives.

Besides, securing of funds was a crucial issue since any project would involve cost elements. The funding was identified, lobbied from the Ubungo Municipality under the community development sub-vote which is fiscal allocative fund for youth development aspects. The survey, consultation, forum discussions and interviews were subsequently conducted in collaboration with aforementioned stakeholders who provided pivotal information, management support and participated in various roles for the project. Under this intervention the ultimate result was reliable access to mining and sand harvesting of sand which would in turn contribute to reducing income poverty at household level.

It was established that income generation from sand mining and harvesting activities can contribute to reduction of poverty in conjunction of other means of income from other sources as youth may chose from time to time in response to ever changing economic conditions and possibly with absolute effects of spatial interaction. In order ensure project implementation plan remain relevant, close monitoring was conducted by the sand mining/harvesting youth  in collaboration with the Kimara B subward leaders. The change agent participated in the monitoring exercise in collaboration with the group monitoring team, however a comprehensive monitoring activities  and largely the evaluation was not achieved due to time constraint.

However, these important participatory actions are in progress and will be closely followed up. On the other hand , the project evaluation activities was undertaken in terms of pre-evaluation which aided in identifying on whether the project is  feasible  and viable taking into consideration of the various factors with a view to ensure  sustainability and inclusivity of the various stakeholders.

From the foregoing, the project commenced in 2017 whereby consultation with the Ubungo Municipal Council was conducted. A letter of introduction from the University facilitated establishment of interaction and communication with the Council. Thereafter the researcher secured letter from the Council to the Saranga Ward Executive Officer and Councilor’s Officer to enable progression of Community Needs Assessment. The WEO at Saranga refereed the researcher to Kimara B subward (mtaa) Executive Officer for CNA and project implementation.

The project implementation was initiated by contacting the youth leader in at Kimara B whereby project objectives were communicated and project implementation plan jointly prepared agreed based on participatory action among the various stakeholders. Did you complete each and everything? If not explain what remains to be done. However, there are activities which were not accomplished as they require multilateral efforts to formalization and recognition of the activity by the various stakeholders as the project progresses.

The activities which have not been implemented include drafting and promulgation of local bye-laws governing the sustainable exploitation of the sand sources, development of guidelines for assisting the youth access and conduct the business in an environmentally responsible manner and annual evaluation of the project implementation. These backlog activities will be undertaken once the project has taken off and in some instances they may warrant for a new community economic development project to cover for a wider base of communities across the country.

# Figure 4.1: Youth Leader Mr. Cyprian Kayombo Providing His View Among The Participant Community In Meeting Forum 1

# Figure 4.2: Youth Leader Demonstrating Objectives for Their Project in Flip Chart

# Figure 4.3: Change Agent and youth leader taking lead in completion of question in meeting forum 1

# Figure 4.4: A section of youth at identified location for sand harvesting

# Figure 4.5: Youth Leader Mr Kayombo at site with the youth community

# Figure 4.6:  A stockpile of Harvested Sand at site awaiting trucking services

Figure 4.8: Change agent discussion on the progress for the project implementation during meeting forum 3

Figure 4.7: Youth Leader offering assistance for completing questionnaire and discussions

Figure 4.7: Youth Leader offering assistance for completing

Figure 4.8: Change agent discussion on the progress for the

# Figure 4.9: Change Agent, Youth Leader and Youth Community Discussing on Project Implementation during Meeting Forum 3

# Figure 4.10: Project Implementation Gantt Chart

# CHAPTER FIVE

# 5.0 PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

  - Introduction

This Chapter expounds on the important aspects on how monitoring and evaluation of conducted for the sand mining and harvesting project as well identifying salient features which must be advanced at all time to ensure that the project remains sustainable after hand over to the key beneficiaries.  By establishing the key elements for the Monitoring information system (MIS) and Evaluation Information System (EIS), it provided a platform for which monitoring and evaluation of the project was conducted.

It cannot be overemphasized that monitoring and evaluation are important for any project in order to ensure that objectives and goals remain in sight and relevant for the mission and activities. On the other hand, sustainability also implies that the projects lead to improvements that will persist and spread beyond the project boundary and time span, and not create dependency. In this regard, involvement of the various key stakeholders along with maintaining the agreed objectives is prerequisite to project sustainability.

  - Participatory Monitoring

Participatory monitoring helps to provide information during the life of the project so that adjustment can be done if necessary.  Participatory monitoring provides a progressive perspective and involvement of the youth community. This is important so that the researcher was able to determine whether activities are implemented in accordance with plan, or whether the activities are deviating from the objectives so that convenient adjustments can be instituted. In essence monitoring is a continuous assessment that aims at providing all stakeholders with early detailed information on the progress or delay of the ongoing assessed activities.  It is an oversight of the activity's implementation stage.

By implementing participatory monitoring, it was ascertained that outputs, deliveries and schedules have been reached or not so that action can be taken to correct the deficiencies as quickly as possible whilst involving as wide range of stakeholders as required.  As a manifestation of time constraint for this project, the monitoring of this project will be executed by the change agent, youth leaders, Kimara B Subward Leaders and Saranga Ward Leaders.

    - Monitoring Information System

The Monitoring information system (MIS) was developed information with a view to aiding the project management team to plan, organize, and monitor the project. The researcher ensured that sufficient information which can be of interest to all the stakeholders is gathered and disseminated. The monitor information involved collection of data in a form, where all the relevant information indicated how the overall project performance. Monitoring information system was performed in terms by undertaking ongoing review to observe changes/milestones in project implementation. In addition, systematic documentation of the changes was analyzed for the purposes of aiding in decision- making and making reflections.

# Table 5.1: Project Monitoring Information System for Sand Mining and Harvesting Project

| S/N | Categories of Information and activities | What elements are to be monitored | Which types of Records to be kept | Who are Responsible for collection of information | Which is target group for the use of information | How to use information | What Decision to be made and output to be achieved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Work Plan activities | Identified Activity and their timing, fund and resource persons | Periodic plans and their status of implementation | Project Manager, Secretary | Project management team and Ward Executive Committee | Identifying type of activities to be executed, personnel | Assess whether the project milestones are adequate including level of funding |
| 2 | Cost and expenditure | Level of funding to be accessed and associated costs of activities | Financial Reports | Treasurer and Project Manager | Key beneficiary to the project and other stakeholders including funders | Making comparative analysis between expenditure and actual project costs | Assessing adequacy of available budget to meet the actual costs for the project |
| 3 | Staff and supervision | Number of project staff, qualification, position | Roles and responsibilities and their capabilities | Project Manager, and Project coordinator, | Project Management Team, Ward Development committee and stakeholders | Assessing performance of each resource person and accountabilities | Determine whether the project team performs as per desired activity plan and costs |
| 4 | Other inputs | Other identifiable additional inputs | Record of inputs required and minutes from the meetings | Project manager, Secretary, treasurer, Project environment, Health and Safety Coordinator | Project Management Team, Ward Development committee and stakeholders | Monitor adequacy of the planned inputs against emerging ones | Determine whether the additional inputs are required for the project to avert= overspending and backlogging of activities |
| 5 | Results | Training provided to the youth, sand sites identified and mined or harvested | Number of youth trainees and quantity of sand mined, harvested and traded | Project management team and change agent | Project Management Team, Ward Development committee and stakeholders r | Assess outcomes against the project sole objectives | Consider for additional training, coordination with other land use authorities, project closure and possible initiation of another project |
| 6 | Project sustainability | Utilization of the resources and ownership among the target community | Performance progress reports (a | Sand Mining Youth and Change Agent | Project Management Team, Ward Development committee and stakeholders | Holistically assess the response of the community against their initial and emerging needs | Assess level of ownership and commitment of the youth community and stakeholders for collaborative decision making |

    - Participatory Monitoring Method

The participatory Monitoring method adopted for this project was the Self-esteem, associative strengths, resourcefulness, action planning, responsibility (SARAR).  (SARAR) is a participatory approach to training that builds on local knowledge and strengthens local ability to assess, prioritize, plan, create, organize, and evaluate. SARAR is a philosophy and practical approach to adult education that seeks to optimize people’s ability to assess, prioritize, plan, self-organize, take initiatives, and shoulder management responsibilities. The SARAR approach is a methodology based on real life experience and holistic in style that deliberately differs in style from conventional “top-down” methods. Its tenet is relies on a group process; it begins with creating a relaxed and congenial atmosphere in which hierarchical differences are set aside (World Bank Group).

Due to the nature of the project, the researcher considered and applied the method as it involved group psychology in collaborative team building, assess the needs, identifying the priorities, establishing goals, design action plans to be implemented ad monitored. The change agent engaged the youth community in the developing training needs assessment (TNA) and actual training areas to be covered that best suits expected outputs. In order to achieve this, interactive class sessions at Kimara B Primary School were conducted and discussions conducted at site in a relaxed environment in order to systematically shift the project ownership mindset from the change agent to the beneficiary youth group whilst involving other stakeholders.

# Table 5.2: Participatory Monitoring Plan

| Objective | Output | Activity | Indicators | Data source | Methods/ tools | Responsible | Timing |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017. | - Conduct one interactive sensitization seminar | - Consult the local authority leaders and youth community informal leadership | Letter of Invitation and Oral Contact and Sensitization | Project Status Report | Interview and Observations | Project Manager/Coordinator | May 2017 |
|  |  | - Establish rapport with the youth community at their sites | Established collaboration | Project Status Report | Interview and Observations | Project Manager/Coordinator | May 2017 |
|  | - 20 sand mining youth attended the interactive seminar | - Prepare the subject matter agenda for presentation | Prepared Presentation and classroom | Project Status Report | Coaching, interview and Observations | Project Manager/Coordinator | May 2017 |
|  |  | - Conduct the seminar based on participatory approach | Seminar Training Material | Project Status Report | Coaching, interview and Observations | Change Agent | May 2017 |
| - 30 sample youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017 | - One training on sustainable exploitation of sand sources conducted | - Prepare budget for the training | Budget Report | Project Status Report | Interview and Observations | Project Manager/Coordinator | May 2017 |
|  |  | - Identify location and develop programme for the training | Training Programme | Project Status Report | Interview and Observations | Project Manager/Coordinator | June 2017 |
|  | - 15 youth in sand mining activities participated in the training | - Outsource for the experts from the industry | Availability of Health, Safety and Environmental experts | Project Status Report | Interview and Observations | Project Manager/Coordinator | June 2017 |
|  |  | - Conduct training on best practice mining/harvesting procedures and principles on environmental protection | Training Material | Project Status Report | Interview and Observations | Project Manager/Coordinator | June 2017 |
| - Identify locations for sand harvesting and establish and implement sustainable exploitation of natural resources by July 2017 | - One meeting involving stakeholders conducted | - Identification of the stakeholders | Acceptance of stakeholders | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
|  |  | - Organize stakeholders forum for discussion and consensual resolution | Forum Discussions | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
|  | - Location for sand harvesting and mining identified | - Identify location for sand mining and harvesting | Location identified | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
|  |  | - Procure tools/equipment for small-scale sand mining equipment using appropriate technology principles | Tools, equipment | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
|  |  | - Prepare and promulgate Guidelines for Sustainable Access and Trading of Sand | Guidelines prepared and promulgated | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
| - Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 | - Disseminate the project through local public announcements, FM Radio and print media | - Prepare and fund for the media promotional services | Media Promotion Material prepared | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
|  |  | - Identify and engage individuals/leaders for the media advocacy | Advocacy conducted` | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
|  | - Approval/license/registration for sand mining/harvesting sources issued to 10 sand mining youth group; | - Solicit funds for approving/licensing the identified sand mining/harvesting sites for the youth community | Funds availed and | Project Status Report | Interview and Observations | Project Manager/Coordinator and Treasurer | July 2017 |
|  |  | - Conduct continuous environmental oversight obligations at local level | Environment assessment conducted | Project Status Report | Interview and Observations | Project Manager/Coordinator | July 2017 |
|  | - 10 youth in sand mining/harvesting maintain legal access to the identified sand sites | - Inaugurate the sand mining/harvesting project | Sand mining and harvesting commences | Project Status Report | Interview and Observations | Project Manager/Coordinator, WEO | July 2017 |
|  |  | - Monitor and evaluate on the best practices for sand mining/harvesting among youth | Monitoring and Evaluation Report | Project Status Report | Interview and Observations | Project Manager/Coordinator,,WEO | July 2017 |

Source: researcher, 2017

  - Participatory Evaluation

Participatory evaluation is an approach that involves the stakeholders of a project with the intention of maximizing degree of ownership and determining causes and effects of the project outcomes as they progress within a life cycle.  In this project, stakeholder involvement was triggered at various stages of the evaluation process, from the evaluation design, data collection and analysis and the reporting of the research. In this project, participatory approach was adopted for impact evaluation design, and with using qualitative data such as face-to face interviews and visits mining and harvesting where youth quantitative were consulted.

It is important to consider the purpose of involving stakeholders and which stakeholders should be involved how, in order to maximize the effectiveness of the approach. In order to realize this goal involvement of the beneficiary youth community, ward and sub-ward leadership and the change agent were effectively involved.

    - Performance Indicators

Performance indicators are measurable values which indicate the degree of success or level of achievement of a project.  Performance indicators can be identified in either from qualitative, quantitative, leading or lagging indicators. The qualitative and quantitative indicators involve those which cannot quantifiable and quantifiable in measurable units respectively. Also, leading indicators are those which predict the outcome of a process whilst lagging indicators are those which present the success or failure of a process or activity post hoc.

In this respect, quantitative performance indicators in this project included number of stakeholders meetings, number of participants, type and quantity inputs collected, number of sand harvesting sites identified and quantity of sand harvested/mined. In addition, reports produced and meeting minutes, stakeholder’s discussions and training material preparation are among the qualitative indicators. Both qualitative and quantitative performance indicators could be either leading or lagging by characteristics. Table 5.3 shows the project performance indicators.

# Table 5.3: Project Performance Indicators

| Objective | Output | Activity | Input Required | Performance Indicators |
| --- | --- | --- | --- | --- |
| - 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017. | - Conduct one interactive sensitization seminar | - Consult the local authority leaders and youth community informal leadership | Youth, WEO change agent | Number of plans |
|  |  | - Establish rapport with the youth community at their sites | Youth, other stakeholders, change agent, stationery | Number of meetings |
|  | - 20 sand mining youth attended the interactive seminar | - Prepare the subject matter agenda for presentation | Youth, other stakeholders, change agent | Presentations in sand harvesting methods |
|  |  | - Conduct the seminar based on participatory approach | Youth, other stakeholders, change agent, stationery | Records of seminar |
| - 30 sample youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017 | - One training on sustainable exploitation of sand sources conducted | - Prepare budget for the training | Youth, other stakeholders, change agent, stationery | List of inputs available |
|  |  | - Identify location and develop programme for the training | Youth, other stakeholders, change agent, stationery | Number of sites for sand harvesting |
|  | - 15 youth in sand mining activities participated in the training | - Outsource for the experts from the industry | Youth, other stakeholders, change agent, stationery | Number of experts from NEMC and Ubungo |
|  |  | - Conduct training on best practice mining/harvesting procedures and principles on environmental protection | Change agent, stakeholders stationery | Number of Training Sessions |
| - Identify locations for sand harvesting and establish and implement sustainable exploitation of natural resources by July 2017 | - One meeting involving stakeholders conducted | - Identification of the stakeholders | Change agent, WEO | Number and type of stakeholders |
|  |  | - Organize stakeholders forum for discussion and consensual resolution | Change agent, WEO | Forum conducted |
|  | - Location for sand harvesting and mining identified | - Identify location for sand mining and harvesting | Youth, WEO, other stakeholders, change agent | Number of sand mining/sand harvesting sites |
|  |  | - Procure tools/equipment for small-scale sand mining equipment using appropriate technology principles | Change agent, WEO, Youth | Type and number of tools and equipment |
|  |  | - Prepare and promulgate Guidelines for Sustainable Access and Trading of Sand | Change agent, WEO, Youth | Guidelines prepared |
| - Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 | - Disseminate the project through local public announcements, FM Radio and print media | - Prepare and fund for the media promotional services | Change agent, WEO | Number and outlets for media promotion |

    - Participatory Evaluation Methods

Participatory Rural Appraisal (PRA) was adopted as the convenient evaluation method owing to the geographical and ethnography of the locality and need for incorporation of already available local knowledge and opinions among the sand harvesters to facilitate review of activities and overall management of the project.

In PRA approach, the researcher engaged the youth community by inquiring which or what are the challenges which have been encountered during planning and implementation of identifiable activities based on set objectives. By drawing information on the challenges, the researcher created a sound basis for making conclusion on the achievement, milestones and backlog to be addressed as the project progress and as it was concluded. Active involvement of the youth community (principal beneficiaries), Mtaa leaders, Ward Development Committee, and other community member was pivotal to conducting inclusive evaluation.

However, due to time and resource constraints, the researcher employed observation method coupled with forum discussions involving all the stakeholders who had various roles and responsibilities. The researcher as change agent repeatedly assessed the project implementation plan (PIP) and took note of the progress attained at various levels along the project life cycle. The information gathered by the researcher during the evaluation phases was shared among the stakeholders for building consensus and collective measurement of progress made for various activities.

    - Participatory Evaluation Summary

# Table 5.4: Participatory Evaluation Summary

| Objective | Output | Activity | Performance Indicators | Expected Outcome | Actual Outcome | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| - 30 youth at Kimara B in sand mining and harvesting identified and sensitized by July 2017. | - Conduct one interactive sensitization seminar | - Consult the local authority leaders and youth community informal leadership | Number of plans | Project Plan developed | Project Plan developed and promulgated | Completed |
|  |  | - Establish rapport with the youth community at their sites | Number of meetings | One Meeting with the target youth | One meeting conducted at Kimara B Primary School | Comprehensive interaction achieved. |
|  | - 20 sand mining youth attended the interactive seminar | - Prepare the subject matter agenda for presentation | Presentations in sand harvesting methods | One presentation made | Presentation accomplished | Inclusive approach was used to get consensus on project issues |
|  |  | - Conduct the seminar based on participatory approach | Records of seminar | One seminar conducted | One Seminar prepared | Seminar will be reactivated at the end of the project to further indoctrinate |
| - 30 sample youth are acquainted with the skills, knowledge on how to manage, exploit and trade sand by July 2017 | - One training on sustainable exploitation of sand sources conducted | - Prepare budget for the training | List of inputs available | Training budget | Training budget secured | Completed |
|  |  | - Identify location and develop programme for the training | Number of sites for sand harvesting | Harvesting sites identified | One harvesting site identified | Training programme implemented |
|  | - 15 youth in sand mining activities participated in the training | - Outsource for the experts from the industry | Number of experts from NEMC and Ubungo | One Expert consulted and engaged | Expert provided guidance | Sustainable use of natural resources indoctrinated |
|  |  | - Conduct training on best practice mining/harvesting procedures and principles on environmental protection | Number of Training Sessions | One Training accomplished | One Training completed | Training recurrence is important for indoctrination |
| - Identify locations for sand harvesting and establish and implement sustainable exploitation of natural resources by July 2017 | - One meeting involving stakeholders conducted | - Identification of the stakeholders | Number and type of stakeholders | 6 Stakeholders identified | Stakeholder actively participated | Inclusiveness should be upheld to project wind up |
|  |  | - Organize stakeholders forum for discussion and consensual resolution | Forum discussion conducted | One forum discussion conducted | 20 stakeholders participated | Multi-sectoral approach to exploitation of natural resource was key |
|  | - Location for sand harvesting and mining identified | - Identify location for sand mining and harvesting | Number of sand harvesting sites | 2 locations identified | 2 locations identified | Multi-sectoral approach to exploitation of natural resource was key |
|  |  | - Procure tools/equipment for small-scale sand mining equipment using appropriate technology principles | Type and number of tools and equipment | 7 shovels, 2 pick axes and 1 wheelbarrow procured | 5 shovels, 2 pick axes and 1 wheelbarrow procured | Youth community procured by using own contribution funds |
|  |  | - Prepare and promulgate Guidelines for Sustainable Harvesting of Sand | Guidelines prepared (Appendix 2) | 1 Guideline prepared by change agent and promulgated | Guideline prepared by change agent and promulgated | Recurrent sensitization of best practices contained in the guidelines planned |
| - Indoctrinate on environmental protection/adaptation methods for sustainable exploitation of natural resources at Kimara B and its vicinities by July 2017 | - Disseminate the project through local public announcements, FM Radio and print media | - Prepare and fund for the media promotional services | Number and outlets for media promotion | Funding for promotional services solicited through WEO | Funding not availed | Change agent to use own……….. for reimbursement |

  - Project Sustainability

Sustainability aspect for this project was regarded more than just development activities that are environmentally sensitive. Sustainability also implies that the projects lead to improvements that will persist and spread beyond the project boundary and time span, and not create dependence.

In order to maintain sustainability for the youth project, interventions elucidated in the project implementation plan (PIP), Information systems, monitoring and evaluation processes have created structures and solutions that will remain institutionally, economically, socially, and environmentally viable when the project ends. The researcher maintains that continuous inclusivity of the male youth community and other important stakeholders shall ensure that appropriate level of benefits are realized for an extended period after the project has ended. In this project, the greatest influences on project sustainability were determined during planning of the project with the underpinning participatory action of the stakeholders in mind. The following factors and activities were focal points to achieving project sustainability for this project.

    - Links Between the Project and National or Regional Activities

The researcher exerted great impetus in ensuring that the project is related to Ward and Municipal activities and priorities particularly those associated with the willingness of the Municipal Authorities, through its own or donor funding, to support income generating projects for the youth in a bid to alleviating poverty among the community. This was an importance phenomenon to increase the likelihood of the continuance of project activities or benefits once external assistance has ended.

    - Links Between the Project and Key Stakeholder Priorities

It was made pre-requisite that all changes to the project remain sustainable through addressing real needs of the youth community and on account of their priorities as they were. The researcher remained aware that a project addresses needs considered important by the youth community to make it successful throughout its life.

    - Financial and Economic Conditions of the Project

A project that depends on external inputs or funding does not lead to long-term change. Large amounts of money being put into a project do not necessarily mean that the project will work, and can sometimes do more harm than good. In this, the project was designed and implemented such that the youth community can help themselves from where it is wound up. The researcher endeavored to build the long-term capacity of beneficiaries so as to make it realistic and beneficial beyond the life of the project.

    - Choice of Technology for the Project

The researcher also understood the fact that working with unemployed youth in sand mining and harvesting environment would require tools and methods to ensure sustainable exploitation of the natural resource. There was no need of introducing new technologies to the target group, or rely heavily on a particular technology then the technology introduced was appropriate for the costs and the culture of the beneficiary community.

    - Participation and Local Ownership

The researcher made all the necessary engagement to ensure that project is implemented based on principles of inclusive and continuous involvement of the key beneficiaries from start to finish. Through active participation ownership of the project for sand harvesting was realized. It cannot be overemphasized that people living in economic in hardships have a tendency to quickly turn to exploitation of resources rather than other entrepreneurial means. Therefore, by improving access and practicing principles of sustainable use of resources, the youth community will own the project and possibly generate other allied projects thereof. Ownership of this youth project was further emboldened by trust that was developed among various stakeholders indicated earlier in this project.

    - Environmental Conservation and Climate Change Adaptation

The protection of natural systems represents not an overarching panacea for achieving economic vitality in the community, but a necessary component of an entire system for achieving economic, social and environmental ‘sustainability’, in which economic prosperity and social reforms are as important. In this respect, the change agent consider it a matter of utmost importance to integrate the concept environmental conservation and climate change adaptation with the purpose of achieving and maintaining sustainable project by the community. It cannot be overemphasized that the concept of development encompasses the various inter-linking paradigms including environment conservation and climate adaptation.

    - Financial Factor for the Project

Initial and progressive and sometime unforeseen intermittent financial demands must be met by the community members through their structured community group as provided for in their draft constitution. In addition, other key stakeholders particularly the host organization must be braced to facilitate the youth to access funding for financing their activities. However, the youth community had shown commitment towards self-sustaining funding through their own contributions since the project was dependent on marginal funding.

    - Political Factor for the Project

The change agent has been fully conscious that prevailing political climate is among the most important overarching factors which can either promote or demote project sustainability resulting into to steady or absolute failure of the entire project. In all fairness, good politics is panacea to harmonious, peaceful coexistence and development as desired for any community. However, the current factual information obtained from  various sources indicate that the political climate at Kimara B was engrossed in visible political tensions between the ruling party (CCM) and the majority elected party at Ubungo District (CHADEMA). These ensuing and existential discords, if remain unchecked, are recipe to non-sustainability of the project.

Therefore, the change agent urged the ward leadership to promote and sustain amicable and harmonious political atmosphere in order to realize long term benefits from the various community development projects including this one.  A case in point is the ongoing civil proceeding against the CHADEMA Councilor which was filed by the Ward Executive Officer recently at the Magistrate court which was proposed to be settled based on mutual understanding and respect for the interest of the wider community.

# CHAPTER SIX

# 6.0 CONCLUSION AND RECOMMENDATIONS

# 6.1 Introduction

From the foregoing Chapters, the researcher has managed derived a wide variety of conclusions and recommendations based on the effectiveness participatory needs/action assessment on one hand; and the available information and observations during the project implementation on the other.  In this respect,   conclusion to this research basically is drawn from the results and perception gained from participatory needs assessment, prioritization, literature review, implementation of the project, monitoring and evaluation (M&E) and project sustainability by considering other cross cutting issues and actors.

On the other hand, the recommendations derived in this project are based on the change agent’s   and community’s  reflections  on the existing opportunities and challenges that can either be exploited or overcome to ensure that the project remain relevant and be regarded as a viable  and responsibly community driven economic effort as well as contributory towards the general body of knowledge in formulating policies and mechanisms that can support other corresponding communities in the initiation and implementation of sustainable community economic development projects.

  - Conclusion

The participatory action assessment of the male youth community was conducted with the purpose of establishing the overarching approach towards identification of social economic challenges experienced by this small group of the community at Kimara B (Temboni). In-depth appreciation of the real and emerging community economic challenges were pivotal to making reflections of the priorities taking into consideration of the community assets, accessible natural resources and a general  community refection on available factors of production at community level  for propelling their economic wellbeing. In this regard, through social mapping the researcher identified a range of sources of income and employment for the male youth at Kimara B with their associated benefits and barriers as well.   The salient features underlying such opportunities as well as barriers were inclusively assessed and analyzed through use of research tools such as questionnaires, covert non- participant observations, randomized face to face discussions and key informant interviews.

From the Community Need Assessment, it was established that 80%of the respondents earn a monthly income ranging between 50,000 TZS - 100,000 TZS. This clearly indicates that a sizeable proportion of the youth community earn significantly low income on monthly basis. Besides, the lowest income bracket group was more pronounced in age group between 31 and 35 years of age which again explains the degree and extent of the scourge of income poverty and prevalence of unemployment in the community.

Much interestingly, since this “oldest” group is both belonging to the “poor of the poor” and unemployed, it can be interpreted a great deal of efforts need to be exerted to this widely expanding problem through equitable use of community assets and natural resources.  In this respect, community-based and controlled use resource use of available resources is pre-requisite to increasing income generation and prosperity among Kimara B youth community. The hierarchy of the economic needs pointed towards use of natural resources as downward pressure for the community to meeting their social economic needs.

From the foregoing analysis, it apparent that the host organization and other stakeholders are constrained towards achieving sustainable use of the community assets thus ensuring project survival, longevity and adoption by other communities with similar social characteristics elsewhere.  In conclusion, the descriptive statistics indicate the community’s inclination and; possibly, over-reliance towards exploitation of the natural resource at their disposal for economic prosperity.

Literature review attest through the Poverty and Human Development (PHDR) issued in year 2002 estimated that 92 percent of youth have primary level education but with no formal skills training. They lack capital and business premises. In many municipal areas the informal sector includes also men and women engaged in sand mining, quarrying and lime making to support the growing construction industry.

In this perspective, literature review indicated that sand harvesting or mining is an alternative income generation activity and it demands marginal financial capital for start-ups finance and running the trade.  Once harvesting locations have been identified, sand can be harvested on budgeted phases and transported to customers by the trucking services.  Since the ancient times and for as long as human race is in existence, sand will continue to remains an indispensable natural resource for various needs particularly housing and other associated infrastructure.

The researcher identified 4 project objectives which were aimed at improving livelihood of male youth engaged in sand harvesting activities. These objectives were further interpreted into activities and outputs’ that were expected from the overall project implementation process.  The researcher in participation of the 30 male youth stakeholders conducted planning and collaborative decision making in the implementation of the plan and activities based on the available resources. The major activities included training on managing and exploitation of sand from natural sources and inclusive identification of sand two harvesting sites. Each of the identified stakeholders had their definitive roles and responsibilities which they had to execute for the purpose of attaining the primary goal to improving livelihood.

The change agent was also cognizant of the fact that a community-based project can only be successful where participatory monitoring and evaluation is collaborative implemented by the various stakeholders.  In achieving this, the change agent adopted SARAR (Self-esteem, associative strengths, resourcefulness, action planning, and responsibility) as participatory monitoring method whilst Participatory Rural Appraisal (PRA) was adopted as the evaluation method for the project. Choice of these methods was made by taking into consideration of their proven effectiveness and making the researcher draw as much consensual understanding of the project milestones and commitment from the stakeholders as possible.

It was estimated that about 90% of the project implementation plan (PIP) was executed in accordance with the presumed timelines save for minor constraints associated with, but not limited to,  delay in coordination and response by the authorities, time lag for identification and assembling of the community and preparation of training material.  The change agents sustained vigilance on the need for sufficiently meeting the project objectives and ensure sustainability by incorporation of key beneficiaries and other necessary multi-sectoral factors.

  - Recommendations

From the foregoing findings and observation for the project, the change agent would advance the following recommendations primarily to ensure project sustainability, continuous ownership among the key beneficiaries and resultant improvement of livelihood of the youth community.

    - Recommendation on the Participatory Assessments

Community need assessment is a relatively effective and results-oriented participatory approach to identifying and implementing project with greater direct impact to the beneficiary community.  In order to ensure continued project sustainability, data obtained from the CNA should be used to guide resource allocation by analyzing and monitoring of income generation, identifying risk factors and potential community problems, and determining community assets.

In addition, the CNA conducted for this project has resulted in an informed planning and implementation of essential economic activities and use of natural resources. It is apparent that the CNA has allowed for increased awareness among the youth communities by engaging the community members in decision making and guide programme implementation. By accommodating the needs and priorities of the community ownership of the project and its sustainability are expected to be realized.

    - Recommendations on the Project Design and Implementation

The project design was based on both quantitative and qualitative methods in order for the researcher. Both project designs are inherently essential in identify and defining social economic and environmental factors associated with the project. It was established by the change agent that the project attributes were associated with the social, economic and environmental dimensions. These attributes and how they have been addressed in this participatory research are as indicated in 6.1

# Table 6.1: Intrinsic Project Attributes and Researcher’s Action for Project Implementation

| Development Dimension | Attributes | Change Agent’s Action on Dealing with the Attribute for Project Implementation |
| --- | --- | --- |
| - Social | - Impact on local community livelihood | Conducted CNA and prepared participatory Project Implementation Plan in response to the community perspective |
|  | - Benefits to disadvantaged groups | Played a role as change agent by conducting analysis of the youth on the rate of unemployment, level of poverty and priority economic needs and activities |
|  | - Health and Safety | Played a role as change agent by conducting participatory training on vocational health and safety to sensitize the community |
| - Economic | - Creation of employment and market opportunities | Played a role as change agent to sustainable use sand for income generation and improvement of livelihood |
|  | - Creation of value addition | Played a role as change agent by conducting training on establishing links with the customers |
| - Environmental | - Reduced Impact on human health | Prepared, and promulgated a Guideline on Sustainable Sand harvesting Practices |
|  | - Environmental protection practices | Prepared and promulgated a Guideline on Sustainable Sand harvesting Practices |

Source: researcher, 2017

The researcher has noted that there is an involuntary tradeoff between economic growth and environment because of desire to high growth and excessive use of resources as a response for improving livelihood among youth.  Unemployed and unskilled male youth as has been observed in this project overwhelmingly rely on natural resources for their daily livelihood. Because they need these resources desperately to fend for their dependants as has been demonstrated in the descriptive statistics, they have little choice, without assets or income, but to utilize the available natural occurring resources.

From the quantitative research data, the researcher has become aware that as the income generation of the youth improves the likelihood to net increase in environmental concerns tend to occur. When the natural resource takes a centre stage as principal factor of production, the two aspects of economics on one hand  and; environment on the other become inseparable. Therefore, it’s obvious that meeting increasing economic demand while keeping environmental within acceptable margin is of paramount importance. In this regard, the researcher was quite observant that multi-sectoral approach to project implementation is important in order to strike a “trade-off” among social, economic and environmental demands. In this way, project sustainability will be realized for a long-term without jeopardizing other competing dimensions of development concept.

Based on the foregoing, the change agent recommends that the concerned Authorities with possible conflicting mandates should negotiate to facilitate an enabling environmental for community projects reliant on natural resources in a bid to alleviate ever increasing rate of unemployment among youth. It cannot be overemphasized that increased spatial interaction is exerting downward pressure on the human economic needs especially among urban youth such as those at Kimara B. With such a clear vision and strategy, equitable improvement of livelihood among youth will have a far reaching economic impact among male youth engaged in sand harvesting.  In the event this vision is achieve, the youth community would have accomplished Goal 12 of the Sustainable Development Goal (SDG) to the Conference of Parties (COP-21) which recognizes the need for ensuring sustainable consumption and production patterns of resources.

    - Recommendations on the Literature Review

In the United Republic of Tanzania as a whole, data and information on harvesting of sand is obtainable from various sociological and engineering practice archives. As a constituent material that supports housing and construction development in communities, its use is inevitable to ramp up livelihood in small scale and large scale infrastructure projects. In this regard, developing and promulgation of best practices and sustainable utilization of sand will be of great impact to the community. The best practices will be in form of Guidelines to Sustainable Use of Sand from Natural Sources which takes into account on the environmental protection and adaptation factors.

Other developing countries like the neighboring Kenya, India and Jamaica have had such practices to respond to such resource-dependent community needs and in particular pressures on improvement of infrastructure and income generation demands brought about by spatial interaction and economic needs of the swelling youth population. Besides, it cannot be overemphasized that the Guidelines will serve as “best practice” reference on sustainable use of the diminishing resource and improvement of livelihood among male youth at Kimara B.

    - Recommendations on the Monitoring, Evaluation  and Sustainability

It has been established elsewhere that participatory monitoring and evaluation methods were essential tools in ensuring that the youth community at hand have clear stake and remain at the central core of implementation and assessing project milestones, outputs and impacts at various intermittent levels as project progresses. This was accomplished through forming committed leadership, inclusive review of the plans and maintaining engagement of Subward (Mtaa) and Saranga Ward leaderships as pre-requisite. By doing so, the sustainability of the project is ascertained since the community is at the nucleus of the project; are actively informed by their leadership and continue to receive technical and logistical support from the WEO, Ward Development Committee (WDC) and other stakeholders. Based on the above, the change agent recommends that lines of communication and the already established mechanism for collaboration must be maintained among the stakeholders including providing recurrent training and sensitization sessions of the youth community on sustainable community development at their local level

    - Recommendations on Policy-Making on Youth Economic Development

The National Youth Development Policy (NYDP) promulgated in 2007 by the Ministry of Labour, Employment and Youth Development provided vast participatory and recognition of youth as an important group for driving economy at local and national levels. In section 3.4 of the policy, it is explicitly stated among other things, that the government shall promote equitable access to land and other resource allocations in order to achieve economic empowerment among various groups of youth.

In this respect, the local authorities should recognize the need for implementing the policy in a bid to addressing youth economic challenges in short, medium and long terms. Furthermore, in conjunction with the economic empowerment among youth, the policy recognizes the fact that most youth groups are not sufficiently knowledgeable on environmental issues, which was also attested from the results of the questionnaire and needs prioritization for this project. To a large extent, youth are not adequately involved in management of environment and conservation of natural resources. In response to this challenge it is stated in section 3.19 of the policy that there shall be a mechanism and strategies to involve the youth in the development, protection and conservation of the natural resources and environment.

From the foregoing, it is recommended that local authorities should enhance coordination with other community administrative organs in addressing all cross cutting issues rather than imposing unilateral sanctions against each other. Efforts to striking a balance on conflicting equally important development paradigms would be an appropriate means in addressing factors associated with sustainable community economic development.

# REFERENCES

Binoy, A. M,, Shiney V. and Kicho, P. (2013). “River Sand Inflow assessment and Optimal Sand Harvesting Policy Development”, Karela, India.

Bristol Bay Native Association, (2004).  “Community and Economic Development”, Guidebook, Alaska, USA.

Garth, A. (2008). “Analyzing data using SPSS”, (A practical Guide), Sheffield Hallam University. London, UK.

Government of India, (2016). “Ministry of Environment, Forest and Climate Change”, Sustainable Sand Mining Management Guidelines, New Delhi, India.

Kareem, A. O. C. & Shaheed, R. (2016). Social, Economic and Environmental Effect of Sand Mining, The International Journal of Humanities & Social Studies, 6(10), 2321 – 9203.

Kothari, R. C. (2004).  Research Methodology, Methods and Techniques, 2nd Ed., New Delhi: International Printing limited.

Magigi, W. (2015), Project Design, Implementation and Resource Mobilization in Competitive Economy, 2nd Ed., Rotterdam: Safi Publishers and Trading Company.

Muendo, M. N. (2015).  The Socio-Economic Effects of Sand Harvesting in River Thwake, Kathiani Division, Machakos County, Journal of Education and Practice , 6(24), 88-97.

Performance Audit Report No. 3 of 2012. Performance Audit Report on Management Sand and Gravel Mining Operations by the Department of Mines, Office of the Auditor General, Gaborone, Botswana.

Republic of Kenya, (2007), “National Environmental Management Authority, National Sand Harvesting Guidelines”, Nairobi, Kenya.

The United Republic of Tanzania, (2004). “The Prime Minister’s Office, The National Economic Empowerment Policy”. Dar es Salaam, Tanzania.

The United Republic of Tanzania, (2005). Vice President’s Office, National Strategy for Growth and Reduction of Poverty (NSGRP). Dar es Salaam, Tanzania.

The United Republic of Tanzania, (2007). National Youth Development Policy, Ministry of Labour, Employment and Youth Development. Dar es Salaam, Tanzania

United Nations Department of Economic and Social affairs, (2003), “Poverty Eradication and Sustainable Livelihood - Focusing on artisanal mining communities”. Halale, Zimbabwe.

United Republic of Tanzania, (2006). “Women Affairs and Children, Community Development Policy”, Ministry of Community Development, Dar es salaam, Tanzania.

# APPENDICES

APPENDIX 1 – INTERVIEWER ADMINISTERED QUESTIONNAIRE

Appropriate box shall be ticked

SOCIAL AND DEMOGRAPHIC ELEMENTS

- Marital Status of the Respondent

Single                       Married                  Widower              Divorced

- Age of the male youths Respondent

Between 18 – 23

Between 24 – 29

Between 30 - 35

- Education Level of the Respondent

Primary

Secondary

Vocational

College

None

- Number  of Dependants for the Respondent

Between 1 and 2

Between 3 and 4

5 or greater

None

- Monthly Income of the Respondent

Between 50,000 TZS and 100,000 TZS

Between 101,000 TZS and 200,000 TZS

Between 201,000 TZS and 300,000 TZS

Greater than 301,000 TZS

- Status of Employment

Self employed

Casually employed

Formally Employed

Unemployed

COMMUNITY ECONOMIC NEEDS AND SUSTAINABILITY ELEMENTS

- What major  social economic problem expeienced by the youth at Kimara (B)Temboni?

Absence of reliable source of income

Poor water quality

Poor access to Education services

Environmental degradation

Poor access to health services

- In the event, you are  unemployed, mention which activity you will engage forn generation of your income ( to reseacher this question was set after study of the available community assets and natural resources)

Motocycle Taxi services (bodaboda)

Sand mining/harvesting for selling

Mason Technical Auxiliary (Fundi Ujenzi)

Vocational Training for Employment

Vegetable husbandry (kilimo cha mboga)

- In the event that  your prefered income generation activity doesn’t appear in question 8 above, which economic actvity would you opt for income generation ?

- What is your view regarding the positive impact of exploitation of natural resources on income generation?

Very high

High

Average

Poor

- Is access to natural resources for income generation convenient for you?

Favourable

Fairly favourable

Least favourable

Unfavourable

- What is your view on the importance of commitment towards sustainable exploitation of natural resources?

Strongly agree

Agree

Disagree

Not sure

- Which area do you consider you require training to enable to achieve your goal in question 8 or 9 above?

Vocational Training

Entrepreneurship

Environmental Conservation

Occupational Health and Safety

Husbandry

- Which other area apart from indicated in question 13 do you consider you require training?

- In case you consider, exploitation of natural resources is the best means for income generation, what is the level of your Environmental Conservation awareness?

High

Average

Poor

Very Poor

- In case you consider Occupational health and safety awareness is very important, what is your level of awareness?

High

Average

Poor

Very Poor

Appendix 2: Guidelines for Sustainable Harvesting of Sand from Natural Sources

Guidelines for Sustainable Harvesting of Sand from Natural Sources

JULY 2017

FOREWORD

This guideline has prepared for the community environmental protection practice This version recognizes the need to adherence with environmental standards and practices that are required in order to ensure sustainable economic development among sand harvesters while taking integrating factors associated with environmental protection, conservation and adaptation to climate change.

This guideline presents procedures and practices that are recommended to be implemented in order to mitigate environmental concerns during sand harvesting from natural sources. In general, the youth community members in their association or as individuals should conform to the recommendations in accordance with what is deemed to be acceptable practice and with regulatory requirements. Variations may be made to accommodate special circumstances if they do not detract from the intent of the guideline.

TARGET GROUP

The target group which is intended to follow these guidelines is youth engaged in sand harvesting and mining activities as means of income generation and improvement of their livelihood

OVERVIEW

Source of harvesting sand  such as rivers is naturally mobilized through aquatic transportation and the sand deposits accumulates in the river banks and forms dunes in the vicinities of rivers or areas close coastal zones.  Traditionally, scientific and environmental friendly methods of sand mining were followed. The sand thus mined was replaced in the rain that followed through aquatic activity. As the local demand for sand increased due the increased demand from the construction sector and employment, the sand mining is now undertaken indiscriminately by vendors and self employed people.

The Kimara B youth have a wide diversity of occupations and responsibilities. Many are involved in different types of economic activities, which are expected to be executed in a cost effective and environmentally responsible manner. A proportion of Kimara B youth community is engaged in harvesting sand from natural sources such as river tributaries and other material deposits. Therefore, responsible environmental management is an inherent part of performing these activities for all the community members.

Furthermore, the Kimara B youth community engaged in sand harvesting work in unison and commune involuntarily as they search for their daily survival.  They frequently work as a team to meet their livelihood desires and needs. An individual community member may or may not have control of, or be solely responsible, for a particular project. To the extent possible, they should understand and manage the environmental aspects of sand harvesting activities they are involved in. All youth are expected to exercise due diligence in the execution of their work. That expectation includes practicing harvesting procedures in accordance with their constitution, and national laws, bye-laws and other established guiding standards.

PURPOSE OF THESE GUIDELINES

The  purpose  of  this  guidelines  is  to  inform,  provide  guidance,  and  to  encourage members and the community to be pro-active in the protection and stewardship of the Environment.

ENVIRONMENTAL PRACTICE

This Guideline for Sustainable Harvesting of Sand from Natural Sources has been prepared to provide advisory guidance on the best practice for sand harvesting in order to ensure sustainability of the economic activity. The formulation of this guideline recognizes the prominent role of Kimara B youth members who are not only concerned with economic development projects and their maintenance, but also with a wide variety of environmental management responsibilities.  Environmental degradation is recognized as a risk to public welfare, and in response community are urged to protect, preserve and enhance the quality of the built environment. The long term objectives are to sustain the viability of our ecosystem, and to ensure that the well-being of future generations is not compromised.

The community members shall recognize that stewardship of the environment is a responsibility of all, and the public expects responsible and sustainable practices in environmental management.

Kimara B youth community shall also recognize the need for continuing development for the benefit of society. A balanced approach will most likely create development that will meet the needs of society. Integrating fundamental environmental sustainability with social and economic considerations will require the community to be innovative and creative in their planning and design of sand harvesting projects. In its broader context, the community shall take a more holistic role in shaping the future, by not only being innovative, but by showing to others how these innovations advance the interests of the following:

- Public safety, health and welfare,

- the natural environment,

- risk mitigation and management, and

- social and cultural values.

SUMMARY OF GUIDELINE

The Kimara B community members are committed to environmental protection and safeguarding the well-being of the public.  Therefore, the community shall

- develop and maintain a reasonable level of understanding, awareness, and a  system of monitoring environmental issues related to their economic activities;

- use appropriate expertise of specialists in areas where the community knowledge alone is not adequate to address environmental issues;

- apply knowledge and responsible judgment in their environmental considerations;

- ensure that environmental planning and management is integrated into all their activities;

- include the costs of environmental protection among the essential factors used for evaluating the economic viability of projects for which they are responsible;

- recognize the value of environmental efficiency and sustainability, consider implementation of Life-Cycle Project Assessment to determine the benefits and costs of additional environmental stewardship, and endeavor to implement efficient, sustainable solutions;

- engage and solicit input from stakeholders in a collaborative manner;

- comply with regulatory requirements by striving towards the application of best available, cost-effective technologies and procedures;

- disclose information necessary to protect public safety to appropriate authorities; and

- work with others in a participatory approach to improve environmental understanding and practices.

Based on the procedures above, the target community members should take active and cooperative role to assist the society to meet environmental challenges. This could apply even though the individual communities members may primarily be involved in economic activities that are apparently have no bearing to environmental concerns. The community is responsible for maintaining their knowledge in areas that have a bearing on the quality of environment and effect of their economic activities.

The foregoing responsibilities and procedures do not imply that every individual member can or should be an environmental specialist. The general obligation is to possess sufficient knowledge of relevant environmental issues to be able to competently judge possible risk factors and mitigation measures when engaged in sand harvesting. Given the low education and unskilled nature of the community, these guidelines have been prepared and promulgated to indoctrinate the community towards understanding on environmental factors and best practices during exploitation of the natural resource.