IMPROVING LIVELIHOOD OF NGUZO NYARUGUSU REFUGEE WOMEN GROUP BY CONSTRUCTING A BEADS PRODUCTS SHOP IN NYARUGUSU REFUGEE CAMP, KASULU DISTRICT, KIGOMA

PHOIBE JOHN MOLLEL

A PROJECT REPORT SUBMITTED IN PARTIAL FULFILLMENT FOR THE REQUIREMENTS FOR THE DEGREE OF MASTER IN COMMUNITY ECONOMIC DEVELOPMENT OF THE OPEN UNIVERSITY OF TANZANIA

2018

# CERTIFICATION

The undersigned certifies that, has read and hereby recommends for the acceptance by the Open University of Tanzania a Dissertation titled “Improving Livelihood of NguzoNyarugusu Refugee Women Group By Constructing Beads Products Shop in Nyarugusu, Kasulu District, Kigoma” in partial fulfillment of the requirements for the award of the Degree of Masters of Community Economic Development of the Open University of Tanzania.

…………………………………………..

Dr. Harrieth G. Mtae

(Supervisor)

………………….……….………..

Date

# COPYRIGHT

No part of this dissertation may be reproduced, stored in any retrieval system, or transmitted in any form by any means, electronic, mechanical, photocopying, recording or otherwise without prior written permission of the author or The Open University of Tanzania in that behalf.

# DECLARATION

I, Phoibe John Mollel, do hereby declare to the Senate of Open University of Tanzania that this project is my own original work, and that it has not been submitted for the similar degree in any other University.

…………………..…………………….

Signature

…………………..………………

Date

# DEDICATION

I dedicate this work to my family because they have been supporting me throughout this course and they are part of my success. I couldn’t have done it without them.

# ACKNOWLEDGEMENT

First I thank God for his blessings that took me through the accomplishment of this project. Secondly I thank all who supported me starting with my supervisor Dr. Harrieth Mtae, my course instructors Dr. William Palangyo and Dr. Mutasa, The UNHCR colleagues, IRC staff, Nguzo Nyarugusu Refugee Women Group and many others who made it possible for me to accomplish this project.

# ABSTRACT

A project to improving livelihood of Nguzo Nyarugusu Refugee Women Group by constructing beads products shop was established at Nyarugusu Refugee Camp, Kasulu district, Kigoma. This report presents the implementation process which involved different stages including community needs assessment (CNA) which was conducted to find out the community needs. The research design used was the descriptive research design and the sampling technique was non-probability sampling. Data collection was for both qualitative and quantitative data done with the use of questionnaires, interview and document review. The analysis methods used were descriptive statistics and content analysis with the assistance of SPSS. The main finding of the study was that the Nyarugusu Refugee Community have low income due to the poor infrastructure for conducting their main economic activity which is beads products making and selling. For this case the prioritized project was construction of beads products shop which will increase sells, improve their income and hence improve livelihood.

TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENT	vi

ABSTRACT	vii

LIST OF TABLES	xii

LIST OF FIGURES	xiii

LIST OF ABBREVIATIONS	xiv

CHAPTER ONE	1

1.0 	PARTICIPATORY NEEDS ASSESSMENT	1

1.1	Introduction	1

1.2	Community Profile	4

1.3	Community Needs Assessment	6

1.3.1	CNA Objectives	6

1.3.2	Research Methodology	8

1.4	Community Need Assessment Findings	12

1.4.1	Demographic characteristics of Nyarugusu Refugee Community	12

1.5	Priority Identified by the Community	18

1.6	Conclusion	19

CHAPTER TWO	20

2.0	PROBLEM IDENTIFICATION	20

2.1	Background of Research Problem	20

2.2	Problem Statement	22

2.3	Project Description	22

2.3.1	Target Community	23

2.3.2	Stakeholders	24

2.3.3	Project Goals	24

2.3.4	Project Objectives	25

2.4	Host Organization	25

2.4.1	Objectives of UNHCR	27

2.4.2	Activities Conducted by UNHCR	27

2.4.3	UNHCR Intervention at NguzoNyarugusu Refugee Women Group	29

2.4.4	2.4.4 Institutional Analysis of UNHCR	29

2.4.5	Role of UNHCR and Researcher in the Project	29

CHAPTER THREE	31

3.0	LITERATURE REVIEW	31

3.1	Introduction	31

3.2	Theoretical Literature Review	31

3.2.1	Definition of Concepts	31

3.3	Empirical Literature Review	34

3.3.1	Motivation for Urban Settlement	34

3.3.2	Economic Empowerment	38

3.4	Policy Review	40

3.4.1	National Micro-finance Policy- 2000	40

3.5	Overall Perception of the Refugees	42

3.6	Community Development Policy of 1996	45

CHAPTER FOUR	47

4.0	PROJECT IMPLEMENTATION	47

4.1	Introduction	47

4.2	Products and Outputs	48

4.2.1	Products	48

4.2.2	Output	48

4.3	Project Planning	49

4.3.1	Project Implementation Plan	50

4.3.2	Inputs	55

4.3.3	Staffing Pattern	55

4.3.4	Project Budget	56

4.4	Project Implementation Report	59

4.4.1	Output Presentation	59

4.4.2	Project Implementation Gantt chart	63

CHAPTER FIVE	67

5.0 PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	67

5.1	Introduction	67

5.2	Participatory Monitoring	68

5.2.1	Monitoring Information System	69

5.1.1 	Participatory Monitoring Methods	72

5.1.2	Participatory Monitoring Plan	73

5.3	Participatory Evaluation	75

5.3.1	Participatory Evaluation Methods	77

5.4	Project Sustainability	80

5.4.1	Social Sustainability	80

5.4.2	Institutional Sustainability	81

5.4.3	Economic Sustainability	82

5.4.4	Environmental Sustainability	83

CHAPTER SIX	84

5.0	CONCLUSION AND RECOMMENDATION	84

6.1	Introduction	84

6.2	Conclusion	84

6.3	Recommendations	86

REFERENCES	88

# LIST OF TABLES

Table 1.1: 	Age and sex Distribution of Respondents	12

Table 1.2: 	Education Level	13

Table 1.3: 	Marital Status	13

Table 1.4: 	Income and Economic Activities	14

Table 1.5: 	Pair Wise Matrix	18

Table 2.1: 	Stakeholders Analysis Matrix	24

Table 2.2: 	SWOC/SWOT Analysis	29

Table 4.1: 	Project Implementation Plan	51

Table 4.2: 	Logical Framework	54

Table 4.3: 	Project Staffing	56

Table 4.4: 	Project Budget	57

Table 4.5: 	Project Implementation Summary	64

Table 4.6:	Ghantt Chart	65

Table 5.1: 	Monitoring Information System	77

Table 5.2: 	Participatory Monitoring Plan	80

Table 5.3: 	Project Evaluation Summary	78

# LIST OF FIGURES

Figure 1.2: 	Knowledge of Nyarugusu Community in Bad Makinh Activity                       in Empowering Women Financially	18

Figure 2.1: 	Organization Structure of Host Organization	26

Figure 3.1: Clay Moulds Used For Beads	32

Figure 3.2: Traditinal Style	33

Figure 4.1: 	Researcher Receiving a Cheque from Programme and Finance                    Unit for NNRWG	60

Figure 4.2: 	NNRWG Group Members When Making the Beads Products	60

Figure 4.3: 	The Researcher and Members of NNRWG during Training                    from an IRC Facilitator	61

Figure 4.4: 	Constructed Beads Shop.	62

Figure 5.1: 	Project Evaluation Cycle	76

# LIST OF ABBREVIATIONS

CAN	Community Needs Assessment

CED	Community Economic Development

FGD	Focus Group Discussion

IRC		International Rescue Committee

MHA	Ministry of Home Affairs

NGO	Non-Governmental Organization

NNRWG	NguzoNyarugusu Refugee Women Group

REDESO	Relief Development Society

SPSS	Statistical Package for Social Sciences

SWOC		Strength Weakness Opportunities Challenges

SWOT	Strength Weakness Opportunities Threats

TCRS	Tanganyika Christian Refugee Service

TSH	Tanzanian shilling

UNDP	United Nations Development Programme

UNHCR	United Nations High Commission for Refugees

URT	 United Republic of Tanzania

WFP	World Food Programme

WHO	World Health Organization

# CHAPTER ONE

# 1.0 PARTICIPATORY NEEDS ASSESSMENT

# Introduction

Community Needs Assessment identifies the strengths and resources available in the community to meet the needs of children, youth, and families. A goal of a community assessment is to develop an informed understanding of the gaps or needs that exist within a community and their impacts upon the community’s members. There is a great need for both NGO’s, governmental organizations and individuals to address severe hardships that is faced by the women and girls in Nyarugusu community since community seems to have everything that can develop their lives but yet they are striving in raising their economy thus there is a need for the Community Needs Assessment.

However, another goal of a needs assessment is to identify the assets of a community and determine potential concerns that it faces. A straightforward way to estimate the needs of a community is to simply ask residents their opinions about the development of services within the community, their satisfaction with services, and what particular services are needed. Their opinions can be used in building an agenda aimed at economically empowering women and girls in Nyarugusu community and bring change that can build the capacity of community-based organizations that are designed to provide its resident’s services and development opportunities.

Two approaches can be used to identify community assets. The first approach is to identify the assets that are already known for supporting community needs. This includes community organizations and individuals that currently provide services to community members or have provided financial support to address the needs. Organizations that provide after-school programs to help youth graduate on time would be included in a community assessment focused on keeping kids in school. Clinics that offer free medical services to low-income seniors should be identified in a community assessment of seniors who need medical financial assistance. Community Needs an access to cultural opportunities (theater, museums, etc.), access to healthcare, affordable housing, availability of commercial goods/services, availability of public transportation, Childcare/ after-school care, Job availability, Job training, Mental health services, Recreational opportunities, Senior care, Strong, well-performing schools, Substance abuse services and other community needs.

This chapter presents the findings of the Participatory Needs Assessment conducted in Nyarugusu camp located in Kasulu District. This attempting to show the involvement of the community in identifying and responding to the real needs of improving income of women and girls in the refugees community through participatory approach. It tries to respond to such questions as what  was  the  real  community  concern on members of refugee women and girls empowerment groups and  how  was  it  addressed  in  the  community’s  needs. It further depicts how the community and other stakeholders in the project area have recognized the concern of improving income of refugees’ women in their empowered groups as a need and accepted it.

The  way  in  which  the  community  was  approached  greatly  influenced  the  sharing  process.  The  findings  are  reported  in  five  main  sections  with  several  respective  subsections.  Section  one  is  about  the  Community  Profile  which  reveals  the  social,  economic  and  cultural  aspects  of  the  community.  This is community situational analysis, which enabled the researcher to determine from the insiders point of view on what activities specifically needed by women and can be supported to improve and empower them economically.

The participatory needs assessment was conducted at Nyarugusu camp located in Kasulu District involving the    researcher and other people with the inclusions of the camp administration, community members and UNHCR authority, which is the   host   organization.   Various   issues   were   discussed   which   resulted   into   the identification   of   the   various   needs , challenges, economic opportunities and income generating projects for   improving income of refugees women in Nyarugusu community were found.   Through   focus   group  discussion the most pressing needs were identified, including the need for well-built  place for beads making and training programs to help them improve their business and hence their livelihood.

In ensuring the success of the participatory needs assessment conducted, various data collection methods were used. This included interviews, questionnaire distribution and focus group discussions. In this section the Community Needs Assessment objectives, questions, methodology, research design, sampling techniques, data collection and analysis methods have been presented in detail. The third section presents in depth details of the Community Needs Assessment findings.  On the other hand,  the  research  involved  getting  information  and  data  through  Focus  Group Discussion (FGD) and Semi-structure Interviews. Section four presents about the community needs prioritization where by four priority needs were observed and noted and were latter ranked.

# Community Profile

The Nyarugusu camp is located about 150 km from the Lake Tanganyika in the Western Province of Kigoma, Tanzania and near the Burundian border. Nyarugusu camp covers 28 square kilometres and is made up of 12 distinct zones comprising 142 villages. Population divides the zones; Zones 1-7 are largely home to Congolese refugees, and Zones 8-12 house Burundian refugees.

NguzoNyarugusu Refugee Women Group   is a   group with 57 people both are women.  Inhabitants  are  Haa,  and  some  few  Wahangaza  (Haa sub  group)  whose  main activities are mixed farming and pastorals occupation in the old semi-nomadic way.  But the apart from the inhabitants there we have the refugees from Burundi, Rwanda and Congo who are also inhabiting there but in their camps; of which within these Refugees the focused group of NguzoNyarugusu Women Group is a group of refugee women who work on beads making, book and diary covers, key holders, bangles and all these are made from the shredded papers supplied from the UN local offices in Nyarugusu camp and these are the ones that the researcher is focused with within the Nyarugusu community.

The  Refugee Women community  at NguzoNyarugusu Women Group in Nyarugusu Refugee Camp offers  authentic cultural ornaments as well as  tourist  attractive  products  such  as  Beads  products from which they produce bracelets for both genders, necklaces, tablemats, stars, key holders, bangles ets. All of these beads products produced from shredded papers available in the area. They also do cultural things that include their traditional dances and basketry (Mats/ African mattress, baskets, bags etc).  Burundians, Rwandese and Congolese history  (Leadership,  age  set,  taboos, tales  festival  ceremonies,  Slotting  ,  eating  natural  food or traditional, and medicinal plant in the Nyarugusu camp.

In the Nyarugusu camp 36% of the refugees engage themselves in selling agricultural products, 27% do petty businesses such as shop vending and selling of non-food items, 10% engage themselves in incentive working. Other main sources of income include; Remittance (7%), NGO income generating activity (5%), Cash transfer/ food vouchers (3%), casual labour (1%), sale of food ration (1%) and brewing (1%).However these could not be the current situation since there were no accurate and latest data available during the research.

The provision of social services remains solely responsibility of the humanitarian agencies lead by UNHCR. There are several funded projects by UNHCR that have shown interest and given the responsibility to work on social services. The Nyarugusu camp has 18 Primary schools 12 for Congolese side and 6 for Burundian side. The community and the curriculum they are using to teach are Congolese and Burundian syllabus own all these schools. There are pre-primary education centers in all primary schools. The presence of Pre-primary education centre’s lead to more than 90% of the primary school enrolment rate in primary schools (EC) Also there are 6  secondary schools, 4 to Congolese side and 2 for Burundians which are also owned by the community in the camp.

# Community Needs Assessment

Needs  assessment  of  a  community  is  a  procedure  carried  out  with  the  purpose  of  collecting, organizing, and analyzing  information available at the local level on the community  status  in  order  to  get involved  with  the  project  to  overcome  the  problem. Considering the fact, that Community Needs Assessment is the key tool in examining the challenges that face a particular society, capacities and actions required by respective community in addressing their challenges.

Needs  assessment  of  a  community  was  done  by  the  researcher,  host  organization, together  with  the  targeted  community  which  is  Refugee Women Empowerment group members and  the community  surrounding. This part is going to elaborate on the community need assessment conducted looking into the objectives of the CNA, CNA questions, the methodology used and finally it will present the CNA findings.

# CNA Objectives

# Main Objective

Overall Objective: The  main  objective  of  conducting  CNA  was  to  collect  information  needed  to establish a Community Economic Development (CED) Project which will lead to the improved livelihood of Women empowerment group members through beads production in Nyarugusu camp.

# Specific Objectives

- To identify challenges faced by the Women empowered Refugees community in Nyarugusu camp.

- To identify economic opportunities present in the Nyarugusu refugee community.

- To  identify  income  generating  project  for  Refugees Women Empowerment Group.

# CNA Questions

The study was guided by the following questions

- What are the challenges faced by the Women empowered Refugees community in Nyarugusu camp?

- What are the economic opportunities present in the Nyarugusu refugee community?

- What are the priorities identified by the community?

1.3.2 CNA Methodology

# Research Design

The  Community Needs  Assessment utilized  the  descriptive  research  design  as this design help  provide  answers  to  the  questions  who,  what,  when,  where  and  how associated with a particular research problem (Saunders et al, 2007). The descriptive design helped to obtain information concerning the status of the community and be able to describe what exists using both qualitative and quantitative data.

The study is concerned with describing the characteristics of a community under the study and highlights the actual situation (Kothari, 2004).Hence this study examines only the members of the Women Refugee Community in the Nyarugusu camp within Kigoma/Kasulu Municipality.

# Sampling Techniques

Since it was difficult to cover the whole population, simple random sampling method were used in conducting community assessment; on the reason that a small group of individuals or elements were convenient for data collection and enough to be a true representative  of  the  population  which  was  selected,  in  most  cases  the  Probability Sampling was used. Probability Sampling incorporates some type of systematic and random selection procedure that ensures each unit to have an equal chance of being selected.

# Data Collection Method

Data  collection  is  important  in  research  as  it  gathers  specific  information  aimed  at proving or refuting some  facts.  It allows for dissemination of accurate information and development of meaningful programs (Kombo and Tromp, 2006).  The study used the following data collection tools.

# Primary Data Collection

Primary information in this study was gathered through the following techniques:

# Research Methodology

# Semi Structured Interviews

This  is  guided  interview  in  which  only  some  of  the questions   and   topics   are   predetermined   and   more   questions   arise   during   the interview. In order to remain focused and carefully controlled, a structured guide or checklist was applied. Unstructured interviews were used to solicit information from key actors and focus group. They are informal and conversational and aim at getting the informant to produce more information. It allows the interviewer to be responsive to individual differences and situational characteristics.

# Questionnaire

Questionnaire  is  a  research  instrument  that  consists  of  a  series  of questions  and  other  prompts  for  the  purpose  of  gathering  information  from  the respondents. Questionnaires were designed to get information about the community from a larger group of respondents. The researcher distributed 52 questionnaires to the community members out of which all-52 questionnaires were returned.

# Focus group discussion

This was used to obtain information through discussions. FGD (Focus Group Discussion) involved various members of the community who had time to have in depth discussion on their community issues.  Through FGD, respondents’ insight was obtained not only on what respondents think but on also why they think that way. The technique helped to get information in detail and depth. This was an opportunity to get unexpected comments and new ideas, which built up the research; one can say this technique gives a high quality result.

# Participants’ Observation

This is a qualitative data collection method that requires direct observation of activity behavior, relationship, phenomena network or process in the field.  It is a classical method of social science inquiry where eyes are used rather than ears.  In  other  words  it  is  an  accurate  noting  and watching of the phenomenon as  it occurs in nature with regard to causes and effects of mutual relations. The process of observation has been of great assistance in the field during assessment  of  the  problem  to  be  addressed,  the researcher  together  with  NguvuNyarugusu Refugee Women group  leaders,  refugee leaders  for  Nyarugusu camp,  UN officilas and  other partners  as  the  host  organization  conducted  a  transect walk around the  NguvuNyarugusu Refugee Women group working area to observe the   environmental situation. The information gathered was also concerned with the economic activities done by the Nyarugusu refugee community.

# Field visit

A field survey was conducted within NguvuNyarugusu Refugee Women group working area under the project. This  was  also  done  in  participatory  manner,  where  the  transit  walk  involved  the researcher, leaders responsible for administrative issues together with two member’s representatives of the refugee council committee moved together step by step while observing  the  environment  condition  of  the  areas.  During the survey photograph pictures were captured and analysis done to assess the real strength of the area for establishment of the project.  This helped us to think of how successful beads making project that is to be implemented for income generating activities can improve the lives of these women in Nyarugusu Refugees community.

# Data Analysis Method

Both qualitative and quantitative techniques of data analysis were used in the study. The quantitative techniques used were descriptive statistics while the qualitative data was analyzed using content analysis method. Data was presented using tables, graph and charts to give an easy understanding of the findings.

# Reliability and Validity

The reliability and validity in a qualitative research study can be improved by the application of pluralized methodologies for triangulation (Gorman and Clayton 2005), as well as by including authoritative guidelines for coding terminology to avoid coder bias (White and McCain 1998). This study employed several methodologies (such as interviews, observation, documents/artifacts data collections, content analysis, and focus group discussions) as data collection techniques to enhance the reliability and validity. Due to the heavily qualitative nature of this study, all research procedures were applied consistently, further enhancing the study’s reliability.

Brenner (1985) recommended three ways to address questions of reliability and validity during interviews:

- Compare account against verification data.

- Scrutinize accounts for overt, observable undesirable influences in the interview situation.

- Employ a cognitive approach for assessment of informants’ motivation states during the interview (Brenner 1985, 155).

These three procedures were systematically followed in this study to ensure reliability and validity.

# Community Need Assessment Findings

# Demographic characteristics of Nyarugusu Refugee Community

Data  collection  was  performed  using  different  methods;  one  of  the  methods  was questionnaire  distribution  of  which  52  questionnaires  were  distributed  to  Nyarugusu refugee community. Out of the 52 questionnaires, all 52 were returned well filled and used for analysis. Out of the respondents, 40 were female and the remaining 12 were male.

# Age of the Respondents

The respondents’ age was between 15 and 70 as seen on table 1 that follows.

# Table 1.1: Age and sex Distribution of Respondents

| Gender * Age Cross tabulation |
| --- |
| Count |  |  | Age |  |  |
|  |  | 15 to 25 | 26 to 35 | 36 to 45 | 46 to 55 | 56 and above | Total |
| Gender | Male Female | 1 6 | 2 15 | 4 10 | 1 5 | 4 4 | 12 40 |
| Total | 7 | 17 | 14 | 6 | 8 | 52 |

# Source: researcher, 2017

# Respondents Education Level

The  respondents education  level  differed tremendously  as  few  of  them  have  never been  to  school  while  others  range  from  having  primary  education  to  tertiary education. Out of the respondents 48% have not been to school, while the remaining 48% have attended school out of which 28.8% attended primary school and 19.2% attended secondary school. Only 4% of the respondents have tertiary education.

# Table 1.2: Education Level

|  | Item | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Not gone to school | 25 | 48 | 48 | 48 |
|  | Primary education | 15 | 28.8 | 28.8 | 76.8 |
|  | Secondary education | 10 | 19.2 | 19.2 | 96 |
|  | Tertiary education | 2 | 4 | 4 | 100.0 |
|  | Total | 52 | 100.0 | 100.0 |  |

# Source: researcher, 2017

1.4.1.3 Marital Status

The researcher found out that out of the 74.9% respondents, 26.9% are separated, 48.0% are widow/widower, while the remaining 24.9% respondents, 13.5% are married, 7.6% are single and 3.8% are divorced.

# Table 1.3: Marital Status

|  | Status | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Married | 7 | 13.5 | 13.5 | 13.5 |
|  | Single | 4 | 7.6 | 7.6 | 21.1 |
|  | Divorced | 2 | 3.8 | 3.8 | 24.9 |
|  | Separated | 14 | 26.9 | 26.9 | 51.8 |
|  | Widow or Widower | 25 | 48.0 | 48.0 | 100.0 |
|  | Total | 52 | 100.0 | 100.0 |  |

# Source: researcher, 2017

# Respondents Economic Activities

The main economic activity of people from Nyarugusu camp is crop cultivation and selling of crops of which 37.5% of the respondents are seen to have curio making and selling as their main economic activity. Other economic activities present at this community include livestock keeping and a small 25% of crop cultivation.  In  these  economic activities  most  respondents  earn  income  between  100,000  Tsh and 500,000  Tsh which is not enough as most of them have an average of 5 to 8 dependants.

# Table 1.4: Income and Economic Activities

| Count | Economic activity | Respondents monthly income |  |
| --- | --- | --- | --- |
|  |  | below 100,000 | between 100,000 and 500,000 | above 500,000 | Total |
| Respondents Economic Activity | Crop Cultivation | 5 | 1 | 1 | 7 |
|  | Livestock Keeping | 2 | 3 | 4 | 9 |
|  | Shop vendors | 3 | 18 | 7 | 28 |
|  | Other business activities | 2 | 5 | 1 | 8 |
| Total | 12 | 27 | 13 | 52 |

# Source: researcher, 2017

Women are seen to have less authority in income related decision making although they work and earn income. This even affect their economy and their life as hole since most of the married women tend to have no decision making in their families instead they are being told what to do while their husbands deciding everything concerning their families. Like for example, when it cames to savings and investment decision making; men were reported to have the biggest say by 35% of the respondents overall (45% in Mtendeli, 31% in Nduta) compared to women for whom only 9% of the respondents (3% in Mtendeli, 11% in Nduta) as this proved to be also applied in Nyarugusu Refugees Camp at Kasulu District men are reported that they are key decisionmaker. Only the few women that had decision on their income and families are only those seen to be single or widows.

# Challenges faced by Nyarugusu Refugee Community

The Nyarugusu Refugee Community is seen to have many challenges, as it is a place where poverty level is high. This expressed by the respondents as they tried to show how such scenario affects NguvuNyarugusu Refugee Women group financially. The respondent expressed their challenges where proper shop for their products support and exposures were seen as the main challenge. This was so because most of the respondents’ economic activity is making and selling bead products; were they feel that once they have a proper bead products shop  they  can  increase  their  income  which  will  bring  solution  to  other  challenges faced. 54% of the respondents said that the challenge of  not having a proper bead shop  was  very  high  while  29.6%  said  it  was  less  challenging.  This is a very high percentage meaning a very big challenge in this community.

The second challenging issue in this community was seen to be skills to interact with the tourists in buying bead product challenge being the lack of exposures especially outside the Refugee camps as revealed by 42.6% of the respondents. Skills in bead products making and access to organizations dealing with such skills are  seen  to  be  less  challenging  as  do  32.8%  and  32.7%  respectively.  It was very impressive to find out that access to school was not a challenge at this community. Although  most  of  the  respondents  had  not  gone  to  school  many  of  their  children know attend school.

# Economic Opportunities Present in the Nyarugusu Refugee Community

The researcher was interested to know the economic opportunities present at Nyarugusu camp   so  that  advice  can  be  given  in  respect  to  the  available  opportunities. As well as helping, the NguvuNyarugusu Refugee Women group with their recent bead making project and empower them to become the biggest project that would save the lives of many refugee omen especially economically. According to the respondents, the available economic opportunities at Nyarugusu camp are crop farming, other business opportunities and animal farming opportunities. Presence of bead making activity or project in Nyarugusu Refugee camp; seen to be the most likely economic opportunity suitable for women at Nyarugusu camp. This can be seen on the figure below.

Figure 1.1: Economic opportunity in Nyarugusu Camp

Source: Research findings 2017

# Knowledge of Nyarugusu Community in Bead Making Activity in    Empowering Women Financially

As seen above, the presence of bead making is the most ranked economic opportunity at Nyarugusu Refugee campwhen looking to the income generating activity to women specifically to the NguvuNyarugusu Refugee Women group, and selling of beads products like books and diary cover, bangles and other bead products are the most depended on income generating activity to NguvuNyarugusu Refugee Women.

The  researcher  was  interested  to  find  out  the  level  of  knowledge  Nyarugusu Refugee community had in serving the economics lives of women in Nyarugusu Refugee camp by empowering the group of NguvuWomen who are dealing with making bead products to generate their income.   57.4% of respondents are knowledgeable of the NguvuNyarugusu Refugee Women beads making activity and the necessity to empower them in their beads making activities while the remaining 42.6% where less knowledgeable or did not know anything on NguvuNyarugusu Refugee Women beads making activity and they do not even see the necessity to empowering them in their beads making activities.  This  calls  for  much training  on all women of the area as  this  community has to help and deal  with  the NguvuNyarugusu Refugee Women group in  their  day  to  day activities.

The research also found out the respondents level of knowledge of foreign language specifically English language. Most of the respondents said that they do not have any knowledge of foreign languages. Out of the respondents only 29.5% noted that they are  very  knowledgeable  and  knowledgeable  on  foreign  language  the  remaining 70.5%  do  not  have  knowledge  on  foreign  language this affects even their shoping since they cannot even get exposure out of their places in case they are being given opportunity to move out and shop their products.

One  thing  that  Nyarugusu Refugee Camp community women especially NguvuNyarugusu Refugee Women group are highly knowledgeable is the making of beads product, 90.2% of the respondents  said  that  they  are  very  knowledgeable  and  knowledgeable  on  beads making. See the figure below;

Figure 1.2: 	Knowledge of Nyarugusu Community in Bad Makinh Activity in Empowering Women Financially

# Priority Identified by the Community

In the community needs assessment conducted at Nyarugusu Refugee Camp community, different needs were identified and due to availability of minimum resources, prioritization was done in a focused group discussion. The prioritization process enabled the selection of one need that can be attended. The prioritization exercise was done using pair wise matrix method as see on the table below.

# Table 1.5: Pair Wise Matrix

| Needs | Needs by number | Score | Rank |
| --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 |  |  |
| External Market Exposures |  | 2 | 1 | 1 | 5 | 2 | 3rd |
| Modern Beads Market |  |  | 2 | 2 | 2 | 4 | 1st |
| Foreign language training |  |  |  | 4 | 5 | 0 | 5th |
| Farm |  |  |  |  | 5 | 1 | 4th |
| Initiation of Beads Making Training Facility |  |  |  |  |  | 3 | 2nd |

# Source: researcher, 2017

According to the results of the pair wise matrix modern beads market is seen to be the first in the prioritized  needs  which  included  the  need  for  Beads Making Training Facility,  External Market Exposures,  farm  and foreign language training.

# Conclusion

This  chapter  gives  an  introduction  to  participatory  needs  assessment  conducted  at Nyarugusu Refugees Community in Kasulu District where a total of 52 community members were involved in the study. The chapter presented community profile is also presented in this chapter and the community needs assessment objectives. Then we have the CNA questions  and  the  description  of  the  methodology  used  in  the  community  needs assessment. Findings from the conducted CNA are also presented and there after the needs prioritization was done using the pair wise matrix method in a focused group discussion.   The   community   needs   assessment   performed   at   Nyarugusu Refugee community enabled the identification of modern market as the most prioritized need that has to be addressed.

# CHAPTER TWO

# PROBLEM IDENTIFICATION

# Background of Research Problem

Lack of beads market, training centre, and knowledge that beads making can change the lives of the NguzoNyarugusu Refuge Women Group. These are the main problems that were identified during community needs assessment conducted in Nyarugusu camp specifically. During the CNA it was also discovered that the main economic activity of the community members especially for these groups is beads making and selling of beads products to the workers of national and international organizations.

The  researcher found  out  that  the  NguzoNyarugusu Refugee women group community  members   had  many  challenges  in making  and selling their products due  to  poor  business  environment  which  included  lack  of well-established market for their bangles, book covers, necklaces, key holders and other bead products . Most of the refugees are from Burundi, DRC Congo, Rwanda and all are known to be pastoralists and agriculturalist who are headers and keepers of livestock and crops cultivation.

Apart from the fact that these refugees are traditionally livestock keepers and farmers, they are not allowed to practice that due to the establishment of various laws, which came with procedures that limited the refugees’ freedom in pastoralist settings. The 1998 Act makes no specific mention of the right of freedom of movement for refugees, however, pursuant to sections 16 and 17, authorities have the power to require any asylum seeker or refugee to reside within a “designated area” which in practice is a campo settlement. Tanzania’s 2003 National Refugee Policy (2003Policy), which is not codified law but frames the general direction the government intends to pursue for refugee matters, affirms in paragraph 28 that “refugees will be hosted in designated areas whereby the international community will be obliged to provide material assistance.”

For the case of the NguzoNyarugusu Refugee Women Group, the products are sold among the refugees themselves and to the workers who works for the refugees from different humanitarian organizations both national and international such as WHO, WFP, TCRS, IRC and others that comes to provide various assistance to the refugees. There are also different types of people who came to visit the refugee projects and buy their products that are sold in the camps including the beads products. All the products made by the NguzoNyarugusu Refugee Women Group are traditional and very marketable if only they can be assisted in marketing. However, it is understood that their movement is restricted by the government, hence they only rely on the internal market within the camp.

For this case, beads products may attract many people and create a big market since the intervention of national and international organizations in helping refugees especially the NguzoNyarugusu Refugee Women Group be self-reliant and perform the task as part of the livelihood activity. With the construction of the Beads products shop within Nyarugusu Camp and beads training centre, the NguzoNyarugusu Refugee Women Group will be in a better position to improve their livelihood as this will help them increase their sales on beads products.

# Problem Statement

Lack of properly constructed beads market building and beads training centre are the main problems identified that are faced by NguzoNyarugusu Refugee Women Group at Nyarugusu in the Nyarugusu Refugees’ Camp. According to the data from the community needs assessment conducted, making and selling beads products is seen to be the main economic activity for NguzoNyarugusu Refugee Women Group from Nyarugusu. This economic opportunity is supported by the presence of the good number of refugees, humanitarian organizations and other national and international organizations, as NguzoNyarugusu Refugee Women Group buyers at Nyarugusu.

The NguzoNyarugusu Refugee Women Group is a talented group and makes attractive beads products hence UNHCR together with IRC is assisting build a good foundation for self-sustainability of these refugees especially women since most of them are heads of families as their husband died due to political unrest in their countries and other left their families. They mostly get income by selling beads product, which include bangles, key holders, necklaces, carvings, table marts and many more. The NguzoNyarugusu Refugee Women Group could make more  income  in  their sales  if they  had a properly constructed Beads market and training centre to increase the production as at the moment most of their items get destroyed due to poor storage and maintenance environment.

# Project Description

The project is constructing a Beads Market for the NguzoNyarugusu Refugee Women Group. This beads market is built by blocks and can accommodate all the group’s beads making and selling activities. However, the project will include the construction of strong rooms or training centre of which the researcher will find a facilitator to facilitate trainings.  The  project  is  the  result  of  the  community  needs  assessment conducted at Nyarugusu Refugee camp which identified lack of beads products market and training centre as the main problems faced by  NguzoNyarugusu Refugee Women Group who are members of Nyarugusu Refugee Camp.

The project involved UNHCR as the host organization that protect the Refugees and supporting development activities taking place in the community.  A  building  of  45m2   was  proposed to be constructed  where  it  can  accommodate  50 community  members  in  their  beads making  and  selling  activities.  This building enables proper handling and keeping of beads products owned by the group.  Training centre will also be built, but in a different area as that will be for only training women found in the refugee camp having no Income Generating Activities. The training centre of at least 100 members capacity as this can increase the production of beads products hence improve the economy of these groups.

# Target Community

The  target  community  for  this  project  is  the  Refugees community  members  of NguzoNyarugusu Refugee Women Group  located   at   Nyarugusu Refugee camp, Kasulu District. The Nyarugusu Refugees community founded the NguzoNyarugusu Refugee Women Group in February, 2016.  The group has managed to organize 57 Women and together their main activity is making and selling beads and many other products to workers of both national and international organization that visit Nyarugusu Refugee Camp. There are also other activities conducted by NguzoNyarugusu Refugee Women Group including tailoring and weaving.

# Stakeholders

The beads marketing and beads making training centre construction project has involved a number of stakeholders who have played various roles towards its success.  This can be seen on the stakeholders’ analysis matrix below.

# Table 2.1: Stakeholders Analysis Matrix

| Stakeholder | Role in the Project | Expectations |
| --- | --- | --- |
| The NguzoNyarugusu Refugee Women Group | Beneficiary of the project | To get a well- built beads market and beads training centre |
| UNHCR, IRC | Sponsors of the project | To see Nyarugusu Refugee community have a well- built market and beads training centre within the Nyarugusu camp |
| Researcher | Initiator | To establish a CED project |
| Nyarugusu Camp Administration | Humanitarian agencies | To see members of their community have a well-built beads market and beads training centre. |
| Tanzania citizens and International missions | Beads buyers | To see a well-built beads market and beads training centre. |

Source: researcher, 2017

# Project Goals

The main goal of this project is to improve income of refugees Women empowerment group members through beads production by constructing beads market and beads training centre.  Through the beads market and beads training centre, the NguzoNyarugusu Refugee Women members of the group will be able to make and sell beads, key holders, book covers, bangles, and neclesses to Tanzania citizens and other national and international organization workers visiting Nyarugusu Refugee camp. By selling the beads products, the group members will be able to get income that will eventually help in improving their livelihood.

# Project Objectives

In order to meet the goal of the project, the following specific objectives were set

- To raise Tsh 60,000,000 million to finance the project by 15th January, 2018

- To allocate and construct 45m2 each for beads shop and beads training centre by 31st January 2018 in Nyarugusu Refugee Camp.

- To furnish the beads shop by 31st, January 2018

- To train provide training of new designs, styles in making beads products and business skills  to 57 members of the NguzoNyarugusu Refugee Women by 31st March, 2018.

# Host Organization

The project is designed to improve income of refugees Women empowerment group members through beads production by constructing beads market and beads training centre shop at Nyarugusu camp. The members of the group agreed upon this project during community needs prioritization when community needs assessment was conducted. The  researcher  and  the  group  leaders  made  an effort  to  approach  UNHCR administration  and  requested  for  their support in  implementing the project which they  accepted as one of their cooperate social responsibilities.

United Nations High Commissioner for Refugees (UNHCR) is one of the most predominant humanitarian organizations helping refugees from Burundi, DRC Congo here in Tanzania for many years. In Tanzania UNHCR does their humanitarian responsibility in refugees’ camp found in Nyarugusu, Kasulu District, Kigoma Region as well as Kibondo District. Its mandate is to provide, on a non-political and humanitarian basis, international protection to refugees and to seek

# permanent solutions for them.

# Figure 2.1: Organization Structure of Host Organization

# Objectives of UNHCR

United Nations High Commissioner for Refugees (UNHCR) has an objective of providing international protection to refugees and others of concern to UNHCR and to search for a durable solution to their situation; while preparing populations of concern for a durable solution, to ensure the provision of humanitarian assistance, in a gender/age and environmentally sensitive manner, and promote a better quality of life and self-reliance through a community development approach; and, to advocate refugee rights, promote effective partnerships with other relevant organizations, and develop a range of diplomatic initiatives aimed at preventing and mitigating the conditions that cause refugee movements.

# Activities Conducted by UNHCR

Activities conducted at Nyarugusu Refugees Camp, Kasulu District include construction of refugees tents, Sponsor students who pass their exams up to the university level by sending them to different universities here in Tanzania through the programme known as DAFI, ensure food, medical facilities and care are provided for refugees, protect refugee from any harm, promotional activities in cooperation with other institutions; to its own promotion and training activities, UNHCR also collaborated with other institutions, within and outside the UN system, in programmes of relevance to refugee issues, UNHCR is also co-organizing and participating in a series of activities in collaboration with the International Institute of Humanitarian Law.

Disseminating best practices when it comes to targeting development assistance: In the framework of its Convention Plus imitative, UNHCR has prepared an Issues Paper on Targeting of Development Assistance and a Statement of Good Practice on Targeting Development Assistance for Durable Solutions to Forced Displacement.

The Statement was the subject of discussion in a meeting convened by UHCR in Geneva in April 2005 and again at a meeting of the High Commissioner’s Forum in May 2005. UNHCR is now working with States participating in the Convention Plus initiative on an agreed text on best practices in targeting development assistance for durable solutions for the uprooted. However, UNHCR Promoting the realization of the Millennium Development Goals: In the context of the Convention Plus initiative, UNHCR prepared a note entitled Putting Refugees on the Development Agenda: how refugees and returnees can contribute to achieving the Millennium Development Goals (FORUM/2005/4 [www.unhcr.ch]). These activities are governed by the following vision, mission and transformation vision:

# UNHCR Vision

Our vision is a world where people can live full lives supported by appropriate, sustainable and resilient infrastructure and by the efficient, transparent use of public resources in procurement and project management.

2.4.3.2 UNHCR Mission

UNHCR, the United Nations High Commissioner for Refugee organization, is mandated by the United Nations to lead and coordinate international action for the world-wide protection of refugees and the resolution of refugee problems.

# UNHCR Intervention at NguzoNyarugusu Refugee Women Group

United Nations High Commissioner for Refugees (UNHCR) and International Rescue Committee (IRC) through their community development program are supporting NguzoNyarugusu Refugee Women Group in the implementation of the proposed project which is the construction of beads shop and building of beads training centre. United Nations High Commissioner for Refugees (UNHCR) contributed 80% for the project implementation while and International Rescue Committee (IRC) contributed 20% which gives the total of 60 million Tanzanian shillings.

# 2.4.4 Institutional Analysis of UNHCR

Before implementation of this project, the researcher conducted institutional analysis with the aim of identifying strengths and weaknesses of United Nations High Commissioner for Refugees (UNHCR) in relation to the implementation of planned activities and realization of expected results. During the analysis the researcher also identified opportunities within Nyarugusu Refugee Camp under UNHCR for smoothly implementation of the project as well as challenges from outside the organization that requires further actions. The researcher used SWOC / SWOT analysis technique during this analysis.

# Role of UNHCR and Researcher in the Project

United Nations High Commissioner for Refugees (UNHCR) is the sponsor for this project. They were approached by the researcher and the leaders of NguzoNyarugusu Refugee Women Group and requested to assist in the implementation of the proposed project. Since the group is operating inside the Nyarugusu Refugees camp at Kasulu District; they saw it is an opportunity as the customers for the beads product are also found within the camp and even the organization itself has played a very great role in marketing these beads products. So they saw the need to improve the environment or market so that the producers of beads products (NguzoNyarugusu Refugee Women Group) can get a better experience in the world of business.

# Table 2.2: SWOC/SWOT Analysis

| Strength | Protection of refugee |
| --- | --- |
|  | Providing security |
|  | Building shelters, provide food, education and medical facilities |
|  | Liase with the government officials on the issue of providing protection for refugees. |
| Weakness | The primary responsibility to take care of refugees laise with the government so they depend on them on many issues such as expanding the settlements and opening the borders for refugees to enter the country. |
|  | It has to delegate some of the responsibilities and activities to other agencies such as WFP, UNICEF and other implementing partners. |
| Opportunity | Government support |
|  | Funds from donors |
|  | The global refugee laws |
| Challenge | Remoteness of the camp makes it difficult to provide medical assistance to refugees who are in critical medical conditions. |
|  | Government restrictions on employment |
|  | Number of refugees increases at any time. |

Source: researcher 2017

The researcher teamed with United Nations High Commissioner for Refugees (UNHCR) to see that the project is implemented successfully; she took part from the survey for the project, data collection, funds collection and other activities in the project implementation. This way she managed to ensure all project objectives are met within the specified time.

United Nations High Commissioner for Refugees (UNHCR) and the researcher will continue taking part in the project until its full implementation.

# CHAPTER THREE

# LITERATURE REVIEW

# Introduction

This chapter will take you through different literature related to the study which will include theoretical literature review, empirical literature review, policy review and lastly the summary for the literature review. Both published and unpublished work will be used to show what other researchers have presented in relation to this research.

# Theoretical Literature Review

# Definition of Concepts

# Beads

A bead is a small, decorative object that is formed in a variety of shapes and sizes of a material such as stone, bone, shell, glass, plastic, wood or pearl and with a small hole for threading or stringing. Beads range in size from under 1 millimetre (0.039 in) to over 1 centimetre (0.39 in) in diameter. A pair of beads made from Nassarius sea snail shells, approximately 100,000 years old, is thought to be the earliest known examples of jewelery. Beadwork is the art or craft of making things with beads. Beads can be woven together with specialized thread, strung onto thread or soft, flexible wire, or adhered to a surface (e.g. fabric, clay) (Wikipedia Encyclopædia Britannica).

Traditional glass beads of Ghana are often referred to as Krobo beads, the Krobo mountains being the main area of production. These beads are made from recycled glass. Bottles and other glass items are first washed and sorted by colours. They are then broken into small fragments for making translucent beads, or pounded with a metal mortar and pestle, and sieved to get a very fine powder for making powder glass beads. Glass powder of different colours is obtained using ceramic dyes. Nguzo Refugee Women group are to be trained adopting various beads making designs and fashion to widen up their market and profits.

The picture below shows various clay moulds used for beads. Moulds are coated with kaolin to prevent fused glass from sticking to the surface. As shown below, the star shaped mould and the other two filled with colored glass powder have cassava stalks put into them. The stalks burn during the fusion leaving holes for threading the beads. The mould in the center with multiple holes is used for waist beads.

# Figure 3.1: Clay Moulds Used For Beads

Adornment – historically, beadwork was the insignia of tribal royalty. This practice has decentralized gradually and developed broader meaning in society. In contemporary southern Africa, beads and seeds have experienced a revival in popularity and are easily visible in everyday dress patterns which incorporate cultural as well and individual expressions. Culture is dynamic, and is just as much individual as it is a societal or communal expression. New styles and uses are being incorporated and fused with traditional representations, which still offer authentic African origin and expression.

# Figure 3.2: Traditinal Style

# Livelihood

According to Collins dictionary livelihood is the job or other source of income that gives you money to buy things you need (Collins, 2017). In other words livelihood is defined as a set of activities, involving securing water, food, fodder, medicine, shelter, clothing and the capacity to acquire above necessities working either individually or as a group by using endowments for meeting the requirements of the self and his household on sustainable basis and dignity (Oxford, 2017).

# Refugee

According to the 1951 UN Convention, a refugee is defined as  "A person who owing to a well-founded fear of being persecuted for reasons of race, religion, nationality, membership of a particular social group or political opinion is outside the country of his nationality and is unable or, owing to such fear, is unwilling to avail himself of the protection of that country; or who, not having a nationality and being outside the country of his former habitual residence as a result of such events, is unable or, owing to such fear, is unwilling to return to it."

# Empirical Literature Review

Several studies in relation to this one have been conducted in the world; different researchers saw the need for such studies but in different contexts. Literature review refers to detailed and justified analysis and commentary of the merits and faults of the literature within a chosen area which demonstrates familiarity with what is already known about your research topic (Saunders et al: 2009) In simple language Ngaiza (2003) as sited in Mkate: 2013, defines literature review as a procedure that guides writers to access both published and unpublished source of information on respect to study”.

# Motivation for Urban Settlement

While there is great variation among asylum-seekers and refugees in urban areas in terms of numbers, gender, age, and social vulnerability, a few themes exist that explain their motivations for settling in urban centres rather than refugee camps. Lifestyle in the country of origin may also determine where refugees settle. Refugees who previously lived in urban centres and have no knowledge of farming do relatively poorly in camps or rural areas, yet do quite well in urban areas where they can use their education, skills and expertise (Crisp etal., 2009, Jacobsen 2004, Marfleet, Sommers 2001).

Horst, Macchiavello, and Sommers 1999 & 2001 all demonstrate the natural connection between refugee camps and urban centres. Many people leave camps in order to work and send remittances back to family members. In camps, money is often scarce and is thus a valuable resource; injections of cash into camps facilitate improvements in general conditions. At the same time, much of the available literature also highlights the difficulties with respect to access to certain services such as secure banking that are often generated by urban living (see section on Protection Challenges).

Refugees in camps are afforded assistance and protection as part of the UNHCR’s mandate and as an incentive by the host government to keep them concentrated in one area. By contrast, in urban centres assistance to refugees can be sparse, unevenly distributed, and insufficient to meet basic needs – if it exists at all. For this reason, urban refugees exercise a higher degree of self-sufficiency than those in camps. Refugees settle in urban centres to avoid dependence on rations, boredom, hopelessness, hardships and restrictions that prevail in camps. They use their skills and pursue opportunities provided by greater economic resources, such as education for their children (Campbell 2005 & 2006, Hovil, Jacobsen 2006, Landau & Jacobsen, Macchiavello, Sommers 1999 & 2001).

Refugees in need of or in search of particular services more readily available in urban centres also may choose this lifestyle over camps. Health and education services are generally better in urban centres than in camps. The presence of hospitals and private medical clinics may act as a pull factor toward urban settlements, as well as accommodation, schooling and vocational training, and recreational and intellectual activities (Macchiavello, Women’s Commission for Refugee Women and Children).

Increased communication with UNHCR and family members is another reason for refugees to settle in urban areas. In some cases it is perceived that prospects for resettlement might be better in a city. Communication with family members abroad via internet is easier, and often there are social networks or ethnic enclaves to provide support and assist in the integration process. Some move to be reunited with family already living in urban areas (Horst, Jacobsen 2006, Kibreab, Landau & Jacobsen, Macchiavello, Women’s Commission for Refugee Women and Children).

Urban settlements may be chosen for relative improvements in personal safety and security as well. Corruption and abuse by authorities fosters a stressful and insecure way of life for refugees in camp settings. As will be discussed later, much of the literature demonstrates that urban living also comes with security problems. Finally, refugees may move to urban centres for the anonymity they provide. (Horst, Jacobsen 2006, Macchiavello, Sommers 1999).

3.3.2 Livelihoods

As noted above, many refugees settle in urban areas based on the assessment that this will make them relatively better off. A central factor to this decision appears to be the greater ability to earn a living. In some cases, refugees living in urban settings who do not do well economically return or migrate to camps. For urban refugees, employment in the informal sector is particularly common. In countries that have not ratified the 1951 Convention or that have not afforded refugees the right to employment, many refugees seek work informally to keep their refugee status hidden.

Often though, employers exploit refugee workers’ dire situation and pay unfair wages, demand long working hours, or expose refugees to dangerous working conditions. This goes unreported because refugees fear identification and possible detention or deportation. Due to the lack of regulations in the informal economy and lower wages, refugees struggle to support themselves and their families (Macchiavello, Alexander, Campbell, Crisp et al., Horst, Jacobsen 2004, Landau & Jacobsen, Sommers 1999). To avoid exploitation, a number of refugee groups have procured fake documents and/or pursued entrepreneurship.

Many who pursue business in their asylum countries bring relevant expertise from their country of origin. Self-sufficient refugees are not an economic strain on the host country, and in many cases authorities turn a blind eye to refugees’ informal work, tacitly acknowledging their contribution.

In fact, they make economic and social contributions to their host cities: rejuvenating communities, expanding markets, importing new skills, and creating transnational linkages. In some cases, such as that of Somali refugees in Nairobi, refugee-run businesses have become integral to the informal markets (Campbell, Grabska, Jacobsen 2004 & 2006, Landau & Jacobsen, Lindstrom, Sommers 1999). Additionally, many children in refugee families work. Gender biases, low wages and lack of opportunity for workers, lack of awareness about the related dangers of child labour, and a host of other factors have made this dangerous occurrence quite common for Afghan refugees in Pakistan. Poverty may also motivate young girls to marry in order to alleviate their economic burden on their family (Women’s Commission for Women and Children).

While lacking access to credit has been shown to prevent many refugees from seeking self-employment (Bailey), refugees may find employment with the help of existing communities of co-nationals. They may rely on social capital in the form of support, advice, employment connections and financial services (Banki, Horst, Jacobsen 2006, Landau). In other cases, transnational networks and remittances have helped refugees secure both credit and inexpensive goods to sell in the informal market. These networks begin at the grassroots and are aided by globalization (Campbell, Crisp et al., Grabska, Landau & Jacobsen, Landau).

# Economic Empowerment

The policy recognizes that without strong economic base the cooperative movement will not be sustainable as most of the cooperatives especially in rural area observed that they are lacking strong financial base. Therefore policy is insisting the cooperative societies to establish financial institutions within the cooperative societies. These include encouraging cooperative societies to establish savings and credits societies which will nurture saving habit and boost financial capacity of the cooperative society.

In special circumstance, government committed itself to guarantee primary cooperative societies when they want to obtain loan from national and international financial institutions. The policy stipulated these, as means to ensure that primary societies builds strong financial base which will sustain their operations and reduce poverty among the members.

# Education and Cooperative Training

Various economic development policies recognized the importance of education and training in promotion and sustainability of the cooperative societies. It has been realized that failure of many cooperatives were aggravated by limited knowledge on management of cooperatives and low level of education among the members which hinders the cooperatives to compete and operate in free market economy after failure.

In order to address the gap on education and training, policy emphasizes that government through local government councils will provide education and cooperative education which aims at building capacity of the cooperatives so that they will be in good position to operate in free market economy. These will put more effort in aspects of organization of the cooperative society, business environment where the cooperatives operates, customer care, leadership and entrepreneurship skills and personally management focusing in hiring qualified personnel’s.

IRC is a good example of some organization that provide training to Nguzo Refugee Women group by giving them training on savings through VICOBA and phones i.e M-pesa, Tigopesa and Airtel Money. Also IRC provide entrepreneurship training to the Nguzo Refugee Women Group as to improve their skills in beads making, tailoring and weaving.

# Role of the Government

The role of the government is to create conducive environment in which people are free to associate in exploiting the available resources for their development. However the government plays a great role to ensure that cooperatives operate in a manner which observes the international principles and standard of cooperatives.

Specifically, Government through the ministry of agriculture, marketing and cooperatives development plays a significant role in registration and deregistration of cooperatives, policy formulation and implementation of the cooperative act. Generally the responsible ministry is building capacity of the cooperatives by providing technical support and consultation which promotes the growth of cooperatives. Also it conducts research on cooperatives development and inspection as well as auditing of the cooperative records and operations in general.

# Policy Review

Tanzania is a county with many policies; some of the policies are directly related to this project. The following gives a review of few of them.

# National Micro-finance Policy- 2000

The role of micro-financial institution in growth of Cooperative society is recommendable hence the study found that it is important to review this policy for the clear understanding and implementation of this project. National Microfinance Policy was formulated following the financial sector reforms of 1991, in order to guide the micro-finance sector in the current socio-economic environment which is dominated by free market economy.

The main objective of this policy is to establish basis for evolution of efficient and effective micro-financial system in the country that serves the low income segment of the society and thereby contribute to economic growth and reduction of poverty.  It provides a framework for the operation of micro-financial institutions which considers gender equity.

# Importance of Micro finance Policy

These policy stipulate the importance of micro-finance in Tanzania in growth of micro and small enterprises as it states  that micro finance gives access for the low income earners and helps them to manage scarce household and enterprises resources efficiently, its protection against risks and gives them future investment opportunities.

# Savings and Credit Services

The policy insists on the importance of savings and credits in economic growth of household, enterprises and other institutions like cooperatives. It is important for individuals, household and other institutions like cooperatives to do savings. Savings ensure the savers during low income period and also allow members of institution to invest for their future investments.

Credit services can perform the same functions which could be done by saving services. Credits can boost short term and long term working capital of individuals and institutions hence leads to economic growth especially in the period when the income flow regarded to be low. As far as Refugees are concerned, according to the Tanzanian Refugees’ Policy, refugees are not allowed to open up bank accounts but they are being trained on how to save their money into their phones and VICOBA to avoid losses.

# Roles and Responsibilities

In process of implementing the microfinance policy, the roles and responsibilities have been assigned to the Ministries, Bank of Tanzania and other governmental institutions. On the other hand, the policy has assigned various responsibilities to non-governmental institutions like commercial banks, non-bank micro finance institutions, NGO and international community. Generally all parties work to ensure that individuals and institutions in Tanzania have access to micro-finance services and works towards poverty reduction.

This project is in this category as it creates employment for members of the Nguzo Refugees Women Group in the Beads making industry.

# Overall Perception of the Refugees

During the last part of the focus group meetings, after the participants had discussed overall relations with the refugees and any problems or conflict between the two groups, I asked whether, overall, the refugee presence was good or bad. The answers to this question were mixed, both among the host community and the refugees as well as within the individual focus groups. However, while there was an overall consensus amongst participants that the refugees have caused environmental degradation which has led to conflict, many of these same participants considered the refugee presence to be a positive thing.

Some of the positive changes discussed included the presence of a cheap labour force and an increase in the level of trade, due to the growth in population. In addition, a few members of the focus group meetings noted that over the years the interaction between the refugees and locals has led to mixed marriages and the development of friendships. Most of the benefits, however, were associated with the projects funded and run by the various international organizations and NGOs working in the region, as none of these organizations were active in the area before the coming of the refugees.

Many participants mentioned the benefits stemming from significantly improved hospitals, overall better access to health care and medicine, additional schools and better roads and public transportation. Many of these projects and improvements to infrastructure were intended specifically to assist the refugees, UNHCR and NGO staff working with the refugees; the local communities were indirect benefactors. However, over the years, UNHCR has implemented a number of refugee-hosting area (RHA) projects aimed at benefiting the local Tanzanian population specifically, with the assistance and financial support of various other donor organizations and NGOs active in the region.

Between 1995 and 2006, UNHCR spent over US$ 36 million on RHA projects in Tanzania that were intended to mitigate the negative impact of hosting refugees, improve security in the region and ensure that the living standards for the local populations were not lower than in the refugee camps. RHA projects focus on infrastructure improvements, access to safe drinking water, education, health, security, local administration and the environment. According to figures reported by UNHCR Tanzania, the environment-related project received the greatest proportion of RHA funds in 2006. Typically, funds are distributed to partner organizations that are responsible for implementing and monitoring environmental management programs.

In Kasulu District, the main agencies responsible were Relief for Development Society (REDESO), a Tanzanian NGO, and the Tanganyika Christian Refugee Services. Environmental management projects include tree plantings, tree seedling nurseries, rehabilitation of water sources, environmental education, promotion of energy saving (wood saving) stoves in the refugee camps and agro forestry education (UNHCR "RHA," 2006).

While this paper has drawn attention to persisting empowering of Nguzo Refugees Women group in Northwestern Tanzania, the problems would almost certainly be greater if not for environmental management projects and other development projects. For example, between 2000-2002, the environmental NGOs, REDESO, planted over 520,000 tree seedlings in Kibondo District, both within the refugee camps and in the hosting areas (Relief, 2007). UNHCR Tanzania reports that between 2002-2006, over 4,850 wood-saving mud stoves were constructed and 312 technicians from 67 zones in Nyarugusu camp, Kasulu District were trained on the building and maintenance of these stoves.

Similarly, in 2005 alone, the REDESO administered Agro Forestry Centre trained 1,560 Tanzanian farmers on sustainable farming and agro forestry practices (UNHCR, 2006 "Refugee"). Environmental Committees have been established both in villages and within the refugee camps to disseminate information on environmental sustainability. Further, international funds have contributed to the drawing up of Village Land Use Plans which designate areas for specific uses, thus aiming to restrict environmental degradation and protect environmentally sensitive areas.

# Community Development Policy of 1996

Since independence Tanzania has been preparing and implementing policies, strategies, long and short term plans which were intended to help people bring their own development. This is one of the policies that have been developed to create a framework which will enable Tanzanian community members develop. In this policy community development refers to those measures which enable people to recognize their own ability to identify their problems and use the available resources to earn and increase their income and build a better life for themselves. This is what has been seen in this project as members of the community were able to identify their needs and got the support to generate income for themselves. The policy also gives some indications of community development which include but are not limited to good housing, health, education, nutrition, clean and safe water and also increase in income. For this case the success of this project will result in development of the Nyarugusu Refugee community, especially the beneficiary of this project; the Nguzo Refugees Women group which will improve their livelihood.

Refugee hosting area projects, in general, are extremely valuable. This is not just due to their obvious, immediate benefits, such as improved health care and better education, but also because they can ultimately improve the relationship between the refugees and hosts and can lessen, or even prevent, conflict between the two groups. I found that while almost all of the participants in the focus groups believed that the refugees caused the environmental problems in the area, when asked whether overall it was a positive thing that the refugees were there, the overwhelming majority answered in the affirmative.

UNHCR is not officially mandated to support or implement development projects, particularly in non-refugee communities. However, in the case of Tanzania, the local communities and the local government officials expected the UNHCR to support both community projects and refugee-specific projects. Unless other UN agencies or other donors are willing to financially support refugee hosting area projects, UNHCR must continue to fund them. These projects may ultimately support long-term and sustainable economic development in the refugee hosting areas (Whitaker 2002), which is significant for Western Tanzania, as it is one of the most underdeveloped areas in Tanzania.

# CHAPTER FOUR

# PROJECT IMPLEMENTATION

# Introduction

This chapter presents the project planning and provides the implementation report of the project. In any successful project planning plays a significant role and it has been considered as critical aspect towards project success and sustainability of the project. In this project, the planning process was effectively done in order to clarify the scope of the project and specify the resources which required accomplishing the objective of the project.

In the same process, it was clearly identified the persons who will be responsible for the implementation of each task needed in order to accomplish the project goal. Additionally the financial part has been taken into consideration since there is no way the project can be successful accomplished without financial contribution hence effective budgeting is very crucial and needs to be included in the project planning process.

The project implementation has to meet the project objectives set inchapter two which included raising Tsh 60 million to finance the project,construction of a 45m2 beads shop and beads training facility centre, furnishing the beads market and training 57members of the NguzoNyarugusu Refugee Women group business skills.

This chapter will concentrate on projects products and output, the projectimplementation plan which includes the logical framework, staff plan and project budget and lastly the project implementation report and the ghantt chart. Different persons participated in the implementation of the project including the researcher, UNHCR administration as well as Nyarugusu Refugees Camp community and members of NguzoNyarugusu Refugee Women Group who are the owner/beneficiaries of the project.

# Products and Outputs

Throughout the project implementation several products and outputs have been realized, this part is going to take us through the different products and outputs of the project.

# Products

The expected product of this project is a well-constructed beads market and beads training facility centre which will benefit members of NguzoNyarugusu Refugee Women Group. The beads market/shop and training facility centre are expected to help them improve their beads making business and hence get more income to improve their livelihood. The project is expected to bring the positive impact to the community level as well as individual level as far as NguzoNyarugusu Refugee Women Group is concerned. The following are expected outputs of the project.

# Output

The following output is expected out of this project

- Raising of Tsh 60 Million for financing the project

- 45m2beadsmarket constructed

- The constructed beads market/ shop and beads training facility centre furnished

- 57 members of NguzoNyarugusu Refugee Women Group trained business skills

- Beads products making and selling take place in the constructed beads shop.

However, various professional and qualified staff will be hired to support the implementation of the project. Members of the NguzoNyarugusu Refugee Women Group will have access to beads product supplies and services.

The project will enhance the market of the beads products hence increase income of the members and Nyarugusu refugees camp in general.

The government sponsored infrastructures will be well maintained and surrounding community will ensure sustainability of the project.

# Project Planning

Project implementation requires a proper project plan; a project plan involved identifying project activities that enables meeting the specified objectives. In the project implementation each activity is clearly defined showing the responsible personnel, resources required, timeline and the budget for each activity. This part is going to give a detailed explanation on the implementation plan, outputs of the project, staffing pattern, project budget, project implementation report and the ghantt chart.

The project is projected to be implemented in two phases, whereby in the first phase the main focus will be on the beads market or shop construction of which the researcher believes it will help the NguzoNyarugusu Refugee Women Group to be empowered in their economic sustenance.

The second phase the main focus will be on training centre capacity building for the prospected members and management of the NguzoNyarugusu Refugee Women Group and surrounding government leaders. In these phase, trainings will be conducted in order to raise community understanding and knowledge of the NguzoNyarugusu Refugee Women Group beads making activities as to empower every women in Nyarugusu Camp in economic sustenance.

The trained members of the NguzoNyarugusu Refugee Women Group among Nyarugusu Refugee Camp community will be supported by UNHCR, IRC (International Rescue Committee) consultant and other government officials to develop infrastructure and systems which will enable the NguzoNyarugusu Refugee Women Groupto function and operate in a meaningful and profitable manner.

# Project Implementation Plan

The implementation of this project involved planned activities derived from project objectives obtained in participation with the community, researcher, host organization and other stakeholders. The project started with a formulation of community driven and participatory implementation plan that provided a road map for the implementation processes. In order to realize the planned goals and achieve objectives several outputs are supposed to be achieved after an implementation of various project activities. This is as seen in the Project Implementation Plan Table 4.1 seen below.

# Table 4. 1: Project Implementation Plan

| Specific Objective | Output | Activity | Time frame | Resources Needed | Responsible Person |
| --- | --- | --- | --- | --- | --- |
| To raise Tsh 60 million to finance the by 15th January, 2018 | Raising of Tsh 60 Million for financing the project | Contacting UNHCR & IRC administration to ask for sponsorship | 01-15 July 2017 | -Pen -Paper -Mobile phone credit | -Researcher -NNRWG chairperson -UNHCR |
| To raise Tsh 20 million to finance the th project by 30 July, 2017 | Raising of Tsh 20 Million for financing the project | Receiving UNHCR & IRC sponsorship | 16 – 30 July 2017 | -Mobile phone credit | -Researcher -NNRWG chairperson -UNHCR |
| To construct a 45m2 beads market/ shop and beads training facility centreby 31st January 2018 | 45m2 beads market/ shop and beads training facility centre constructed | UNHCR offered piece of land to be used for the project | 01-16 August 2017 | Tape measure Note book Pen Time | NNRWG leaders Researcher UNHCR administration |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | The building constructor visited the site and made measurements and needs estimations. | 17-20 August 2017 | Tape measure Note book Pen Constructor Time | NNRWG leaders Researcher UNHCR administration |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | Building materials were purchased | 21-24 August 2017 | Money Time | NNRWG chairperson Researcher |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | Construction of the beads market/ shop and beads training facility centre was done | 25-31 August 2017 | Building materials Constructor Time | Constructor Researcher UNHCR administrator NNRWG chairperson |
| To furnish the beads market/ shop and beads training facility centre by 31 January 2018 | The constructed beads market/ shop and beads training facility centre furnished | Window shopping for be furnishing resources | 01-03 November 2017 | Bus fare Mobile phone credit Pen Note book | NNRWG chairperson and few members researcher |
| To furnish the curio shop by th 15 November, 2017 | The constructed curio shop furnished | Purchasing furnishing resources including chairs, tables, shelves | 04 – 08 November 2017 | Money List of resources | NNRWG chairperson and few members researcher |
| To furnish the curio shop by th 15 November, 2017 | The constructed curio shop furnished | Installing and furnishing the the beads market/ shop and beads training facility centre | 09-15 November 2017 | Furnishing resources | NNRWG chairperson and few members |
|  |  |  |  |  | Researcher |
| To train 57 members of the NguzoNyarugusu Refugee Women Group (NNRWG) business skills by 31st March 2018 | 57 members of NNRWG trained business skills | Identification of the best business skills trainer | 16 – 19 November 2017 | Mobile phone credit | Researcher UNHCR administrator |
| To train 40 members of TECG business th skills by 30 November, 2017 | 40 members of TECG trained business skills | Identification of the training venue | 20 – 24 November 2017 | Mobile phone credit | Researcher UNHCR administrator NNRWG chairperson |
| To train 40 members of TECG business th skills by 30 November, 2017 | 40 members of TECG trained business skills | Conducting the training | 25 – 30 November 2017 | Pens Note books Refreshments | Trainer Researcher NNRWG members |
| To train 40 members of TECG business th skills by 30 November, 2017 | Beads products making and selling take place in the constructed curio shop | Making use of the beads market/shop and beads training facility to make and sell beads products | 1 December, 2017 on wards | Beads products to sell | NNRWG members |

Source: Field Research, 2017/2018

After the project was identified during the community needs assessment conducted at Nyarugusu Refugees Camp, the researcher and NguzoNyarugusu Refugee Women Group members thought of the project implementation plan. In this case they decided to go ask UNHCR and IRC to be the project sponsors as NguzoNyarugusu Refugee Women Group is operating close to UNHCR since the NguzoNyarugusu Refugee Women Group is operating under UNHCR. UNHCR and IRC agreed to sponsor the project and they both contributed a total of Tsh 60 million which was received by the researcher together with NguzoNyarugusu Refugee Women Group (NNRWG) chairperson; of which UNHCR contributed 40 million which is 80% of the project and IRC 20 million which is 20%.

After securing the funds construction of the beads market/ shop and beads products training facility centre started, it involved identifying the piece of land to be used for the construction, selecting the building contractors and him visiting the site, purchasing building materials and lastly the construction is in progress. The main responsible persons at this stage included the contractor, researcher, UNHCR administrator and NguzoNyarugusu Refugee Women Group (NNRWG) chairperson.

Following the completing shop construction, furnishing will be needed.

At this stage NguzoNyarugusu Refugee Women Group (NNRWG)chairperson and few members together with the researcher will go for window shopping in close towns of Kasulu and if possible Kigoma town to see the quality and pricing of different resources needed to furnish the beads market/ shop and beads products training facility centre. Based on the findings the decision will be made and the required furnishing resources will be purchased and installed in the curio shop. Towards the end of the project the researcher and UNHCR administration see the need to provide training to the members of NNRWG, the training will be on how to manage their business and keep records to ensure that no mistakes are made and the project can reach its objective which is to improve livelihood of member of NNRWG

# Table 4.2: Logical Framework

| Intervention Logic | Objectively verifiable Indicators | Means of Verification | Assumption |
| --- | --- | --- | --- |
| Overall Objective |  |  |  |
| Improving livelihood of NNRWG by constructing beads market/ shop and beads products training facility centre |  Improved livelihood of members of NNRWG  Members of NNRWG can meet basic needs |  Project evaluation report |  All stakeholders play their part as expected  Tourists continue to come to UNHCR |
| SO1: To raise Tsh. 60millions to finance the project by 15th January,2018 |
| Output 1 | Objectively verifiable Indicators | Means of Verification | Assumption |
| Raised of Tsh 60 Million for financing the project | Money available for the project | Documents from UNHCR showing their contribution | UNHCR is ready to sponsor the project |
| Activities |  |  |  |
| 1.Contacting UNHCR administration to ask for sponsorship | Letter to UNHCR requesting for sponsorship | Project progress report | NNRWG members are ready to go to UNHCR for assistance |
| 2.Receiving UN sponsorship | Cheque from UNHCR | Cash withdrawn from bank | UNHCR sponsorship is in cash |
| SO 2: To construct 45m2 beads market/ shop and beads products training facility centre by31st January, 2018 |
| Output 2 | Objectively verifiable Indicators | Means of Verification | Assumption |
| 45m2 beads market/ shop and beads products training facility centre constructed | Beads products market /shop available | Site visit Project progress report | Contractor and materials available on time |
| Activities |  |  |  |
| 1.NNRWG offered piece of land to be used for the project | Land available for the project | Site visit Project progress report | NNRWG members are ready to offer their land |
| 2.The building constructor visited the site and made measurements and needs estimations. | Contractor availability | Project progress report | Contractor will be available on time with the necessary requirements |

Source: Field Research, 2017/2018

# Inputs

Several resources were needed as inputs for the implementation of this project. Throughout the implementation of the project objectives different activities wereperformed and several inputs required. The first input was money which wasobtained from the contribution made by UNHCR and IRC authority. Then piece of land wasanother input offered by The United Republic of Tanzania Government to UNHCR for the NguzoNyarugusu Refugee Women Group (NNRWG)project to take place. Bricks, cement, sand,stones, water and the constructor were input for the construction of 45m2beads market/ shop and beads products training facility centre.

Tables, shelves, chairs and cabinets will be inputs for furnishing the beads market/ shop and beads products training facility centre.

Other inputs include human resource such as the researcher, UNHCR administrator, NNRWG chairperson and members, Trainer and the constructor involved in the building process.

# Staffing Pattern

The project did not and will not recruit any staff but instead it will be managed by NNRWG under the supervision of UNHCR administration whose staff will assist in some issues such as accounting, procurement and store keeping. UNHCR will take part in monitoring the project and they also took part in planning for the project implementation. The training they will receive is expected to be enough to make the NNRWG manage the project. They will be in contact with the researcher so that in case they face any difficulties she can assist them. Moreover the researcher’s knowledge on various matters including project management facilitated some parts of the project.

Moreover, in this project, there are two categories of staff, these include the qualified personnel hired on contractual basis and the second category includes volunteers.

Qualified staff includes Project manager, accountant, procurement officer, store keeper and Internal Auditor who is expected to work on part time basis.The job distribution of these stake holders is as seen in Table 4.3 below.

# Table 4.3: Project Staffing

| STAKEHOLDER | RESPONSIBILITY |
| --- | --- |
| Researcher | Project Manager |
| UNHCR Counterpart | Lydia Kishimba |
| UNHCR Focal Point | George Tibaijuka |
| Aaron Keyella | Accountant |
| Robina Kibisa | Procurement Officer |
| Kevina Rugakingila | Store Keeper |
| Trancisius Missana | Internal Auditor |

Source: Field Research, 2017/2018

# Project Budget

For successful implementation of the project a total of Tsh60,000,000 is needed as the budget. Out of it Tsh 40 million which is 80% of the budget was covered by UNHCR. The remaining 20% which is Tsh 20,000,000 is expected to be contributed by members of IRC and the researcher. The following table shows the project budget based on the different activities that are taking place.

# Table 4.4: Project Budget

| Specific Objective | Output | Activity | Resources Needed | Quantity | Unit price | Total (Tsh) |
| --- | --- | --- | --- | --- | --- | --- |
| To raise Tsh 60 million to finance the project by 15thJanuary, 2017 | Raising of Tsh 60 Million for financing the project | Contacting UNHCR administration to ask for sponsorship | -Pen -note book -Mobile phone credit | 4 3 4 | 1200 1500 7000 | 4800 4500 28000 |
| To raise Tsh 20 million to finance the project by 30 July, 2017 | Raising of Tsh 20 Million for financing the project | Receiving UNHCR sponsorship | -Mobile phone credit | 1 | 5000 | 5000 |
| To construct 45m2 beads market/ shop and beads products training facilitycentreby 31st January, 2018 | 45m2 beads market/ shop and beads products training facility centre constructed | NNRWG offered piece of land to be used for the project | Tape measure Note book Pen | 1 3 2 | 7500 1500 1000 | 7500 4500 2000 |
| To construct a 232m curio shop by The 30 October, 2017 | 32m2 curio shop constructed | The building constructor visited the site and made measurements and needs estimations. | Tape measure Note book Pen Constructor Time | 3 3 1 | 1500 1000 2800000 | 4500 3000 2800000 |
| To construct a 2 32m curio shop by The 30 October, 2017 | 32m2 curio shop constructed | Building materials were purchased | Money |  | 19000000 | 19000000 |
| To furnish the beads market/ shop and beads products training facility centre by 31stJanuary, 2018 | The beads market/ shop and beads products training facility centre furnished | Window shopping for be furnishing Resources | Bus fare Mobile phone credit Pen Note book | 5 4 6 5 | 20000 5000 1000 1500 | 100000 20000 6000 7500 |
| To furnish the Th curio shop by 15 Novembe, 2017 | The constructed curio shop furnished | Purchasing furnishing resources including chairs, tables, shelves | Money |  | 3900000 | 3900000 |
| To train 57 members of NNRWG business skills by 31st March, 2018 | 57 members of NNRWG trained business skills | Identification of the best business skills trainer | Mobile phone credit | 3 | 5000 | 15000 |
| To train 40 members of TECG business skills by the 30 November, 2017 | 40 members of TECG trained business skills | Identification of the training venue | Mobile phone credit | 2 | 5000 | 10000 |
| To train 40 members of TECG business skills by the30 November, 2017 | 40 members of TECG trained business skills | Conducting the training | Pens Note books Refreshments | 43 43 43 | 1000 1500 5000 | 43000 64500 215000 |
|  |  |  | contingency |  |  | 3,285,250 |
| Total | 22,827,750 |

Source: 2017/2018 Field Research

# Project Implementation Report

The implementation of this project involved various activities and a total budget ofTsh60, 000,000which were implemented from January, 2018. These activities included Contacting UNHCR and IRC administration to ask them to sponsor the project. UNHCR and IRC accepting and providing Tsh 60 million which were used in the project implementation. The remaining amount in the project budget in case as contingency will be contributed by NNRWG members and the researcher.

Another activity which involved NNRWG was identifying the land were the beads market/ shop and beads products training facility centre will be built. The beads market/ shop and beads products training facility centre is in the building process and will be furnished ready to be used for beads products making and selling. NNRWG members will then be trained business skills which will help them improve the way they operate and hence ensure higher sales that will impact their livelihood.

This part therefore provides project report for the accomplished and the expected to be accomplished activities and the output obtained. It also compares the planned activities against the actual implemented activities with remarks on efficient and effective utilization of resources. It also presents the Ghant chart which represent show the project is managed in terms of time management and sequence of activities.

# Output Presentation

Different outputs were realized during the project implementation, this part is going to give a detailed explanation of them.

# Raising of Tsh 60 Million for Financing the Project

This output was realized by accomplishing two activities which included contacting UNHCR and IRC administration and requesting them for support in the project implementation which they accepted and supported the project by issuing Tsh 60 million for the project implementation. However, during the project implementation other uncalculated costs occurred which resulted into the increase of the project budget from tsh 60 million to tsh 60,887,980 million. The difference will be covered by the contributions from the researcher. Figure 4.1 shows the researcher and leaders of NNRWG with UNHCR administrators signing documents on receiving the finds given in form of cheque.

# Figure 4.1: Researcher receiving a chequefrom Programme and Finance Unit for NNRWG

# Figure 4.2: NNRWG Group Members When Making the Beads Products

# 45m 2 Beads Market/ Shop and Beads Products Training Facility Centre Constructed

The second output which was the construction of the beads market/ shop and beads products training facility centre was realized through four activities which are identification of land to be used for the project, identification of the building contractor, purchasing of the building materials a lastly construction of the beads market/ shop and beads products training facility centre.

In the first activity NNRWG chairperson showed the research and UNHCR administrator the area were they wish for the beads market/ shop and beads products training facility centre to be built as seen on figure 4.2. The researcher and UNHCR administrator had no objection on the proposed area hence that’s where the beads market/ shop and beads products training facility centre was built. The building contractor was then identified and shown the project site which he made the necessary measurements and gave estimates of the required resources as seen on Figure 4.3.

# Figure 4.3: The Researcher and Members of NNRWG during training from an IRC facilitator

# Figure 4.4: Constructed Beads Shop

# The Constructed Beads Market/ Shop and Beads Products Training Facility Centre Furnished

The third output in the implementation of this project is expected to be the furnishing of the constructed beads market/ shop and beads products training facility centre. This will be accomplished with the implementation of three activities which included first window shopping for the required furnishing resources which will be done in the nearby towns of Nyarugusu and Kasulu town. Then the identified resources will be purchased and transported to the project area. Lastly installation of the furnishing resources will be done as the third activity, this will involve setting the shelves at the right place, putting chairs and tables in a more comfortable way as well as displaying the curio in a way that attracts customers. This output is expected to be accomplished on the 31st January, 2018.

# 57 Members of NguzoNyarugusu Refugee Women Group Trained Business Skills

57 Trained NNRWG members is expected to be another output in this project, this output will be realized through the accomplishment of three activities which included firstly the identification of the best business skills trainer of which the researcher expecting to consult IRC organization who were previously providing such services i.e. entrepreneurial skills, money saving skills and other business skills to the group, identification of the training venue and lastly the training to be conducted. In the first activity several facilitators will be consulted and lastly one of them will be selected. The trainees are expected to be offered training facilities and refreshments as it will be done for the whole day.

# Beads ProductsMaking and Selling Take Place In The Constructed Beads Market/ Shop and

Beads Products Training Facility Centre: The final output of the project is the beads market/ shop and beads product straining facility centre being used for making and selling of beads products. In this output members of NNRWG will be able to make beads in a nice organized place which gives them comfort ability that helps increase production and sales. It is expected that as they increase sale their livelihood will be improved. At the moment while waiting for the beads market/ shop and beads product straining facility centre they make and sell beads products i.e. book covers, bangles, neclesses etc. in a very difficult environment as seen on the figure below.

# Project Implementation Gantt chart

This part is going to give us the project schedule showing all activities of the project and the time frame for their implementation. The ghantt chart shows the project objectives, output and activities and the project duration distributed in months from January to March, 2018

# Table 4.5: Project Implementation Summary

| Specific Objective | Output | Activity | Implementation Status | Reasons for deviation |
| --- | --- | --- | --- | --- |
| To raise Tsh 60 million to finance the project by15th January, 2018 | Raising of Tsh 60 Million for financing the project | Contacting UNHCR administration to ask for sponsorship | Done |  |
| To raise Tsh 20 million to finance the project by th 30 July, 2017 | Raising of Tsh 20 Million for financing the project | Receiving UNHCR sponsorship | Done | Other supporters had to contribute as the budget exceeded Tsh 60 million |
| To construct 45m2 beads market/ shop and beads products training facility centre by 31st January, 2018 | Construct 45m2 beads market/ shop and beads products training facility centre by 31st January, 2018constructed | NNRWG offered piece ofland to be used for the project | Done |  |
| To construct 2 a 32m curio th shop by 30 October, 2017 | 32m2 curio shop constructed | The building constructor visited the site and made measurements and needs estimations. | Done |  |
| To construct 2 a 32m curio th shop by 30 October, 2017 | 32m2 curio shop constructed | Building materials were purchased | Done |  |
| To construct 2 a 32m curio th shop by 30 October, 2017 | 32m2 curio shop constructed | Construction of the curio shop was done | In progress |  |
| To furnish the beads market/ shop and beads products training facilitycentre by 31stJanuary, 2018 | The constructed beads market/ shop and beads products training facility centrefurnished | Window shopping for be furnishing resources | Not yet Done |  |
| To furnish the curio th shop by 15 November, 2017 | The constructed curio shop furnished | Purchasing furnishing resources including chairs, tables, shelves | Not yet Done |  |
| To furnish the curio th shop by 15 November, 2017 | The constructed curio shop furnished | Installing and furnishing the curio shop | Not yet Done |  |
| To train 57 members of NNRWG Business Skills by 31st March, 2018 | 57 members of NNRWG trained business skills | Identification of the best business skills trainer | Not yet Done |  |
| To train 40 members of TECG business th skills by 30 November, 2017 | 40 members of TECG trained business skills | Identification of the training venue | Not yet Done |  |
| To train 40 members of TECG business th skills by 30 November, 2017 | 40 members of TECG trained business skills | Conducting the training | Not yet Done |  |
| To train 40 members of TECG business th skills by 30 November, 2017 | Beads products making and selling take place in the constructed beads shop | Making use of the Beads market/ shop and beads training facility centre to make and sell beads products | Not yet Done |  |

Source: 2017/2018 Field Research

# Table 4.6: Ghantt Chart

| Specific Objective | Output | Activity | Time frame | Project implementation schedule |
| --- | --- | --- | --- | --- |
| Specific Objective | Output | Activity | Time frame | January | February | March | April | May |
| To raise Tsh 60 million to finance the project by 5th December 2017 | Raising of Tsh 60 Million for financing the project | Contacting UNHCR administration to ask for sponsorship | 01-16 July207 |  |  |  |  |  |  |
| To raise Tsh 20 million to finance the th project by 30 July, 2017 | Raising of Tsh 20 Million for financing the project | Receiving UNHCR sponsorship | 16-30 July2017 |  |  |  |  |  |  |
| To construct 45m2 beads market/ shop and beads products training facility centre by 15thDecember 2017 | 45m2 beads market/ shop and beads products training facility centreconstructed | NNRWG offered piece of land to be used for the project | 01-18 August 2017 |  |  |  |  |  |  |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | The building constructor visited the site and made measurements and needs estimations. | 19-22 August 2017 |  |  |  |  |  |  |  |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | Building materials were purchased | 23-28 August 2017 |  |  |  |  |  |  |  |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | Construction of the beads market/ shop and beads products training facility centre shop was done | 29 Aug to 04 Sept 2017 |  |  |  |  |  |  |
| To furnish the beads market/ shop and beads products training facility centreby 31December 2017 | The constructed beads market/ shop and beads products training facility centrefurnished | Window shopping for be furnishing resources | 01-03 November 2017 |  |  |  |  |  |  |
| To furnish the curio shop by th 15 November, 2017 | The constructed curio shop furnished | Purchasing furnishing resources including chairs, tables, shelves | 04-07 November 2017 |  |  |  |  |  |  |  |
| To furnish the curio shop by th 15 November, 2017 | The constructed curio shop furnished | Installing and furnishing the beads market/ shop and beads products training facility centre | 08-17 November 2017 |  |  |  |  |  |  |  |  |
| To train 57 members of NNRWG business skills 31 March 2018 | 57members of NNRWG trained business skills | Identification of the best business skills trainer | 18-20 November 2017 |  |  |  |  |  |  |  |
| To train 40 members of TECG business skills th by 30 November, 2017 | 40 members of TECG trained business skills | Identification of the training venue | 21-24 November 2017 |  |  |  |  |  |  |  |
| To train 40 members of TECG business skills th by 30 November, 2017 | 40 members of TECG trained business skills | Conducting the training | 25-30 November 2017 |  |  |  |  |  |  |

Source: 2017/2018 Field Research.

# CHAPTER FIVE

# 5.0 PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

# Introduction

In order to ensure proper planning and implementation of the project, the project needs to consider how they can make periodic reflection of the project and assess whether the project has been implemented within the standards, if there is any diversion  what can be done to improve it and also to learn if the project meet the intended objectives. This process is what popularly known as monitoring and evaluation.

Considering the active role of the beneficiaries and other stakeholders as the fact that the project intends to offer continued training to new members of the fisheries cooperative society, hence  the project will be using the participatory monitoring and evaluation approach. This approach  provides a great room for improvement as it offers a forum for stakeholders to articulate their needs and make collaborative decisions(Estrella:1998).Therefore it gives clear understanding of the gaps and helps the stakeholders to develop  long term strategies of their project.

In this chapter, the paper is going to discuss how the community and other stakeholders will be involved in ensuring the project is properly monitored and evaluated in order to ensure the project is within the agreed standards and achieve its objective but also providing guidance on how the project can be improved for the benefit of the NguzoNyarugusu Refugee Women Group.

Participatory monitoring and evaluation (PM&E) is a process through whichstakeholders at various levels engage in monitoring and evaluation of the particularproject. They then share the results of the monitoring and evaluation process thentake relevant actions (World Bank, 2017). Participatory monitoring and evaluationensures that the implementation of the project is within the defined plan and theexpected outcomes are realized.

To ensure effective participatory monitoring and evaluation a sufficient monitoringplan was designed. This has enabled the UNHCR, the researcher, members of NNRWG andother stakeholders to develop the project properly throughout its implementation(UNDP, 2009).This chapter therefore explains how the project is monitored andevaluated, it also shows project sustainability and strategies undertaken to ensure itscontinuity after phasing out and being left under the ownership of NNRWG.

# Participatory Monitoring

Participatory monitoring is the process of routinely gathering information about allaspects of project from and through collaboration of key stakeholders. It enablesthem to obtain information required in analyzing the current project situation,understand problems and find solutions, discover trends and patterns so as to maintain project activities on schedule, measure progress toward objectives, and decide on resource utilization. In other words participatory monitoring refers to process of engaging key project stakeholders in regular collection and  analysis of information to assist timely decision making, ensure accountability and provide the basis for evaluation and learning  (Mbondo,P and Ochieng G:2011). Participatory monitoring implies involvement of the community in setting a Monitoring Information System (MIS) which is the base of the follow up of the activities of the project.

In this project, stakeholders like members of NguzoNyarugusu Refugee Women Group (NNRWG) in collaboration with the other refugees and UNHCR officers together with the project manager were involved in monitoring the daily activities in order to study the trend of the project by measuring, collecting, processing and communicating information which helped other members and other development partners to make decision of the project.

# Monitoring Information System

Monitoring Information System (MIS) can be defined as “a system designed to collect and report information on a project and project activities to enable a manager to plan, monitor, and evaluate the operations and performance of the project”. This system provides powerful outputs; it is a tool for effective planning and project adjustment if needed. It helps on prioritization and informs decision making, performance sustainability, impacts and financial appraisal of the project input and output. It is a system which allows stakeholders or users to capture information related to the project implementation, process and disseminate information in systematic manner in order to provide a broad picture of the status of the project.

# Components of Monitoring Information System

The successful project needs to have effective and efficient monitoring information system. The following are the key components of the monitoring information system

- Baseline information

- Selection of indicators related to activities, outputs and objectives

- Tools for collecting information

- Collection of information

- Process information

- Analysis of information

- Presenting and communication of the results in an appropriate ways

- Using information (UN-HABITAT 2002)

In this case of the beads market/ shop and beads products training facility centrebuilding at Nyarugusu Refugees Camp; members of NNRWG are the owners of the project and they had to set out the Objectively Verifiable Indicators (OVI) against which the realization of the planned activities and the project objectives are checked.

These indicators are referred to activities of the project as planned in the previous chapter. The MIS in this project is essentially made of the reporting which will provide information about inputs, outputs, and impacts of the project. The kind of information which will be gathered for monitoring purposes will include information on all activities taking place in the project implementation.

# Table 5.1: Monitoring Information System

| Category of Information | What to monitor | What records to keep | Who collects data | Who uses data | How to use information | What decision can be made |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Work plan activities | Activities carried out | Expenditure plans | Host organization and researcher | Host organization and researcher | Ensure planned activities are implemented | Availing more resources |
| 2. Cost and expenditures | Budgeted amounts and their use | Financial reports | Host organization and researcher | Host organization and researcher | Cost-benefit analysis | Minimize cost |
| 3. Staff and supervision | Members of NNRWG willingness to participate | Training attended | researcher | researcher | Assessment of income generated | Training needed |
| 4. Commodities | Amount of curio sold monthly | Number of curio items sold | NNRWG members | NNRWG members and researcher | Proper record keeping | What curio items are needed more |
| 5. Results | Number of NNRWG members participating and income earned | Sales ledger | Project accountant and researcher | Host organization | Assessment of achieved project objectives | Extend the project to other Refugees’ communities |

Source: 2017/2018 Field Research.

# 5.1.1 Participatory Monitoring Methods

The project used participatory monitoring system which employed different monitoring methods. The system was used to monitor the implementation of the project at Nyarugusu Refugees Camp, Nyarugusu, Kasulu District. Different activities were involved in the implementation of this project and their implementation was carefully monitored. Data collected in the monitoring process was both qualitative and quantitative. Methods used in monitoring these activities differ from one activity to the other but they include site visit, check list, stakeholders’ discussions and meetings, daily and weekly reports, purchasing receipts, and other forms of lists.

Site visit is a monitoring method that allows visual assessment of progress. It allows the comparison between expected progress and the actual progress. It gives an immediate picture of the project status. It is used to monitor a number of activities in this project. On the other hand, Check list is also used to monitor several activities in this project. It gives a list of what is to be assessed and the expected progress. Once the status is different from expected it will be indicated and a further analysis will be done.

Furthermore, Stakeholders will also be involved in the monitoring process; this will be done through discussions and meetings. Contents for the discussions and meetings will come from the daily and weekly reports presented. It is in these discussions and meetings that big decisions are made. These decisions could be unchanging project activities or modifying them due to challenges faced. Receipts and lists are also used as they represent the evidence of certain transaction.

# 5.1.2 Participatory Monitoring Plan

The monitoring of activities aims at assessing achievements against set goals and objectives. The comparison between the plans and actualizations are based on the schedule summarized in the following Table5.2.

# Table 5.2: Participatory Monitoring Plan

| What was monitored | Performance indicator | Results/ Achievements observed | Remarks |
| --- | --- | --- | --- |
| Implementation of planned activities | Number of meetings with United Nations High Commissioner for Refugees (UNHCR) administration | Three meetings conducted with UNHCR & IRC administration | Done |
| Implementation of planned activities | 60 million received from UNHCR & IRC sponsorship | 60 million received from UNHCR & IRC | Done |
| Implementation of planned activities | Meters of land Tanzanian Government via UN offered for land to be used for the project | Land for the project offered | Done |
| Implementation of planned activities | Time for visit of the building constructorto the site and made measurements andneeds estimations. | Project site visited | Done |
| Implementation of planned activities | Number of building materials purchased | Building materials purchased | In progress |
| Implementation of planned activities | Time used for construction of the beads market/ shop and beads products training facility centre | Beads market &beads products training facility centre construction inprogress | Not yet achieved |
| Implementation of planned activities | Time used for window shopping for furnishing resources | Window shopping for furnishing resources done | Not yet achieved |
| Implementation of planned activities | Number of purchased furnishing resources including chairs, tables, shelves | Furnishing resources purchased | Not yet achieved |
| Implementation of planned activities | Time used for Installing and furnishing the beads market/ shop and beads products training facility centre | Furnishing resources installed | Not yet achieved |
| Implementation of planned activities | Time for identification of the best business skills trainer | Business skills trainer identified | Not yet achieved |
| Implementation of planned activities | Time used for identification of the training venue | Training venue identified | Not yet achieved |
| Implementation of planned activities | Time used for conducting the training | Training conducted | Not yet achieved |
| Implementation of planned activities | Amount of money generated through selling beads products. | Income generated through beads products | Not yet achieved |
| Stakeholders and community participation in the project | Participatory project implementation and evaluation strategy developed and contribution from all stakeholders received. | All stakeholders participated in the implementation and evaluation of the project. As well stakeholder provided their contributions on time. | Participation of all stakeholders in priority setting and in implementing and evaluating the project created a sense of ownership and commitment among stakeholders. |
| Effective resources utilization | Project financial report and the planned budget | Budget and financial report for the project available | A good financial management system has been established among group leaders and project management team to ensure effective utilization of funds. |
| Time management | Activity implementation report indicating time frame | Activity implementation report available | Proper time management was facilitated by the commitment of stakeholders in implementing project activities. |

Source: 2017/2018 Field Research.

# Participatory Evaluation

Participatory evaluation is a process of self-assessment, collective knowledge production, and cooperative action in which stakeholders in development intervention participate substantively in the identification of evaluation issues, the design of the evaluation, the collection and analysis of data, and action taken as well as a result of evaluation findings.

Participatory evaluation can be a formal process that requires substantial resources or an informal one that addresses accomplishment of the project, quality of the project and areas of improvement. It has been observed that Participatory evaluation is an approach which adjusts and redefines objectives by considering the knowledge and values of the recipient community, and also reorganizing institutional arrangements or re-allocating resources, this promotes community ownership and accountability. Participatory Evaluation requires three steps, these includes

- Articulating Participatory goals whereby the participants of the evaluation process clearly defines and list goals of their participatory evaluation.

- Defining Participatory Outcomes, in these step participants agree on the indicators which justifies if the project goals have been met.

- Assessment or measurement of the outcome by using the agreed indicators.

This project considers participatory evaluation as a customary and periodic activity and it will be conducted in manner which explained by the following cycle.

# Figure 5.1: Project Evaluation Cycle

Source: 2017/2018 Field Research.

Project evaluation is a systematic and objective assessment of an ongoing orcomplete project. It is done to determine the relevance and level of achievement ofproject objectives, impact and sustainability of the project. It also feeds lessonslearned into the decision making process of the project stakeholders includingdonors, implementers and beneficiaries (UNDP, 2009). Project evaluation involvessystematic collection of information about the activities, characteristics andoutcomes of an activity or action. Evaluation can take place at any time in a project;however the most appropriate timing will be governed by the nature of the projectand the reasons for carrying out the evaluation. It is most effective when it is built inas a fundamental part of the overall project and should be considered during theproject design (IFRC, 2011).

# Participatory Evaluation Methods

The participatory evaluation process in this project is conducted through theapplication of different methods; these methods were selected due to the nature of theproject, stakeholders of the project and the effectiveness of these methods. Theselected methods include interviews, questionnaires, evaluation stories, directmeasurements and participants’ observations.

The interview method will be usedbecause it has the ability to enable the researcher get in depth information from therespondents. This way the evaluation process will be successful as much informationwill be obtained. Moreover questionnaires are used because they enable theresearcher reach a greater number of respondents at the same time. Evaluation storiesare used to cement on the information collected through interviews andquestionnaires. These methods will be used depending on the nature of the activity tobe evaluated.

Physical methods that involve direct measurements and participants observations areused because they give the real physical status of the project. They report on what isseen on the project and this can be compared with what is expected to be seen. Direct measurements give a physical count on things involved in the project. More overwith the participants observation data is collected by listening, watching anddocumenting what is seen and heard. The combination of all these methods from theasking methods category to the physical methods category will enable the evaluationof this project and enable a reasonable conclusion to be made.

# Table 5.3: Project Evaluation Summary

| Specific Objective | Output | Activity | Performance Indicator | Expected Output | Actual Output |
| --- | --- | --- | --- | --- | --- |
| To raise Tsh 60 million to finance the project by 15th January, 2018 | Raising of Tsh 60 Million for financing the project | Contacting UNHCR & IRC administration to ask for sponsorship | Number of meetings with UNHCR & IRC administration | Five meetings with UNHCR & IRC administration | Three meetings conducted with UNHCR & IRC administration |
| To raise Tsh 20 million to finance the th project by 30 July, 2017 | Raising of Tsh 20 Million for financing the project | Receiving UNHCR & IRC sponsorship | 60 million received from UNHCR & IRC sponsorship | UNHCR & IRC administration agree to sponsor the project | 60 million received from UNHCR & IRC administration |
| To construct a beads Products market/shop and training facility centre by 31st January 2018 | 45m2 beads Products market/shop and training facility centre constructed | Tanzanian government via NHCR offered piece ofland to be used for theproject | Meters of land Tanzanian government via UNHCR offered for land to be used for the project | Tanzanian government via UNHCR have land to be offered for the project | Land for the project offered |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | The building constructor visited the site and made measurements and needs estimations. | Time for visit of the building constructor to the site and made measurements and needs estimations. | Constructor has time to visit the site | Project site visited |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | Building materials were purchased | Number of building materials purchased | Materials to be purchased are available | Building materials purchased |
| To construct a 2 32m curio shop th by 30 October, 2017 | 32m2 curio shop constructed | Construction of the curio shop was done | Time used for construction of the curio shop | Constructor available for the building process | Beads market& training facility centre construction in progress |
| To furnish the Beads Products market/shop and training facility centre by 31st January 2018 | The constructed beads Products market/shop and training facility centre furnished | Window shopping for be furnishing resources | Time used for window shopping for furnishing resources | Time and members available for Window shopping furnishing resources | Not yet achieved |

| 2017 | furnished | Purchasing furnishing resources including chairs, tables, shelves | Number of purchased furnishing resources including chairs, tables, shelves | Available furnishing resources for purchasing | Not yet achieved |
| --- | --- | --- | --- | --- | --- |
| 2017 | furnished | Installing and furnishing the curio shop | Time used for Installing and furnishing the beads products market & training facility centre. | Available furnishing resources for installation | Not yet achieved |
| To train 57 members of NNRWG business Skills by 31st March, 2018 | 57 members of NNRWG trained business skills | Identification of the best business skills trainer | Time for identification of the best business skills trainer | Available business skills trainer | Not yet achieved |
| To train 40 members of TECG business th skills by 30 November, 2017 | 40 members of TECG trained business skills | Identification of the training venue | Time used for identification of the training venue | Available training venues | Not yet achieved |
| To train 40 members of TECG business th skills by 30 November, 2017 | 40 members of TECG trained business skills | Conducting the training | Time used for conducting the training | Trainers and trainees available for training | Not yet achieved |

Source: 2017/2018 Field Research.

# Project Sustainability

Project sustainability  is the whole process of ensuring that the  institutions supported through projects and the benefits realized are maintained and continue after the end of the project (IFAD:2007).

Sustainability of a project is judged on the basis of its capacity to continue functioning after external support has stopped. Different stakeholders intervened in supporting the implementation of this project but a after this support is gone the project should remain. A sustainability plan should be prepared the way in which it will continue to exist. In order to ensure sustainability of the project, the following factors needs to be assessed and taken into consideration as far the planning is concerned: institutional sustainability, financial sustainability and political sustainability. A sustainability of a project is judged on the basis of its capacity to continue functioning after external support has stopped.

# Social Sustainability

The project is established in a participatory manure were all stakeholders were involved in decision making. The host organization and the researcher performed the community needs assessment which identified the needs for the community. For this case it is the members of the community that identified their needs and suggested a project that will help them meet that need. The project has started to undertake social assessment social analysis and assessment which will enable them to identify social opportunities which can ensure sustainability of the project. These included full involvement of women in project planning and implementation.

Also, the project has managed to identify the risks which might threats the sustainability of the project like low level of education and gender inequality. Members decided to develop mitigation strategies and also advised the facilitators as they were planning training sessions so that they can deliver training according to the level of education of the participants. There is a plan of sensitizing women and girls to join with NguzoNyarugusu Women Group in order to reduce their dependence in terms social and financial support from the donors instead depending on their livelihood activities to generate their income while boosting u their economy and take a comfortable care of their families. This means members of this community are ready to take part in the project as it is their idea in the first place. Members of NNRWG are very much involved in the project hence are in a good position to take care of the beads market/shop and beads training facility centre.

# Institutional Sustainability

Institutional sustainability is ensured because the project is established at the land provided by Tanzanian government via UNHCR of which the land is within Nyarugusu Refugees Camp. Nguzo Nyarugusu Refugees Women Group already has its administration, procedures, rules and regulations that are followed in the day to day operation. It has different ways of ensuring accountability for its members hence the same is extended to the running of the project. The group is also the beneficiary of the project which means they are the ones to loose in case the project fails. However, considering the principles of NguzoNyarugusu Refugees Women Group, values and ethnics, members plan to select leaders with high integrity and respecting the guiding principles.

Also to draft a constitution, it has been clearly stipulated the organizational structure and terms of leadership hence it is expected that elected leaders will be transparent and will lead according to rules and regulation which will minimize the risks which could threat existence of the NguzoNyarugusu Refugees Women Group and Refugee Camp at large. On the other side, NguzoNyarugusu Refugees Women Group expected to set bylaws which will guide operations of the NNRWG and will provide guideline to individual member.

# Economic Sustainability

The main aim of this project is to construct a beads market and training facility centre that will help member’s of NNRWG sell more beads items and hence increase income which will help improve their livelihood. The sustainability of this project is ensured because resources to run the project are available even after the host organizations withdrawal. These resources include human resources which include members of NNRWG and financial resources which will be obtained from selling beads products.

In order to ensure financial sustainability, members agreed to strengthen the internal sources of funds by membership fees, sell and purchase of cooperative shares coupled by other sources like interest which will be obtained from money provided to members as loan. Also, members agreed to contribute part of their daily beads products in which the NNRWG will sell and earned income will be used as an initiative to boost capital of the NNRWG. Moreover the host organization ensured that NNRWG members received training that will help them runthe business successfully. These skills will be applied in running the project hence ensure sustainability of the project.

# Environmental Sustainability

The project is carried out in an environment friendly manner. The environment is not negatively affected anyhow by the existence of the project but rather affected positively in support of the ecosystem as well as recycling the waste products such as shredded papers.

# CHAPTER SIX

# CONCLUSION AND RECOMMENDATION

# Introduction

The conclusion and recommendation is derived from the previous chapters including the community needs assessment, problem identification, literature review, and project implementation and project monitoring and evaluation. Therefore this chapter summarizes all the findings of the whole project from chapter one to five.

# Conclusion

In establishing the project to improve livelihood of the NguzoNyarugusu Refugee Women group by constructing a beads selling shop, different stages were involved which are presented as chapters in this document. The first activity was the participatory needs assessment presented in chapter one whereby different activities took place which include describing the community through the community profile that gave a description of the Regugee Community in the Nyarugusu camp, in Kigoma municipality, respondents education level and economic activities. It also explains the community needs assessment which was conducted at Nyarugusu Refugee Camp in a participatory manner. The community needs assessment had the aim of collecting information needed to establish a CED project which will lead to the improvement of livelihood for NRRWG members.

The specific objectives of the CNA included identification of challenges faced by NguzoNyarugusu Refugee Women Group, identifying economic opportunities present at Nyarugusu Camp and lastly identification of income generating project that can be run by members of NNRWG and hence improve their livelihood. The research design used was descriptive research design while the sampling technique was non-random sampling. The data collection methods used included methods to collect both qualitative and quantitative data, these included document review, questionnaire distribution and interviews. The CNA findings gave a demographic characteristic of Nyarugusu Refugees which included number of respondents, gender, education, economic activities and income earned. The most important findings in chapter one are on the identified needs of which construction of beads shop was highly prioritized according to the pair wise matrix presented.

The second chapter presents the problem identification which includes explanation on the background to the research problem which gives a detailed explanation on the background to the problem. The second part of this chapter gives the problem statement whereby lack of beads shop and was seen as the main problem that brought about this study. The chapter also gives the project description which elaborates on the target community which is the members of NNRWG community from Nyarugusu Camp and also involved stakeholders. Moreover, in the second chapter objectives of the project are defined, they include raising Tsh 60 million by 15th January 2018, To construct and furnish a 45m2 beads selling shop by 31 January 2018 and lastly train members of NNRWG business skills by 31 March 2018. Lastly this chapter gives a detailed explanation on the host organization which is the UNITED Nations High Commissioner for Refugees (UNHCR).

The third chapter is the literature review which gives a brief review of literatures related to this study. It includes the theoretical literature review and the empirical literature review which presents other studies related to this one. Lastly the literature review gives a summary on different policies related to the study. Chapter four represents the project implementation giving a detailed explanation on how the project was implemented. It explains on the products and output resulting from the project. It give a description on the project planning, project implementation plan, logical framework, project budget, project implementation report, output presentation and the ghantt chart. Lastly the fifth chapter represents the project participatory monitoring, evaluation and sustainability. This explains on the participatory monitoring and information system, the participatory monitoring methods used and participatory evaluation. Lastly project sustainability is explained which includes social, institutional, economic and environmental sustainability.

In conclusion the implementation of this project had a total of 10 activities of which some of them have been executed successfully while the remaining will be realized at later stages of the project. All the realized activities were successfully implemented and the output was realized as expected. This is giving a good feedback and ensures the success of the project which is improving livelihood of NguzoNyarugusu Refugee Women Group by constructing a beads products shop.

# Recommendations

Based on the findings of the study and the project implementation, the researcher recommends the following.

- Firstly to the government, to find a way of conducting CNA in the Refugee Community so that they can identify challenges that they face in a more participatory way that ensures success.

- The government should also find a more effective way that they can support refugee groups which are doing some economic activities but their environment is not very conducive.

- To the host organization (UNHCR) the researcher recommends that they keep introducing and support more livelihood activities in the Refugee camps so that they can improve their livelihood and reduce dependency on the Humanitarian Aid.

- The Government should look on the possibility to provide exit/entry permits to the Refugee Group Leaders to go to the markets around the Kigoma region to sell their products during the market days

- More research to be done on the success of this project.

# REFERENCES

Birchall, J. (2009). Cooperatives and Poverty Reduction, Evidence from Sri Lanka and Tanzania, Cooperative College, RAP Spider web, Manchester, UK.

Bulayi,  M. E. (2001), Establishment of Community Based Cooperative Fisheries, Management of Lake Victoria Fisheries in Tanzania, University of Iceland, Reykjavik, Iceland.

Centre for Development and Population Activities (1994) Project design for Program Managers, Washington, DC.

Estrella , M (1998)  Learning from Change: Issues and experiences in participatory monitoring and Evaluation, Intermediate Technology Publications.

IFAD, (2009). Sustainability of Rural Development Projects, Best practices and lessons learned by IFAD in Asia, Asia and Pacific Division.

Kigoma Ujiji Municipal Council, (2008). Environmental Profile, Kigoma, Tanzania.

Kigoma Ujiji Municipal Council, (2011). District Profile, Kigoma, Tanzania.

Kothari C. R. (2004). Research Methodology, Methods and Techniques, New Delhi: New Age International.

Lyimo, F. F. (2012). Rural Cooperation in the Cooperative Movement in Tanzania, Dar-es-salaam: Mkuki and Nyota Publishers.

Ovando, D. (2011). Baja California regional federation of the Fishing cooperative societies, Fisheries Cooperatives as a Management Institution, California.

Saunders. M, Lewis .P and Thornhill.A (2009). Research methods for business students, New York: Pearson.

Sharma, A., Lanum. M. and Balcazar, Y. (2000). A Community Need Assessment Guide, Loyola University, Chicago.

Shija, A. (2007). Establishing Community Based and Managed Saving and Credit Group Systems to People Living with HIV/AIDS in Marumbo Ward in Kisarawe District, Final CED Project, The Open University of Tanzania, Dar-es-salaam, Tanzania.

Sizya, M. J. (2001). The Role of Co-operatives play in Poverty reduction in Tanzania, paper presented at the UN in International Day for Poverty Eradication October 2001.

SPCP report available in www.unhcr.org accessed on 15th September 2017 at 20.24 PM.

Tanzanian Federation of Cooperatives, (2006). Cooperatives and Development In Tanzania: A Simplified Guide to the Cooperative Development Policy and the Cooperative Societies Act of Tanzania Mainland. Dar-es-salaam, Tanzania.

The 1951 International Refugee Conversion.

UN-HABITANT, (2002). “People’s Process in Post-disaster and Post-conflict Recovery and Reconstruction: Chapter 7: Monitoring Information System”

URT, (1997) Cooperative Development Policy, Dar-es-salaam

URT, (1998) Kigoma region Socio-economic profile, Dar-es-salaam, Tanzania

URT, (2000) ,National Micro-finance Policy, Dar-es-salaam, Tanzania

URT, (2000) Poverty Reduction Strategy Paper, Dar-es-salaam, Tanzania

URT, (2003) Cooperative Development Policy, Dar-es-salaam, Tanzania

URT, (2005) National Strategy for Growth and reduction of Poverty, Dar-es-salaam, Tanzania.

# Text boxes

The Tanzania Government

Group Manager

Service International

UNHCR– Tanzania

Group Manager

Border Security

Group Manager

Service Delivery

Group Manager

Service International

Refugee Division

Immigration Offices in NZ & Overseas

Secretary of Labour

Immigration Profiling Group

Central Verification Unit

Refugee Status Branch

Refugee Quota Branch