INCREASED HOUSEHOLDS INCOME OF HOPE TRUST WOMEN GROUP IN EKENYWA VILLAGE THROUGH POULTRY KEEPING IN ARUMERU DISTRICT

SELINA NGURUMWA

A PROJECT REPORT SUBMITTED IN PARTIAL FULFILMENT FOR THE REQUIREMENT OF THE DEGREE OF MASTER IN COMMUNITY ECONOMIC DEVELOPMENT OF THE UNIVERSITY OF TANZANIA

2017

# CERTIFICATION

The undersigned certifies that she has read and hereby recommends for the acceptance by the Open University of Tanzania (OUT) a project entitled, “Increased household income of Hope trust women group in Ekenywa village through poultry farming Arumeru district”, in partial fulfilment of the requirements for the degree of Master of Community Economic Development of the Open University of Tanzania

………………..………………

Dr. Herieth Mtae

(Supervisor’s)

.................................................

Date

# COPYRIGHT

No part of this dissertation may be reproduced, stored in any retrieval system, or transmitted in any form by means, electronic, mechanical, photocopying, recording or otherwise without prior written permission of the author or the open university of Tanzania in that behalf.

# DECLARATION

I, Selina Ngurumwa, do hereby declare that this CED project report is my own original work and that it has not been presented and will not be presented to any other University for similar or any other degree award

.....................................................

Signature

........................................................

Date

# DEDICATION

This work is dedicated to my beloved husband, parents, sons and daughters for their love and tolerance they shows me when I was studying, they really encouraged me and supported me a lot for their encouraging words.

# ACKNOWLEDGEMENT

I would like to express my gratitude to all those who gave me the possibility and assistance to facilitate the production of this project report. However it will not be possible to mention everyone by name, they all owe my heartily gratitude. For the few people who will be mentioned, I am particularly indebted to my supervisor Dr. Herieth Mtae for her tireless efforts which enabled me to write and complete this project report.

I sincerely appreciate her support.  I also wish to convey my thanks to my lecturers and all Open University staff for their efforts to make this course possible. I would also like to appreciate CED post graduate students (2016 – 2017), for their useful help, encouragements and criticisms in the course of preparing my project report. I do recognize the support of Arumeru District Council staff especially from agriculture and livestock, community development departments for their support.

# ABSTRACT

This study is the product of CED student which aimed to increase households income of Hope Trust women group in Ekenywa village found in Arumeru.The researcher conducted his study through Tumaini VICOBA group in Ekenywa village which is a socio-economic financial group.Hope Trust group is a five women group which was formed aimed to unite their efforts of marginalized women group to improve their households’ income in Ekenywa village. The study carried participatory community needs Assessment. The assessment was done through identification of community needs in participative manner. The study involved collection of data through interview and focus group discussion and through informant group in the community. It was therefore through pair wise ranking that poultry project was identified. The study revealed that poultry project was economically viable and implementable in Hope Trust women group. The goals which were implemented included, determine the economic activities that is undertaken by Hope Trust group members, examine the possibility of establishing the income generating project in the Hope Trust group and access and build capacity of Hope Trust group in management and sustainability of chicken project by 2017.The expected result increased productivity of poultry project, resulted to functioning and efficient poultry project through Hope Trust group. More women are now attracted to the project very eager to establish new poultry projects in Ekenywa village. The three objectives were met with exception of selling project product which will be achieved by December 2017.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENT	vi

ABSTRACT	vii

TABLE OF CONTENTS	viii

LIST OF TABLES	xii

LIST OF FIGURES	xiii

LIST OF ABBREVIATIONS	xiv

CHAPTER ONE	1

1.0 PARTICIPATORY NEEDS ASSESSMENT	1

1.1 	Background Information	1

1.2.2 	Health Services	3

1.1.4 	Education Services	3

1.3	Community Needs Assessment	4

1.3.1	Objectives of Community Need Assessment	6

1.3.2 	Community Needs Assessment Methodology	7

1.3.3 	Research Design	7

1.3.3.1   	Sampling Techniques	8

1.4   	Data Collection Methods	9

1.4.1   	Secondary Data	9

1.4.2   	Primary Data	9

1.5   	Data Analysis Methods	10

1.6	Community Assessments Needs Findings	10

1.5.1   	Age distribution of Women in Hope Trust Group	11

1.5.2   	Education of Respondents	12

1.3.3	Sources of Income	12

1.3.1.2	Impact of Poultry Keeping to Community Members	13

1.4 	Community Needs Prioritization	13

1.7   	Chapter  Conclusion	15

CHAPTER TWO	16

2.0 PROBLEM IDENTIFICATION	16

2.1 	Background to Research Problem	16

2.2 	Problem Statement	17

2.3 	Project description	18

2.3.1 	Target Community	18

2.3.2 	Stakeholders	18

2.3.3 	Project Goals in CED Terms	19

2.3.4	Project Objectives	20

2.4 	Host Organisation Profile	20

2.4.1 	Vision	20

2.4.2 	Mission	21

2.4.3 	Activities	21

2.4.4 	Tumaini VICOBA Structure Chart	21

2.3.5 	SWOT Analysis of the Community Based Organization	21

2.4.6 	Role of CBO in the Project	22

2.3.7 	The Role of CED Student in the Project	22

CHAPTER THREE	23

3.0 LITERATURE REVIEW	23

3.1 	Introduction	23

3.2 	Theoretical Literature	23

3.2.1 	Definitions of Key Concepts	23

3.2.1.1 	Poultry Farming Production As Source Of Household                                    Income Raising	23

3.3 	Empirical Literature	27

3.3.2 	The Traditional Treatment and Careering of Poultry for                               Productive Manner	28

3.3.2 	Poultry production in other African countries	30

3.4 	Policy Review	32

3.5 	Literature Review Summary	34

CHAPTER FOUR	36

4.0 PROJECT IMPLEMENTATION	36

4.1 	Introduction	36

4.2 	Project Outputs	36

4.3 	Project Planning	39

4.3.1 	Project Implementation Plan	39

4.3.2 	Inputs	46

4.3.3 	Staffing Pattern	48

4.3.4 	Project Budget	48

4.4   	Project Implementation	51

4.4.1 	Project Implementation Report	54

4.3.2 	Project Implementation Gantt chart	56

CHAPTER FIVE	60

5.0 PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	60

5.1 	Introduction	60

5.2 	Participatory Monitoring	62

5.2.1	 Monitoring Information System	65

5.2.2 	Participatory Monitoring Methods used to Engage                            Community in the Monitoring the Project	68

5.1.2.3 	Group Interview	69

5.3 	Participatory Monitoring Plan	69

5.3   	Participatory Evaluation	73

5.3.1 	Performance Indicator	74

5.3.2 	Participatory Evaluation Methods	74

5.3.3   	Project Evaluation Summary	76

5.4 	Project Sustainability	78

CHAPTER SIX	81

6.0 CONCLUSION AND RECOMMENDATION	81

6.1 	Introduction	81

6.2 	Conclusion	82

6.3 	Recommendation	84

REFERENCES	87

APPENDICES	90

LIST OF TABLES

Table 1.1: Age Distribution of Respondent	11

Table 1.2: Education Levels of Respondents	12

Table 1.3: Sources of Income	13

Table 1.4: Impact Assessment of Poultry Keeping on Economic Income	13

Table 1.5: Pair Wise Matrix	14

Table  4.1:   Project Objective and Output	37

Table 4.2: Project Implementation Plan	41

Table 4.3: Project Logical Framework	44

Table 4.4: Project Inputs	47

Table 4.5: Project Budget	49

Table  4.6:  Project Implimentation	55

Table 4.7:  Actual Project Implementation Summary	55

Table 4.8:   Project Implementation Gantt Chart	57

Table  5.1:   Project Monitoring Information System	67

Table  5.2: Participatory Monitoring Plan	71

Table  5.3: Project Performance Indicators	75

Table 5.4: Project Evaluation Summary	77

# LIST OF FIGURES

Figure 2.1: Tumaini VICOBA Structure Chart	21

Figure 4.1: CED Student with Community Members During Training	54

Figure 4.2: CED Student with the 5 Women Trained After Training	58

Figure 4.3: Group Members Beside Constructed Building for Chickens	58

Figure 4.5: Some of the Chickens Among the One Bought By The Group Members  Within Their Built House	59

# LIST OF ABBREVIATIONS

CAN 	Community Needs Assessment

CBO	Community Based organization

CED	Community Economic Development

CTI	Confederation of Tanzania Industries

FAO	Food and Agriculture organization

GDP	Gross Domestic Product

ILRT	International Livestock Research Institute

OVC 	Orphans and Vulnerable Children

TCAL	Tanzania Chamber of Agricultural Council and Livestock

TCCIA	Tanzania Chamber of Commerce, Industry and Agriculture

TPBA	Tanzania Poultry Breeders Association

URT	united Republic of Tanzania

VAT	Value Added Tax

# CHAPTER ONE

# 1.0 PARTICIPATORY NEEDS ASSESSMENT

# 1.1 Background Information

In Tanzania chickens play an important role in rural economies in most of the people living in rural areas and urban area. In the rural area chicken are mostly kept by women who always households care taker and 90% of chicken are chickens where as 72% are kept traditionally in rural areas.  The chicken is used as source of income to women living in rural areas. An average chickens kept in Tanzania is between 5-20househould are 12 chickens.  Women use chicken to buy food, nutrition, shelter, paying of energy bills such as kerosene for those without electricity and clothing. Women however use income from chickens for school requirement such as scholastic materials and uniforms.

Despite of the above advantages of keeping chickens, chicken keeping is still at an infant stage both in the commercial and traditional sub-sector. The small scale poultry keepers have not maximized chicken productivity due several challenges accompanied with keeping them. Small scale chicken keepers are faced inadequate or poor chicken keeping which cause low yield. Keeping chicken need capital, knowledge on management for anyone to realize benefits of keeping chicken. At the same time availability of extension services in the rural settings has not yet encouraged chickens productivity.

In Tanzania you can hardly find livestock extension officer per village. Most of those extension officers are allocated per ward. Due to lack of transport means such as motor cycles it’s also very difficult for them to support each household. It’s because of mentioned factors that you find that there are many chickens nearly each household but very low income. The community during needs prioritization in collaboration with stakeholders, researcher found establishment of chicken project women sound viable and economically. The community ranked chicken keeping of group to support them in generating income easily. The group will help them get education on chicken husbandry more easily from extension officers and other expertise. The group productivity will be higher and there will have higher income.

During needs assessment exercise, the CED student applied various methods to gather data from the community, such as Focus Group Discussions (FGD), Individual key- informants, Office records, previous research reports and physical observations of events and situations. The information collected supported researcher to prepare community profile, community prioritization of needs and identified community opportunities with can be used to solve community problem.

  - Community Profile

Hope Trust group is a women group which identified and organized themselves in collaboration and support of CED Student. The group members comprises of women with different ages dealing with several economic activities. Among the income generating activities include poultry keeping, beads making, cattle keeping, sheep keeping and farming of maize, beans and sunflower. The level of education of most group members is primary education. The group members live in Ekenywa village found in Mwandet ward found in Arusha District council. Arusha District Council was established with effect from the 1st July, 2007 from the former Arumeru District Council. The Council is located South of the equator in between Latitudes ‘3010- 4000’ and Longitudes 34047’-350 56’ East. Arusha District Council covers an area of 1446.692 square kilometers.

1.2.1 Climate

The climate of Arusha District Council in which Ekenywa village is within is Characterized by two rainy seasons, long and short rains.  A long rain begins on April to early June while short rains begin in October to December and ranges between 800mm to 1000mm per annum. The mean annual rainfall is 900mm with a humidity of 42% minimum and 50% maximum, while the temperature ranges from 16˚C to 33˚C throughout the year.

# 1.2.2 Health Services

Ekenywa village has health services which are accessed by its residents more easily. The health services found included Olturumet hospital, Catholic health center. The pharmacy centers are always found at Ngaramtoni small town.

1.2.3 Economic activities

The economic activities found in the village include agricultural and livestock activities which include beans, maize, lablabs, sunflower, sweet potatoes, tree nursery (Radio Habari Malumu institute) and cows, poultry, sheep, donkeys, pigs and goats respectively. The village has mining activity which provides most of youths known as Kilimamoto where stones are dug for construction in village.

# 1.1.4 Education Services

Ekenywa village has primary schools, secondary schools,training institutes and vocation training college. The Primary schools found includes Ekenywa and Baptist English Media primary school. The secondary school found is Ekenywa secondary school. The colleges are Radio Habari Maalum Journalist College, and Catholic vocational training college.

1.1.5 Financial Services

The ward has several financial services including VICOBA groups, CRBD bank, NBC and NMB bank services which are either accessed physically or through mobile money systems such as M-PESA or TIGO –PESA and Airtel Money.

# Community Needs Assessment

Community needs assessment for Hope Trust group was conducted to identify gaps in the community. The gaps, opportunities were identified by the community and ranking of needs according to resources and opportunities. The community needs assessment of Hope Trust was conducted in a participatory way to enable identification of the real needs of the community and thereafter made interventions to the critical problem.

The assessment was done based on the appropriate use of research design and research methods. Community Needs assessment is one of the critical stage in the project development process. Systematic needs assessment is reasonably a new phenomenon in the development. There is a rising conformity among development practitioners to consider needs assessment as a process to identify and measure gaps between “what is” and “what should be” prioritize the gaps, and determine the way to bond them. Development projects require precise, reliable, usable information which are participative in manner that missions and needs of a specific community are people’s centered.

The community needs are unlimited so by community need assessment the community will get opportunity to sort and find those very crucial compared to another in order to meet the scarce resource. Needs should originate directly from ideas articulated by representative groups of the target population and other stakeholders in a community. Project ideas and objectives should be based on such needs. Needs assessment should be done in participatory manner with target population. This will strengthen community commitment to overcome poverty in the community and hence sustainability of the project. Besides igniting project ideas, community needs assessment generates data to develop indicators for evaluation; furthermore needs assessment help in creating community ownership in a project. It is an effective system of inquiry that provides information to help decision makers.

During this stage of need assessment, different development practitioners in the community were given an opportunity to appraise analysis and give comments on the identified needs and come up with priorities. The exercise was done in a participatory approach where group members positively participated in all discussions to identify their needs. The purposes of this need assessment lie on the fact that the project life cycle begins with a needs assessment. Prior to a successful project is established, it is crucial and significant to have a good understanding of the project setting based on the community needs assessment.

Needs assessment was conducted to identify a broad range of problems within a community and decide which a project need will addressed. Various methods and techniques need to be used to collect information on the community needs assessment to identify the community needs and find solution to their problems. Information for situation analysis and problem definition is collected with the involvement of the community members using several techniques. This was to ensure validity, reliable and comprehensive information about the community and its problems. The situation analysis involved the identification and definition of the characteristics and problems; it was done by collecting information necessary to understand the community. Situation analysis is very important before any attempts to solve the problem because it provides an opportunity to understand the dynamics of the community; helps to clarify social, economic, cultural and political conditions. Situation analysis also provides an initial opportunity for people’s participation in all project activities and enables the definition of community problems and solutions.

Methodology to put into operation a community needs assessment is determined by the type of assessment that is being performed. Generally proposed methodology included focus group discussion, collecting and analyzing data, producing a final report and planning action committees. In order to implement community needs assessment, CED student selected community and people who will structure the community needs assessment.

# Objectives of Community Need Assessment

The overall objective of the study is to organize and form a social- economic group for the purpose of identifying community economic gap(challenges) within their household and provide possible viable solution to overcome the constraints.

The specific objectives of the study

- To identify challenges facing Hope Trust Group

- To determine the available resources which can be used to overcome the challenges   that are facing Hope Trust group members.

- To examine the possibility of establishing the income generating project for Hope Trust group.

Community Needs Assessment questions

- What are the economic activities carried out by Hope trust women group members?

- What can be alternative potential income generating project that will increase the income to Hope trust women group members?

# 1.3.2 Community Needs Assessment Methodology

The targeted community is Ekenywa village population that was identified at Arumeru district council specifically for the department Community development and Agriculture that works with more than one community in facilitate them to accomplish their goals. The assortment of the Ekenywa village based on the community need as well as with the visit to the area of operation after consultation with village management. The visit discovered that the village is very appropriate for this research.

# 1.3.3 Research Design

The research done was descriptive in nature, in this descriptive study, both qualitative and quantitative methods for data collection were used. Quantitative approach involves collection of quantifiable data which are normally in terms of quantities (numbers) and qualitative data were also collected such as sex of respondents. These qualitative data and quantitative data collected from the study were represented in form of tables.

# 1.3.3.1   Sampling Techniques

The study was carried out in Ekenywa Village. During the field work both simple random and purposes sampling technique had been used to determine the sample size and sample elements. The respondents were of two types. Those who were randomly selected and those purposively selected due to their virtue of responsibilities. Simple Random Sampling: Has property that any one has an equal chance of being selected. This technique was being used to obtain respondents among member of the community villagers where the projects do exist, performed. This has been done in order to avoid biasness and bring equal representation among the population in which 12 members were selected.

Purposive Sampling: Researcher selected only those elements which he/she believes that were able to deliver the required data. At this juncture the sample selected were as follows 10 Government Officers at the village and ward, 10 livestock-keepers and 8 poultry keepers. The total number of respondents are 40. The study consisted of 40 respondents who were randomly and purposely sampled from the community (influential person and representatives from each sub-village) where simple random sampling was used. After field work all 40 questionnaires were filled in and returned.

# 1.4   Data Collection Methods

Data were collected through primary sources and secondary sources. Both secondary and primary data were collected through various methods and these methods were;

# 1.4.1   Secondary Data

Secondary data were taken from available data or information that were in documentations in various offices. These data collected were taken through documentary review method, in which, the abstract from different reports, pamphlets, books, event reports and Journals.

# 1.4.2   Primary Data

These are the data collected by the researcher directly from the respondents that were selected through the determined sampling procedures. Interviews, Focus Group Discussions and other methods were used by the researcher. The following are methods and tools used in the exercise;

Questionnaires: Data were collected through the use of questionnaires. Questionnaires were distributed to forty respondents and all respondents returned the questionnaires. The respondents had ability to read and write. The questionnaire helped in collecting general information about the interviewee such as age, level of education, respondents’ income, respondents’ occupation, community economic activities.

Interview Method: Interview method was used in primary data collection. The researcher collected information/data from the respective respondents by using interview method by using structured and unstructured questions as a main tool. Questionnaires used had some questions that were used to interview the respondents.

Focus Group Discussion: Focus Group Discussion method was very useful in collecting data or Information from the community or respondents by using two groups of participants or respondents. Community members had a Focus Group Discussion on various issues like income generating activities existing within their community and the potential projects that would increase households’ income. Focus Group Discussion apart from being used as data collection method, bringing capacity building to group members when participating in answering some questions.

# 1.5   Data Analysis Methods

The data collected from the study was analyzed both quantitatively and qualitatively. The data from primary source was analyzed through frequency distribution table. Also the data collected was presented in tabular format. Qualitative data were collected through the use of Focus Group Discussion that was conducted during the study. During the study some were given questionnaires, some were interviewed and some were collected or gathered for Focus Group Discussion in order to collect data. Community members had a Focus Group Discussion on various issues like income generating activities existing within their community and the potential projects that would increase households’ income. So, during the study both qualitative and quantitative data were collected.

# Community Assessments Needs Findings

The findings from the CNA in Ekenywa village are presented below based on the method and type of data collection. The Researcher used questionnaire to get information on person’s views particulars and general understanding on various issues regarding socio-economic development The researcher used Focus Group discussions with various stakeholders where opportunity to get additional information was possible. The FGD helped to enrich information from interviewees and even those from secondary sources. Gathering of information using the questionnaire the researcher prepared forty questionnaires where all were returned while properly filled. The findings from the questionnaire show the respondents age and level of education. Thereafter, follows the general overviews on economic activities. Qualitative data collection included 40 interviewees.

# 1.5.1   Age Distribution of Women in Hope Trust Group

The Community Needs Assessment findings done at Ekenywa village basing on the methods of data collection used, can be explained in percentage way basing on the age distribution of the respondents. According to findings shows that women between  age of 25-32 were 50 % of the  population of 40 followed by those with age between 32-39 in which they were 37.5% and the last group was between 39- 46 in which they were 12.5%. The researcher was encouraged with this group distribution of population that they had enough capability and efforts of establishing and implementing the project sustainability, had been derived from different methods of data collection such as questioners, focus group discussion observation and interview. Table 1.1 shows the age of the responded in percentage ways.

# Table 1.1: Age Distribution of Respondent

| Age of respondent | Frequency | Percentage(%) |
| --- | --- | --- |
| 25-32 | 20 | 50 |
| 32-39 | 15 | 37.5 |
| 39-46 | 5 | 12.5 |
| Total | 40 | 100 |

Source: Study finding 2017

# 1.5.2   Education of Respondents

# Table 1.2: Education Levels of Respondents

|  | Frequency | Percentage (%) | Valid percent | Cumulative percentage |
| --- | --- | --- | --- | --- |
| Not attended to school | 2 | 5 | 5 | 5 |
| Standard seven | 33 | 82.5 | 82.5 | 87.5 |
| Form four | 5 | 12.5 | 12.5 | 100 |
| Total | 40 | 100 | 100 |  |

Source: Study findings 2017

From the above table findings show that women who were in the group had different level of education. The data shows that 5% didn’t attend to school at all, 87.5% attended only primary school and 12.5% attended secondary school. Findings show that most of the Hope trust women group members who are the respondent are educated as it is being categorized in the Table 2 above. Hence they are the people  with knowledge and experiences in reading and writing .This gives them a big opportunity  in doing business  as it will easy the search for the markets for the project products and also will help in the financial management of the project  as well as  in making the right decision at right time for fund utilization.

# Sources of Income

Most of the women in the Hope trust group had different economic activities that they perform in order to get earning that made them and their families to sustain as 50% were dealing with maize farming production activities, 15% poultry keeping, 32.5% were doing cattle keeping production and 2.5% were receiving monthly salary. This can be found at the Table 3.1.

# Table 1.3: Sources of Income

|  | Frequency | Percent (%) | Valid percent | Cumulative percent |
| --- | --- | --- | --- | --- |
| Maize Farming | 20 | 50 | 50 | 50 |
| Poultry keeping | 6 | 15 | 15 | 65 |
| Cattle keeping | 13 | 32.5 | 32.5 | 97.5 |
| Monthly salary | 1 | 2.5 | 2.5 | 100 |
| Total | 40 | 100 | 100 |  |

Source: Study findings 2017

# Impact of Poultry Keeping to Community Members

The women were grouped into three groups to access the impact of poultry keeping. As the results, finding shows that the project of Poultry keeping will bring an impact of 72.5% in the economic status or income status of the community members at household level up to the community level at large.25% of the respondents said that the project will have an economic impact while a third class was comprised with2.5% who said that the project will have an impact though low impact. The table below shows the explained results.

# Table 1.4: Impact Assessment of Poultry Keeping on Economic Income

|  | Frequency | Percent (%) | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| First group of women | 29 | 72.5 | 72.5 | 72.5 |
| Second group of women | 10 | 25 | 25 | 97.5 |
| Third group of women | 1 | 2.5 | 2.5 | 100 |
| Total | 40 | 100 | 100 |  |

# Source: researcher, 2017

# 1.4 Community Needs Prioritization

The project of poultry keeping was been identified and recognized by Hope trust women group members through focus group discussion method. This method was used to identify and recognize potential project to be implemented.  The potential projects were identified then Pair wise Ranking method has been used to rank the identified projects so as to find out which one could be the initial and best project to be implemented. Through Pair wise ranking, the project of poultry keeping has been given the first priority to be implemented as it score more than others. The identified and recognized potential were: the project to beads making production, cattle farming production, maize farming production and tailoring.

Through ranking all the identified potential projects, the group members ranked them for the purpose of finding out the project that will be feasible and that will cost less. Also the project  that will be sustainable and which achieve their planned goal and have economic impact by increasing household incomes for the purpose of turning them  into having positive improvements in  economic status. The members of the group play a part in the identification as well as in making ranking of their potential projects in which they result up of poultry keeping project. The group agrees together as they found that the project to be implemented will led to income generation for the purpose of reducing income poverty and for the affordability of their needs.

# Table 1.5: Pair Wise Matrix

|  | Beads making project | Cattle keeping project | Poultry farming production | Maize farming project | Tailoring project | Score | Ranks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Poultry farming production |  | Poultry farming production | Poultry farming production | Poultry farming production | Poultry farming production | 5 | 1 |
| Maize farming production |  |  | Maize farming production | Maize farming production | Maize farming production | 4 | 2 |
| Beads keeping production |  |  |  | Beads keeping production | Beads making production | 3 | 3 |
| Maize farming production project |  |  |  |  | Poultry farming | 1 | 4 |
| Tailoring project |  |  |  |  |  | 0 | 5 |

Source: Study findings 2017

# 1.7   Chapter  Conclusion

The chapter had more focused with the Participatory Needs Assessments which was the involvement of the community members in the identification of their needs and wants, as well as ranking them for purpose of prioritizing their needs and wants in order to find the possible interventions and ways to solve them. The participatory Needs Assessments done at Hope trust women group Ekenywa village  had shows that there will be an increase of household income through formulation and implementation of  poultry keeping project  as it was  declared by community members to be feasible and sustainable.

# CHAPTER TWO

# 2.0 PROBLEM IDENTIFICATION

# 2.1 Background to Research Problem

Hope Trust women group members are among Tumaini VICOBA members found within Ekenywa village. Tumaini VICOBA meets every Saturday. VICOBA group contributes five thousands Tanzanian shillings as their shares stipulated in their constitution. Many of the Hope Trust women group members fail to contribution shares and this made them to very nearly lose their membership. It is through VICOBA were they can have an access to loan that they can support them to run different socio-economic activities which can support them to meet their basic needs of living as well as raising the socio-economic income of their families.

It was through participatory assessment that was made and different methodology that was used as a key arrangement in identifying problems affecting them it was were the problem had been identified . The assessment helped the investigator in determining major needs rising from the identified problem and arrangement on the ways to solve them. From all the problems income is at high demand, with income they can meet all other need like payment of their weekly VICOBA shares that will enable them to be active members so that they can easily access loan from it so that to run different socio-economic activities.

Income poverty has become a challenge to most of Tanzanians for both living in rural and living in urban areas. Many families live under income poverty, they live under 1 US $ per day. It is due to this reason that made also Hope Trust women group to lack five thousands Tanzanian shillings to pay as their weekly VICOBA shares so as to enable them to have access of loan from it so that to support them to run their socio-economic activities. For Hope Trust women group members to afford payment of their VICOBA weekly shares for every moment they meet there is a need of establishing income generating project that will increase their level of income hence consistence in their shares contribution payments. As having other source of income through establishment of income generating project, Hope Trust women group members will also get extra money of which it will support increases of their household income and household improvements.

# 2.2 Problem Statement

Hope Trust women group are in a highly require of the money for the contribution of their weekly shares in VICOBA in order to have access of loan to run out socio-economic activities for the increase of their families’ income. Although the group members join VICOBA but still they cannot afford to provide basic needs to their families to the failure of accessing loan from VICOBA to run their socio-economic activities. This is due to the failure of paying their weekly contribution shares  due to lack of money as the result of Income poverty among the members. Therefore Hope Trust women Group members need to access more sources of incomes in order to meet their obligations and also improve their household status. Hence Hope Trust women group members have to establish poultry keeping project as a faster income generating project in order to meet their   requirements.

According to the dissertation done by an CED student Angela Kiama Mvaa(2015) on Capacity  building to Engosengui women group in Improving local chicken production in per urban of Arusha City at Sokoni 1 ward ,it shows that the training  of women project on poultry husbandry has made a great impact to both the Engosengiu women group as it has led to the raise of their families income. The community itself are proud of coming out from darkness after several training conducted.  This project aimed at strengthening the Engosengiu women group through selected areas of capacity building (training) in order to hasten achievement of the desired benefits, which are primarily vested in increased income and food security.

# 2.3 Project description

The poultry keeping was executed by Hope Trust women group who were struggling to increase their income for family basic needs. The group analyzed and prioritized their needs and finally came up with poultry keeping project which help them meet their basic needs. The group will acquire land to start their project(for constructing  an office and poultry keeping building).

# 2.3.1 Target Community

The project will be implemented by Hope Trust group. The identification of this group was done after consultation and discussion with the key relevant stake holders including CED student in collaboration with team work and team spirit of women and ward leadership. The leadership and some of its members will be trained and guided on how go about need analysis.

# 2.3.2 Stakeholders

The stakeholders of this project will be all groups dealing with poultry in the village and NGO which deal with women empowerment in the village in collaboration with CED student. This NGO is among other including World Vision Tanzania which deals with community empowerment in Mukulat division. The other stakeholders include Lutheran church groups, Roman Catholic Church, Tumaini VICOBA and Tanzania Assemblies of God church.

The government including Arumeru council is one of stakeholder in support of group as legal entity and support through expertise for capacity building. Community development officers, Ward executive officer were frequently consulted in implementation of project.

Table 2.1: Role of Different Stakeholders in the Project

| Name of the stakeholder | Roles in the project | Their Expectation |
| --- | --- | --- |
| HOPE TRUST WOMEN GROUP | -Beneficiary of the project –They will offer time, ideas, physical and manpower | -They expect the project to become viable, liable, and accessible so as to benefit them and become sustainable too. |
| WARD EXECUTIVE OFFICER | -Security and administrative support | -The project to be reachable and successfully achieved by the beneficiaries in a peacefully way |
| COMMUNITY DEVELOPMENT OFFICER | -To support and facilitate in building the capacity of group on poultry keeping | -She/he expect Hope Trust women group to be well capacitated of knowledge on how to run their project in order to be successfully and sustainable |
| CED STUDENT | -To coordinate and write the project by combining community ideas through Project participatory, planning, monitoring and evaluation for their benefit . | -She expect the project to be achievable to the beneficiaries and sustainable. |

# 2.3.3 Project Goals in CED Terms

According to CED philosophy the primary beneficiary are women community, the

project goal is to increase the income level to the low income earners Hope Trust women group through poultry keeping  project.

# Project Objectives

2.3.4.1 General Objective

General objective of the project is to increase the income level to low income earners Hope Trust women group through poultry keeping.

2.2.3.2 Specific Objectives

Project intends to;

- Training of 5 women  on poultry keeping by May 2017

- Acquiring land for office building and production of poultry keeping by June 2017

- Undertake production of the first 50 batch of live chicken by July to August 2017

- To sale 50 live chicken by  September  to October 2017

# 2.4 Host Organisation Profile

The host organisation is Tumaini VICOBA which is found at Ekenywa Village. Tumaini VICOBA has members from different parts of  Ekenywa village and  it includes of women  only. Tumaini VICOBA always meets once a week in which each member gives out their weekly contribution shares of five thousands Tanzanian shillings. The purpose of Tumaini VICOBA is to improve the incomes of their members through building of their capacity as well as to provide loan to its members.

# 2.4.1 Vision

Community members lives in friendly environment in which poverty  have been eliminated in the community and sustainable development being attained  socially and economically.

# 2.4.2 Mission

To improve social-economic status of marginalized rural communities with emphasis to women through innovations and inversions with sustainable result.

# 2.4.3 Activities

Activities are collecting savings from members, issuing loans to members and becoming market to members’ produced products. Training for entrepreneurship and access to Finance.

# 2.4.4 Tumaini VICOBA Structure Chart

# Figure 2.1: Tumaini VICOBA Structure Chart

# 2.3.5 SWOT Analysis of the Community Based Organization

| Strength | Weakness | Opportunities | Threats |
| --- | --- | --- | --- |
| Committed and strong leadership | Insufficient funds for the project | Availability of market for project products | Diseases |
| Group has an access to Financial Institutions | Inadequate knowledge in Poultry keeping | Availability of extension workers within the ward | Theft due to lack of watchman |
| Strong unity among the members | Distance between the Poultry building and the office | Members volunteering for the project |  |

Source: researcher, 2017

# 2.4.6 Role of CBO in the Project

- To support in fund raising for the project

- To assist in the training of Poultry keeping project

- To support in identification of trainees

- To support in lobbing and advocacy of Poultry keeping project

# 2.3.7 The Role of CED Student in the Project

The CED Student in the Project has got important roles of making sure that the plans are implemented as they are planned so as the group members can achieve the goal. The roles are listed as follows:

- To support   in the identification of potential trainees of poultry keeping project.

- To assist in the training of 5 women who are the trainees in Poultry keeping.

- To assist Hope Trust women group members in finding of land for buildings an Office for Poultry keeping.

- To support Hope Trust women group members in purchase of poultry equipments, feeds and chickens.

- To advise the group members on how to search for market of their product.

- To support and facilitate in building the capacity of group leaders for monitoring and evaluating of the project.

# CHAPTER THREE

# 3.0 LITERATURE REVIEW

# 3.1 Introduction

This chapter focuses on increased household income to women with very low income through commercial poultry keeping project at Ekenywa village .Literature review was conducted through passing to various researchers conducted study on poultry keeping for the aim of improving income at community. The researcher will review journals; reports to identify gaps need to be addressed as well as learning parts. The chapter is divided into three main sections; theoretical literature where concepts, principles and theories related to poultry commercial keeping for income increase. The other part of this chapter gives empirical evidence of poultry keeping and its significant in increased household income in the community. The study also shows challenges for poultry keeping for commercial purpose. Thirdly are policies in Tanzania which address intentional efforts by government in ensuring implementation and support of poultry sector.

# 3.2 Theoretical Literature

# 3.2.1 Definitions of Key Concepts

### 3.2.1.1 Poultry Farming Production As Source Of Household Income Raising

Guèye, (2002) clearly explain that, poultry farming production is very important as it provide additional incorne to the generally resource-poor small farmers, especially women. Although requiring low levels of inputs, Poultry farming contributes significantly to food security, poverty alleviation and ecologically sound management of natural resources. According to Guèye (2000d) Family Poultry production is also a source of employment for underprivileged groups in many local communities.

Gu`eye,(1998) describe  the importance of native breeds of poultry birds for rural economy in developing and underdeveloped countries mostly in Asia and Africa is very high. They are part of balanced farming system that have vital roles in the rural households as a source of high quality animal protein and emergency cash income and play a significant role in the socio-cultural life of the rural community and woman empowerment. According to  Gu`eye,(1998) Chicken assisted women in many cases as they are the owners of family poultry as more than 75% of rural families in Asia and Africa keep more than one species of poultry in which women are the owners of them in 70%.

Guèye (2000c) describe that the skills of small farmers in all aspects of poultry management must be improved through training and education. Poultry farmers should also be provided with credits or loans, taking into account the economic circumstances and socio-cultural context in which the beneficiaries live. In addition, the marketing system must be improved, for the benefit of both Family Poultry production keepers and consumers

However, constraints facing Family poultry production systems in

3.2.1.2   Poultry Farming Management system

Riise (2004) describe that nearly all rural and peri-urban families keep a small flock of poultry. These are mostly owned by women and managed by women and children. Profits are usually low and products are used for home consumption, as gifts and for religious purposes. Also .Riise explain that village-based poultry production systems may be divided into at least three different categories which traditional free-range, improved free-range and small-scale confined rearing systems (semi-scavenging system).The small-scale confined systems, also called small scale industrial poultry production. According to   Guèye (2000c) there is no doubt that adoption of one or more management sub-system(s) is largely determined by the availability of resources and inputs like housing, cages, feed, drugs and time.

3.2.1.3 Indigenous/Native Breeds of Chickens

Chickens are the most popular poultry worldwide irrespective of culture and region. Dessie et al. (2012) reviewed the current state of knowledge on indigenous chicken genetic resources of the topics as domestication, distribution, and documentation of information on the genetic resources.

Dessie et al. (2012) documented the phenotypic characteristics of native chickens in tropics which include Matrouh, Mandarah, and Fayoumi breeds of Egypt and Tilili, Chefe, and Tepi of Ethiopia and southern, northern, and central ecotypes of Bolivia. They also reported the Ac and H’Mong of Vietnam, Kampung breed of Indonesia and Malaysia, Ching’wekwe, Kuchi, and Mbeya of Tanzania, local birds of Nigeria, Naked neck of Cameron, Koekoeak, Leowavenda,Ovambo, and Naked neck of South Africa. They also provided a summarization about Aseel, Kadaknath, Naked neck, and Sikkimese frizzle of India. The literature indicates that native fowl are more concentrated mostly in developing and underdeveloped countries than the developed countries.

3.2.1.4 Housing for Poultry Production Development

According to .Riise (2004) housing is essential to protect poultry against predators, thieves, rough weather (rain, sun,very cold winds, dropping night temperatures) and to provide shelter for egg laying and broody hens. A suitable or comfortable poultry house is also important for efficient production and convenience of the poultry farmer. Depending on availability of materials, weather, and tradition  you will find different types of poultry houses and shelters in tropical regions. Choice of chicken house should be built upon a rationale involving an estimate of the costs, the durability, and immediate gain of using a house for the poultry .Riise(2004).

3.2.1.5 Diseases and Healthy Management of Poultry

Disease are the mostly high striking problems  in poultry production as they lead up to their mortality  rate  from 80-90%  if none of the reaction will not be taken in a seriously way. According to  Riise(2004) explain that it is very important for the farmer to learn how to detect an unhealthy or sick  chicken/bird, so he/she can initiate the right action .Healthy chicken/birds may be able to fight against the diseases themselves whereas unhealthy chicken/ birds will have difficulties in fighting diseases. It is important to isolate unhealthy or sick chicken /birds from the healthy flock in order to ensure a minimum of loss.

### If you find an unhealthy or sick Chicken/bird, isolate the it and call for the veterinarian or health assistant for disease identification and further advice. If the chicken/bird dies, burn it or bury it. You should remove dead birds, so that the germs are not left on the ground to be passed on to the other birds  Risise, (2004).

3.2.1.6 Profitability and Marketing of Poultry Products

Before starting any production, it is important to know the market situation, the investment costs, running costs, and expected revenue for the different products.

According to Riise (2004) it is advisable to know the local situation very well through detailed market studies and cost and benefit analysis, before deciding on the type of production to introduce. At village level, it will often be advisable to start with a production based on local breeds, local feeds, and local demands, before entering into a more sophisticated production system with improved breeds and a need for a more stable market outlet. In general the economic outcome as well as the need for investments and the risk involved in the production, will be very different for improved free-range.systems (relatively low risk) and small-scale confined systems (higher risk).Riise (2014).

# 3.3 Empirical Literature

The Empirical literature review was done for the seek going process of poultry production in deep on the studies conducted elsewhere. The review helped researcher to identify gaps on their study of poultry keeping.

3.3.1 The Scale of Poultry Production Industry in Tanzania

According to Kay Mary (2016) small-scale poultry production provides income and food for the family. In developing countries including Tanzania women and children often raise chickens and other poultry. Women in rural households raise poultry primarily to sell the eggs and an occasional chicken. The income from poultry is often one of the few significant sources of income for women. Maintaining a poultry flock is also an important food-security strategy for people living in stressed environments and changing climatic conditions. When livestock are in decline in drought years, poultry production can be particularly important for household income and as a source of nutrition. However, poor animal health and husbandry practices limit animal production, and related economic growth and public health benefits throughout Africa.

The poultry industry seems to have a bright future in Tanzania, as the Government in collaboration with stakeholders is supporting and strengthening technical support services and promoting use of appropriate technologies in poultry production. In addition they support the establishment of quality breeding farms and hatchery facilities; poultry producers and trade associations are promoted and encouraged. The government is enforcing the law for the production of quality poultry products. Breeding flock and Hatcheries regulation and registration for hatcheries have been established, whereas hatcheries meet set standards, have been registered and are producing better quality DOC’s. In addition, the country has feed inspectors and feed analysts for law enforcement.

# 3.3.2 The Traditional Treatment and Careering of Poultry for Productive Manner

There are husbandry practices, cheap vaccines and other disease prevention and control measures that can reduce mortality and increase poultry production in homestead or small scale flocks. Poor rural communities that need disease prevention and animal husbandry information lack access to extension services. Generally, extension programs do not have adequate capacity to disseminate technical information or to deliver training programs to remote rural communities. However, primary schools exist in most rural communities. The schools represent potential sites for extension education in village communities for health & livelihood skills such as poultry production.

Women, with the assistance of children, are the primary caretakers of poultry in villages. ( Kay Mary 2016) Children feed the chickens, collect the eggs, and put the chickens in the coop at night. The school is a good site for training. The children can learn in a demonstration coop built at or near the school. The children can be encouraged to apply and share what they learned with their family at home.

The single most important constraint of local chicken rearing is their high mortality as result of poor health control, poor housing, and inadequate feeding. Most chicken diseases can be controlled by vaccination (e.g. Newcastle disease) or timely administration of drugs. While vaccines and drugs are sufficiently available in the country (see below), the bottleneck is their distribution to the rural areas and professional administration in good time. Especially the survival rate of chickens is rather low, only 10% to 20%, however also 20% to 30% of the mature chickens do not survive and sometimes the entire flock is wiped out when disease strikes. Poor housing makes chicken and more so the small chickens vulnerable to predators on the ground and from the air.

Traditionally SLC roam freely to find their own food; studies have shown that this practice results in many cases in poorly nourished chickens, slow weight increase, and may even cause death, Particularly mineral deficiencies, the third highest rated cause of death, is the result of poor feeding. Although local breeds are well adapted to the harsh living conditions of SLC, in many villages not the most optimal chicken breed is being used. Having better suited breeds the survival rate, the weight gains, the number of eggs, and the fertility of the chicken stock can be improved. Because of the high risks associated with chicken rearing, most rural people do not regard chicken rearing as a serious business. Consequently chicken keepers do not invest in better chicken housing, improved breeds, vaccinations or drugs, and chicken feeds. This vicious cycle can be illustrated in the causal loop diagram below Ahlers et al., (2012) .

# 3.3.2 Poultry production in other African countries

In Malawi most poultry (85%) were housed in human dwelling units search was the main source of feed. The majority (77.6%) of farmers supplemented their chickens erratically with energy-rich feeds, mostly maize bran. Most supplementation took place during the cold-dry season. It was also noted that women were playing an important role in the daily management of backyard poultry (FAO 2004). Rural poultry is also an important element in diversifying agricultural production and increasing household food security. The village chickens provide readily harvestable animal protein to rural households, and in some parts of Africa are raised to meet the obligation of hospitality to honoured guests Chale and Carloni (2013) reviewed the attributes of chicken meat and eggs in rural areas. Egg dishes and chicken meat cook faster than pulses and red meat, and therefore use less fuel wood.

In the same review, citing poultry projects in Africa, there is a need to authors highlighted the importance of chickens as a diversification component in rural farming systems, particularly for women. Income accrued from the sale of eggs in a women's project in the Sudan was used to purchase household consumable goods, thus increasing household welfare. Gittinger, Leslie and Hoisington (1987), in a survey on food production by women and its impact on food security, found that rural households that had cropping as their only source of food production were more food insecure than households that had livestock, including poultry. Indicated that diversification including poultry would be beneficial to women.

Many African countries are currently unable to produce large feed surpluses over and above the needs of the human population. Therefore, the intensive poultry industry has become a liability rather than an asset. Smallholder rural poultry production, if properly developed, appears to hold prospects for sustainable poultry production. What is needed is a coordinated programme which addresses, at the same time, the problems of breeding, feeding, housing and disease control and specifically directed the small farmer. The programme should develop projects geared towards understanding rural poultry production systems and their weaknesses; developing and testing new methods which will not only overcome these weaknesses but will also be affordable and sustainable.(FAO 2004).

In Mozambique extensive small-scale, rural, family-based poultry systems continue to play a crucial role in sustaining livelihoods in developing countries, supplying poultry products in rural but also peri- urban and urban areas, and providing important support to women farmers. Small-scale poultry production will continue to offer opportunities for income generation and quality human nutrition as long as there is rural poverty (FAO 2013). According to ILRI (2010) Ethiopia women owned and managed chicken and controlled the cash income generated from the sale of chicken and eggs. Gueye (1998) also reported that more than 70% of village chicken owners in rural sub-Saharan Africa are women

# 3.4 Policy Review

In Tanzania livestock sector has been realized as paramount in development and reduce inequality and increased income of Tanzania. It is therefore because of this reason that Tanzania has been going through amendment of livestock policy to fit in development goals. Tanzania has been going amendment of livestock policy although efforts in making indigenous poultry meaning full has not brought advantages to rural women despite that Tanzania has 30millions.(Tanzania National Livestock policy 2006).

The policy states that the Tanzania government will sensitize encourage and promote establishment of poultry producers and traders associations. This has not real gone to grass root where rural women are confronted with poverty. Women keeping poultry are not organized enough for easy accessibility of extension services. Deliberate efforts are needed from government and all development partners to make poultry business in rural area meaningful. The objective of the policy according to National Livestock policy 2006 aims at both quantity and quality of poultry in Tanzania. It is yet to attain this especially in rural areas where poultry are kept traditionally with either minimal or zero returns. The rural women at village do not know well challenges facing poultry such as disease and quality management.

Tanzania promotes private sectors investment to attain sustainable development goals. The issue is that there are no deliberate strategies and plan to ensure poultry keepers are organized and support well. There is a need to have deliberate efforts to promote poultry sector in Tanzania for economic transformation and reduction of poverty for rural women. In Mozambique poultry sector is well performing due to deliberately efforts placed by government. The government of Mozambique, chicken processing and conservation were established (National Agriculture Investment Plan 2014–2018). It’s now the right time for Tanzania government to buy the idea and ensure both quality and quantity chickens are kept in both urban and rural areas. There is a need to establish processing and packaging unit which will create higher demand and price of chickens. The government should also encourage nongovernmental organizations dealing with livestock keeping in Tanzania. There is a need for government to do VAT exemption for poultry foods and drugs in order to reduce higher cost of meeting drugs and food. The government should encourage industries dealing with poultry processing in the country.

“The livestock industry has a clear development vision, based on the Tanzanian development Vision 2025 that states; By year 2025, there should be a livestock sector, which to a large extent shall be commercially run, modern and sustainable, using improved and highly productive livestock to ensure food security, improved income for the household and the nation while conserving the environment’’ (Tanzanian livestock policy, chapter 2.1).It’s good for the government through livestock department to put these in practice.

Tanzania has several associations supporting livestock production such as Tanzania Chamber of Commerce, Industry and Agriculture (TCCIA), Tanzania Chamber of Agricultural Council and Livestock (TCAL) and the Confederation of Tanzania Industries (CTI).Yes  policies are well written and analyzed but when you go to the ground where majority marginalized groups are found. In order to recognize transformation development the government must establish village fields learning classes where graduates from our institutions use as practical center. If the government establishes rural field practical centers, the challenge of extension officers will have been solved.

# 3.5 Literature Review Summary

The study review clearly showed several benefits and challenges of poultry keeping in different contexts. The poultry keeping in Tanzania and rest of Africa and the world contributes to poverty reduction to marginalized groups and has been a performing commercial sector. It’s obvious that if livestock expertise are well used by government and those dealing with poultry keeping GDP of particular country must improve and hence attainment of sustainable development goals by 2030.

Tanzania government made several policies to support livestock keeping and ways to reduce challenges facing poultry keepers. The gaps from good policies made and amended, is execution and enforcement of the policies. Other countries including Mozambique has gone beyond and remove of VAT from poultry feeds and drugs. Those countries which made deliberate efforts to support poultry sector are well performing poultry products exports.

Currently chicken keeping in Tanzania has gained momentum due to sector contribution in household income and transformation development. The increased poultry business through investors in poultry sectors has made possible for small scale farmers to keep chickens. The established livestock and agricultural institutes has added value to sector. It is therefore with evidences of literature review that Hope Trust project will be sustainable and contribute to poverty reduction.

# CHAPTER FOUR

# 4.0 PROJECT IMPLEMENTATION

# 4.1 Introduction

This chapter gives a summary of poultry keeping by Hope Trust group in Ekenywa village. It briefly analyzes on the procedures which were taken through project identification and the project implementation results. The project passed through chapters on Community Needs Assessments, Problem identification, Literature review, Project implementation, Participatory Monitoring, Evaluation and sustainability of the project.

The report covers project implementation in relation to previous chapters which include project identification, problem identification and literature review on identified project. The identified project therefore was implemented in chapter four through participatory manner. On the other hand, this chapter will carry a wrapping up which enables researchers, policy makers, decision makers, and other developments partners and stakeholders who need to make poultry sector meaningful  to obtain information for further improvement.

# 4.2 Project Outputs

- Training of 5 women on poultry keeping by May 2017

- Acquiring land for office building and production of poultry keeping by   June 2017

- To purchase the first batch of 50 chicken by July  to August 2017

- To sale 50 live chickens by September  to October 2017.

# Table 4.1:   Project Objective and Output

| Objectives | Outputs | Activities |
| --- | --- | --- |
| 1.Training of 5 women on poultry keeping by May 2017 | 1.1 5 women were trained on Poultry keeping | Identification of trainees |
|  |  | Conducting one day training workshop at Ekenywa village on poultry keeping |
| 2. Acquiring Land for office building and poultry keeping by June 2017 | 2.1 Part of land for office building and poultry keeping production in place | 2.1.1Meetings with members of the group to discuss where and how to get land |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building |
|  | 2.2. To fundraise for finding funds for buying materials for repair of the building | 2.2.1 Collecting of materials for repairing an office and poultry keeping building |
|  |  | 2.2.2 The masons start to repair the building for office and poultry keeping which given by a member of the group |
| 3. Undertake production of the first batch of chickens by July to August 2017. | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify a good quality of chickens |
|  |  | 3.1.2 To Purchase chickens |
|  | 3.2. Purchase 3 bags of Chickens’ feeds were bought | 3.2.1 To identity the Feeds with required nutrients for the chickens |
|  |  | 3.2.2 To purchase 3 bags of chicken feeds |
|  | 3.3 Poultry keeping required feeding equipments were purchased | 3.3.1 Purchasing of the suitable identified equipments |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 Identifying the veterinary expert for vaccination |
|  |  | 3.4.2 To do vaccination exercise |
| 4. To sale 50 live chicken on September to October 2017 | 4.1 Buyer identified | 4.1.1To do lobbing and advocacy for accessible and reliable market |
|  |  | 4.1.2 To transport the live chicken |

Source: researcher, 2017

The project which has been identified so that to be implemented had focuses at different expected outputs as well as five objectives which are training of five women on poultry keeping by May 2017, Acquiring an office and a building for poultry keeping by June 2017, Undertaking production of the first 50 batch of chickens by August 2017, to sale 50 live chicken by September to October 2017 .Hence the objectives leads the project to have outputs and these outputs are explained as follows;

Output one was the training of five women on poultry keeping. Women were trained in order to be capable with knowledge on the management of the project so as to make it sustainable. The five women trained were the ones found and identified by the CED student. These will be representatives and trainers’ of others during the study also to be frontline in project formation and implementation for sustainability.  One day workshop on poultry keeping was conducted in order for the 5 women to have knowledge on the best selection of the quality chicken, purchase of the suitable equipments for the project, vaccination of the chicken, identifying the quality feeds for the chickens, feeding and knowing the maturity of the chicken.

The other output was to find and purchase land for an office and building of poultry production house. This output was achieved where by one of the member within the group gave part of her land which contained a building enough for making an office and for constructing poultry keeping building. All women group members agreed with the idea of being given a piece of land temporarily until next year. The group is planning to collect fund to buy their own land by next year.

The masons did a repair to the office building and build a temporary poultry keeping building. The project managed to purchase one batch of 50 chickens with 3 bags of feeds, purchase of suitable equipments for poultry feeding. Purchase of the chickens went hand on hand with vaccination in order for the chickens not to be affected by diseases. On the progress of project implementation and identification of reliable markets for the chickens was done. Only the transportation and sales of the chicken had remained up to October.

# 4.3 Project Planning

This part is the procedural step in project management in which required documentation is created to ensure successful project completion. Documentation includes all actions required to define, prepare, integrate and coordinate additional plans. The project plan clearly defines how the project is executed, monitored, controlled and closed. Project planning requires an in-depth analysis and structuring of the setting project goals, identifying project deliverables, creating project schedules and creating supporting plans. Schedules such as Gantt Charts are used to plan and subsequently report the progress within the project environment. The project goal is defined and the appropriate methods or activities are planned in order to implement the project. The necessary activities and duration are planned into a work breakdown structure. Project planning also organises different areas of the project for instance project plans, workloads and the management of teams and individuals, funding or budgeting and materials. Usually project planning is being done before the project is actually started.

# 4.3.1 Project Implementation Plan

This is a technical document that provides a high level view of the overall structure of the project. It’s the implementation of the plan in order to achieve project overall goal, objectives and output. It describes how the activities will be carried out in order to achieve outputs includes time to be spent, resources to be used and responsible person. In order to achieve the overall goal of the Poultry keeping project, there are some activities to be carried and these activities are the identification of the community, conducting a one day workshop on poultry keeping, Conducting a meeting with members of the women group to discuss where to get the land for office building and for poultry keeping production, identification and purchase of chickens, purchase of equipments and chickens’ feeds and marketing and selling of the poultry after maturity. Resources needed are community members and poultry expert for human resources and funds as financial resource and some stationery.

For the project to be executed, time frame was planned for each activity to be carried out. For the month of May 2017, the month was planned for the Community Needs Assessment followed by identification of the Host organization, identification of Trainees and Project identification as well as for the preparation of material for workshop and conducting workshop as well as the community to identify the potential project. For the month of June it was planned for search of purchasing of land for an Office and project building. For the month of July, planned activities were to identify and purchase of suitable equipments for the project itself to be in place and its management.

Sales of project products are expected to be done in followed by project evaluation. In September to October was planned for fumigation/cleanliness for preparation of the second phase if evaluation will give a positive impact of the project to community. December will be the month for the start of second phase if first phase will approve successfully.

# Table 4.2: Project Implementation Plan

| Objective | Output | Activity |  | Resource needed | Responsible person |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |
| 1. Training of 5 women on poultry keeping by May 2017 | 1.1 : 5 women were trained on Poultry keeping | 1.1.1.Identification of trainees |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time Stationery | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 1.1.2Conducting one day workshop on poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time Stationery | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
| 2. Acquiring an office and a building for poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time Stationery | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time Stationery | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  | 2.2.Fundraise for finding funds for payment of the mason cost and funds for materials collection | 2.2.1 To fundraise for funds of mason’s costs and collection of materials |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time Stationery | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 2.2.2To collect the materials and the masons start to repair the building for office and poultry keeping which given by a member of the group |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
| 3. Undertake production of the first batch of chickens by July August 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 3.1.2 Purchase of chickens |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chickens |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 3.2.2 To purchase chicken feeds |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | Livestock Officer, CBO leaders& other Stake holders |
|  | 3.3 Poultry suitable feeds equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 3.3.2 To purchase the equipments |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 3.4.2 Doing vaccination activity |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
| 4. To sale 50 live chicken by September to October 2017 | 4.1 buyer identified | 4.1.1 Buyer identified |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time | CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders CED Student, Comm. Dev. Officer, Livestock Officer, CBO leaders& other Stake holders |
|  |  | 4.1.2 Transport of live chicken |  |  |  |  |  |  |  |  |  |  |  |  | Human, Funds Transport, Time |  |

# Table 4.3: Project Logical Framework

| Hierarchy of Objectives | Objectively Verifiable Indicators (OVIs) | Means of verification (MOV) | Assumptions |
| --- | --- | --- | --- |
| Goal (Impact): Reducing Income Poverty by 2017 | Income increased and the living standard of the community improved | Evaluation report, monitoring report, annual reports and monthly report | The willingness of community members to disclose their economic status. |
| Objective 1: Training 5 womens on poultry keeping by May 2017 |
| Output 1.1: 5 womens were trained on Poultry keeping | 5 womens were trained on Poultry keeping | Training report | Womens become aware about poultry project |
| Activities |
| 1.1.1.Identification of members to be trained | 5 members identified and trained | Participants list of members trained | Women gained knowledge and awareness on poultry keeping |
| 1.1.2. To conduct one day training workshop on poultry keeping | 5 members of the group attended the training workshop | Attendance list | Women become aware about poultry project |
| Objective 2: Acquiring land for office and a building for poultry keeping by June 2017 |
| Output 2.1 Part of land for office building and poultry keeping production in place | Part of land was found | Minutes of the meeting of the groups | Women can access office building and poultry keeping building |
| Activities |
| 2.1.1 Meetings with members of the group to discuss where and how to get land | Meeting conducted | Minutes of the meeting | Materials bought repair process start |
| 2.1.2. To fundraise for finding funds for buying materials for repair of the building | Funds raised | Funds allocated | Occupying an Office and poultry keeping building |
| Output 2.2: Fundraise for finding funds for payment of the mason cost and funds for materials collection | Amount allocated | Amount allocated | The mason paid, Women occupy the office and poultry occupying the building |
| Activities. |
| 2.2.1. To fundraise for funds of mason’s costs and collection of materials | Funds raised | Funds allocated | Women occupy the office and poultry placed to their building |
| 2.2.2. The materials collected and the masons start to repair the building for office and poultry keeping which given by a member of the group | Materials collected and office as well as poultry keeping production building repaired | Office and poultry building available | Women occupy the office and poultry placed to their building |
| Objective 3: Undertake production of the first of chickens by July 2017 |
| Output 3.1: One batch of 50 chickens were bought | Receipt for payments | Chickens in the poultry building centre | Chickens in the poultry building centre |
| Activities |  |
| 3.1.1.To identify good quality chickens | Quality of Chickens bought | Physical appearance of the bought chickens | Physical appearance of the chickens |
| 3.1.2. To purchase chickens | Receipt showing purchase payments done | Receipts and chickens in chickens building | Receipt of payment and presence of the chickens in poultry keeping building/centre |
| Output 3.2. Three bags of Chickens’ Feeds were bought | Feeds in the project area | Presence of feeds to the project area | Receipt for payment and presence of feeds at project area. |
| Activities |  |
| 3.2.1. To identify the Feeds with required nutrients for the chickens | Labels showing the type of feeds and their contents | Labels showing the type of feeds and their contents | Physical healthy of the chickens |
| 3.2.2. To purchase three bags of Chickens’ Feeds | Receipt for payments and quantity of feeds bought | Receipt for payments and feeds available | Availability of chicken feeds |
| Output 3.3. Poultry keeping required feeding equipments were purchased | Equipments in place | Receipt for payments and availability of equipments | Equipments in place |
| Activities |  |
| 3.3.1. To identify the needed suitable equipments | Equipments were identified | Quality of equipments bought | Labels showing quality of equipments |
| 3.3.2. To purchase the equipments | Receipt for payments and quantity of equipments bought in place | Quality of equipments bought | Equipments in place |
| Output 3.4. One vaccination done to 50 chickens | Number of chickens vaccinated | Progressive report | Visit done by Veterinary officer |
| Activities |  |
| 3.4.1. To identity the veterinary expert for vaccination | Veterinary officer was identified | Progressive report | Poultry were vaccinated |
| 3.4.2. Doing vaccination activity | Number of chickens vaccinated | Physical health of chickens | Payment receipt for vaccination |
| Objective 4. To sale 50 live chicken by August to September 2017 |
| Output 4.1. Buyers identified | Number of poultry sold | Increase of income through sales | Sales report |
| Activities |  |
| 4.1.1. To identify buyers | Sensitization for poultry | List of sensitized people | Readiness of community members to support the project |
| 4.1.2 Transport of live chicken | Chicken loaded in a truck | Truck with loaded live chicken | Chicken are ready for sale |

# 4.3.2 Inputs

At the project implementation point, some inputs were used in order to implement the poultry keeping project. The inputs that were used during implementation of the project were human resources inputs, materials inputs and financial inputs. Human resources inputs were the use of human beings as project manpower and also as project management team. For the material resource, some materials were used for the execution of the project and also financial resources were used as input for the project. Financial resource used was the use of funds/money for the payment of  the materials for repairing of  an Office and poultry keeping building, purchase for poultry keeping equipments, payment for  masons, purchase of chickens, purchase of Feeds, purchasing vaccination medicines and other payments done for the execution of the project.

# Table 4.4: Project Inputs

| Objectives | Outputs | Activities | Required Inputs | Price/Unit |
| --- | --- | --- | --- | --- |
| 1. Training of 5 womens on poultry keeping by May 2017 | 1.1 : 5 womens were trained on Poultry keeping | Identification of trainees | Nill | * |
|  |  | Conducting one day training workshop on poultry keeping | Meeting venue | 80,000 |
|  |  |  | Facilitator’s Fee | 200 |
|  |  |  | 5 pcs of pens | 1,000 |
|  |  |  | 5 pcs of notebooks | 10,000 |
|  |  |  | 1 pc of flip chart | 6,000 |
|  |  |  | 1 pc of marker Pen | 1,000 |
| 2. Acquiring Land for office building and poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land | Soft drinks | 20,000 |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building | Soft drinks | 40,000 |
|  |  |  | Fund Venue cost | 1,000 |
|  | 2.2. To fundraise for finding funds for Paying the masons and to collect materials for repair | 2.2.1 To collect of materials for repairing an office and poultry keeping building | Truck and labour cost Fund , | 20,000 |
|  |  | 2.2.2 The masons start to repair the building for office and poultry keeping which given by a member of the group | Funds | 20,000 |
| 3.Undertake production of chickens by July to August 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens | Poultry expert | 1300 |
|  |  | 3.1.2 Purchase of chickens | Funds | 20,000 |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with required nutrients for the chickens | Poultry Expert | 50,000 |
|  |  | 3.2.2 To purchase chicken feeds | Funds | 20,000 |
|  | 3.3 Poultry keeping required feeding equipments were purchased | 3.3.1 To identify the needed suitable equipments | Poultry Expert |  |
|  |  | 3.3.2 To purchase the equipments | Funds | 15,000 |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination | Veterinary Expert | 20,000 |
|  |  | 3.4.2 Doing vaccination activity | Veterinary Expert | 30,000 |
|  |  |  | Funds | 10,000 |
| 4.To sale 50 live chicken by September to October 2017 | 4.1 Buyers identified | 4.1.1 Lobbing and Advocacy for Marketing | Funds for transportation | 10,000 |
|  |  | 4.1.2 Transport of live chicken | Funds | 10,000 |
| TOTAL COST |  | 997,000/= |

# 4.3.3 Staffing Pattern

Poultry keeping project’s execution will be carried by group members themselves with the support from external people who are poultry experts. Group members divided duties and responsibilities to each member in order to have equal participation in the execution of the project. Some were given activities of supervision of the project, some were given the task of cleaning and fumigating the building in order for the poultry to be free from pests, insects, parasites that would affect the poultry’s health. Others were given a role of feeding the chickens and others were given the sales and marketing role to play. Each group member was given a task to perform in order to enhance participatory. Supervision people were also given the task of keeping documents and reports for the project that would be used for monitoring and evaluation purposes.

# 4.3.4 Project Budget

In order for any project to be implemented well, there should be a budget for the project. Project implementation Budget was planned by the Hope trust group members and they raised fund for the project. The budget is well planned and will enable planned activities to be carried out in order for the project to achieve its goal of increasing household incomes to the low income earners who are Hope trust women group members. Inputs for each planned activity were allocated with the amount of fund that would be spent to fulfil the planned activity. Below is the Table showing project implementation budget with the allocated amount of fund.

# Table 4.5: Project Budget

| Objectives | Outputs | Activities | Resource needed | Quantity | Price/Unit | Total Tsh |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Training of 5 womens on poultry keeping by May 2017 | 1.1 : 5 womens were trained on Poultry keeping | 1.1.1.Identification of trainees | * | * | * | * |
|  |  | 1.1.2Conducting one day workshop on poultry keeping | Facilitator( verterinary) | 1 | 80,000 | 80,000 |
|  |  |  | Stationeries | Pens 7 | 200 | 1,400 |
|  |  |  |  | Notebook 7 | 1,000 | 7,000 |
|  |  |  |  | Flip Chart 1 | 10,000 | 10,000 |
|  |  |  |  | Marker pens 1 box | 6,000 | 6,000 |
| 2. Acquiring Land for office building and poultry keeping by June 2017 | 2.1 Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land | Soft drinks | 40 | 1,000 | 40,000 |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building | The community, Soft drinks | 1 | 20,000 | 20,000 |
|  |  |  | Fund | Months 12 | 40,000 | 480,000 |
|  | 2.2. To fundraise for finding funds for paying of the mason and collection of the materials for repair | 2.2.1To collect materials for repair of the building | Fund | 30 | 1,000 | 30,000 |
|  |  | 2.2. 2 The masons start to repair the building for office and poultry keeping which given by a member of the group | Community and masons | 1 | 20,000 | 20,000 |
| 3. Undertake production of 50 first batch of chickens by July to August 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens | Poultry expert | 1 | 20,000 | 20,000 |
|  |  | 3.1.2 Purchase of chickens | Fund | 100 | 1300 | 130,000 |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with required nutrients for the chickens | Poultry expert | 1 | 20,000 | 20,000 |
|  |  | 3.2.2 To purchase chicken feeds | Fund | 3 Bags | 50,000 | 150,000 |
|  | 3.3. Poultry keeping required feeding equipments were purchased | 3.3.1 To identify the needed suitable equipments | Poultry expert | 1 | 20,000 | 20,000 |
|  |  | 3.3.2 To purchase the equipments | Poultry brooders and heaters | 5 | 15,000 | 75,000 |
|  |  |  | Poultry feeders and troughs | 5 | 15,000 | 75,000 |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination | Veterinary | 1 | 20,000 | 20,000 |
|  |  | 3.4.2 Doing vaccination activity | Veterinary | 1 | 30,000 | 30,000 |
| 4. To sale one hundred live chicken to at least two reliable markets by September to October 2017 | 4.1 Two buyers identified | 4.1.1 To do lobbing and Advocacy for Marketing | Transport | 1 | 10,000 | 10,000 |
|  |  | 4.1.2 Transport of live chicken | Funds | 1 | 10,000 | 10,000 |
| TOTAL COST | 997,000/= |

Source: researcher, 2017

The project budget was prepared to facilitate each objective to be achieved as planned. Every objective got its outputs and activities that will be carried out so as to achieve the objective effectively. Every activity has been linked with the resources needed, quantity, price per unit and total cost in order to make the activities  to be done as planned. Objective number one was to train five women on poultry keeping by May 2017.The output for this objective is  five women were being trained and the planned activities are identifying the trainees and conducting one day  training workshop on poultry keeping. For the training of five women to take place the  resources needed are the facilitator and stationeries like pens, notebooks, flip chart, marker pens and each resource has been allocated the quantity and total costs to be incurred by the project.

Acquiring the building for an office and for poultry was planned to have two main activities which are meetings with members of the group to discuss where and how to get land and to fundraise for raising funds for buying materials for repair of the building and the resources needed are funds for buying of soft drinks for the community and payment of the masons . For the project to undertake production of the first batch of chickens, activities identified were to identify good quality chickens, identifying the feeds required for the chickens, purchase of chickens, identifying the needed suitable equipments for the project and purchasing them, identifying the veterinary expert for vaccination and doing vaccination activity. These activities will need some resources which are hiring an expert in poultry and funds that will be used for payment of the required resources.

Project will need to sale fifty live chicken by the month of  September to October 2017. Resources needed to support sales will be funds that will be used for facilitating the activity. These all activities will need some funds to facilitate them. Each objective has been planned with activities to be carried out and each activity has been budgeted for in order for the project to achieve its goal.

# 4.4   Project Implementation

This part describes the actual project implementation. It described how the project was executed step by step. Also it shows how the activities were implemented and the resources utilized in for the activities to be performed well .Activities performed are those that were planned in the project design. Project implementation requires a coordination of a wide range of activities, the overseeing the team, the management of the budget, communication and other issues associated with the project. Project implementation is the phase where visions and plans become reality. The follows table describe and explain on how poultry project implementation will be executed.

# Table 4.6: Project Implementation

| Objective | Output | Activity | Project Implementation month | Resource Needed | Responsible person |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |
| 1. Training of 5 women on poultry keeping by May 2017 | 1.1: 5 women’s were trained on Poultry keeping | 1.1.1 Identification of trainees |  |  |  |  |  |  |  |  |  |  |  |  | Meeting venue | VICOBA,CED Student |
|  |  | 1.1.2 Conducting one day training workshop on poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  |  | Facilitator,CED Student, VICOBA Members |
| 2. Acquiring an office and a building for poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land |  |  |  |  |  |  |  |  |  |  |  |  | Soft Drinks | VICOBA Members, Hope trust women group members ,CED Student, community members. |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2. To fundraise for finding funds for buying materials for repair of the building | 2.2. 1 . To collect materials for repair of the building |  |  |  |  |  |  |  |  |  |  |  |  | Soft drinks, Funds | VICOBA, Hope trust women group members ,CED Student, community members. |
|  |  | 2.2.2 The masons start to repair the building for office and build poultry keeping house which on a part of land given by a member of the group |  |  |  |  |  |  |  |  |  |  |  |  | Materials | Hope trust women members ,CED Student, mason |
| 3. Undertake production of the first batch of chicks by July to August 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1. To identify good quality chicken |  |  |  |  |  |  |  |  |  |  |  |  | Poultry expert | Hope trust women group members, CED Student |
|  |  | 3.1.2. Purchase of chicks |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Hope trust women group members, CED Student |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1. To identify the feeds with required nutrients for the chicken |  |  |  |  |  |  |  |  |  |  |  |  | Poultry expert | Hope trust women group Members, CED Student |
|  |  | 3.2.2. To purchase three bags of chicken feeds |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Hope trust women group members, CED Student |
|  | 3.3. Poultry suitable equipments for poultry keeping were purchased | 3.3.1. To identify the needed suitable equipments |  |  |  |  |  |  |  |  |  |  |  |  | Poultry expert | Hope trust women group members, CED Student |
|  |  | 3.3.2.To purchase the equipments |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Hope trust women group members, CED student |
| 4. To sale 50 live chickens by September to October 2017 | 4.1. Buyers identified | 4.1.1 Lobbing and Advocacy for Marketing |  |  |  |  |  |  |  |  |  |  |  |  | Funds for transportation | Hope trust women group members |
|  |  | 4.1.2 Transport of live chicken |  |  |  |  |  |  |  |  |  |  |  |  | Funds | Hope trust women group members |

# 4.4.1 Project Implementation Report

Project implementation was done and planned activities were carried out as planned. The following activities have been conducted and some are accomplished while others are still on progress. Project design and planning was done and identification of trainees was done. Five women were identified for training and one day  training workshop on Poultry keeping was conducted in order to have group members with a capacity that will manage the project to become sustainable. There was a need for the group to search for the funds for buying of the materials for repair of an office and poultry keeping as well as paying of the mason’s. Fund’s were raised and building for an office and for poultry keeping was done.

The follows figure will show the women training at Ekenywa Village on poultry keeping project.

# Figure 4.1: CED Student with Community Members During Training

Source: Field study May 2017

# Table  4.7:  Actual Project Implementation Summary

| Objectives | Outputs | Activities | Actual Implementation |
| --- | --- | --- | --- |
| 1. Training 5 women on poultry keeping by May 2017 | 1.1 : 5 women’s were trained on Poultry keeping | Identification of trainees | 5 women’s were identified for training |
|  |  | Conducting one day training workshop on poultry keeping | One day training workshop on Poultry keeping was conducted |
| 2. Acquiring an office and a building for poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land | Meeting done |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building | Funds were raised |
|  | 2.2. To fundraise for finding funds for paying the mason and to collect materials for repair and building of poultry house and office | 2.2.1 1To collect materials for repair of the building | Repair materials for the office and building of poultry keeping house collected |
|  |  | 2.2.2 The masons start to repair the building for office and poultry keeping which given by a member of the group | Building and repair had completed in June 2017,the masons paid and Hope Trust group members have a building in place as well as poultry are in their building too. |
| 3. Undertake production of chickens by July to August 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens | Healthy Chickens were identified in July 2017 |
|  |  | 3.1.2 Purchase of chickens | Healthy chickens were purchased in July 2017 |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with require Nutrients for the chickens | Feeds with required nutrients for the chickens were identified in July 2017 |
|  |  | 3.2.2 To purchase chicken feeds | Feeds with required nutrients for the chickens were purchased in July 2017 |
|  | 3.3 Poultry suitable feeds equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Suitable equipments to support poultry keeping were identified |
|  |  | 3.3.2 To purchase the equipments | Suitable equipments with quality that support poultry keeping were purchased in July 2017 |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination | Veterinary expert for vaccination was identified |
|  |  | 3.4.2 Doing vaccination activity | Vaccination was done in July,2017 for the chickens to become healthy |
| 4. To sale 50 live chicken by September to October 2017 | 4.1 Buyers identified | 4.1.1 Lobbing and Advocacy for Marketing | Lobbing and advocacy for marketing will be conducted in August to September 2017 |
|  |  | 4.1.2 Transport of live chicken | To be done in September 2017 |

A one day training to the women at Ekenywa village which had been facilitated by CED student in collaboration with a community development officer of Mwandet ward the above Figure 2: shows CED student during training of the women group  for poultry Project in Ekenywa village. From the support of the veterinary or poultry expert, the equipments for the poultry keeping were purchased, Feeds were purchased and healthy chickens were purchased.

Some activities were done like identifying the quality needed equipments, needed and recommended feeds with the quality nutrients and thereafter the chickens were purchased and being kept in their  repaired poultry building. Feeding of the chickens proceeded and vaccination was done to make the chickens healthy by being free from diseases attack. Supervision for feeding and records keeping went hand on hand in order for the project team to observe the maturity of the chick. Lobbying and advocacy for markets as well as registration still in progress. The follows table shows a summary of the project implementation.

# 4.3.2 Project Implementation Gantt chart

Gantt charts are tools used for analyzing and planning complex projects. They help in planning out the tasks that need to be completed, they give a basis for scheduling when these tasks will be carried out, and they assist in allocation of the resources needed to complete the project and also helps to work out the critical path for the project in terms of date of project completion. When a project is under way, Gantt charts help to monitor whether the project is on schedule.

# Table 4.8:   Project Implementation Gantt Chart

| Objective | Output | Activity | Activity Implementation Monthly |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 1. Training of 5 women on poultry keeping by May 2017 | 1.1 : 5 women’s were trained on Poultry keeping | 1.1.1 Identification of trainees |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.1.2 Conducting one day training workshop on poultry keeping |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Acquiring an office and a building for poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2. To fundraise for finding funds for buying materials for repair of the building | 2.2.1 . To collect materials for repair of the building |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.2.2 The masons start to repair the building for office and build poultry keeping house which on a part of land given by a member of the group |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Undertake production of the first batch of chickens by July to August 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.1.2 Purchase of chickens |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chickens |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.2.2 To purchase chicken feeds |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.3 Poultry suitable feeds equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.3.2 To purchase the equipments |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3.4.2 Doing vaccination activity |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. To sale 50 live chicken by August to September 2017 | 4.1 Buyers identified | 4.1.1 Lobbing and Advocacy for Marketing |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 4.1.2 Transport of live chicken |  |  |  |  |  |  |  |  |  |  |  |  |

# Figure 4.2: CED Student with the 5 Women Trained After Training

Figure 3 shows CED students with the 5 women trained on poultry project after training. The women are very happy as they are well full capacitated of knowledge on how to take off the implementation of their project so that it could be sustainable.

Figure 4.3: Group Members Beside Constructed Building for Chickens

The above figure number 4. Shows group of five women who were already trained and form Hope Trust women group in Ekenywa village. The group has already constructed a house for chickens within a part of land given by one of the group member. The group has already bought chickens for their project.

# Figure  5.4: Some of the Chickens Among the One Bought By The Group Members  Within Their Built House

# CHAPTER FIVE

# 5.0 PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

# 5.1 Introduction

This chapter illustrate on how project participatory monitoring and evaluation will be carried out for the project to become achievable and sustainable. Hence for the project to become achievable and sustainable there should be effective and efficient project monitoring and evaluation. The monitoring of the project will show if the project activities are being implemented as planned as well as the resources planned are utilized as it   was planned too. So monitoring gives a direction to the project team  so that they can determine if they are moving towards the planned direction in order to accomplish the project objective hence achievement of the project overall goal. But also Evaluation has to be done as it will assist the team to get accurate information to recognize if their project could reach its goal and be sustainable or not.

Participatory monitoring is the systematic recording and periodic analysis of information that has been chosen and recorded by stakeholders (insiders) of the project with the help of outsiders (experts).The main purpose of participatory monitoring is that it provides information during the life of the project, so that adjustments and/or modifications can be made if necessary. Also it provides an ongoing picture that will allows the community to determine whether the activities are progressing as planned and it also shows when activities are not leading to objectives, so that early adjustments can be made.

Hence participatory evaluation gives an opportunity time for both insiders (community members) and outsider (expert) so that they can reflect on the project past implementation in order to make decisions for the upcoming future implementation. Community members are supported and given confidence by experts as a way of encouraging them to take different tasks as well as responsibilities like control of planning, evaluation and analysis of the information and presenting evaluation results. But Participatory evaluation cannot be taken as a last judgement of if project activities have been successful achieved or not. So the information have to advise and encourage for the changes and adjustments on  project activities either during  its life span or for  the future phases of the  activities.

Hence this chapter explain and highlight project participatory monitoring, evaluation and sustainability of the Poultry Keeping project. So the information that has been collected and analysed for the aim of monitoring and evaluating the project to find out if it will achieve the intent goals and sustain. The Monitoring and evaluation was been undergone  for the purpose of ensuring that the activities planned for Poultry keeping project has been executed as intended,  the resources planned were better utilized and  if fully stakeholders participation made. Hope trust women group members participated in project planning as well as on how monitoring and evaluation will take place.

Hope trust women group members play a part in monitoring and evaluation for as some of them did volunteered in cleanliness of the Poultry building, making cleanness of the building as it was a participatory process they saw everything that was happening at the project site. Some of the group members participated during vaccination as it is a part of monitoring on how Poultry are vaccinated. They also monitored the medicine used for vaccination as well as the number of the poultry that were been vaccinated.

Through participating on the activity of vaccination   as well as for medicine it supported them to know how much it costs for the purchase of the medicine hence they did the evaluation of that activities. There are group members who are the supervisors and leaders of the project so by being leaders of the project was one way of them to participate in the management of their project and that become part of their monitoring and evaluation of their project. So through participation of many Hope Trust women group members in different project stages this made the expectation of the project to be sustainable.

# 5.2 Participatory Monitoring

This is the regular participation observation and recording of activities taking place in a project. Also it is the systematic way of recording and periodic analysis of information chosen and recorded by insiders with support and facilitation of outsiders. Through participatory monitoring it gives the important information during the life of the project, so that adjustments and/or modifications can be made if necessary and by doing so, it helps to measure the progress of the project. Participatory monitoring helps to keep track of activities by recording information on a daily, weekly ,monthly or seasonal basis and taking the time to stop and analyze the information monitored can provide important immediate feedback and can be used in the future for participatory evaluations. Keeping of tracks gives information for decision making.

Participatory monitoring does not only keep records but also giving a room for people to add up, discuss, integrate the information. The time to stop and analyze vary according to the nature and/or seasonality of activities. In order for community members to participate in monitoring there should be an agreement on why they are making monitoring and everyone should be informed on the progress towards planned objectives and activities. These members should be given an opportunity for trainings in order to have the ability to combine qualitative (descriptive) information with qualitative (number) information, providing a more complete analysis. By having an ability to track qualitatively and quantitatively, community members become able to track the progress towards objectives and activities.

Participatory monitoring is being done due to the reasons that it gives a room for knowing an ongoing picture that allows a community to determine whether activities are progressing as planned. Also it shows if the activities are not leading to objectives so that early adjustments can be made. Monitoring provides an early warning which identifies problems at an early stage hence solutions can be sought before the problems get out of hand. By doing monitoring, good standards are maintained. Continuous feedback throughout the life of the activities ensures that the quality of the activities is sufficient to provide good results.

Participatory monitoring shows the required resources that are required to produce a certain effect or how necessary resources can be distributed differently to get a better effect. Participatory monitoring ensures the equally representation in decision making and equally distribution of costs and benefits. In this project, community members have participated fully at each stage. On project identification, group members joined together voluntarily and participated in the stage of identification of which project will be executed that will generate income in order for the group members to benefit from incomes that will be derived from the selling of the project products.

Hope  trust women group members came from different occupations which are beads making, maize farming  and livestock keepers hence participation was done fully and they organized themselves and made an agreement on the project to be executed. They all participated in identification by using scoring ranking method of the thought projects and came up with the establishment of the poultry keeping project as they became aware that this will be viable and it is not too expensive to start and manage the project.

In project planning, each group member participated by giving his or her views concerning the project. Project planning needed their consent as it is the ones who are the owners of the project and are the ones that will have to implement the project. By implementing the project, they have to make monitoring and controlling of the project during project executions in order to control the resources to be used in order to manage the project planned budget. Implementation of the project will be done by group members. Group members have volunteered to perform some tasks in order to reduce the project management costs and also it is a part of learning to the group members. The members have volunteered to perform cleanliness, assist in vaccination activities, doing feeding of the poultry and also they volunteered in searching for the markets in order to be sure of the selling of the project products.

Hence participatory monitoring will be done in collaboration with the group members, this has been planned and it was organised by themselves. This aims to empower the group members for future project sustainability. This participatory monitoring will empower them as they will either establish new projects or increase the size of the project in order to increase the sales of their project products hence the increase of their incomes. Evaluation of the project will be done by the project evaluation expert in collaboration with the group members. Fully participation of the group members in project evaluation will empower the group members in order for them to perform evaluation of their projects for their future projects. Group members will be trained on how evaluation of the project is being done and they will learn by doing the evaluation activities during evaluation of the current project.

# 5.2.1 Monitoring Information System

This is the system that has been designed purposely in order  to collect project activities information that will support the project supervisor  for planning, monitoring and evaluation of the operations and performance of their project. For any project monitoring system to be  successful and efficient  all the information for the monitoring system should has to be designed in a  timely bound and  reliability  for the purpose  of achieving the intended information that  can show the required changes that were taking place. Also cost, range and extent of the information to be composed for monitoring should be considered by the system as well the time for proficiency when forecast or deciding on the system that should be used for monitoring. The system of monitoring of information should be both qualitative and quantitative in nature especially when planning as quantitative are  time cost  especially for the resources and qualitative are in  need  of people with capability and skills of conducting project monitoring activities. Hence one has to thing before on what category of the monitoring information system has could use during monitoring.

The system for monitoring of information should be developed in a manner that it will be suitable to be managed.  For any monitoring system always the resources are required by the management team for the purpose of supporting them to make sure that they perform it in a successful way in order to achieve the intended project goal and not damage the status among stakeholders for poor management. Information are like an engine machine that drives the monitoring system of the project to achieve its goals as lacking of the information it will be possible to track the changes that are taking place. Hence for any project to function well it should has a monitoring system  that will facilitate it to accumulate suitable information of the work they were doing in timely bases for the purpose of  decision-making, reporting and on  the learning on changes  that occurs .

Monitoring information system also gives an opportunity to manage the value of the information collected for the purpose of analysing and ensuing actions will not  be ruined by the poor value of the information existing for the project. For the poultry project its monitoring information system had been planned for the purpose of supporting the monitoring team of the project to monitor the project well. Its monitoring information system was designed by Hope trust group members in collaboration with the CED Student. The system has been designed so that it will help out the members to monitor if the activities are being implemented as intended

as well as the costs and expenditures the keeping of records .Also it assist them to monitor who collects reports and the decision makers on the reports as well as time planned, time spent and others resources that were used.

# Table  5.1:   Project Monitoring Information System

| Categories of information | What to Monitor | What Record to Keep | Who Collects Data | Who Uses Data | How to use Information | What Decisions can be made |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Work plan Activities | Time spent Activities performed Resources spent | Resources’ Utilization record | CBO team. CED Student. Hope trust group members. | CBO team CED student Hope trust group members | Ensure planned activities are performed as planned through making reference to work plan. | Reschedule of activities if needed. |
| 2. Cost and Expenditure | Resources spent Equipments purchased Time management Operating within Budget | Purchasing records Inventory Time management Payment records | CBO team. CED Student. Hope trust group members. | CBO team CED student Hope trust group members | Compliance with Financial plan agreed by group members. | Determine needs for other funding sources. Budget review |
| 3. Volunteers | Performance of group members volunteering | Performance progress report | Hope trust group members. CED Student | Hope trust group members. CED Student | Information will determine if the poultry building is of hygiene or not | Either volunteers to proceed or be removed. |
| 4.Equipments and Feeds | Quality of equipments purchased. Quality of Feeds purchased. | Feeding reports. Purchasing receipts and reports. | Hope trust group members. CED Student | Hope trust group members. CED Student | Ensuring purchased Equipments and Feeds followed quality planned. | Feeds purchased to feed the chickens or purchasing other Feeds. |
| 5.Marketing and Sales | Marketing activities done. Cost of marketing and costs associated with Sales. Number of poultry sold | Sales and Marketing reports | Hope trust group members. CED Student | Hope trust group members. CED Student | Sales report to be used to determine if the project gets profit or loss. | Reschedule marketing activities. Re-pricing if the project does not make profit |
| 6.Project sustainability | Resources’ utilization. Project sustainability | Performance progress reports | Hope trust group members. CED Student | CBO team CED student Hope trust group members | Comparing work plan and Actual in order to determine if the project is on the right track. | Reschedule activities if not on the right track. Search for other funding sources if funds are insufficient. |

# 5.2.2 Participatory Monitoring Methods used to Engage Community in the Monitoring the Project

The project used Participatory Rural Appraisal (PRA) as the participatory monitoring method.  The  method  had supported the use of the methods in a participatory manner,  it ensures that all the members of the group were  been concerned in making  decision of methods  that will be suitable, in planning and designing them as well as by gathering  of the information. By making the members of the group to participate in examining and analysing the information of the project had being a great important chance for the stakeholders and project staff to learn from the experience. The monitoring methods used were;

5.2.2.1 Documentation

This method was used in collecting daily, weekly reports for monitoring progress of the project. Reports were collected from group members, extension worker and host organization and information that were collected were documented in various offices. The information composed was taken to assist the team of the project for monitoring their poultry keeping project to bring about its intended goals reach to its sustainability.

5.1.2.2 Participant Observation

Participant observation method was used by Hope trust group and other project stakeholders to monitoring activities that were carried for the project for the purpose of monitoring of the project. Monitoring is a regular daily activity that is being performed by studying what was being made, significance of what was  in relation to the project’s  planed activities. Every member was given a space to play a part in monitoring activity for the purpose of deciding if their project is efficiently affecting towards its plans.

# 5.1.2.3 Group Interview

This method was used to gather the data for the monitoring purpose as well it gives information regarding the practice and perception of the group concerning the progress of the project. Each participant got an opportunity to speak out of their views and practice relating to the project.

# 5.3 Participatory Monitoring Plan

This refers to a comprehensive proposal for performing monitoring, it is a plan of achievement, it is a way of making choice and creating actions for participatory monitoring to go forward. Monitoring arrangement shall be produced following the development phase and earlier than the plan phase of a project or interference. This plan must comprise in sequence information on how project stakeholders will take part in monitoring .The arrangement must bring about a hypothesis on which the success of the project aim depend as well as expected relationships among activities, outputs and outcomes.

The project participants and beneficiary that play a part in the setting up of how monitoring activities will be carried out examined and made the prioritization of their developmental requirements and experts make use of the information to design projects. Also during participatory arrangement the authority in planning were specified to community constituent as well as they were engaged in making of decision on what they attend to accomplish. Every member of the group was being engaged in the plan  of each project  such collecting, measuring recording as well as in  communicate the  information  needed  so as support  everyone in need  for  making of decision. The purpose of this was to ensure the sense of ownership is among the members of the group and the community in general for their project.

For the poultry project, participatory monitoring plan was done by Hope trust group members who are project owner with the help of external experts. The members were capable to place the project objectives, project outputs, project activities, indicators, data sources, method/tools for data collection person responsible and allocated time frame for each activity to be carried out. The following table will shows a summary of the participatory monitoring plan for the Poultry keeping project. All group members of Hope trust women group take part in monitoring arrangement and everyone got a duty to carry out for monitoring of their project.

# Table  5.2: Participatory Monitoring Plan

| Objectives | Outputs | Activities | Indicators | Data Source | Method/Tools | Person Responsible | Time Frame |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Training of 5 women on poultry keeping by May 2017 | 1.1 : 5 women were trained on Poultry keeping | Identification of trainees | List of Participants | Progressive report | Meeting | Tumaini VICOBA,CED Student | May,2017 |
|  |  | Conducting one day training workshop on poultry keeping | Training report | Progressive report | Lecture, Group discussion | Facilitator, CED Student, Tumaini VICOBA Members | May,2017 |
| 2. Acquiring an office and a building for poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1Meetings with members of the group to discuss where and how to get land | Meeting done and a part of land given by one of the member of the group in which it contain a building for an office | Progressive report | Meeting | Tumaini VICOBA Members, Hope trust group members, CED Student | June,2017 |
|  |  | 2.1.2To fundraise for finding funds for buying materials for repair of the building | Fund raised | Progressive report | Meeting | Tumaini VICOBA | June,2017 |
|  | 2.2. To fundraise for finding funds for paying the mason and for collecting materials for repair of the building | 2.2.1 To collect materials for repair of the building | Materials for repair in place | Progressive report | Meeting | Tumaini VICOBA Members, Hope trust group members, CED Student | June,2015 |
|  |  | 2.2.2 The masons start to repair the building for office and poultry keeping which given by a member of the group | Building for poultry built and an office repaired. The mason paid | Progress report | Meeting | Tumaini VICOBA | June,2017 |
| 3. Undertake production chickens by July to August 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens | Chickens in place | Analytical Report | Screening of chickens | Extension Officer, Hope trust group Members,CED Student | July,2017 |
|  |  | 3.1.2 Purchase of chickens | Purchasing report, Chickens in place | Delivery Note, Goods receivable note | Purchasing | Hope trust group members, CED Student | July 2017 |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chickens | Feeds in place | Analytical report | Identification report | Extension Officer, Hope trust group members, CED Student | July,2017 |
|  |  | 3.2.2 To purchase chicken feeds | Feeds in place | Purchasing report | Payment receipt | Extension Officer, Hope Trust members, CED Student | July, 2017 |
|  | 3.3 Poultry suitable equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Identification report | Identification Report | Purchasing analysis report | Extension Officer, Hope trust members, CED Student | July 2017 |
|  |  | 3.3.2 To purchase the equipments | Equipments in place | Goods receivable note | Inventory | Hope Trust group members, Extension Officer | July, 2017 |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination | Identified Extension Officer | Identification/Progressive report | Screening report | Hope Trust group members, CED Student | July 2017 |
|  |  | 3.4.2 Doing vaccination activity | Chickens vaccinated | Vaccination report | Injection | Extension Officer, Hope Trust members, CED Student | July 2017 |
| 4. To sale 50 live chicken by September to October 2017 | 4..1 Buyers identified | 4.1.1Lobbying and Advocacy for Marketing | Displayed advertisements done | Progressive report | Advertisements | Hope group members | August to September,2017 |
|  |  | 4.1.2Transport of live chicken | Live chicken loaded in a truck ready for transportation | Receipt for transport payment | Hired Truck | Hope Trust group members | August to September,2017 |

Source: researcher, 2107

# 5.3   Participatory Evaluation

This component provides a summing up of the project participatory evaluation. Evaluation is an approach that can be applied to make sure that execution of the different intended activities of the project will be well executed for the purpose of achieving the planed goal of the project. Participatory evaluation  illustrate  in detail the degree of achievement of the project  in terms of its goal, objective, efficiency, competence, impact as well as its sustainability in general. Participatory evaluations brings a joint venture approach among the stakeholders of the project during  making arrangement as well as on the implementation of evaluation activities in all phases of project.

As a result evaluation provides a cyclic appraisal of the implication and performance of the project. Also it provides comments to the team of the project on what it can done in a different way as to achieve the objectives. Evaluations do assess the impact of project as well as its sustainability. The evaluation for this project was designed by its stakeholders together with some experts as the team. Participatory evaluation for poultry keeping project is still in progress as it has been designed, being planned and implemented by Hope trust women group members. The Participatory Evaluation of the project provides a space where by specialized evaluators and all project stakeholders to bring their efforts together for the purpose of improving the community’s quality of life. Participatory evaluation is the process of a project to comprise the setting up the required logistical activities for the intention of setting them up and run them. Execution is the real performance works of managing the project where by outcomes are the consequence of the project’s existence.

Hope Trust women group members play a part in their project evaluation for the purpose assessing if the intended goal of the project is being really achieved by finding out if the intended resources were used as planned. Hope Trust women group members take part in evaluating if all intended activities were completed, costs that the group inquired, quality of chick purchased, quality of feeds purchased, equipments purchased, costs incurred for paying the masons for repairing an Office and building a Poultry building and also they will evaluate if the sales that they will get will convey a profit or loss to their project.

# 5.3.1 Performance Indicator

For any of the project to attain its planned goals and become sustainable, there must be performance indicators designed for the purpose of measuring its success. Performance indicators can be defined as variables that illustrate the level of improvement that are the results of the project. They assist to assess the quantities, quality and timeliness of what was intended. They asses the significance of progress in attaining outputs and outcomes. They also explain significance, performance and success of the project in   progressing to meet up its outputs and outcomes.

# 5.3.2 Participatory Evaluation Methods

Participatory Rural Appraisal (PRA) was being used as the Participatory Evaluation Method. The method brought a participatory manner by giving the group members a space and chance to make a decision of the methods that will be suitable, they planned them, and collecting the information. Through the involvement of the group members to analyse the information for positive changes has given a big possibility that project stakeholders will gain knowledge from the practice. Also through this method stakeholders find out more on what worked well and why worked well and this goes hand in hand with the observation and learning of the things that have not worked well and why they did not work as they intended so.

# Table  5.3: Project Performance Indicators

| Objectives | Outputs | Activities | Resources Needed | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. Training of 5 women’s on poultry keeping by May 2017 | 1.1 : 5 womens were trained on Poultry keeping | 1.1.1 Identification of trainees | * | List of Trainees identified |
|  |  | 1.1.2 Conducting one day training workshop on poultry keeping | Facilitator, Stationary, Allowance | List of trainees participated |
| 2. Acquiring an office and a building for poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land | Funds | Attendant list |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building | Funds | Funds raised |
|  | 2.2. To fundraise for finding funds for paying the mason and collecting materials for repair of the building | 2.2.1 2.2. To collect materials for repair of the building | Funds and materials | Materials collected |
|  |  | 2.2.2 The masons start to repair the building for office and poultry keeping which given by a member of the group | Masons and materials | Building repaired |
| 3. Undertake production of the first batch chickens by July 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens | Extension Officer | Chickens identified |
|  |  | 3.1.2 Purchase of chickens | Funds, Extension Officer | Chickens purchased |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chickens | Extension Officer, Funds | Feeds Identified |
|  |  | 3.2.2 To purchase chicken feeds | Extension Officer, Group members, Funds | Purchased Feeds, Payment receipts |
|  | 3.3 Poultry suitable equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Extension Officer | Identified equipments |
|  |  | 3.3.2 To purchase the equipments | Extension Officer, Hope trust group members, Fund | Equipments purchased in place |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination | CV of Extension Officer | Identified extension Officer |
|  |  | 3.4.2 Doing vaccination activity | Extension Officer, Funds, Hope trust group members | Chickens’ healthy |
| 4. To sale 50 live chicken by September to October 2017 | 4.1 Markets were found | 4.1.1 To do lobbying and Advocacy for Marketing | Hope trust group members, CED Student | Sales Report |
|  |  | 4.1.2 Transport of live chicken | Funds | Number of live chicken reached market place |

Source: researcher, 2107

For participatory evaluation, the general and instant objectives were still continued to significance and success of the activities and all were put into explanation. Participatory Evaluation also can make use of the information from Participatory Assessment, Participatory Baseline and Participatory Monitoring. The Information that is from participatory monitoring will provide movement and tendency as well as total summation. Stakeholders  will  get significant  and helpful information through examination of activities independently in relative to objective  and this will support them make decision on either  the objectives and activities  can stay the same or could be changed. This method  was been applied to assist the utilization of Questionnaire, Focus Group Discussion and Key informants Interview methods which was being designed to be exercised during evaluation of the project.

# 5.3.3   Project Evaluation Summary

Under this part it the one that provides a general summing up of participatory evaluation. Evaluation is an approach that can be applied to make sure that execution of the different intended activities of the project will be well executed for the purpose of achieving the planed goal of the project. Participatory evaluation  illustrate  in detail the degree of achievement of the project  in terms of its goal, objective, efficiency, competence, impact as well as its sustainability in general. A participatory evaluation brings a joint venture approach among the stakeholders of the project during making arrangement as well as on the implementation of evaluation activities in all phases of project.

# Table 5.4: Project Evaluation Summary

| Objectives | Outputs | Activities | Performance Indicators | Expected Outcome | Actual Outcome |
| --- | --- | --- | --- | --- | --- |
| 1. Training of 5 women on poultry keeping by May 2017 | 1.1: 5 women were trained on Poultry keeping | Identification of trainees | List of Trainees identified | Identified Trainees | 5 Hope trust group members identified for Training |
|  |  | Conducting one day training workshop on poultry keeping | Progressive report | 5 Hope trust group members to be trained on Poultry keeping | 5 Hope group members Trained on Poultry keeping Project |
| 2. Acquiring an office and a building for poultry keeping by June 2017 | 2.1. Part of land for office building and poultry keeping production in place | 2.1.1 Meetings with members of the group to discuss where and how to get land | Attendance list | Meeting done | Meeting done |
|  |  | 2.1.2 To fundraise for finding funds for buying materials for repair of the building | Fund raised | Fund to be raised | Fund raised |
|  | 2.2. To fundraise for finding funds for paying of the mason and collecting of materials for repair of the office and building of poultry building | 2.1.2 To collect materials for repair of the building | Materials collected | Materials collected | Materials were collected |
|  |  | 2.2.2 The masons start to repair the building for office and poultry keeping which given by a member of the group | Building repaired | Building repaired | Building for office and Poultry in place |
| 3. Undertake production of the first batch of chickens by July 2017 | 3.1. One batch of 50 chickens were bought | 3.1.1 To identify good quality chickens | Chickens identified | Chickens to be identified | Chickens were identified |
|  |  | 3.1.2 Purchase of chickens | Chickens purchased | Chickens to be purchased | Chickens in place |
|  | 3.2. Three bags of Chickens’ Feeds were bought | 3.2.1 To identity the Feeds with required Nutrients for the chickens | Feeds Identified | Feeds to be identified | Feeds with required nutrients were identified |
|  |  | 3.2.2 To purchase chicken feeds | Purchased Feeds, Payment receipts | Feeds to be purchased | Feeds in place/Feeds purchased |
|  | 3.3 Poultry suitable equipments for poultry keeping were purchased | 3.3.1 To identify the needed suitable equipments | Identified equipments | Equipments to be identified | Suitable Equipments were identified |
|  |  | 3.3.2 To purchase the equipments | Equipments purchased in place | Equipments to be purchased | Purchased Equipments in place |
|  | 3.4 One vaccination done to 50 chickens | 3.4.1 To identity the veterinary expert for vaccination | Identified Extension Officer | Veterinary expert to be identified and chickens to be vaccinated | Veterinary expert was identified |
|  |  | 3.4.2 Doing vaccination activity | Chickens’ healthy | Chickens to be vaccinated | Chickens were vaccinated |
| 4. To sale 50 live chicken by September to October 2017 | 4.1 Buyers identified | 4.1.1To do lobbying and Advocacy for Marketing | Sales Report | Market for chicken | Chicken to be sold |
|  |  | 4.1.2 Transport of live chicken | Number of chicken reached the market for Sales | Increase in Hope trust group members income | Hope trust group members increased their incomes |

Source: researcher, 2107

# 5.4 Project Sustainability

Project sustainability means the necessity of our generation to  take control of the resource  available for the purpose of  ensuring that we can potentially  share the future coming generations. Development can only be is sustainable if the non-decreasing standard quality of life can be included. For any project to be sustainable there must be well consumption of resources and opportunities by accepting the inter connections among economy, society and environment and living as well as utilizing resources within the limit. The good management and utilization of resource in a useful manner will make the project to become sustainable.

The use  of limited resources can led the project to be accomplished only if resources are available and enough Hope trust women group members measure the required amount of resources and contrast it to the existing resources base and this will help Hope trust women group members to manage the project in a sustainable manner. The hard work to attain successful management will led better achievement  but only if the use of  available resources will never exceed the amount of resources necessary for the project completion. For that means Hope trust women group members find out the significance of distributing project resources to only prioritized directions according to their strategy. Resources distribution activities must be designed for the long-term perception and consumption by bearing in mind the expectation of stakeholder. For this project to become sustainable, Hope trust women group members cautiously supervised the process of project conceptualization to develop a concept that is logical to available project resources and meet up the hopes of stakeholder as well as it fits into their plans. Hope trust group members identified themselves and organized themselves in order to become the project resource managers for the aim of the project to become sustainable.  In case of minimizing waste, project beneficiaries to design the use of resources for the purpose of avoiding wastage of resources. Includes standards and communication of the project, Hope trust women group members included their values in order to fit their expectations and these were all members to communicate to their project as a team.

For project sustainability plan of poultry keeping, Hope trust group members prepared a document that illustrate how the project management was going to act upon changes, actions, disaster  and other factors which would confront feasibility and significance of their project. This arrangement made also was severely emphasising on the resources to be used. For this project, the resources needed are easily to be reach as Poultry Feeds are many sold at different places in  Ngaramtoni town and Arusha mjini, Vaccination medicines are also available.

Through these measures and steps that are being taken into consideration, it is the   expectation of the project recipient that their project will be sustainable and the incomes that will be attained by the selling of the project products will led to the greater increase of their households’ income and therefore the improvement of their economic together with their living standards. It openly known that market for poultry increases as days go on hence this will led to the project to be sustainable. Through the increase in poultry product demand provide an opportunity for the project to be sustainable.

In a case of institutional sustainability was been shown at the beginning of as there was fully participation of project stakeholders from project identification, designing, implementation, monitoring and evaluation, this brings the sense of project ownership. Because they feel being the owner of the project they will have strategies to make the project sustainable. They had planned to sale project products inorder to raise their project capital and income in general. For the case of financial sustainability this will be reached for the reason that the Hope Trust women group members had designed and planned to volunteer in implementing other activities in order to minimize running costs for the project. They have planned to have some months without distributing the profits to themselves in order to increase the money for future expansions of the project.

# CHAPTER SIX

# 6.0 CONCLUSION AND RECOMMENDATION

# 6.1 Introduction

This chapter gives a summary of Hope Trust women group which deals with poultry keeping in Ekenywa village. The chapter summary analyzes on stages that were carried out from project identification up to the project implementation results. The chapters include Community Needs Assessments, Problem identification, Literature review, Project implementation, Participatory Monitoring, Evaluation and sustainability of the project. This chapter therefore shows conclusion which enables, development frontline practitioners including researchers, decision makers, policy makers, and other developments partners in poultry to collect necessary information on poultry keeping and finally come up with ideas for improvement of the sector.

During problem identification Community Needs Assessment was done in participatory manner and hence evidenced those low income earners. The women in Hope Trust group fail to contribute their weekly shares to their VICOBA group which they do get loans for their petty business. Knowing the problem facing Hope Trust women group, members ranked potential projects which they thought could help them. It was therefore through pair wise ranking the group identified poultry keeping as their project. The CED student therefore went through Literature review to find information to find if the project is economically sound.

The literature review revealed that the project was viable and economically sound. The policy analysis also showed that there are deliberate efforts by Tanzania government to support the sector also markets were not a challenge for the project.

The CED student led group through project cycle which is identification, planning organizing, implementation, participatory monitoring and evaluation. This chapter six therefore gives a brief narration of what was done in the previous chapters and recommendation and conclusions.

# 6.2 Conclusion

The Hope Trust women group poultry project is supported by Tanzania livestock and agriculture policy. The policy likewise well aligns with Sustainable Development Goal (SDGs) 2030.  Project was identified through community participation therefore all stakeholders and partners know the project well. Community Needs Assessment, Problem identification, Literature review and Project Implementation were well planned and implemented. Monitoring and Evaluation was carried in order for the project team and community to measure if their project will be sustainable.

The researcher found that Tanzania is gifted with chickens and 72% of those chickens are kept traditionally in rural areas. The chicken keeping in Tanzania has been a solution to most women living in rural areas. Women use chicken to buy food, nutrition, shelter, paying of energy bills and contribution to financial institution such as VICOBA. The assessment however showed that despite the fact that rural women keep poultry, they are yet to maximize their profit. The CED student in collaboration with community found that rural women who keep chicken are faced with challenges such as insufficient extension services, shelter, food, and pests and diseases. According to findings Ekenywa shows that women between  age of 25-32 were many in that population of 40 followed by those with age between 32-39 and the last group was between 39– 48. The researcher was encouraged with this group distribution of population that they had enough capability and efforts of establishing and implementing the project sustainability.

The study found that poultry keeping is being done at different places like in rural and urban, and at different countries. Poultry keeping is done by both rural and urban dwellers as poultry contributes for household incomes which lead for the families to meet their social obligations, increasing food supply and nutrition to household members by either eating the meat or eggs from poultry. Chickens keeping are done in different countries like Malawi, Tanzania, Mozambique and others. Poultry keeping is beneficial as it increases income, nutrition and is environmental friend, the production faces constraints like diseases and parasites, poor feeds supply, limited to financial credit access, high prices in inputs, insufficient of marketing strategies, low management skills.

The objectives like Capacity building was achieved as the identification of trainees was done and 5 womens who were the trainees attended a one day workshop on poultry keeping. Acquiring an Office and building for poultry keeping was achieved since one of group member gave her part of land for stating of the project .The project will later acquire land for the project. The group members also organized funds to built poultry building and for repair of their office, acquired chicken for keeping which were in good condition, purchased food for chickens, purchase of equipments and vaccination was also successfully. But other objectives like selling of project products will be done later although the market had already been identified.

# 6.3 Recommendation

The researcher recommends that during implementation of a poultry project community authentic participation indicates to good impacts of the project. However community needs assessment is very necessary since community has many needs but through proper community assessment, the community will come out with viable project. Community transparency before start of project will create sense of ownership of the community and hence sustainability. The researcher would recommend one to use Participatory Rural Appraisal (PRA) since it gives room for shared learning between local people and outsiders (development practitioners, government officials) to plan together on appropriate interventions. By community participation knowledge and experiences that minimize wastage of resource especially during the planning, designing, budgeting exercise is shared to all.

It is also very important for researcher and those dealing with development projects to building capacity of community. This is because the study revealed that most of the community members had insufficient knowledge on the project management and factors to bear in mind for sustainability. Skills on project identification implementation, management, monitoring and evaluation should be adhered to for poultry projects to be sustainable.

The needs for Community Participation, Transparency and Accountability are inevitable for the sustainability of the projects. Give a room for members to participate fully, allow and encourage Transparency in every stage from project identification to implementation and Monitoring and Evaluation. In order for the projects to be effectively and efficiently, project design should be done systematically and each component needed should been accounted for. There is a need for detailed plan that shows the overall objective, specific objectives, output and activities to be carried out. Schedule of activities to be should be assigned with responsible people to ensure implementation is done on time to avoid delays.

Researcher recommends for the Literature review to be done effectively by gathering information from many different data/document sources. The researcher according to the study made the following recommendations.

- The government of Tanzania in collaboration with livestock and agriculture department should encourage vaccination and availability of local extension officers in every village. Extension officers will make sure that training is done to traditional poultry keepers in order to benefit from poultry business.

- Tanzania government need to put more efforts on poultry sector through VAT exemption to drugs, equipments and foods for poultry in order to increase supply and affordability to low income earners especially vulnerable groups in rural areas such as women.

- In order to add value to poultry in Tanzania the government need to put efforts on establishment of poultry butchery in the zones that poultry are kept in high percentage.

- The livestock and agriculture sector should need to organise and form poultry keepers groups in the rural areas for few extension officers to easily access and be able to educate them within their locality.

- Establishment of Poultry practical field classes. The government should ensure that every village has a poultry practical field class. The field classes will be used by groups for training and learning. In order to make these effectives students from colleges and universities dealing with livestock should be encouraged to do their fields in those centres so that they will exercise what they learnt with poultry keepers in rural areas.

# REFERENCES

Ahlers, G. R. (2012). Poultry housing and management in developing countries. Retrieved on 28th March, 2017 from: http://www.fao.org/docrep/019/i3531e/ i3531e04.pdf cited on 11th August 2017.

Dessie, T. (2012).  “Current state of knowledge on indigenous chicken genetic resources of the tropics: domestication, distribution and documentation of information on the genetic resources,” World’s Poultry Science Journal, 68(1), 11–20.

FAO, (200). Small-scale Poultry Production Technical guide. Retrieved on 13th July 2017 from: http://www.fao.org/3/ a-y5169e.pdf cited.

# FAO, (2004). Local chicken production system in Malawi: Household flock structure, dynamics, management and health. Retrieved on on 11th August 2017 from: https://link.springer.com /article/10.1007 /s11250-006-4293-8.

FAO, (2013). Mozambique Livestock country reviews Animal Production and Health Poultry sector. Retrieved on 13th July, 2017 from: http://www.fao.org/docrep/018/i3487e/i3487e.pdf cited on 13th July 2017.

FAO, (2017). Promoting socially inclusive rural development in Europe and Central Asia: Action for the 2030 Agenda http://www.fao.org/3/a-i7020e.pdf cited on 13th July 2017.

Guèye, E. F. (2000). The role of family poultry in poverty alleviation, food security and the promotion of gender equality in rural Africa. Journal article, 29(2), 129-136.

Guèye, E. F. (2002). Family poultry research and development in low-income food-deficit countries: approaches and prospects. Agriculture, 31(1), 13–21.

# ILRI, (2016). Unlocking the potential of Ethiopia’s livestock sector: growth, jobs and environmental sustainability https://news.ilri.org/2016/02/04/cited on 20th August 2017

Jimoh, K. B. (2007). Improved Practices in Rearing Indigenous Chickens https://publications.cta.int/media/publications/downloads/1379_full_text.pdf cited on 15th August 2017.

Kay, M. F. (2016). Small-Scale Poultry Processing retrieved on 11th August 2017 from: https://attra.ncat.org/attra-pub/summaries/summary.php?pub=235 cited

Government of the Republic of Mozambique, (2015). Ministry of Agriculture National Agriculture Investment Plan 2014-2018. Maputo, Mozambique.

Mvaa, A. K. (2015). Women group in Improving local chicken production at Sokoni Arusha City for Income raising CED student Dissertation for building capacity to Engosengui, unpublished masters thesis, Open University of Tanzania. Dar es Salaam, Tanzania.

# Pagani, P. and Wossene, A. (2008). Participatory evaluation of chicken health and production constraints in Ethiopia, Workshop to Help Small-Scale Poultry, Maputo, Mozambique.

# UN, (2016). Sustainable Development Goals. Retrieved on 14th July, 2017 from: http://www.un.org/sustainabledevelopment/sustainable-development-goals/.

URT, (2005). National Strategy for Growth and Reduction of Poverty (NSGRP) https://extranet.who.int/nutrition/gina/sites/default/files/Tanzannia National%20Strategy%20for%20Growth%20and%20Poverty%20Reduction%20.pdf cited on 4th July 2017.

URT, (2006). The ministry of livestock development https://www.tnrf.org/files/E INFO_National_Livetock_Policy_Final_as_per_Cabinet_Dec-2006.pdf cited on 13th July 2016.

# APPENDICES

# APPENDIX – 1 STRUCTURED QUESTIONNAIRE FOR COMMUNITY MEMBERS

Tick where appropriate and fill the information where required.

1.   Respondents Personnel Particulars

1.1   Age:    a) 25-32    (     )        b) 32-39           (      )    c) 39-46.

2. Respondent’s level of Education:

01) Not attended school                                                               (     )

02) Standard seven                                                                      (     )

03) Form four                                                                                (     )

3. What is the source of your income?

01) Maize keeping                                                                 (     )

02) Poultry keeping                                                                (     )

03) Cattle keeping                                                                    (     )

04) Monthly Salary                                                                  (     )

05) Others …………………………………………………………………………

4. How did you get land to do your income generating activity?

- From my parents (  )

- I bought it      (    )

- I was given by my husband (   )

- We had been given by our fellow member.(    )

5. What are the major economic activities in the community?

01) Vegetable farming     (    )	 02) Cattle keeping     (     )    03)tailoring   ( )            04) Beads making (    )        05) Poultry keeping (     )	06) maize farming    (    )

6. What kind of project/business do you think is potentially, sustainable and economically practicable?

1) Cattle keeping (     )   2) poultry keeping    (     )    3) Vegetable farming     (     )

4) Maize farming      (     )    5) Food processing      (     )   6) Bee keeping    (     )

7) Beads making      (      )

7. Can the business in number six (6) operate throughout the year?

01) Yes   (     ) 		02) No   (       )         02)    I do not know       (     )

8. What will be the impact of that project?

Please, cycle the appropriate score using the following scale

1=First class     2=Second class   3=Third class

These classes means as follows;

1. Increase in individual income

2. Decrease of dependence

3. Creation of employment

9. What challenges do you think you may face in implementing the proposed project?

01) Inadequate capital (    )        02) Unreliable Market (    )    03) Lack of technical skills

04) Pest and Disease                  (    )      05) I do not know       (    )

10. Do you think the project will decrease dependency in the community?

i) Yes (    )          ii) No   (     )   iii) I do not know      (      ).

11. How many people  can project number  6 above employ in the community?

a) 10-25     (    )    b) 25-50    (    )       c) 50 and above

12. Does the government/private institutions provide support to income generating activities in the community?

01) Yes (    )		 2) No (     ) 		03) I don’t know (     )

13. If yes what kind of support do they get?

01) Financial support        (    )   02) Entrepreneurship skills (     )

03) Tools and equipments (    )   04) No Support                   (    )

05) Other Support             (     )

# APPENDIX – 2  INTERVIEW GUIDE FOR FOCUS GROUP DISCUSSIONS WITH CBO

Date of Interview     ___/___/___	Date  ________________

Name of supervisor       ________________________________

Name of the CBO: _________________________________________________

- How many members of VICOBA are male and female? a)Male_____ b)Female___

- When did VICOBA start? (Year)……………….

- Is the CBO registered?

- What support CBO financially?

- What is the overall goal of CBO?

- What are the income activities being undertaken in this community.?

- Do you produce or work in profit in your day to day activities  i)Yes (   )  ii) No (   )         iii)      (    )

- Do you think the income from the established project will be beneficial to the members?.......................

- What are the other potential economic projects in the community?.........................

- What are the challenges facing the project?................................................

- Is there any training do CBO members receive?

- Do members benefits from income from the group?....................................

- What kind of support has CBO received from the Government/any other development institution?

- What can be done in order to help group progress with what is doing ?.................................................................................................

# APPENDIX  3: APPLICATION LETTER TO CBO

# APPENDIX  4: LETTER  FROM  CBO CED STUDENT

# APPENDIX 5: APPLICATION LETTER OF THE HOPE TRUST WOMEN GROUP MEMBERS TO THEIR FELLOW MEMBER FOR THE REQUEST OF LAND FOR BUILDING A POULTRY HOUSE AND AN OFFICE

# APPENDIX 6: LETTER FROM THE MEMBER OF HOPE TRUST WOMEN GROUP FOR   THE AGREED OF GIVING HER PART OF LAND FOR BUILDING A POULTRY HOUSE AND AN OFFICE

# Text boxes

TRESURER

DISCIPLINE

SECRETARY

CHAIR PERSON