IMPROVING COMMUNITY INCOME OF KAMWENE VILLAGE COMMUNITY THROUGH ESTABLISHMENT OF RICE VALUE ADDITION PROJECT IN KILOMBERO DISTRICT MOROGORO REGION

SEBASTIAN SAMBUO MUSHI

A PROJECT REPORT SUBMITTED IN PARTIAL FULFILLMENT OF THE REQUIREMENTS FOR THE OF DEGREE OF MASTER IN COMMUNITY ECONOMIC DEVELOPMENT OF THE OPEN UNIVERSITY OF TANZANIA

2017

# CERTIFICATION

The undersigned certifies that he has read and hereby recommends for the acceptance by the Open University of Tanzania (OUT) a project entitled, Improving Community livelihood through rice value addition project in partial fulfillment of the requirements for the award of degree of Master of Community Economic Development of the Open University of Tanzania.

...................................................

Dr. Emmanuel Mallya

(Supervisor)

.............................................

Date

# COPYRIGHT

No part of this dissertation may be reproduced, stored in any retrieval system or submitted in any form by any means, electronic, mechanical, photocopying, recording or otherwise without prior written permission of the author or The Open University of Tanzania in that behalf.

# DECLARATION

I, Sebastian Sambuo Mushi, do hereby declare that this CED project report is my own original work under supervision of Dr. Emmanuel Mallya and that it has not been presented and will not be presented to any other university for similar or any other degree award

………………………………….

Signature

………………………………….

Date

# DEDICATION

This work is dedicated to the special people in my life who are my beloved Parents my Father Mr. Michael Kitabera Mushi and my mother Mrs. Laurencia Simon Sarukoki Mushi.

# ACKNOWLEDGEMENTS

I would like to sincerely thank all those whose assistance has contributed to the preparation until success of this research work. The myriad thanks should go to the Almighty God, for a man without God, regardless of how energetic, how important and how vigorous he may appear, is actually dead. Sincere thanks should go to my course coordinator Dr. Harrieth Mtae and my supervisor Dr. Emmanuel Mallya for being patient and comprehensively leading me in all phases of this work as my Supervisor.

Furthermore, my sincere thanks go to the management, academic staff, support staff and the whole community of the Open University of Tanzania Kinondoni  main campus and all campuses  starting with the Vice chancellor/ Rector Prof. Eliphas Bisanda for his good fatherly guidance to the OUT administrative machinery that enables our academic ball to keep on rolling smoothly, without forgetting various OUT directorates and heads of departments who co-works with him to assure that we reach our academic excellence. I cannot forget my family which permits me to take this endeavor, among these are my beloved father Mr. Michael Sambuo Kitabera and my mother Laurencia Simon Sarukoki, for their lovely formation and upbringing to this moment.

I am indebted to my brothers and Sisters who accompanied me very close in all my studies materially and morally. Among these are my brother Vincent Mushi, Evarister Gregory, Christine Mushi, Lucy Mushi Mmasy and Lilian Mushi Mallya. My uncle Eng. Aloyce Mushi has been a green light to me and academic star who always was showing me the way.  Thank you all, it is only God who can reward you.

# ABSTRACT

The proposal on promoting value addition to rice for contributing in increasing income and poverty reduction in Kilombero by installing rice milling plant in Kamwene came up as an idea from the village community which was obtained after conducting Community Needs Assessment (CNA) which was done with Kamwene village community in Kilombero district. Prior to project intervention, the CNA exercise was conducted which came up with the community needs and problems. In the hierarchy of problems, the main problem which was listed by the community which faces majority of community members in Kamwene Village was the prevalence of income poverty. Among other activities Kamwene community members do engage in rice production as their food and cash crop which contribute to their household income for income poverty reduction. However, rice producers have been facing market problem for their produce and low prices. Under this study were three objectives which are set to facilitate the process of solving the problem, these are: To improve farmers’ awareness on the importance of value addition to their crops/paddy. To facilitate availability of capital for farmers’ investment in the value addition project. To ensure operation and sustainability of value addition project. The project has planned to achieve three objectives namely: One objective has been achieved partly which is to facilitate availability of capital for farmers’ investment, farmers have acquired land for establishing milling machine. The construction process has begun by dinging foundation and the work is going on well which will lead to successful implemented. Another activity which has started in collecting shares in form of crops/paddy.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	iv

ACKNOWLEDGEMENTS	vii

ABSTRACT	viii

LIST OF TABLES	xiv

LIST OF FIGURES	xv

LIST OF ABBREVIATIONS	xvi

CHAPTER ONE	1

1.0	COMMUNITY NEEDS ASSESSMENT	1

1.1	Background Information	1

1.1.1	Rice Processing and Branding	2

1.1.2	Sales of High Quality Products	2

1.2	Kamwene Village Community Profile	3

1.2.1	Administrative Structure	3

1.2.2	Demographic Features	4

1.2.3	Ethnicity	4

1.2.4	Economic Activities	4

1.3	Community Need Assessment	5

1.4	Objectives for Community Needs Assessment 	6

1.4.1	CNA General Objective	6

1.4.2	Specific Objectives	6

1.4.3	Research Questions	6

1.5	CNA Research Methodology	7

1.5.1	Types and Sources of data	7

1.5.2	Sources of Data	7

1.5.3	Research Design	9

1.5.4	Data collection Methods	11

1.6	Findings of the Participatory community Assessment	13

1.6.1	Respondents Characteristics	13

1.6.2	Available Resources for Establishing Paddy Processing Plant to                     Improve Community Income	16

1.6.3	Challenges Which Hinder Development in Kamwene Village                     Community	16

1.6.4	Selling of Raw Paddy than Finished Product/ Rice	17

1.6.5	Minimal Access to Credit	19

1.7	Community Need Prioritization	19

1.8	Chapter Conclusion	22

CHAPTER TWO	23

2.0 	BACKGROUND TO THE RESEARCH PROBLEM	23

2.1	Statement of the Problem	23

2.2	Project Description	26

2.2.1	Target Community	26

2.2.2	Stakeholders	27

2.3	Project Goal	28

2.4	Project Objectives	28

2.4.1	General Objective	28

2.4.2	Specific Objectives	28

2.5	Host Organization CBO	29

2.5.1	Organization and Management of Day to Day Activities	29

2.5.2	Host Organization Leadership	30

2.5.3	Vision of the Host Organization	31

2.5.4	Mission of Kamwene Village Council	31

2.5.5	Kamwene Village Council Organization Structure	31

2.5.6	Analysis of Strength, Weaknesses, Opportunities and Challenges for Kamwene Village	32

2.5.7	The Roles of CED Student in the Project	33

2.5.8	The roles of the Host Organization	33

2.6	Chapter Summary	34

CHAPTER THREE	35

3.0	LITERATURE REVIEW	35

3.1	Introduction	35

3.2	Definition of Some Important Concepts	35

3.2.1	Paddy Rice	35

3.2.2	Commodity Exchange Market	36

3.3	Empirical Literature Review	36

3.3.1	Rice Consumption Trend in Tanzania and Africa	36

3.3.2	Rice Growth in East Africa and Tanzania	37

3.3.3	Rice Market Overview	39

3.3.4	Added Advantage for Tanzania Production and Trade on Rice	40

3.3.5	Inadequate Quality Harvesting	41

3.3.6	Poor Post-Harvest Management Practices	41

3.3.7	Processing Challenges	41

3.3.8	Lack of Known Brand and Branding Strategies at All Rice                          Value Chain Nodes	42

3.3.9	Unstructured Trade and Inadequate Market Linkages	43

3.3.10	Minimal Access to Credit	43

3.3.11	Unfavorable Business Enabling Environment	44

3.3.12	Sales of High Quality Products	44

3.4	Policy Review	45

3.4.1	National Agricultural Development Policy 2013	45

3.4.2	Marketing Infrastructure, value Addition and Rural Finance Project	45

3.4.3	Kilimo Kwanza and its Impact in Rice Subsector	46

3.4.4	Chapter Summary	47

CHAPTER FOUR	48

4.0	PROJECT PLANNING AND IMPLEMENTATION	48

4.1	Introduction	48

4.2	Project Products and Outputs	48

4.2.1	Products and Outputs	48

CHAPTER FIVE	68

5.0	PROJECT PARTICIPATORY, MONITORING EVALUATION                 AND SUSTAINABILITY	69

5.1	Introduction	69

5.2	Participatory Monitoring	69

5.2.1	Participatory Monitoring Tools That Were Used	70

5.3	Monitoring Information System (MIS)	71

5.4	Project Participatory Monitoring Plan	72

5.5	Monitoring Results	75

5.6	Participatory Evaluation	76

5.7	Performance Indicators	76

5.8	Participatory Evaluation Methods	78

5.9	Project Evaluation Summary	80

5.10	Project Sustainability	83

5.10.1	Organizational Capacity	83

5.10.2	Financial Sustainability	84

5.10.3	Socio - Political sustainability	84

CHAPTER SIX	86

6.0	CONCLUSION AND RECOMMENDATION	86

6.1	Introduction	86

6.2	Conclusions	87

6.3	Recommendations	89

REFERENCES	91

APPENDICES	111

# LIST OF TABLES

Table 1.2: 	Gender of Respondent	13

Table 1.3: 	Education Level of Respondent	16

Table 1.4: 	Importance of Value Addition Project in the Community	17

Table 1.5: 	Do You Sell Your Paddy Before or After Adding Value?	18

Table 1.6: 	Pair Wise Ranking Table	20

Table 1.7: 	Proposed Projects That They Are Real Community Needy In     Kamwene Village?	21

Table 4.1: 	Project Activities Table	52

Table 4.2: 	Project implementation Plan	53

Table 4.3: 	Project Log Frame Matrix 	56

Table 4.4: 	Project Budget 	60

Table 4.5: 	Project Time Management Table 	64

Table 4.6: 	Project Implementation Report Table	67

Table 5.1: 	Participatory Monitoring Plan	73

Table 5.2: 	Performance Indicator Table	77

Table 5.3: 	Project Evaluation Summary	81

# LIST OF FIGURES

Figure 1.1: 	Marital Status of Respondents	14

Figure 1.2: 	Income of Respondents	32

Figure 1.3: 	Market Problem	18

Figure 1.4: 	Community Members Making Follow Up of the Prioritization      Exercise	21

Figure 2.1: 	Administration Structure for Kamwene Village	31

Figure 4.1:	Community Members Making Follow Up of the Meeting                            Proceedings during One of the Village Meetings for Sharing                       Progress Report	50

Figure 4.2:	Community Members Filling Soil in the Foundation for the                       Milling Machine and Office Building	51

# LIST OF ABBREVIATIONS

AGM 	Annual General meeting

CNA 	Community Needs Assessment

EAC 	East Africa Community

FGD 	Focus Group Discussion

FGD 	Focus Group Discussions

MIS 	Monitoring Information System

OUT 	Open University of Tanzania

URT	United Republic of Tanzania

VDC 	Village Development Committee

VEO 	Village Executive Officer

# CHAPTER ONE

# COMMUNITY NEEDS ASSESSMENT

## Background Information

Struggling for poverty alleviation is a multi- disciplinary which needs multi-dimensional approach. According to URT (2011), Poverty for a long time has said to be rural phenomena whereby majorities are engaging in subsistence farming and are worse affected. Due to this fact agricultural diversification is one among the possible way to address the problem. Since 2000 Tanzania development plans, Researches, Assessments, and any development program are emphasized to base on the Tanzania National Development Vision 2025 under which different strategies have been in place to ensure the welfare of Tanzanians in future.

Those strategies include; United Nations Millennium Development Goals (URT, (2008) which has adopted by Tanzania and the Strategy for economic Growth and Poverty Reduction (MKUKUTA). Rice is widely cultivated crop in many parts of the world. Statistics show that; “in 2016 the world produced 483.1 million metric tons” United States Department of Agriculture USDA 2016. In 2011 the production Worldwide was forecasted by FAO to be 168.9 million metric tons of rice (FAO, 2015:1-7). This progress in Rice production is a result of farmers increase in both production and productivity and application of modern agricultural practices. Rice producers use this crop as both food and cash crop because it helps them to earn some money which in turn can contribute in household income poverty reduction.

Furthermore rice is rich in sugar, glucose, calcium, potassium, and organic acids. Apart from its dietary value, rice can also be used to make crackers, burns, cakes as well as for breweries in making beer. According to USDA (2016) the production of Rice in the 25 European Union countries in 2016 was 2,082,000 million tones. Rice production is also done in different African countries and it has been contributing at large in the peoples income earning. Rice production is done in East African region both in highlands where farmers grow highland varieties for irrigation and low lands where they grown rain fed rice. In Kenya, Uganda, Tanzania and Ethiopia rice is grown in the southern and south-western highlands.

## Rice Processing and Branding

According to AGRA (2011) “…There is lack of consistent weights and measures in the market as a result traders benefit more than farmers and thus skewed the income distribution among players. In addition, coordination among agriculture value chain members is missing”. There is a need for better coordination among stakeholders, which would allow for promoting collective crop processing, packaging, branding,  marketing and strengthening market linkages nationally and regionally for farmers and thus facilitate crop branding and brand ownership and protection. Crop processors / Millers need to be able to work with larger groups of aggregated farmers who have a better quality product and higher volumes to offer. The millers and subsequently traders will therefore be able to reduce their costs both in the lower value chain stream and in the higher value chain stream.

## Sales of High Quality Products

According to BRITA I project (2007), aimed at expanding markets, developing linkages, securing reliable supply systems of quality raw products, and introducing appropriate new technology and improved hygienic conditions at the processing plants. The increased sales of value-added products produced in-country rather than exporting the raw products to foreign locations will lead to increased employment at the processing plants and lead to increased incomes for the farmer-owned as well as farmers providing quality raw products to the processing plants.

In addition the training of the apexes to generate their own income, ideas for charging a nominal fee for the business service providers on training with income going to the apex and associations a percentage of sales revenue from collective marketing activities to be retained by the apex association. This will encourage association members and other interested participants to value the training offered and put into practice once it is finished.

## Kamwene Village Community Profile

## Administrative Structure

Kamwene Village is one of 152 Villages in Kilombero District situated in Mlimba division, at Kamwene ward. Kilombero District is one among 7 District in Morogoro Region. It is about 97km from Ifakara town council which is district headquarters. Kamwene Village is one among 5 Villages in Kamwene ward which is in Mlimba division. It is located at southern part of Kilombero District headquarters and it is 97km apart. The Village administration structure is Village assembly (Village government), Village Council, Hamlet leaders (representatives). Leaders at Village level are Village chairman and the Village Executive Officer (VEO) whereby at the hamlet level the leader is the Hamlet chairperson.

## Demographic Features

The Village has 954 households. According to the 2012 statistic extracted from the village register, basing on the National census of 2002, the village has a population of 3490 people whereby 1492 are males and 1998 are females. The population distribution in the Village is as follows; Children (0-17YRS) were 1280 whereby female were 687 and males were 593. Adults who are in working force were 1157 whereby 516 were Males and 641 are females. The rest of the population about 1053 people are at the age of retiring from 60 years and above.

## Ethnicity

Ethnicity wise, the villages comprises of Luguru tribe, Ndamba, Pogoro, Sukuma, Hehe, Maasai, and wakinga. The most dominant tribs in the Village are Ndamba, Luguru, and Pogoro who are the native of the area. Other tribes are immigrant from neighboring regions due to economic activities especially the Sukuma people who came down with herds of flock to look for pastures but now they are settled doing both crop farming and animal keeping. For the case of religion, the area is dominated with Christians and Muslims and few people are traditionalists.

## Economic Activities

The people in Kamwene Village engage in different economic activities including; farming, Livestock keeping and small business. Agriculture employs more than 98% of the population (KDC, 2010). In arable farming food crops and cash crops are cultivated in the Village. Food crops which are cultivated are; Rice, Maize, banana, Sorghum, Sweet potatoes, palm, teak, Irish potatoes and beans.

The government through its extension officers has been encouraging Kamwene community to increase rice production by adapting Good Agricultural practices (GAP). Apart from food crops the Kamwene community engages in production of cash crops. The main cash crop here is cocoa which is cultivated in a very small scale. Many people in this village are also engaged in animal keeping. Animals which are kept in this village include cow, goat, sheep, pig, and poultry.

## Community Need Assessment

The researcher conducted Need Assessment (NA) through survey and desk review for Kamwene village community where by the villagers were involved in brainstorming of the economic situation of the community members followed with the discussion on the causes of such problems/needs. All needs were identified, prioritized and the community comes up with top 3 community needs as follows: The first need was processing plant for their paddy, market access for their rice and irrigation schemes for their rice farms. After prioritization of needs the researcher conducted a cause and effect relationship in order to design the appropriate project intervention.

Community Needs Assessment (CNA) is a process of identifying assets of the community and determining potential concerns that face a particular community in the respective locality. A community needs assessment in depth is a way of gathering information about a Community’s opinions, needs, challenges, and assets used to determine which project(s) will meet the real needs of the community. Kamwene Community Needs Assessment (CNA) was conducted adhering on this principle and its essence of conducting it at any community.

## Objectives for Community Needs Assessment (CNA)

The intention of the Community Needs Assessment (CNA) exercise was to disclose/unveiling the needs of the community as well as their challenges thereafter find the solutions for some critical identified challenges. Assumptions on any component seem to hinder the execution of the activity to combat the identified challenges were employed.

## CNA General Objective

The overall objective of this study is to generate information that can be used to come up with the project which can improve livelihood and income of Kamwene village community in Kilombero district

## Specific Objectives

- To identify characteristics of Kamwene village community in Kilombero district

- To assess the income level of Kamwene village community in Kilombero district

- To identify available resources for establishing paddy processing plant to improve community income

- To identify challenges which hinder development in Kamwene village community

## Research Questions:

- What are social and economic characteristics of Kamwene village community?

- What is the income level of Kamwene village community members?

- What are the available resources that can be used for establishing paddy processing machine in Kamwene village community?

## CNA Research Methodology

## Types and Sources of data

Primary and Secondary Data: Both primary and secondary data was collected for the study. The primary data was collected at the household levels, group leaders, warehouse/ milling machine operators, and village extension leaders.

Secondary Data: These type of data was collected from the published and unpublished documents from the farmers’ association offices, from apex offices, and warehouse information. Other sources was from organizations which are working with rice millers. Many information was obtained from the host organization which include project write up documents, project annual reports, and monitoring and evaluation report papers.

## Sources of Data

## Interview

Personal interview was conducted to the farmers in order to acquire information on the social and economic improvement, created employment opportunities and investment made by different investments in value addition projects.

## Questionnaire

Questionnaire was administered to the 40 respondents especially for the paddy farmers’ representatives who are the members of the Kamwene farmers’ community so as to get the real situation in the field. About 40 farmers’ households will form key respondents who have given the real situation of income status in the community.

## Focus Group Discussions

This method was used whereby Kamwene farmers’ community support officers who are also government employees at the village level were taken from different group making the total of 5 people. Then they were given instructions and discussed together and answer the questions which will be administered to them by the researcher.

## Observations

This was done physically to see the field which has been prepared by the community for erecting rice milling machine. This will was done by visiting the land which has been acquired from the Kamwene village government. This methodology was also used to see the amount of crops harvested in the due season by visiting the warehouses in Kamwene village and also a visit was made to see rice milling machine operations in other villages.

## Secondary Data Review

Here review were made on the official documents in the warehouses offices, review was done for other project documents related to value addition which have had successful accomplishment so as to get the best practice for learning.

## Primary Data

These types of data were collected directly from the field and through consultation with the key beneficiaries who are members of different rice farmer’s Associations.

## Research Design

The nature of the study is explanatory study, therefore, the cross sectional design was adapted as the ideal design. The reason behind this selection is that, the design allows the researcher to collect various data at single point in time and data collected at once from various respondents (Jamal, 2008). Apart from been economic way for the researcher it also avoided the tediousness approach to the respondents because they responded once and for all. Both qualitative and quantitative data were collected in which both secondary and primary data were collected from relevant sources. Primary data were collected directly from the rice producers, and rice traders.

## Sample Design

Sampling Frame: The sampling frame was formed by a total number of households in Kamwene Village focusing on the households engaged in the rice production. The total number of Kamwene villagers is 2,522, but numbers of people who are engaged in rice production in different categories are estimated to be 1,896. Out of this number of rice producers, 107 rice farmers will be purposively selected so as to obtain the number of household respondents/ rice farmers who are members of the Kamwene rice farmer’s community.  Therefore, the sampling frame under this study will be 107 farmers’ households who are members of the Kamwene rice famers’ community.

## Sampling Unit

The sampling unit in this study is the individual head of household. Key informants were interviewed here and this category was formed by the District Agricultural and Livestock officer (DAICO), District cooperative officer, District community Development officer and VEO. The sample size (key informants inclusive) that was selected and interviewed was 45 which is more than 90% of the frame. The respondent’s breakdown is as shown in table 1.1.

The probability sampling (simple random sampling and systematic sampling) was used in selection of the respondents, whereby it facilitated the researcher not to be biased when selecting the respondents at household level. However non probability sampling (Purposive sampling) was also used to select key informants and some of the respondents who are medium level rice growers (those owning from 5 acres and above)

## Sample size

The sample size was 40 respondents which were picked out of 50 total populations under study. Plus 1 DAICO, 2 Cooperative officers, plus 1 District community Development officer, plus 1 village extension officer making total of 45 respondents. The researcher will had a total of 45 respondents as a sample size.

To get the sample size of 45 respondents the following formula was employed

n =    		N

1 +N(e)2

N=total population, n=sample size, and e = rescission (error) source: Yamane (1967)

Breakdown of this sample size is shown in the table 1.1

Table 1.1: Sample Size

| Category | Sample Size |
| --- | --- |
| Household representatives from one village | 40 |
| DAICO | 1 |
| Cooperative officers | 2 |
| District Community Development officer | 1 |
| Village extension officer- Kamwene village | 1 |
| TOTAL | 45 |

Source: Field study 2017

## Data collection Methods

In this study both secondary and primary data were collected. Distinction was made in data collection methods and tools between secondary and primary data.

## Secondary Data

These are readily available data/information in the particular/ intended office. These data were collected through documentary review method, in which, the abstract from different reports, books, pamphlets, and Journals were executed.

## Primary data

These are the data which were collected by the researcher directly from the respondents who selected through the determined sampling procedures. Interviews guided by the tested questionnaires will be used in soliciting and collecting primary data. The following methods and tools will be used in the exercise.

## Interview Method

This method was effectively used in primary data collection. The researcher solicited the in-depth data/information from the respective respondents here mainly the rice farmers’ households by using questionnaire as a main tool. Semi-structured and unstructured questionnaires were used in extracting data from the respondents through series of designed questions. This tool was useful in collecting data from the respective officers at the District, ward, and village level as well as to the household respondents.

## Focus Group Discussion

This method was used in collecting data/Information from small groups of 5 to 7 participants. All groups were involved in the exercise (women and youths in particular). Under FGD participants were given chance to discuss on various issues which are hindering development in their village and they designed strategies to overcome income poverty in their community. The researcher facilitated the discussion by using arranged checklist/guiding questions which helped the researcher to arrange and conduct the discussion in logical order. This method seemed to suit the village officials who seemed to be used more to checklist and unstructured questionnaires.

## Observation Methods

The primary data were collected by looking or observing physically on the phenomena under study. In this case, fields, planted Rice, bags of rice stored in the warehouses (because it is a harvesting season), rice which is stored in different milling machines, and physical development activities prevailing in the village will be observed and photographed.

## Data Processing

In data processing (what did you do in data processing?), computer facilities was used, which includes special programme like Microsoft Excel and SPSS 11.5. In data presentation the results of the research will be presented by using combinations of graphs, tables, and equations. Data were analyzed by using SPSS 11.5 computer programme; other alternative programme will include Microsoft Excel which will assists in making more clear charts and graphs for different volumes of rice produced in consecutive years, size of farms cultivated by different villagers and amount of income earned by each. It will also make clear the figures of rice sold processed against the paddy which was sold unprocessed and the income earned by each category.

## Findings of the Participatory community Assessment

## Respondents Characteristics

## Gender of Respondents

Gender of the respondents was more skewed in the side of female. We had more female who responded to our interview about 53.7% than male who are about 45%. This might be caused by social characteristics for the community where as during this off season in the morning women are always at home while men work up and go out to seek other income earning activities. However during farming season it has been observed to be different, whereas women work up early in the morning to go and work in the family farms.

# Table 1.2: Gender of Respondent

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Male | 18 | 43.9 | 45.0 | 45.0 |
|  | Female | 22 | 53.7 | 55.0 | 100.0 |
|  | Total | 40 | 97.6 | 100.0 |  |
| Missing | System | 1 | 2.4 |  |  |
| Total | 41 | 100.0 |  |  |

Source: Field study 2017

## Age of respondents

Old age seems to dominate more in agriculture with 29.3% of respondents were aged between 68 years and above. According to land tenure of this area this age category of seniors is the one which mostly owns the land, and the one with the say on the produce which have been obtained from the land.

Table 1.2: Age of Respondent

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | 18-28 | 4 | 9.8 | 10.0 | 10.0 |
|  | 29-38 | 6 | 14.6 | 15.0 | 25.0 |
|  | 39-48 | 11 | 26.8 | 27.5 | 52.5 |
|  | 49-58 | 6 | 14.6 | 15.0 | 67.5 |
|  | 59-68 | 12 | 29.3 | 30.0 | 97.5 |
|  | 68 and above | 1 | 2.4 | 2.5 | 100.0 |
|  | Total | 40 | 97.6 | 100.0 |  |
| Missing | System | 1 | 2.4 |  |  |
| Total | 41 | 100.0 |  |  |

Source: Field study 2017

## Marital Status of Respondents

Most of farmers are married people who are leading in number according to pie chart bellow. Single people who are involved in agriculture seems to be very few compared even to widow and widower

# Figure 1.1: Marital Status of Respondents

Source: Field study 2017

## Income of Respondents in 10,000’ Tshs per year

Most of respondents are farmers whose majority seem to be more between those who have an earnings of  Tshs. 85,000/= Those with earnings below 25,000/= seem to be very few  below 5. Those with higher income are found among the farming community as per bar chart below. This gives reason for high potentials available in agriculture and agro processing hence more investment in agro processing is still viable. The income level for respondents whose major economic activity is non agriculture seems to be very low below 2.

# Figure 1.2: Income of Respondents

Source: Field study 2017

## Education Level of Respondents

Education level of respondents seems to be skewed more towards primary level. More than 70% of respondents hold primary education with few 17.1% with secondary education level. While the rest of education levels are below 1% as shown in the table below. This shows that there is a large gap between agriculture and education level. In Tanzania for decades agriculture has been regarded as an endeavor for non-educated or for those who failed in education. This has a big impact on decision making on the issues regarding agribusiness and agricultural investment. So the project will concentrate more in knowledge provision to farmers

# Table 1.3: Education Level of Respondent

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Primary School | 29 | 70.7 | 72.5 | 72.5 |
|  | Secondary school | 7 | 17.1 | 17.5 | 90.0 |
|  | High School | 1 | 2.4 | 2.5 | 92.5 |
|  | 6 | 3 | 7.3 | 7.5 | 100.0 |
|  | Total | 40 | 97.6 | 100.0 |  |
| Missing | System | 1 | 2.4 |  |  |
| Total | 41 | 100.0 |  |  |

Source: Field study 2017

## Available Resources for Establishing Paddy Processing Plant to Improve Community Income

This study found that Kamwene village community has different resources at their disposal which can be used for establishing paddy processing plant to improve community income. The available resources which were identified by means of eye observation was the land/ plot for construction which was provided by the village government as their contribution towards the establishment of the project, human resources from the village community which will be/ is being used for construction of the house for installing machine, Kamwene village is endowed with stones which are used for construction and for making aggregates, sands for construction and storage facilities which are also offered by the village government.

## Challenges Which Hinder Development in Kamwene Village Community

The main critical issues in Kamwene Village were found to be the following:-

Prevalence of income poverty to many households: There is income poverty within the community which affect majority in different ways, low prices for the farmers’ produces; this has been a threat to majority within Kamwene community.

The presence of middle men who passes among farmers dishing out loans which in turn farmers will repay paddy which is raw material in terms of 1 bag of crop in return for each 20,000 Tshs: Currently, another critical issue especially during farming season is the presence of middle men who passes among farmers dishing out loans which in turn farmers will repay paddy which is raw material in terms of 1 bag of crop in return for each 20,000 Tshs which was received by each farmer. By establishing rice processing project these farmers will no longer sell raw material but rather finished goods which will increase their income and these middle men will have no room for exploiting smallholder farmers. The importance of value addition was assessed and the results were as reported in the table below:-

# Table 1.4: Importance of Value Addition Project in the Community

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Yes | 37 | 90.2 | 92.5 | 92.5 |
|  | No | 3 | 7.3 | 7.5 | 100.0 |
|  | Total | 40 | 97.6 | 100.0 |  |
| Missing | System | 1 | 2.4 |  |  |
| Total | 41 | 100.0 |  |  |

Source: Field study 2017

## Selling of Raw Paddy than Finished Product/ Rice

The number of farmers who do sell raw material was found to be higher than those who process and sell finished goods as per table below. This shows that more than 70% of farmers in Kamwene village sell raw paddy. It means that the one who benefit from the big profit share of the market which is available at the upper value chain stream is the rice dealers, rice traders who are mostly millers and final sellers who include street kiosks, super markets, and mini super markets.

# Table 1.5: Do You Sell Your Paddy Before or After Adding Value?

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Before adding value | 28 | 68.3 | 70.0 | 70.0 |
|  | After adding value | 12 | 29.3 | 30.0 | 100.0 |
|  | Total | 40 | 97.6 | 100.0 |  |
| Missing | System | 1 | 2.4 |  |  |
| Total | 41 | 100.0 |  |  |

Source: Field study 2017

Rice market at the regional level has deteriorated because of the government policy of imposing export ban on maize, rice and other staple foods. This also caused internal / local market to deteriorate because most of sellers depends on Dar es salaam market as the only big market ata the national level. According to finds in this pie chart below, Dar market seems to occupy more than 25% of the whole markets. It means ones Dar market has flourished by crops to the extent of dropping the crop price the same situation can spread to other crop markets in the country.

# Figure 1.3: Market Problem

Source: Field study 2017

## Minimal Access to Credit

The researcher conducted Focus Group Discussion (FGD) which involved Village Executive Officer (VEO), Community development officer, and village extension support officer who gave their views that among other problems, access to capital has been identified as a constraint by smallholder farmers, millers, traders, agro-input dealers, and providers of mechanized services to formalize and grow their businesses.

The needs range from working capital, for example to accommodate and manage larger volumes of paddy for milling and trading, to capital investments for rehabilitation/upgrading/expansion of storage, milling machines and purchase of machineries for mechanized harvesting. Increased financial inclusion can also assist farmers’ associations to collectively purchase in bulk inputs and services at more competitive prices and negotiate better prices for their outputs.

## Community Need Prioritization

In the community needs assessment exercise, Kamwene community came up with various projects/needs which if fulfilled would be in the income and living standard in the community could be better and income poverty would be reduced for their suitable livelihood. However, the community had to do various strata of prioritization exercise so as to come up with a reasonable decision on what to implement first. This important step was done in Focus Group Discussion. The exercise was conducted by using the Pair wise Ranking Matrix techniques as it is shown in the Table 1.6.

# Table 1.6: Pair Wise Ranking Table

| NEEDS | Livestock keeping | Agriculture crop value addition | Poultry keeping | Fish keeping | Water project | Input selling | Health project | TOTAL POINTS | RANK |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Livestock keeping |  | Poultry keeping | Water project | Input selling | Health project | Agriculture crop value addition | Agriculture value addition | 1 | 7 |
| Agriculture crop value addition | Agriculture crop value addition |  | Agriculture crop value addition | Water project | Agriculture crop value addition | Agriculture crop value addition | Poultry keeping | 13 | 1 |
| Poultry keeping | Agriculture crop value addition | Water project |  | Livestock keeping | Health project | Agriculture crop value addition | Health project | 3 | 5.5 |
| Fish keeping | Livestock keeping | Health project | Livestock keeping |  | Agriculture crop value addition | Agriculture crop value addition | Poultry keeping | 3 | 5.5 |
| Water project | Health project | Water project | Water project | Poultry keeping |  | Input selling | Health project | 5 | 3 |
| Input selling | Fish keeping | Agriculture value addition | Health project | Fish keeping | Input selling |  | Agriculture crop value addition | 4 | 4 |
| Health project | Water project | Input selling | Livestock keeping | Health project | Agriculture crop value addition | Fish keeping |  | 6 | 2 |

Source: Field study 2017

# Figure 1.4: Community Members Making Follow Up of the Prioritization Exercise

Source: Field survey 2017

During household survey which was done with questionnaires which were administered at household level, the farmers mentioned several projects in Kamwene village community. They mentioned eight projects which are necessary for reducing poverty in Kamwene village as they are indicated in the table bellow:-

# Table 1.7: Proposed Projects That They Are Real Community Needy In Kamwene Village?

|  |  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- | --- |
| Valid | Rice value addition project | 23 | 56.1 | 57.5 | 57.5 |
|  | Animal keeping project | 9 | 22.0 | 22.5 | 80.0 |
|  | Agriculture | 2 | 4.9 | 5.0 | 85.0 |
|  | Poultry keeping project | 1 | 2.4 | 2.5 | 87.5 |
|  | Fish keeping | 1 | 2.4 | 2.5 | 90.0 |
|  | Water Project | 2 | 4.9 | 5.0 | 95.0 |
|  | Input selling project | 1 | 2.4 | 2.5 | 97.5 |
|  | Health project | 1 | 2.4 | 2.5 | 100.0 |
|  | Total | 40 | 97.6 | 100.0 |  |
| Missing | System | 1 | 2.4 |  |  |
| Total | 41 | 100.0 |  |  |

Source: Field study 2017

By using the same tool the community issues were listed and prioritized by starting with one that seemed to have more people as shown above. As per priority table above, rice value addition seemed to have more scores than any other issues which were raised up by farmers.

## Chapter Conclusion

Farmers in Kamwene village community have managed to identified and prioritize their needs which they think that by addressing such need they it can contribute in reducing income poverty in the village. Different strategies have been mentioned in the narrative part of the chapter that can work in addressing the community problem in Kamwene village. By using such strategies and methodologies the project will be successful. The farmers in Kamwene have already acquired a piece of land for establishing the project. The early stages of digging foundation have started by using man power from the village community.

# CHAPTER TWO

# 2.0 BACKGROUND TO THE RESEARCH PROBLEM

Leave alone rice processing, crop value Crop processing in Tanzania has been a problem in Tanzania for few decades especially after the collapse of processing industries which were established in early 1970s and late 1980s. During trade liberalization era, most of these processing industries/plants after collapse were sold to private investors who were running them in joint venture with the government and others solely as their properties. Some of investors turned some industries in to go downs in which they stored imported goods from other countries. This was a time when Tanzania as country started falling in the levels of world industrialization rates because most industries were dormant and others died completely. Many studies have been conducted on crop processing but none of them has touched how rice processing can contribute in reducing income poverty in the community.

The Government of Tanzania is propagating the idea of industrialization of Tanzania especially in the agro-processing but according to the findings of this study, it has been found that most of farmers are still selling raw material instead of selling finished goods. This shows that there is a need for having agro processing plants in this village.

# Statement of the Problem

Rice producers in Tanzania are facing a lot of challenges like absence of reliable supply of inputs, using fake inputs, land crisis because of absence of land use plan, dependence on rains, absence of crop marketing technology, absence of reliable public owned warehouses, expensive farm mechanization costs, few and non-reliable crop processing industry, packaging and absence of crop brand for Tanzanian farmers especially small holder farmers. Since the farmer has no inputs he/she gets very small yield per acre and the quality that is obtained is also poor. These entire challenges force farmers to sell raw paddy earlier after harvesting or within the farm before harvesting so that he/she can get money earlier so as to solve his/her issues, hence contributing to their poverty circle. This study aims at going further to see.

According to Katto T (2013), REPOA in their research on impact of agricultural input subsidies on poverty in Tanzania, it stipulates areas of success where input subsidies contributed in increasing productivity by timely delivery of inputs to farmers. The study also shows the negative side where the input voucher system had failed by sometimes being grabbed by larger farmers who were not targeted by the program. Again this study does not show how was that increase in yield was turned into money, the money which in turn was used for development of the smallholder farmers.

Increase in maize and rice does not mean that automatically that amount which has increased will have processing facility so as to fetch a good price in the market. According to the findings of this study rice farmers have increase yield per acre because to much support through business linkages with input suppliers and other service providers. This study aims at going further and sees how an increase in yield can increase the smallholder farmers’ income by establishing processing project which will help farmers to add value to their produce.

Some of researches have been conducted so as to help farmers come out of poverty. The outstanding one is the one by REPOA (2010) which looks at different agricultural systems and assess the income poverty level of the farmers who are practicing those systems. This research by REPOA did not find out which is the best investment subsector that can contribute in poverty reduction among smallholder farmers. The aim of this study is to test whether investing in value addition will be able to reduce poverty in Kamwene village community and at which rate.

Research which was conducted by Sarris A, Savastano S and Christiaensen (2006) looked at the role of agriculture in reducing poverty in Tanzania, exploring how farm productivity affects poverty and how various factors including market affects farm productivity. They found that the poor farmer possesses fewer assets and they are much less productive. This study will go extra mileage to see how we can reduce poverty of farmers by encouraging them to add value for their produce instead of selling raw paddy.

In the process of identifying and prioritizing different projects for supporting Kamwene village community, rice processing was project for the farmers’ was given the highest priority in the scale of priorities. Kamwene farmers normally sell their paddy freshly without adding value. In this case the buyers take advantage of value addition cost in bargaining for low price to farmers. Again by selling raw paddy the farmer cannot bargain the price of the by product which is obtained from paddy processing like rice bran which is also sold as animal feed. Unlike Mbeya rice, Kilombero or Morogoro rice has no recognition in the crop market of Tanzania. The project will also seek technical advisory for branding Kilombero rice so that it can come out as Kilombero rice. In this sense, Kamwene village community earmarked this problem as central and it needs quick action for solution. Hence the researcher has designed the project proposal for establishing rice milling machine/ milling plant at Kamwene village.

# Project Description

The project “Improved Community Income and livelihood through rice value addition by establishing rice value addition project in Kamwene village community Kilombero district Morogoro region” will operate in supporting smallholder rice farmers in value addition, training on financial literacy and other support to smallholder farmers. The project will be situated in Kamwene village, Kamwene ward which is located in South Kilombero near Udzungwa mountain national park few kilometers from Mlimba TAZARA station in Kilombero district Morogoro region.

The project will be executed by groups of smallholder rice farmers who will join the rice value addition project through their shares which will be sold by the project. Shareholders will choose their own board which will be managing project activities on behalf of the shareholders. The day to day activities will be managed by the project executive committee. This executive committee will be appointed by the board so that when they underperform they can hold them responsible.

# Target Community

The project is targeting smallholder rice growers in Kamwene village. The study has found that smallholder rice farmers need to be capacitated in value addition so that the good quality of rice which they are producing it can be processed and sold by farmers directly without passing through the middle men who normally take a large share of the sales profit. The study has also shown that in order to have high quality rice farmers need also to have good and quality value addition machinery. This rice value addition project has been prepared to solve the problem of unreliable rice value addition plants which are found in Kamwene village and it is expected that having this project will help farmers to mill high quality rice and ultimately they will obtain rice market easily.

# Stakeholders

The rice value addition project complies to the decision of Kilombero District council (KDC) which have decided to promote rice farming as both cash and food crop for the district. All district agronomists from the district to the village level are promoting the method of increasing rice yield called System of Rice Intensification (SRI). Through SRI farmers in the district have managed to increase yield from 10 to 15 bags of 100kgs (District productivity report 2010/2011), to 28 to 32 bags of 100 kg per acre (District productivity report 2015/2016).

The project is expected to work in a close collaboration with the District Agricultural, Irrigation and Cooperative officer (DAICO), ward and village level extension support officers, rice farmers’ associations, Village leaders, village development committee and other stakeholders who will be interested to support the project like the rice transporters who will be transporting rice from Kamwene village to the market. Tanzania and Zambia Railway Authority (TAZARA) Mlimba station will be major stakeholder for transport to ensure that in case of large consignments they are reaching markets early and easily.

# Project Goal

The project goal is to improved community income and livelihood through promotion of rice value addition by establishing rice value addition project in Kamwene village community in Kilombero district Morogoro region. This rice value addition project will help Kamwene village in reducing poverty because it will offer market for farmers’ produce, it will create employment among the rice milling machine operators, rice feeders, those who will be drying rice, loading and unloading labors and food vendors

# Project Objectives

# General Objective

To reduce household income poverty and improve livelihood by establishing rice value addition project in Kamwene village by 2018.

# Specific Objectives

- To train 40 Kamwene farmers’ association members on rice value addition by June, 2018

- To acquire land for building an office and for installing paddy processing machine by July, 2018

- To purchase 1 rice milling machine by September, 2018

- To link Kamwene farmers’ asoociation members and market by November, 2017.

# Host Organization CBO

The host organization for this project is Kamwene village council. The village is located in Kamwene ward in Mlimba division Kilombero district. Kamwene village is one of the villages which were established emergently after Ujamaa and self reliance through MFUMAKI village development program. The village is lead by village chairperson and the village executive officer (VEO). The village has a village council which has representatives from all hamlets in the village. This committee co-works with the chairperson and the VEO advising them on various issues of development.

This committee is lead by the village chairperson. Within the village council there is a Village Development Committee (VDC) which advises the village chairperson on the issues of development alone. In the advent of this project the VDC formed a committee of 7 people in which 4 are women and 3 are men to form a steering committee and these will be the front runners in implementing this project. The steering committee is supposed to work in a close collaboration with village council and the rice farmers’ associations/groups in the village.

# Organization and Management of Day to Day Activities

The host organization for this project is Rural Urban Development Initiatives (RUDI) in collaboration with Kamwene Village Government in which Village Council have been vested the day to day activities which will be conducted on behalf of the Village government. Village government leaders are Village chair person and the Village Executive Officer (VEO) who is the secretary of the Village government. The Village Development Committee (VDC) also is led by the Village chair person and the VEO. The VDC members have enormous activities/duties, from among them are as follows;-

- Planning: All local government plans are initiated here

- To ensure peace and harmony within the Village

- To ensure that community members participate into different development activities

- To ensure availability of different social services within the Village such as Education, water, Health services and Roads

- Formulation and implementation of different plans and projects to be executed within the Village

- Conducting different meeting in the village

- Supervision of different projects intervention within the village

- Overseer of all activities undertaken by different CBOS and organization within the Village

- Emphasizing formulation of different Community Based Organizations

- Composing by laws and monitoring its implementation

# Host Organization Leadership

Kamwene village is lead by village chairperson and the village executive officer. Under these village leaders there is a village council whose members are advisors of these two leaders. For the sake of rice value addition project there is steering committee which works in collaboration with the village council. The steering committee has its chairperson, vice chairperson and secretary. In total the steering committee has 7 members

# Vision of the Host Organization

To be an outstanding village in bringing development, self-reliance and good live to the village natives through improved agriculture and animal husbandry.

# Mission of Kamwene Village council

Kamwene village council intends to become an organization of choice in serving its citizens through social and economic services provision so that the people may have a good income and live a better life.

# Kamwene village Council Organization Structure

Kamwene village council leaders have a responsibility of implementing day to day village activities. The village assembly meets once per year in their Annual General meeting (AGM) , but they can meet at any time when demand arise for addressing different issues which needs village general assembly. Under village chairperson we have different committees which advises the village chairperson on different issues

# Figure 2.1: Administration structure for Kamwene Village

Source: KDC (2011)

# Analysis of Strength, Weaknesses, Opportunities and Challenges for Kamwene Village

The researcher conducted SWOC analysis for Kamwene village council to identify internal and external variables which can be used and adhered to during project implementation. SWOC consists of “Strength” which is the internal variable which is value that can be used by the community in implementing the project; make the project successful and sustainable. “Weaknesses” are also internal variable which is vise and it can impede the project implementation and impede project sustainability. Opportunity is an external value which originate outside the community but it can be accessed and used to make the project successful while challenges are external variables which are vises, although they do not originate within the community but still they can damage the project.

Table 2.1:  Analysis of the Situation of the Host Organization

| S/N | STRENGTH | WEAKNESSES | OPPORTUNITIES | CHALLENGES |
| --- | --- | --- | --- | --- |
| 1. | Presence of village extension officer | The extension officer is doing veterinary, meat check up and agronomical activities. | -Farmers have managed to increase yield -Trained Project steering committee | Sometimes he is given responsibility to serve other villages |
| 2. | The VEO is a employed by the government | He is over tasked by other village activities like health, education, MCH, and natural resources | Always available for the community works | His salary is not good to motivate him. |
| 3. | Availability of land for the project | The individual community members may lack ownership of the land | The land is easily accessible by any kind of transport | The land has not been surveyed. |
| 4. | Good village leadership | Leaders have no any material or immaterial motivation | Ward and division leaders have committed themselves to support the project | Leaders are coming from different political parties |
| 5. | Good geographical location near the main road | No any premise so far | Building materials are available in the village prior to approval by Village Natural resources committee | The road is poorly maintained |

Source: Findings by the researcher

The Strength, Weaknesses, Opportunities and challenges for Kamwene village council as identified and listed in Table 2.1.

# The roles of CED Student in the Project

The student’s main responsibility in the project will be to ensure that all planed project activities are implemented as per project schedule. In this sense the student’s activities will be the following:

- Provision of technical support to all smallholder rice farmers groups in the village

- To facilitate business to business meeting between farmers and machine/equipment suppliers for acquiring rice processing machine

- To facilitate contract signing between farmers and different service providers

- To facilitate training to village community members on management, operation and maintain the project equipments.

- To facilitate market linkage between smallholder rice farmers’ groups and reliable markets in Dar es Salaam, Dodoma and other parts within and outside the country.

- To participate in and ensure participatory project monitoring and evaluation

- Participate in all project meetings that will be convened

# The roles of the Host Organization

- To coordinate all project stakeholders in the community

- To ensure that the project complies with the village by laws and government regulations in general.

- To attend required trainings

- To spearhead the community sensitization activities as planned by the project

- To participate in resource mobilization for obtaining funds for the project

- To ensure safety and security for the project

- To manage the project portfolio for the whole project life

# Chapter Summary

We have presented study findings in this chapter; it shows that there is an extreme poverty among the faming community. Again the aging generation is the one which is interested with agriculture. In analyzing Tanzanian situation agriculture sector is the sector which when you are working there one has to be dirty, one has to work in a heavy sunny day and rainfall. That is why it is regarded as a preoccupation for the elders and women. Young people who are engaged in agriculture are those for who have nothing to do at home or in the street and they do not have anything to do. Value addition has been found as an important project which can contribute in reducing poverty among farmers.

# CHAPTER THREE

# LITERATURE REVIEW

# Introduction

This section gathers readings from different sources which studies the same issues which are related to this subject matter which is studied in this research. In the first part of this section we are provided with an overview of the objectives of rice sub sector in general, support to agricultural processing activities and how agriculture commercialization needs investment in agro processing. The second part provides advantages which accrue from rice production and processing sector, followed by the sustainability measures for these supported projects. The last part is the recent policies and programme and how they have impacted on rice agribusiness.

In this chapter we will be presented with different readings from different studies and writers who have worked in rice subsector concerning the part of value addition and rice marketing in general. So many people have written about rice production, agronomical services provision, finances and other support services in the rice sub sector.

# Definition of Some Important Concepts

# Paddy Rice

According to Greek wise dictionary (2016); Paddy rice is the individual rice kernels that are in their natural, unprocessed state. Sometimes referred to as rough rice, it is harvested directly from rice fields or paddies and transported to a processing site. As part of the processing, the protective hull is removed, leaving only the actual rice kernel for consumption.

# Commodity Exchange Market

This is a marketing platform which is made up with well-established hardware infrastructure as well as software infrastructure that can enable trading of a certain commodity at a given time. Tanzania mercantile exchange is one good example for commodity exchange market. According to Ultimate guide to Commodity exchange (2015); A commodity exchange is an organized, regulated market that facilitates the purchase and sale of contracts stipulating the delivery of commodities, such as Brent Crude oil or corn, at a future date decided by the involved parties and subject to rules agreed by members and management of the exchange. A commodity exchange market may also be used to sell contracts for financial instruments such as Eurodollars or U.S treasury bills

# Empirical literature Review

# Rice Consumption Trend in Tanzania and Africa

Rice is the fastest growing food source in Africa. Demand for rice in East Africa Community (EAC), has been growing in recent years and far outstripping the population growth. This trend is predicted to continue for the next years.

According to Kilimo Trust report (2014) consumption of rice in EAC grew at an average rate of 4% per annum over the ten year period to 2012, a trend projected to continue in the foreseeable future.  The increase is driven by: i) increasing population, ii) growth in demand by expanding middle income class- willing to pay for the convenience provided by storage and cooking characteristics of rice compared to traditional staples; and iii) increasing consumption by producers themselves.  Rice demand in the EAC region exceeds supply, USD 500 million per annum spent on rice imported into EAC market indicate an opportunity for rice market in the    region.

Tanzania is the second largest producer of rice in Southern Africa after Madagascar with production level of 1.9 million MT (MALF statistics 2014).  Tanzania accounts for 65% of the total rice produced in East African Region. Rice subsector is among the major sources of employment, income and food security for Tanzania. About 94 % of the rice grown in Tanzania is produced by smallholder farmers. Currently Tanzania rice consumption stand at 1.18 million MT (Kilimo Trust 2014) indicating an exportable surplus of more than 0.7 million MT under current farming conditions.

The current trajectory of recent developments in the rice industry in the EAC community, points to increasing interest among stakeholders in entrenching the rightful place of rice, in contributing towards food and income security agenda of the region. This is consistent with strategic food security policies of these countries that have traditionally and gradually regarded rice both as a food and an essential cash crop and in varying degrees. However, self-sufficiency in rice prospects of the region are further complicated by processes of urbanization, income growth and rapid increase per capita consumption that have pushed the conventional production limits of most of the EAC countries including Tanzania, the biggest producer of rice in the region.

# Rice Growth in East Africa and Tanzania

Rice is the fastest growing food source in Africa. Demand for rice in East Africa Community (EAC), has been growing in recent years and far outstripping the population growth. This trend is predicted to continue for the next years.  According to Kilimo Trust report (2014) consumption of rice in EAC grew at an average rate of 4%per annum over the ten year period to 2012, a trend projected to continue in the foreseeable future.  The increase is driven by: i) increasing population, ii) growth in demand by expanding middle income class- willing to pay for the convenience provided by storage and cooking characteristics of rice compared to traditional staples; and iii) increasing consumption by producers themselves.  Rice demand in the EAC region exceeds supply, USD 500 million per annum spent on rice imported into EAC market indicate an opportunity for rice market in the region.

Tanzania is the second largest producer of rice in Southern Africa after Madagascar with production level of 1.9 million MT (MALF statistics 2014).  Tanzania accounts for 65% of the total rice produced in East Africa Region. Rice subsector is among the major sources of employment, income and food security for Tanzania. About 94 % of the rice grown in Tanzania is produced by smallholder farmers. Currently Tanzania rice consumption stand at 1.18 million MT (Kilimo Trust 2014) indicating an exportable surplus of more than 0.7 million MT under current farming conditions.

Rice production in Kilombero district has been emphasized since 1970s during villagization era when several Ujamaa villages were established in Kilombero district and the following wards were the early adapters:-  Kidatu, Msolwa,  mang’ula, Kiberege, Mlimba and Utengule mainly using local rice breed. Then new improved rice varieties were introduced with the establishment of Katrini Agricultural Research Institute. With Katrini new varieties have been introduced and adopted by farmers like the SARO 5 or TXD 306 were introduced. Few farmers adopted early in the same year while others were slowly adopting it. Having seen the success from the precede farmers, currently, many farmers are engaging in rice the production using improved seeds like Nerika and TXD306.

Rice production in Kilombero district goes hand in hand with other crops like Sunflowers, maize, sorghum, cassava, cocoa, teak, common bean and coconut and palm. The government is emphasizing Rice production throughout the District in all areas where rice can be grown so as to contribute in their income at household level as well as contributing to district income through cess tax which is levied on each bag of paddy which is harvested by famers.

Under the needs assessment exercise, the researcher will use various methods to gather data and information from the community, these are: Interview, Focus Group Discussions (FGD), Individual key- informants, abstraction of different reports, previous research reports, and observations on the particular phenomena.

# Rice Market Overview

Rice markets internationally, and locally, are becoming increasingly segmented by quality. In main rice consuming areas of Tanzania and other countries of EAC, strong demand exists for aromatic and high quality rice. High quality rice, in Tanzania, can be characterized as rice with a low percentage of broken rice, young rice, with relatively long kernels which are transparent in color, with not more than 13 percent moisture content, absence of stones and which possess a strong aromatic smell.

There is growing demand for rice from Tanzania’s major markets. The demand   by urban medium high consumers is increasing for quality and branded aromatic rice, which is primarily produced in Tanzania. Likewise most neighboring countries have rice unmet demand, which makes the regional block a highly attractive market if efficient supply chains are developed. Tanzania has established Commodity exchange market for selling different commodities through auctioning (TMX). The process for establishing this market started like 5 years ago but it has officially opened the doors ready for operation this year. Since TMX is more interested with processed, and packed commodities, with this rice processing project farmers can be sure that they can trade their rice in the TMX

# Added Advantage for Tanzania Production and Trade on Rice

The opportunities for increasing  Tanzania rice production and trade are: i) Availability of land (21 million Ha) suitable for rice and abundant water resources (underground, rivers and lakes) for irrigation; ii) Availability of seed production ventures and seed certification systems (conventional and community based); iii) 18% of the agricultural households are engaged in rice production; iv) Political will of the Government to enhance production and productivity of rice; and v) Suitable policy environment such as exemption of taxes on agricultural inputs and farm machinery and vi) Increasing rice demand in the region.

Despite these opportunities Tanzania rice remain less competitive in the regional markets due to poor quality and more expensive as a result of high cost of production, lack of known brands despite having aromatic varieties and high market costs that make it more expensive over imported Asian rice. Furthermore, rice trade in the region is lacking well connected linkages and strong business to business relationship for handling Tanzania rice:- High cost of production and poor quality of Tanzania rice is attributed to the following issues:

# Inadequate Quality Harvesting

Farmers fail to harvest at optimum maturity and use inadequate/inappropriate tools, resulting in losses at each step (harvest, drying, hand-threshing, storage in the home). Limited availability of mechanized harvesting service providers combined with fragmented cultivation practices, prevent farmers from using mechanized harvesting.

# Poor Post-Harvest Management Practices

Limited availability of storage due to inadequate number, poor constructed, poor management of warehouse facilities and insufficient access to capital to construct or upgrade/ rehabilitate storage facilities are other key issues. Even rice that is stored in a warehouse is susceptible to postharvest losses as facilities are of low quality, particularly due to a lack of good hygiene including cleanliness and lack of standard food safety measures. With regards to harvest and postharvest management practice, mixing of seeds and rice varieties is a challenge in terms of quality and standardization.

# Processing Challenges

Millers largely act as service providers and majority operate single-pass machines, which do not have cleaning, de-stoning, sorting, or grading facilities. Millers are rarely involved in grading, branding, and marketing of the rice produced in their mills. Milling produces a large amount of broken rice, resulting in up to 50% lower yields post-grading. While a market for broken or lower quality rice does exist, revenues are not high enough to cover losses due to reduced yield of graded rice after the milling and grading process. There is lack of awareness to smallholder farmers, millers, and traders on EAC and international standards and grades to compete with imported rice.  Rice produced is usually of mixed varieties and quality, which occurs due to a variety of reasons including mixing at various stages from planting, using mixed seeds, mixing at harvesting, mixing at collection stage, mixed storage, and practices at the milling and post-milling stages.

# Lack of Known Brand and Branding Strategies at All Rice Value Chain Nodes

As a result neither farmers nor millers are working towards branded rice that may fetch premium prices to farmers/millers and also   prevent blending that has been happening. Traders from larger urban markets purchasing in the proposed project area expect lower quality and low prices versus paying a premium for high quality rice produced in other regions of the country such as Mbeya. This aspect reduces incentive for grading and improving quality of produce as well. Furthermore, there are problems with standardization. There is lack of consistent weights and measures in the market as a result traders benefit more than farmers and thus skewed the income distribution among players.

In addition, coordination among rice value chain members is missing. There is a need for better coordination among stakeholders, which would allow for promoting collective marketing and strengthening market linkages nationally and regionally for farmers and thus facilitate rice branding and brand ownership and protection. Millers need to be able to work with larger groups of aggregated farmers who have a better quality product and higher volumes to offer. The millers and subsequently traders will therefore be able to reduce their costs both in money and time.

# Unstructured Trade and Inadequate Market Linkages

Rice trade in EAC from Tanzania normally is traded in small volumes through informal cross border trade as well as formal trade.  The small volumes add cost to the cost of transaction and finally the cost of rice. Well-functioning market require a multi-pronged approach that tackles intermediary markets, information, awareness and trust in contract agreements among value chain actors in the region. Strong business and structures to handle rice business is needed for rice subsector growth and and thus allow optimum contribution to reducing poverty as well as improving food security.

# Minimal Access to Credit

Access to capital has been identified as a constraint by smallholder farmers, millers, traders, agro-input dealers, and providers of mechanized services to formalize and grow their businesses. The needs range from working capital, for example to accommodate and manage larger volumes of paddy for milling and trading, to capital investments for rehabilitation/upgrading/expansion of storage, milling machines and purchase of machineries for mechanized harvesting. Increased financial inclusion can also assist farmers’ associations to collectively purchase in bulk inputs and services at more competitive prices and negotiate better prices for their outputs.

# Unfavorable Business Enabling Environment

Trade of rice in the EAC is facing present and future Tariff and non-tariff barriers to free trade despite of ratified protocols among the EAC countries. The Action will work with national and the Regional respective organization in finding lasting solution to the current and future issues that seem to affect free trade. As a result of the above factors, Tanzania rice export in EAC market has remained low. According to FEWSNET, EAGC and RATIN (2012), Tanzania exported 76,260 MT of rice to neighboring countries (Rwanda, Burundi, Uganda, Kenya and DRC). With the rapidly growing demand for rice in East Africa, Tanzanian farmers can increase volume of rice trade in the regional market through increased quality rice production and improved structured rice market.

# Sales of High Quality Products

BRITA I project (2007), aimed at expanding markets, developing linkages, securing reliable supply systems of quality raw products, and introducing appropriate new technology and improved hygienic conditions at the processing plants. The increased sales of value-added products produced in-country rather than exporting the raw products to foreign locations will lead to increased employment at the processing plants and lead to increased incomes for the farmer-owned as well as farmers providing quality raw products to the processing plants.

In addition the training of the apexes to generate their own income, ideas for charging a nominal fee for the business service providers on training with income going to the apex and associations a percentage of sales revenue from collective marketing activities to be retained by the apex association. This will encourage association members and other interested participants to value the training offered and put into practice once it is finished.

# Policy Review

# National Agricultural Development Policy 2013

National Agricultural Development Policy (2013), depicts the responsibility of the government in establishing good agricultural infrastructure like building of irrigation canals, water reservoirs, roads and all necessary infrastructure for facilitating production and value addition for both crop farmers and pastoralists/livestock keepers, but it does not say much about the establishment of value addition infrastructure for rice. The Government has implemented this policy in different ways mainly by setting budget each year for constructing irrigation, transport infrastructure and maintenance of rural roads which have a lot of contribution in improving agriculture. But still a little has been done in the area of value addition.

# Marketing Infrastructure, value Addition and Rural Finance Project (MIVARF)

The government thorough the project called Marketing Infrastructure, Value addition and Rural Finance (MIVARF) have addressed most of these problems, but more efforts was put in the construction of ware houses, markets, pack houses and could rooms. According to IFAD (2016) in their MIVARF supervision report very small has been done in supporting smallholder farmers in the area of value addition to rice. So rice value addition for southern highlands of Tanzania still needs a lot of intervention Kilimo.

# Kilimo Kwanza and its Impact in Rice Subsector

According to the URT, Kilimo Kwanza (April 2009), Kilimo Kwanza is expressed as a strategy towards poverty reduction. KILIMO KWANZA recognizes the central role of the agricultural sector in Tanzania in bringing about social and economic development and in particular poverty reduction.  Unlike past initiatives KILIMO KWANZA takes a holistic approach constituted in the ten pillars and it is said to be private sector driven initiatives.

According to this document, KILIMO KWANZA is said to be a catalyst for implementation of Agricultural Sector Development Program (ASDP) and accelerates implementation and achievement of MDGs and MKUKUTA targets and objectives, with a strong emphasis on pro-poor growth especially in supporting and capacitating smallholder farmers. Furthermore, it provides national coordination of resources, planning and accountability for implementation of agricultural transformation and enhances strong private sector participation as a key agent towards realization of goals.  It comprises a holistic set of policy instruments and strategic interventions towards addressing the various sectoral challenges and taking advantage of the numerous opportunities to modernize and commercialize agriculture in Tanzania.

These initiatives for Kilimo Kwanza are vested in some deliberate implementation like an importation of small hand tractors for every district. How far are those tractors going to benefit the women, poor, and other marginalized Tanzanian farmers is questionable. Doubtlessly they will still remain there to be hired by the economically able farmers rather than small holder farmers who are the target group. Again the KILIMO KWANZA initiative did not show what will be done to ensure that smallholder farmers are able to add value to their produce that is what is being done by this rice value addition project.

# Chapter Summary

The researcher managed to read different literature and most of them shows the gap which exists between farmers production, increase in yield, value addition and profit which is earned by farmers. When the farmer just ends by selling paddy as raw material to traders and processors, this section of the study has shown that the one who benefit more with the value chain is the trader rather than the farmer. So this value addition project is worthwhile starting.

# CHAPTER FOUR

# PROJECT PLANNING AND IMPLEMENTATION

# Introduction

This chapter is important because it is here that the plans for whole project will be presented. Activities which are emanating from each objective will be presented here and its implementation schedule will be presented in this chapter. All project activities will be derived from each specific objective. Each objective will provide activities which are contributing towards the accomplishment of the objective. All activities are described hereunder with their respective objectives from where they are derived.

# Project Products and Outputs

# Products and Outputs

The project life cycle was planned to be accomplished in the fourth quarter of 2018

The planned project product is to facilitate access to milling facilities for small holder farmers in Kamwene village community by establishment of rice milling machine for the village community. Products and outputs of the project were set based on the project objectives with their respective activities as detailed below:

To train 40 Kamwene farmers’ association members on rice value addition by June, 2018;

Project outputs:

- A total of 40 community members profiled

- One day village general meeting for sensitization convened

To acquire land for building an office and for installing paddy processing machine by July, 2018;

Product output:

- Meeting with village government convened

- Village general assembly convened for sharing land request from VDC and ward land committee

- Land acquired from the village government

To purchase 1 rice milling machine by September, 2018;

Project Output:

- Village resource mapping conducted by 2019

- Fund raiser for purchasing rice milling machine

To link Kamwene farmers’ association members and market by November, 2018;

Project output:

- Village meeting convened

- All opportunities defied

- Resources  which are available in the village mapped

To train 40 Kamwene farmers’ association members on rice value addition by June, 2018;

Under this objective we shall have the following activities:

Project outputs:

- A total of 40 community members profiled

- One day village general meeting for sensitization convened

- Training to 40 association members facilitated

To acquire land for building an office and for installing paddy processing machine by July, 2018;

Under this objective we shall have the following activities:

- Village VDC meeting convened

- Village general assembly convened for sharing land request from VDC and ward land committee

- Land acquired from the village government

# Figure 4.1: Community Members Making Follow Up of the Meeting Proceedings during One of the Village Meetings for Sharing Progress Report

Source: Field report 2017

To purchase 1 rice milling machine by September, 2018;

Under this objective we shall have the following activities

- Village resource mapping conducted by 2019

- Fund for purchasing rice milling machine raised

- Village general meeting convened

- Resources mobilized for the project conducted

- General meeting conducted to sensitize Community members to contribute their power and skills in for construction

- Community mobilized to contribute through buying shares

- Bank account opened for shares collection

- Price quotation of machines obtained

- Construction work starts

- Milling machine purchased and installed

# Figure 4.2: Community Members Filling Soil in the Foundation for the Milling Machine and Office Building

Source: Field survey 2017

To link Kamwene farmers’ association members members and market by November, 2018;

Under this objective we shall have the following activities

- Business to business B2B meeting convened for bringing farmers and rice buyers in one table

- Rice milling machine purchased and installed

# Table 4.1: Project Activities Table

| OBJECTIVE 1: To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 |
| --- |
| PROJECT OUTPUTS | PROJECT ACTIVITIES: |
| Training to 40 association members facilitated | A total of 40 community members profiled |
|  | One day village general meeting for |
|  | Sensitization convened |
|  | Training materials prepared |
|  | Training to 40 association members facilitated |
| One day village general meeting for sensitization convened | Logistics and communication |
|  | Preparatory meeting with village leaders convened |
|  | One day village general meeting for sensitization convened |
| OBJECTIVE 2: To acquire land for building an office and for installing paddy processing machine by July, 2018 |
| i. Meeting with village government for land request convened | Village VDC meeting convened |
|  | Village general assembly convened for sharing land request from VDC and ward land committee |
|  | Land acquired from the village government |
| ii.Village general assembly convened for sharing land request from VDC and ward land committee | Land request letters and documents prepared |
|  | Meeting facilitated and land request documents submitted |
| Land acquired from the village government | Land acquisition documents submitted to Kamwene farmers’ community |
| OBJECTIVE 3: To purchase 1 rice milling machine by September, 2018 |
| Village resource mapping conducted by 2019 | Fund for purchasing rice milling machine raised |
|  | Resources mobilized for the project conducted |
|  | Village resource mapping conducted by 2019 |
|  | Village general meeting convened |
| Construction work started | General meeting conducted to sensitize Community members to contribute their power and skills in for construction |
|  | Community mobilized to contribute through buying shares |
|  | Bank account opened for shares collection |
|  | Price quotation of machines obtained |
|  | Milling machine purchased and installed |
| OBJECTIVE 4: To link Kamwene farmers’ association members members and market by November, 2018 |
| Village meeting convened for linking farmers to rice buyers | Business to business B2B meeting convened for bringing farmers and rice buyers in one table |
|  | Rice milling machine purchased and installed |
|  | All opportunities defied |
|  | Resources which are available in the village mapped |

# Table 4.2: Project implementation Plan (PIP)

| OBJECTIVE 1: To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 |  |
| --- | --- |
| Activities | YEAR | Resources /Input | Responsible |
|  | 2017 | 2018 |  |  |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | A3 | Q4 |  |  |
| Output 1.1: Training to 40 association members facilitated | A total of 40 community members profiled |  |  |  |  |  |  |  |  | 1.Public address equipments 2.Meeting costs 3.Transport costs | Reuben Mfanga |
|  | One day village general meeting for |  |  |  |  |  |  |  |  | 1.Meeting costs 2.Meeting venue 3. Transport | Reuben Mfanga |
|  | Sensitization convened |  |  |  |  |  |  |  |  | 1.Venue hiring 2.Transport costs 3.Stationaries 4. Training gears 5.Refreshments | Sebastian Sambuo |
|  | Training materials prepared |  |  |  |  |  |  |  |  | 1.Venue hiring 2.Transport costs 3.Stationaries 4. Training gears 5. Refreshments | J. Mafie |
|  | Training to 40 association members facilitated |  |  |  |  |  |  |  |  | 1.Venue hiring 2.Transport costs 3.Stationaries 4. Training gears 5. Refreshments | Sebastian Sambuo |
| ii. One day village general meeting for sensitization convened | Logistics and communication |  |  |  |  |  |  |  |  |  |  |
|  | Preparatory meeting with village leaders convened |  |  |  |  |  |  |  |  |  |  |
|  | One day village general meeting for sensitization convened |  |  |  |  |  |  |  |  |  |  |
| Land acquired from the village government | Village VDC meeting convened Meeting facilitated and land request documents submitted |  |  |  |  |  |  |  |  | 1.Venue hiring 2.Transport costs 3.Stationaries 4. Training gears 5. Refreshments | Reuben James |
|  | Village general assembly convened for sharing land request from VDC and ward land committee Land acquired from the village government |  |  |  |  |  |  |  |  | 1.Venue hiring 2.Transport costs 3.Stationaries 4. Training gears 5. Refreshments | Reuben James |
|  | Land request letters and documents prepared |  |  |  |  |  |  |  |  | 1.Venue hiring 2.Transport costs 3.Stationaries 4. Training gears 5. Refreshments | J. mafie |
|  | Land acquisition documents submitted to Kamwene farmers’ community |  |  |  |  |  |  |  |  | 1.Public address equipments 2.Meeting costs 3.Transport costs | Sebastian Sambuo |
| Village general assembly convened for sharing land request from VDC and ward land committee | Village general assembly convened |  |  |  |  |  |  |  |  |  |  |
| Meeting with village government for land request convened | Meeting with village government for land request covered |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 2: To acquire land for building an office and for installing paddy processing machine by July, 2018 |
| i. Meeting with village government for land request convened sources of obtaining funds for capital | Village VDC meeting convened Meeting facilitated and land request documents submitted |  |  |  |  |  |  |  |  | 1.Meeting venue 2.Stationary | Village community and village chairperson |
|  | Land acquisition documents submitted to Kamwene farmers’ community |  |  |  |  |  |  |  |  | 1.Public address equipments 2.Meeting costs 3.Transport costs | Reuben Mfanga |
|  |  |  |  |  |  |  |  |  |  | 1.Meeting venue Stationeries | Sebastian Sambuo |
| Village general assembly convened for sharing land request from VDC and ward land committee | Village general assembly convened for sharing land request from VDC and ward land committee Land acquired from the village government |  |  |  |  |  |  |  |  | 1.Meeting costs 2. Stationary | Reuben Mgonja |
| Land acquired from the village government | Land request letters and documents prepared |  |  |  |  |  |  |  |  | 1.Stationaries 2. Food and refreshment for those collecting shares | Mafie |
| OBJECTIVE 3: To purchase 1 rice milling machine by September, 2018 |  |
| Village resource mapping conducted by 2019 | General meeting conducted to sensitize Community members to contribute their power and skills in for construction |  |  |  |  |  |  |  |  | 1.Transport | Sebastian, Mfanga and Reuben |
|  | Community mobilized to contribute through buying shares |  |  |  |  |  |  |  |  | 1.Transport 2.Meeting costs 3.Communication | Sebastian, Mfanga and Reuben |
|  | Bank account opened for shares collection |  |  |  |  |  |  |  |  | 1.Transport 2.Meeting costs 3.Communication | Sebastian, Mfanga and Reuben |
| Construction work started and purchase process | Price quotation of machines obtained |  |  |  |  |  |  |  |  |  |  |
|  | Milling machine purchased and installed |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 4: To link Kamwene farmers’ association members members and market by November, 2018 |
| Village meeting convened for linking farmers to rice buyers | Business to business B2B meeting convened for bringing farmers and rice buyers in one table |  |  |  |  |  |  |  |  | 1.Transport 2.Meeting costs 3.Communication | Sebastian, Mfanga and Reuben |
|  | Rice milling machine purchased and installed |  |  |  |  |  |  |  |  | 1.Meeting costs 2.Communication | Sebastian, Mfanga and Reuben |
|  | All opportunities defied |  |  |  |  |  |  |  |  | 1.Stationaries | J. Mafie |
|  | Resources which are available in the village mapped |  |  |  |  |  |  |  |  | 1.Stationaries | J. Mafie |
|  |  |  |  |  |  |  |  |  |  | 1.Transport 2.Stationaries | J. Mafie Sebastian, Mfanga |

# Source: researcher, 2017

# Table 4.3: Project Log Frame Matrix (PLFM)

| Hierarchy of Objectives | Objectively verifiable Indicators | Means of verification | Assumptions |
| --- | --- | --- | --- |
| Project Goal: Promoting value addition to rice in Kilombero for income generation and poverty reduction by installing processing rice processing machine at Kamwene village |
| Project Objectives and Outcomes |
| Objective 1: To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 |
| Output 1: Training to 40 association members facilitated |  |  |  |
|  | Number of farmers who have been trained | FOs Training records | Awareness campaign will be done as planed |
|  |  | Attendance sheets | Baseline and midterm survey will be done efficiently |
| Output 1.2: ii. One day village general meeting for sensitization convened | Number of village community members with knowledge on value addition | Survey records/reports | Baseline data and midterm survey data will be available |
|  | Number of farmers who have attended the meeting | Steering committee records | Training on value addition will be done effectively |
| Output 1.3 Meeting with village government for land request convened | Number of community members who have attended the meeting | Steering committee records | Sensitization will be done effectively |
| OBJECTIVE 2: To acquire land for building an office and for installing paddy processing machine by July, 2018 |
| Output 2.1 i. Meeting with village government for land request convened | Number of meetings conducted for sensitizing the village government to offer land | Steering committee reports | Sensitization will be done sufficiently |
|  | Number of official letters sent by the steering committee to the village government | Steering committee reports | The village government will offer full cooperation in supporting the project |
| Output 2.2: ii. Village general assembly convened for sharing land request from VDC and ward land committee | Number of VGM convened | Steering committee reports | There will not be crop failure |
| Output 2.3 Land acquired from the village government | Amount of land acquired | Land handling over documents and contracts Steering committee reports | There will be enough and continuous sensitization |
| OBJECTIVE 3: To purchase 1 rice milling machine by September, 2018 |
| Output 3.1 Village resource mapping conducted by 2019 | Number, type and value of village resources that has been mapped | Steering committee reports | Mapping process will go on smoothly |
|  | Number of resource that will be available in the village | Steering committee reports | The work will be done effectively |
| Output 3.2: Construction work started | Number of milling machine house constructed | Steering committee reports | All required capital will be raised and ready available for commencing the project |
| Output 3.3: Mobilization of resources for purchasing milling machine conducted | Amount of resources available ready for purchase of milling machine | Steering committee reports | Mobilization exercise will be done effectively |
|  | Number of contributors who are ready pay for the project | Steering committee reports | Mobilization will be done effectively and successfully |
|  | Number of shareholders who are ready to own the project through their shares | Steering committee reports & Progress reports | Mobilization exercise will be done effectively and successfully |
| Output 3.4 One milling machine purchased and installed | Type and number of rice milling machine that has been purchased | Steering committee reports & Progress reports Procurement documents like the profoma invoice and receipts Machine installation report | Capital will be available for that work |
| OBJECTIVE 4: To link Kamwene farmers’ association members and market by November, 2018 |
| Output 4.1 Village meeting convened for linking farmers to rice buyers | Number of B2B meetings conducted between farmers and buyers | Meeting records Attendance sheets | Farmers will participate in the meeting and the buyers will be available |

# Source: researcher, 2017

# Table 4.4: Project Budget (PB)

| OBJECTIVE 1: To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 |
| --- |
| Output and Activities | Resources | Unit | Quantity | Unit cost | Total |
| Output 1.1: Training to 40 association members facilitated | Activities: 1.1.1 A total of 40 community members profiled | 1.Public address equipments | Days | 2 | 150,000 | 300,000 |
|  |  |  | Pc | 4 | 300,000 | 1,200,000 |
|  |  | 2.Meeting costs | Days | 4 | 50,000 | 200,000 |
|  |  | 3.Transport costs | Each | 25 | 200,000 | 5,000,000 |
|  | Activities:1.1.2 One day village general meeting for sensitization | 1.Meeting costs | Each | 25 | 50,000 | 1,250,000 |
|  |  | 2.Meeting venue | Days | 4 | 30,000 | 120,000 |
|  |  | 3. Transport | Each | 40 | 40,000 | 1,600,000 |
|  | Activities: 1.1.3 Training materials prepared | 1.Venue hiring | Days | 4 | 30,000 | 120,000 |
|  |  | 2.Transport costs | Each | 40 | 20,000 | 800,000 |
|  |  | 3.Stationaries | Days | 4 | 20,000 | 80,000 |
|  |  | 4. Training gears | pc | 10 | 40,000 | 400,000 |
|  |  | 5.Refreshments | Each | 40 | 10,000 | 400,000 |
|  | 1.1.4 Conduct training on different alternative ways of adding value to paddy and the economies involved in each method | 1.Venue hiring | Days | 4 | 30,000 | 120,000 |
|  |  | 2.Transport costs | Each | 40 | 10,000 | 400,000 |
|  |  | 3.Stationaries | Each | 10 | 20,000 | 200,000 |
|  |  | 4. Training gears | pc | 10 | 40,000 | 400,000 |
|  |  | 5. Refreshments | Each | 40 | 10,000 | 400,000 |
|  | 1.1.5 Conduct training to the community on different useful products which are obtained as by products in the process of value addition to paddy. | 1.Venue hiring | Days | 4 | 30,000 | 120,000 |
|  |  | 2.Transport costs | Each | 25 | 10,000 | 250,000 |
|  |  | 3.Stationaries | Pc | 10 | 20,000 | 200,000 |
|  |  | 4. Training gears | pc | 10 | 40,000 | 400,000 |
|  |  | 5. Refreshments | Each | 25 | 10,000 | 250,000 |
| Output1.2 One day village general meeting for sensitization convened | 1.2.1 Logistics, meeting venue and communication | 1.Venue hiring | Days | 6 | 30000 | 180,000 |
|  |  | 2.Transport costs | Each | 200 | 10000 | 2,000,000 |
|  |  | 3.Stationaries | pc | 10 | 20,000 | 200,000 |
|  |  | 4. Training gears | pc | 10 | 40,000 | 400,000 |
|  |  | 5. Refreshments | Each | 200 | 10000 | 2,000,000 |
|  | 1.2.2 Conduct Preparatory meeting with village leaders | 1.Venue hiring | Days | 6 | 30000 | 180,000 |
|  |  | 2.Transport costs | Each | 12 | 10,000 | 120,000 |
|  |  | 3.Stationaries | pc | 10 | 20,000 | 200,000 |
|  |  | 4. Training gears | pc | 10 | 40,000 | 400,000 |
|  |  | 5. Refreshments | Each | 12 | 10000 | 120,000 |
|  | 1.2.3 Conduct training to milling machine board on occupational and industrial safety | 1.Venue hiring | Days | 8 | 30000 | 240,000 |
|  |  | 2.Transport costs | Each | 12 | 10,000 | 120,000 |
|  |  | 3.Stationaries | pc | 4 | 40,000 | 160,000 |
|  |  | 4. Training gears | Pc | 4 | 40,000 | 160,000 |
|  |  | 5. Refreshments | Each | 12 | 10,000 | 120,000 |
|  | 1.2.4 One day village general meeting for sensitization convened | 1.Public address equipments | Days | 2 | 50,000 | 100,000 |
|  |  | 2.Meeting costs | Each | 2 | 50,000 | 100,000 |
|  |  | 3.Transport costs | Each | 25 | 10,000 | 250,000 |
| OBJECTIVE 2: To acquire land for building an office and for installing paddy processing machine by July, 2018 |
| Output 2.1 Meeting with village government for land request convened | 2.1.1 Village VDC meeting convened for receiving land request from FOs | 1.Meeting venue | Days | 6 | 30,000 | 180,000 |
|  |  | 2.Stationary | pc | 6 | 40,000 | 240,000 |
|  | 2.1.2 Village general assembly convened for sharing land request from VDC and ward land committee | 1.Public address equipment | Days | 6 | 50,000 | 300,000 |
|  |  | 2.Meeting costs | Each | 6 | 40,000 | 240,000 |
|  |  | 3.Transport costs | Each | 25 | 10,000 | 250,000 |
|  | 2.1.3 Convene meeting for land handling over ceremony | 1.Public address equipments | pc | 4 | 50,000 | 200,000 |
|  |  | 2.Meeting costs | Each | 4 | 40,000 | 160,000 |
|  |  | 3.Transport costs | Each | 25 | 10,000 | 250,000 |
|  | 2.1.4 land acquired for the project | 1 Meeting costs | Each | 25 | 10,000 | 250,000 |
| OBJECTIVE 3: To purchase 1 rice milling machine by September, 2018 |
| Output 3.1 Village resource mapping conducted by 2019 | 3.1. Fund for purchasing rice milling machine raised | 1.Transport | Each | 25 | 10,000 | 250,000 |
|  |  | 2. Communication | Each | 25 | 5,000 | 125,000 |
|  |  |  |  |  |  | - |
|  | 3.1.2 Resources mobilized for the project conducted | 1.Meeting costs | Each | 8 | 40,000 | 320,000 |
|  |  | 2.Communication | Each | 25 | 5,000 | 125,000 |
|  | 3.1.3 Village resource mapping conducted by 2019 | 1.Stationaries | Each | 4 | 80,000 | 320,000 |
|  | 3.1.4 Village general meeting convened | 1. Transport | pc | 4 | 20,000 | 80,000 |
| Output 3.2 Construction work for office and milling machine house started | 3.2.1 Facilitate all ground leveling and building foundation for milling machine house | 1.Food for work | Each | 200 | 5000 | 1,000,000 |
|  |  | 2. Building materials | Each | 15 | 500,000 | 7,500,000 |
|  |  | 3. Payment for technical masons and laborers | Each | 20 | 500,000 | 10,000,000 |
|  | 3.2.2 Erect structure and finishing work for milling machine building | 1.Food for work | Each | 200 | 5000 | 1,000,000 |
|  |  | 2. Building materials | Each | 20 | 500,000 | 10,000,000 |
|  |  | 3. Payment for technical masons and laborers | Each | 20 | 350,000 | 7,000,000 |
|  | 3.2.3 Installation of rice milling machine | 2. Building materials | Each | 20 | 500,000 | 10,000,000 |
|  |  | 3. Payment for technical masons and laborers | Each | 20 | 200,000 | 4,000,000 |
| Output 3.3 Milling machine purchased and installed | 3.3.1 Conduct seminar to milling machine board on business management and financial literacy | 1.Training materials | pc | 10 | 40,000 | 400,000 |
|  |  | 2.Stationaries | pc | 10 | 10,000 | 100,000 |
|  |  | 3.Transport | Each | 25 | 10000 | 250,000 |
|  | 3.3.2 Conduct seminar to milling machine board on daily mailing machine operations and how to reduce overhead cost | 1.Training materials | pc | 10 | 40,000 | 400,000 |
|  |  | 2.Stationaries | pc | 4 | 20,000 | 80,000 |
|  |  | 3.Transport | Each | 25 | 10,000 | 250,000 |
|  | 3.3.4 Conduct training to the community on a good stewardship of community projects | 1.Training materials | pc | 10 | 40,000 | 400,000 |
|  |  | 2.Stationaries | pc | 10 | 10,000 | 100,000 |
|  |  | 3.Transport | Each | 25 | 10,000 | 250,000 |
| OBJECTIVE 4: To link Kamwene farmers’ association members and market by November, 2018 |
|  | Business to business B2B meeting convened for bringing farmers and rice buyers in one table | 1.Transport | each | 2 | 30,000 | 60,000 |
|  |  | 2.Venue hiring | each | 40 | 20,000 | 800,000 |
| GRAND TOTAL | 78,140,000 |

# Source: researcher, 2017

# Table 4.5: Project Time Management Table (Gantt chart)

| OBJECTIVE 1: To train 40 Kamwene farmers’ association members on rice value addition by June, 201 |
| --- |
| Activities | YEAR | YEAR |
|  | 2017 | 2018 |
| Outputs level | Activities Level | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | A3 | Q4 |
| Output 1.1: Training to 40 association members facilitated | Activities: 1.1.1 A total of 40 community members profiled |  |  |  |  |  |  |  |  |
|  | 1.1.2 One day village general meeting for |  |  |  |  |  |  |  |  |
|  | 1.1.3 Conduct training to the community on the importance of value addition as way of raising farmers’ income |  |  |  |  |  |  |  |  |
|  | Training materials prepared |  |  |  |  |  |  |  |  |
|  | Training to 40 association members facilitated |  |  |  |  |  |  |  |  |
| Output 1.2: One day village general meeting for sensitization convened | 1.2.1 A total of 40 community members profiled |  |  |  |  |  |  |  |  |
|  | 1.2.2 Training materials prepared for sensitization |  |  |  |  |  |  |  |  |
|  | 1.2.3 One day village general meeting |  |  |  |  |  |  |  |  |
|  | 1.2.4 Training to 40 association members facilitated |  |  |  |  |  |  |  |  |
| OBJECTIVE 2: To acquire land for building an office and for installing paddy processing machine by July, 2018 |
| 2.1 Meeting with village government for land request convened sources of obtaining funds for capital | 2.1.1 Village VDC meeting convened |  |  |  |  |  |  |  |  |
|  | 2.1.2 Village general assembly convened for sharing land request from VDC and ward land committee seminar for all |  |  |  |  |  |  |  |  |
|  | 2.1.3 Land acquired from the village government |  |  |  |  |  |  |  |  |
| 2.2 Village general assembly convened for sharing land request from VDC and ward land committee | 2.2.1 Land request letters and documents prepared |  |  |  |  |  |  |  |  |
|  | 2.2.2 Meeting facilitated and land request documents submitted |  |  |  |  |  |  |  |  |
|  | 2.2.3 Land acquisition documents submitted to Kamwene farmers’ community |  |  |  |  |  |  |  |  |
| 2.3 Land acquired from the village government | 2.3.1 Conduct meeting for handling Land acquisition documents to Kamwene farmers’ community |  |  |  |  |  |  |  |  |
| OBJECTIVE 3: To purchase 1 rice milling machine by September, 2018 |
| Output 3.1: Village resource mapping conducted by 2019 | 3.1.1 Fund for purchasing rice milling machine raised |  |  |  |  |  |  |  |  |
|  | 3.1.2 Resources mobilized for the project conducted |  |  |  |  |  |  |  |  |
|  | 3.1.3 Village resource mapping conducted by 2019 |  |  |  |  |  |  |  |  |
|  | 3.1.4 Submit land request documents to the VDC |  |  |  |  |  |  |  |  |
|  | 3.1.5 Continue with follow up process for land request response from the VDC |  |  |  |  |  |  |  |  |
|  | 3.1.6 Village general meeting convened |  |  |  |  |  |  |  |  |
| Output 3.2: Construction work started and installation | 3.2.1 General meeting conducted to sensitize Community members to contribute their power and skills in for construction |  |  |  |  |  |  |  |  |
|  | 3.2.2 Community mobilized to contribute through buying shares |  |  |  |  |  |  |  |  |
|  | 3.2.3 Price quotation of machines obtained |  |  |  |  |  |  |  |  |
|  | 3.2.4 Facilitate all ground leveling and building foundation for milling machine house |  |  |  |  |  |  |  |  |
|  | 3.2.5 Erect structure and finishing work for milling machine building |  |  |  |  |  |  |  |  |
|  | 3.2.6 Installation of rice milling machine |  |  |  |  |  |  |  |  |
| Output 3.3: Community sensitized on ownership and operation of milling machine | 3.3.1 Conduct seminar to milling machine board on business management and financial literacy |  |  |  |  |  |  |  |  |
|  | 3.3.2 Conduct seminar to milling machine board on daily mailing machine operations and how to reduce overhead cost |  |  |  |  |  |  |  |  |
|  | 3.3.4 Conduct training to the community on a good stewardship of community projects |  |  |  |  |  |  |  |  |
| OBJECTIVE 4: To link Kamwene farmers’ association members and market by November, 2018 |
| Village meeting convened for linking farmers to rice buyers | Business to business B2B meeting convened for bringing farmers and rice buyers in one table |  |  |  |  |  |  |  |  |

# Table 4.6: Project Implementation Report Table

| OBJECTIVE 1: To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 |
| --- |
| Outputs | Activities | Implementation status | Reason for Deviation |
| Output 1.1: Training to 40 association members facilitated | 1.1.1 A total of 40 community members profiled | Total of 40 community members were profiled | None |
|  | 1.1.2 One day village general meeting for sensitization convened | The meeting was done successfully | None |
|  | 1.1.3 Training materials prepared | Training materials for all participants were prepared | None |
|  | 1.1.4 Training to 40 association members facilitated | All 40 members were trained |  |
| Output 1.2: One day village general meeting for sensitization convened | 1.2.1 Logistics and communication | Necessary resources for facilitating communication and logistics were available | None |
|  | 1.2.2 Preparatory meeting with village leaders convened | The meeting was done successifully | None |
|  | 1.2.3 One day village general meeting for sensitization convened | The meeting was done with a good turn up by village members | None |
|  | 1.2.4 Conduct sensitization meeting with village farmers’ community on the importance of value addition | The meeting was done with a good turn up by village members | None |
| OBJECTIVE 2: To acquire land for building an office and for installing paddy processing machine by July, 2018 |
| Output 2.1 Meeting with village government for land request convened | 2.1.1 Village VDC meeting convened | The meeting was done and only one VDC member was missing | None |
|  | 2.1.2 Village general assembly convened for sharing land request from VDC and ward land committee | The meeting was done with a good turn up by village members | None |
|  | 2.1.3 Land acquired from the village government | Land was provided for the project use as it was requested | None |
| 2.2 Village general assembly convened for sharing land request from VDC and ward land committee | 2.2.1 Land request letters and documents prepared | Letters were prepared and submitted | None |
|  | 2.2.2 Meeting facilitated and land request documents submitted | The meeting was done | None |
| 2.3 Land acquired from the village government | 2.3.1 Land acquisition documents submitted to Kamwene farmers’ community | All documents were submitted | None |
| OBJECTIVE 3: To purchase 1 rice milling machine by September, 2018 |
| Output 3.1: Village resource mapping conducted by 2019 | 3.1.1 Village general meeting convened | The meeting was done with a good turn up by village members | None |
|  | 3.1.2 Conduct Fund raising for purchasing rice milling machine | The fundraising activity was done but turn up of villagers was not good | None |
|  | 3.1.3 Village resource mapping conducted by 2019 | Resource mapping was successful by 70% | Community awareness on the available resources is still very low. |
|  | 3.1.4 Fund for purchasing rice milling machine raised | Funds were raised for 55% | It was because of poor turn up of the community |
|  | 3.1.5 Continue with follow up process for land request response from the VDC | Follow up was done and completed | None |
| 3.2: Milling machine purchased and installed | 3.2.1 Facilitate all ground leveling and building foundation for milling machine house | All ground work was done well | None |
|  | 3.2.2 Erect structure and finishing work for milling machine building | All work was done well | None |
|  | 3.2.3 Installation of rice milling machine | Machine was installed successfully | None |
| OBJECTIVE 4: To link Kamwene farmers’ association members and market by November, 2018 |  |  |
| 3.3: Village meeting convened for linking farmers to rice buyers | 3.3.1 Business to business B2B meeting convened for bringing farmers and rice buyers in one table | B2B meeting was done successfully | None |

# Source: researcher, 2017

# CHAPTER FIVE

# PROJECT PARTICIPATORY, MONITORING EVALUATION AND SUSTAINABILITY

# Introduction

This chapter covers participatory monitoring, participatory evaluation and project sustainability. Participatory monitoring as part of this chapter is essential to the well being of the project as it analyze the current situation, identify problems and find solutions, discover trends and patterns, keep project activities on schedule, measure progress towards objectives, formulate/revise future goals and objectives and make decisions about human, financial and material resources. On the other hand, participatory evaluation analyzes information to determine whether the project is carrying out its planned activities and the extent to which the project is achieving its stated objectives through these activities to find out how effective the project is to learn how well things are being done and to learn from experience so that future activities can be improved.

# Participatory Monitoring

Participatory Monitoring is the systematic recording and periodic analysis of information that has been chosen and recorded by insiders with the help of outsiders. Participatory monitoring was intended to monitor all project activities which included: mobilizing the target group on importance of investing in rice value addition, establishing their own saving system which will ensure sustainability of the project by contributing to their shares, sensitizing farmers to be true project owners through share contribution. To make follow up of the project implementation which is led by the project steering committee formed by farmers. To conduct formative evaluation of the project with the project steering committee after 3 months of the project implementation, conduct a summative evaluation of the project together with the project committee during the end of the project and conduct a phase out strategy workshop to project committee with other key stakeholders in the project.

# Participatory Monitoring Tools That Were Used

Two participatory methods were applied in monitoring the project implementation. These were PPRA, transect walk and focus group discussion (FDG). The information which was obtained was treated as the primary data which were collected directly. PRA is a tool that was used in conducting project monitoring and Evaluation. The researcher started with appreciating local knowledge where villagers will be encouraged to teach the researcher how to do various activities. The researcher learnt how much skill and strength are required to do day-to-day rural activities, gaining an insider's perspective on a situation.

Transect walk was used to observe new established business, available resources in the village that can be used for the project sustainability then group members hold meeting to share the results. Focus group discussion was applied to assess time as an important element. FO members were asked as to whether every activity was implemented according to the plan and if there is need to reverse the implementation plan. During the discussion every member was given an opportunity to assess how time used in project operations and hence responses were recorded for further analysis. The CED student acted as a facilitator to keep the discussion on.

# Participatory Rural Appraisal (PPRA)

According to (Lugi Covestro 2003), “…participatory Rural Appraisal (PRA) is considered one of the popular and effective approaches to gather information in rural areas. This approach was developed in early 1990s with considerable shift in paradigm from top-down to bottom-up approach, and from blueprint to the learning process. PRA is a tool that will be used in conducting project monitoring and Evaluation. The researcher will start with appreciating local knowledge where villagers will be encouraged to teach the researcher how to do various activities. The researcher will learn how much skill and strength are required to do day-to-day rural activities, gaining an insider's perspective on a situation.

# Transect Walks across Kamwene village

The researcher and key informants conducted a walking tour through areas of interest to observe, to listen, to identify different zones or conditions, and to ask questions to identify problems and possible solutions. With this method, the outsider quickly learnt about topography, soils, land use, forests, watersheds, and community assets. Transect walk was done from Kamwene dispensary across the village directly to transporter hamlet. Different things were noted on the way like farms which had a rice residue, soil with different texture and when the team was approaching transporter hill stones were noted on top of the soil. Along the transporter hill there is a forest with very big trees.

# Monitoring Information System (MIS)

Monitoring information system based on the weekly recorded information pertaining to activities that were arranged in a specified period of time. It includes community members participating in the exercise for instance in mobilizing target group on the importance of developing a saving spirit. Weekly list showing target group members agreed to buy shares so that they can be owners of the project/rice milling machine providing good information for project monitoring. In this case monitoring information such as number of shares bought in two weeks’ time when the meeting is conducted can easily be traced and therefore giving monitoring information which shows how the process of buying shares is proceeding. Special documents also may be prepared which can help community to conduct participatory monitoring as monitoring team can see and become ready to note all progress. Here each FO is given a special card or form which contain necessary indicator so that he/she can fill the card or form monthly or weekly according to the follow up time table.

# Project Participatory Monitoring Plan

The objective of participatory monitoring was to monitor project objectives, activities implemented and the outcomes of the project. Also to monitor project inputs, assess if the action plan was implemented accordingly and whether the project stakeholders were kept informed of the progress, challenges and lessons learnt during the project implementation. The table below indicates participatory plan as agreed by the project steering committee which was involved fully in developing it.

# Table 5.1: Participatory Monitoring Plan

| Objective | Outputs | Activities | Indicators | Data source | Method | Responsible | Time frame |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 | Training to 40 association members facilitated | 1.One day village general meeting for 2.A total of 40 community members profiled 3.Training materials prepared 4.Training to 40 association members facilitated | Training register | FOs and steering committee records | Meetings | Steering committee | December 2018 |
|  | One day village general meeting for sensitization convened | 1.Logistics and communication 2.Preparatory meeting with village leaders convened 3.One day village general meeting for sensitization convened | Meeting records/ minutes | Steering committee records | Meetings | Steering committee and VDC | August 2018 |
| To acquire land for building an office and for installing paddy processing machine by July, 2018 | i. Meeting with village government for land request convened | 1.Village VDC meeting convened 2.Village general assembly convened for sharing land request from VDC and ward land committee 3.Land acquired from the village government | Meeting records/ minutes Land hand over documents and contracts | Steering committee records Steering committee records | Meetings Observation | Village govt. and steering committee Student and Steering committee | October 2018 February 2018 |
|  | ii.Village general assembly convened for sharing land request from VDC and ward land committee | 1.Land request letters and documents prepared 2.Meeting facilitated and land request documents submitted | Meeting records Land hand over documents and contracts | Steering committee records | FO meetings | Student and Steering committee | May 2018 |
|  | Land acquired from the village government | 3.Land acquisition documents submitted to Kamwene farmers’ community | Land hand over documents and contracts | Steering committee records | Data collection | Student and steering committee | June 2018 |
| To purchase 1 rice milling machine by September, 2018 | Village resource mapping conducted by 2019 | 1.Fund for purchasing rice milling machine raised 2.Resources mobilized for the project conducted 3.Village resource mapping conducted by 2019 4.Village general meeting convened | Procurement documents and receipts Meeting records and minutes Resource map and report Meeting reports and minutes | Project and Steering committee records Project Steering committee records Steering committee records | Focus group discussion | Student and steering committee | August 2018 |
|  | Construction work started and purchase of milling machine | 1.General meeting conducted to sensitize Community members to contribute their power and skills in for construction | Meeting records | FO progress report | Observation | FO leaders and the student | August 2018 |
|  |  | 2. Community mobilized to contribute through buying shares 3. Price quotation of machines obtained 4.Milling machine purchased and installed | Mobilization report | FO reports | Bank statements, and reports | Steering committee and the student | September 2018 |
| To link Kamwene farmers’ association members and market by November, 2018 | Village meeting convened for linking farmers to rice buyers | 1.Business to business B2B meeting convened for bringing farmers and rice buyers in one table | Meeting report and business linkage agreements | Steering committee records | Meetings | Steering committee and the student | July 2018 |

# Source: researcher, 2017

# Monitoring Results

Monitoring activity included the participants like the researcher (CED student), project steering committee and farmers’ association members. All the information obtained were discussed and analyzed qualitatively by following this modality below:

- 87% attended the fund raising/resource mobilization meeting for raising fund for the project and they were ready to buy shares.

- The memorandum of understanding between the milling machine board and Farmers’ association was signed for smooth operation of the business to enhance the operation of the milling machine

- 90% of farmers’ association members attended training on good stewardship and they show their readiness to monitor milling machine business

- Items were bought as they were planned such as construction materials for office and milling machine, purchase of milling machine and its accessories and other item a receipt book for shares collection

- Tanzania Agricultural Development Bank (TADB) has come up and advised the steering committee that if their project/business will be registered under the registrar of cooperatives it will qualify for getting loan from TADB soon.  The steering committee has started the process of preparing documents for registering the company with the Tanzania Federation of Cooperatives (TFC)

- 95% of the steering committee members attended training on management and project supervision skills which included proper record keeping and internal auditing.

# Participatory Evaluation

A participatory evaluation is an opportunity for stakeholders to reflect on the past in order to make decisions about the future. It intends to bring out program success, growth areas and lessons learnt for project progress improvements. Farmers’ association members and the project steering committee members participated in the whole exercise showing ownership of the impact.

We conducted evaluation because of the following reasons:-

- Evaluation seeks to collect evidence on the effectiveness of a project.

- Evaluation strives to identify ways to improve a project, in this regard determine what works, what does not work and why, while assessing future needs and improving the usefulness of project materials.

- Evaluation seeks to compare a project with other projects of different or of the same nature so as to collect a lesson that can be replicated

Participatory evaluation was conducted by focusing at project goal which stated as Improving Community Income and livelihood of Kamwene village community through establishment of rice value addition project in kamwene village community in kilombero district morogoro region

# Performance Indicators

Performances are variables that show the extent of change that resulted from the project. They help to measure what actually happened in terms of quantity, quality and timeliness against what was planned. They measure progress in achieving outputs and outcomes. They show relevance, performance and effectiveness of the project as well as progress towards meeting its output and outcomes. Based on the project objectives and project goal performance indicators, indicators were developed as shown in the table 5.2.

# Table 5.2: Performance Indicator Table

| Objective | Outputs | Activities | Resources | Performance Indicator |
| --- | --- | --- | --- | --- |
| To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 | Training to 40 association members facilitated | 1.One day village general meeting for 2.A total of 40 community members profiled 3.Training materials prepared 4.Training to 40 association members facilitated | Meeting venue Training material Allowances | Number of trainees Training manuals prepared |
|  | One day village general meeting for sensitization convene | 1.Logistics and communication 2.Preparatory meeting with village leaders convened 3.One day village general meeting for sensitization convened | Meeting venue Transport Public address facility | Meeting reports minutes |
| To acquire land for building an office and for installing paddy processing machine by July, 2018 | i. Meeting with village government for land request convened | 1.Village VDC meeting convened 2.Village general assembly convened for sharing land request from VDC and ward land committee 3.Land acquired from the village government | Meeting venue Allowances for village leaders Transport Land fees | Signed contracts Land handling over documents from village government |
|  | ii.Village general assembly convened for sharing land request from VDC and ward land committee | 1.Land request letters and documents prepared 2.Meeting facilitated and land request documents submitted | Meeting venue Transportation | Meeting minutes and reports |
|  | Land acquired from the village government | 3.Land acquisition documents submitted to Kamwene farmers’ community | Transport Venue | Land documents |
| To purchase 1 rice milling machine by September, 2018 | Village resource mapping conducted by 2019 | 1.Fund for purchasing rice milling machine raised 2.Resources mobilized for the project conducted 3.Village resource mapping conducted by 2019 4.Village general meeting convened | Transportation Meeting costs Allowances Payment for the machine | Procurement documents and receipts |
| To link Kamwene farmers’ association members and market by November, 2018 | Village meeting convened for linking farmers to rice buyers | 1.Business to business B2B meeting convened for bringing farmers and rice buyers in one table | Transportation Venue hiring Allowances | Meeting report and business linkage contracts |

# Source: researcher, 2017

# Participatory Evaluation Methods

Various methods of data collection methods and technique were used such as questionnaire, checklist, interviews, observation and group discussion to find out whether the project is on schedule. Individual interviews, focused group discussion were conducted to beneficiaries through their respective entities that is farmers’ Organization (FO)s by the use of checklist.

Unstructured discussion with the key informants and direct observation as means of data collection were also employed in order to have a wide variety of information on the progress and achievement of the activities and objectives. Any information gathered was shared with all project stakeholders for assistance and to keep them all up dated to enhance contribution of new ideas for progress and for better performance of the project. For this second quarter of the project a participatory evaluation exercise was done and the following results have been noted:

- Two objectives were achieved early in the first month of the project design they were achieved already, as the land has was acquired for the construction of milling machine and office. Again the construction work started even before the project document was completed by the following phases. Phase one of collecting building material was accomplished by the man power from the village community and FO members, phase two of starting the building by digging foundation, laying basement and starting the walls construction was accomplished also by contribution from the village both human and material resources were available that is why the first months of construct the work was very quick. Resources were effective utilized through the heavy eye watch and follow up by the steering committee.

- The training was conducted for 40 FO members but the attendance showed 37 participants which is equivalent to 97% which also indicate a success in the exercise.

- Establishment of small businesses which are supported by the milling machine wastes like poultry which will use the rice bran husks have been established as most members have already started plan to establish build poultry huts.

- FO members’ participation in project implementation is improved and has attracted other community members who are not members of the Farmers’ Organizations to join their fellow

- Members of the FO have designed energy efficient cooking stoves which use rice husks as a fuel for cooking. Your people who have been using trees and logs for burning bricks for construction are now using rice husks for that purpose instead of tree logs

# Project Evaluation Summary

During evaluation three major project objectives were examined using several performance indicators for each objective. Expected outcomes and actual outcomes were also examined and noted in detail during the midterm evaluation exercise which was conducted in June 2018.

# Table 5.3: Project Evaluation Summary

| Objective | Outputs | Activities | Resources | Performance Indicator | Expected Outcome | Actual Outcome |
| --- | --- | --- | --- | --- | --- | --- |
| To train 40 Kamwene farmers’ association members on rice value addition by June, 2018 | Training to 40 association members facilitated | 1.One day village general meeting for 2.A total of 40 community members profiled 3.Training materials prepared 4.Training to 40 association members facilitated | Meeting venue Training material Allowances | Number of trainees Training manuals prepared | Participants gained knowledge | 97% were trained |
|  | One day village general meeting for sensitization convened | 1.Logistics and communication 2.Preparatory meeting with village leaders convened 3.One day village general meeting for sensitization convened | Meeting venue Transport Public address facility | Meeting reports minutes | Good uptake of information | Meeting was conducted and more than 50% of the community members participated |
| To acquire land for building an office and for installing paddy processing machine by July, 2018 | i. Meeting with village government for land request convened | 1.Village VDC meeting convened 2.Village general assembly convened for sharing land request from VDC and ward land committee 3.Land acquired from the village government | Meeting venue Allowances for village leaders Transport Land fees | Signed contracts Land handling over documents from village government | Positive response from the village government | The land was provided for the project |
|  | ii.Village general assembly convened for sharing land request from VDC and ward land committee | 1.Land request letters and documents prepared 2.Meeting facilitated and land request documents submitted | Meeting venue Transportation | Meeting minutes and reports | Turn up by the community was good | More than 50% of the village community participated |
|  | Land acquired from the village government | 3.Land acquisition documents submitted to Kamwene farmers’ community | Transport Venue | Land documents | Good response | Documents were provided for the land ownership |
| To purchase 1 rice milling machine by September, 2018 | Village resource mapping conducted by 2019 | 1.Fund for purchasing rice milling machine raised 2.Resources mobilized for the project conducted 3.Village resource mapping conducted by 2019 4.Village general meeting convened | Transportation Meeting costs Allowances Payment for the machine | Procurement documents and receipts | The machine was purchased timely | Machine purchased and installed |
| To link Kamwene farmers’ association members and market by November, 2018 | Village meeting convened for linking farmers to rice buyers | 1.Business to business B2B meeting convened for bringing farmers and rice buyers in one table | Transportation Venue hiring Allowances | Meeting report and business linkage contracts | Good turn up by the FO members and steering committee members | B2B meeting was done successfully |

# Source: researcher, 2017

# Project Sustainability

Project sustainability refers to the capacity of project to continue functioning, supported by its own resources. This project intends to assist target group to identify their own workable initiatives which are sustainable and appropriate for their area. These initiatives will tell more about ways of generating household income. Attainment of these initiatives needs thorough analysis and creativity, changing, diversification and integration of different sustainable initiatives. Therefore a sustainable project is one that can deliver benefits to the target group for an extended

period of time after the main assistance has come to an end. However, sustainability of this project can be observed at the following aspects:

# Organizational Capacity

The sustainability of VICOBA project at Kamwene village Community is most likely to be sustainable since human resource is readily available towards project implementation. The project steering committee which includes the committee chairperson, secretary, treasurer and two clerks have been trained on proper Organizational management (OM), Organization Capacity Assessment (OCA) and thus they can assess their performance at any time during their time of office and continue building others whom they think that they can take over when their term of office is over.

Training which has been provided to FO members and the steering committee on good stewardship involved business planning, business management, Ethics and honesty to the community resource. This type of training will contribute to project sustainability since they are sure of profit making, employment and their conscious will be manifesting towards any idea of dishonesty.

The sense of ownership has been created by putting the community in the drivers’ seat in this project. We cannot say that the community is participating but rather the community is leading the whole process of project implementation. The community has performed all necessary stages of the project like identifying, designing, planning, implementation; monitoring and evaluation of the project and these are the key issue that creates sense of ownership that leads to sustainability of the project.

# Financial Sustainability

Most of members of Kamwene Farmers’ Association from the beginning were motivated to buy shares and contribute to the working capital of the project. Farmers are sensitized to contribute shares either by cash or by contributing crops measurements which are equivalent to the amount of shares needed. The minimum shares which a member can buy is three shares which is equivalent to Tshs. 30,000, or the one who had no cash could contribute three tins of paddy which is also has a value of Tshs. 30,000/=

# Socio - Political sustainability

Socially project is being celebrated in Kamwene village by those who are members of FO and non-members. In short the project is saving all people equally because even the steering committee is made up of both those who are FO members and non-members. Political wise, there is a good environment existing between local government and the community members at Kamwene. The village is made up with mixed political ideologies. More than 70% of the community is from opposition side while the rest are from the ruling party. When we come to development all political ideologies are set aside. Since the project is well known by the local government, local leaders, member of parliament for Mlimba constituency, District Executive Director and even the councilors in the area, it is easier to get support from the government where need arises. The project utilizes an opportunity of working with different people.

# CHAPTER SIX

# CONCLUSION AND RECOMMENDATION

# Introduction

According to different stages of this project like designing stage, implementation stage and findings presentation stage, the researcher has tried to elaborate briefly on the findings of the research, tools used in the project from the first stage of Participatory Need Assessment (PNA), to the last stage of Sustainability analysis. By using these findings as which were gathered from the findings, the researcher has a ground for drawing recommendations which will assist others who would do the similar or even different project to take a lesson from this project.

The problem which was envisaged by the researcher is the absence of quality rice processing machine which contributed to large extent low price for rice which is produced by Kamwene village farmers’ community. This rice value addition project aims at contributing in reducing poverty among smallholder farmers by establishing rice value addition project in Kamwene village. Many literatures are written on how far different donors funds given to rice farmers in Kamwene and most of the support has been in terms of trainings, capacity building, renovation of warehouse, but this study has shown that without having a value addition project all these efforts cannot unlock development of Kamwene village community.

These types of project has shown success in other parts of Kilombero district like in Mang’ula the village community has established rice value addition project since 2012 and the project is working with a lot of success todate. Another project was rice and maize value addition project which was established in 2016 in Kiroka village Morogoro rural. Kiroka village was regarded as the most poorest village in Morogoro rural but after establishing this community project the village has changed to small township in terms of service provision, electricity reached Kiroka for the first time by the influence of the project.

# Conclusions

During participatory needs assessment in Kamwene village, the researcher found out that more than 90% of the community members were farmers and they depend totally on farming for earning their daily bread and for business activities. Rice was found the major crop which is used both as food crop as well as cash crop. Age wise the Kamwene farmers’ community was dominated by age of majority. In other words there was extremely young people who are farming, most of the age was skewed few from 45 years to 50 and 60years. So those aged 45 and above formed more than 60% of the population under study. This shows directly that these people have been doing agriculture for more 3 one decades. They have been doing agriculture for such a long period of time but they are still poor and others are in “extreme poverty” in the sense that they cannot afford one meal per day. Furthermore other factors relating to poverty was dependency ratio being very high, More than 80% had more than one dependant, insufficient skills and knowledge on business and entrepreneurship were the common problem facing the community.

The study findings showed that the project had helped to improve the livelihood of its members and reduce poverty. In Comparison with baseline, the numbers of economic activities that the members of FO through the project were engaged have increased. The project had led to increased accumulation of assets for its members. The researcher came out with the decision to work at Kamwene village in Mlimba division, the aim is to look at the challenges and opportunities available in the ward. Based on the community needs assessment conducted by the researcher it revealed that the Kamwene village community is facing many challenges by prioritizing the few Lack of milling machine for adding value to their crops, inadequate entrepreneurs and business skills, inadequate access to loans and savings and inadequate employability skills. Hence the researcher with the agreement with the community decided to address the problem of inadequate rice milling facilities though the establishment of rice milling machine in Kamwene village Kamwene Ward. The project objective were to;

- To train 40 Kamwene farmers’ association members on rice value addition by June, 2018

- To acquire land for building an office and for installing paddy processing machine by July, 2018

- To purchase 1 rice milling machine by September, 2018

- To link Kamwene farmers’ association members members and market by November, 2018

Most of the objectives were successfully achieved and other activities like trainings, mobilization of more farmers to continue buying shares are progressing up to the end of the first cycle of the project which will be accomplished by the end of fourth quarter 2018. In participatory monitoring and evaluation, it was evident that the lives of members had to some extent changed because of establishing the project. Increased income as a result of improved business was significantly notable with 56.2 % of the group members mentioning it.  Now many farmers have ability to save, they have developed saving habits and improved standard of living especially in Education ability to pay school fees has increased, increased income that is capital and improved housing were three main changes. All changes seem to be related either to business growth on finished goods (rice) or improved livelihoods. The project was sustainable in terms of Gender, financial, institutional and political.

# Recommendations

Based on the project work that arises from community need, in order to help the development of farmers’ organizations and to assist others who would like to pursue the similar project, I recommend the following that have risen from the findings, literature review, project monitoring and evaluation and sustainability. Some results in community assessment show that majority of farmers are people of the old age that is between 50 years and above. By reading different literature that is a national tendency. Young people do not like farming, but rather they was short term income generating activity. The researcher recommends effective and deliberate action to be taken so that agricultural sector may have a young generation. The government has removed VAT for all agricultural equipments and other agric technologies. This is the opportunity which can be taped by the young generation to offer these farm services like mechanization and inputs to farmers.

Through the study done rice milling machine is beneficial and sustainable because the business is using raw materials which are owned by farmers, and the same farmers’ community are the owner of project/milling machine. Farmers association members have agreed to form their own saving and credit scheme in form of Village Community Bank (VICOBA). By so doing once the FO members have a shortage of money they can borrow from VICOBA while at the same times members can have a stake in VICOBA. Through their savings farmers can take a soft loan from different financial institutions the loan which in turn it will be dished out to members.  Because members know each other well, there is more flexibility in offering quick loan disbursement and individualized repayment schedules and finally, this can help VICOBA leverage their social capital and organizational capacity to link into agricultural development efforts, heath and education. To those who intend to do the project in a similar field as I have done keep note of the following issues:

- The work of supporting farmers need perseverance because farmers normally change their mind and what was “yes” within 10 minutes may change to be “ no”. Here one needs to be patient and humble so as to win them

- Do not plan over and above what is available in the village map. Once farmers see a visitor they raise expectations that God’s grace has arrived and they will think that you will provide solution for all their problems especially by distributing money to them which is not the case.

- Work hand in hand with the local government to support socio-economic groups as they tend to help most of the poor families to reduce poverty.

- Anyone who intends to initiate community project to make through literature review so as to have the opinion of others what they have done to such projects and identify policies that comply with the project to be developed.

# REFERENCES

Finscope, (2009). The Demand for, and Barriers to Accessing Financial Services in Tanzania. Dar es Salaam: FSDT.

Finscope, (2017). The Demand for, and Barriers to Accessing Financial Services in Tanzania. Dar es Salaam: FSDT.

FSDT, (2011). The Agricultural Finance Markets Scoping (AgFiMS) Survey, retrieved on 19-1-2013 from; http://www.agra.org/AGRA/en/what-we-do/seed/#sthash.kx2pVFzy.dpuf.

Kambewa, E,,  Matieyedou, K., Bertus, W. and Mariana, W. (2013). Do all Roads lead to the Market? Learning From AGRA’ Market Access Programme, Royal Tropical Institute (KIT) and Alliance for a Green Revolution in Africa AGRA: Nairobi.

Kariuki, G. and Place, F. (2005). Initiatives for rural development through collective action: The case of household participation in group activities in the highlands of central Kenya. CAPRi Working Paper No. 43. Washington D.C.

Lwoga, E. T. (2010). Bridging the Agricultural Knowledge and Information Divide: The Case of Selected Telecenters and Rural Radio in Tanzania. The Electronic Journal of Information Systems in Developing Countries, 43(6), 1-14.

Mowo, J. G., B. H. Janssen, O. Oenema, L. German, J. P. Mrema and R. S. Shemdoe (2003). Agriculture, Ecosystems and Environment - Soil Fertility Evaluation and Management by Smallholder Farmer Communities in Northern Tanzania, African Highlands Initiative (AHI), Working Papers No. 18. Dar es Salaam, Tanzania.

NBS, (2008). Ministry of Finance, Agriculture Sample Census Survey – Iringa and Ruvuma Region.  Reference ID -TZA-NBS-AGRSCS-2007/2008v01, NBS: Dar es Salaam.

OPM, (2011). Skills and Innovation for Micro Banking in Africa (SIMBA) program, Lusaka, Zambia.

OPM, (2013). Stock-take of the Existing Skills in Tanzania’s Financial Sector ‒ Draft ‒ Final Report, retrieved on 20th May, 2017 from; http://www.who.int/hrh/com-heeg/reports/en/.

Parvizian, F., Hosseinnejad, G. H. and Lashgarara, F. (2011). Investigating the Role of Radio and Television Programs on the Improvement of Agricultural Extension, American Journal of Scientific Research, 16(1), 6-14.

Shetto, M. C. (2008). Assessment of Agricultural Information Needs in African, Caribbean and Pacific (ACP) States Eastern Africa Country Study: Tanzania. Ministry of Agriculture, Food Security and Cooperatives on behalf of the Technical Centre for Agricultural and Rural Cooperation (CTA). Retrieved on 30th June, 2017 from; http://icmpolicy.cta.int/filesstk/Tanzania_Final-report-081209.pdf.

Sife, A. S. (2010). Contribution of Mobile Telephone, Radio and Television to Rural Livelihoods and Poverty Reduction in Morogoro Region, Tanzania. Unpublished PhD thesis, University of Dar es Salaam, Tanzania.

Tchale, H. (2002). Informal cross-border trade: The case of beans in Eastern and Southern Africa-implications on bean seed multiplication, dissemination entrepreneurship and quality. In proceedings of a bean seed workshop held January 12-14 at Arusha, Tanzania.

URT, (2013). National Agriculture Policy review, Dar es Salaam: Government Printers.

Wolter, D. (2009).  Tanzania – Why a potential Food Exporter is Importing Food, retrieved on 16th June, 2017 from; www.oecd.org.

World Bank, (2013). The New Microfinance Handbook, a Financial Market System Perspective, Washington DC: World Bank Publications.

World Bank, (2012).  Agribusiness indicators: Tanzania. Washington DC: World Bank.

APPENDICES

Appendix I: CNA STUDY TOOLS / Questionnaires

Introductory Information

| Name of Respondent | Gender | Family Position | Age (Years) | Marital Status | Economic Activity |
| --- | --- | --- | --- | --- | --- |
|  | Male | A. H/H | A. 18-24 | A. Married | Farming |
|  | Female | B. Wife | B. 25-35 | B. Single | Animal keeping |
|  |  | C. Child | C. 36 - 45 | C. Divorced | Business |
|  |  | D. Others | D. 46- 55 | D. Widow | D. Others mention |
|  |  |  | E. 56- 65 | E. Widower |  |
|  |  |  | F. 65 And above |  |  |

- What type of crops are you producing? A) Rice B) Maize C) Beans D) Both E) Others mention

- What is the size of your farm? A) 1 to 2 acre B) 3 to 4 acre c) 5 to 6 acre D) 7 acre  to 8 E) 8 and above

- How many bags of paddy worth 100 kg do you harvest per acre? A) 1 to 4 bags B) 5 to 8 bags C) 9 to 12 bags D) 13 and above bags

- Do you sell your paddy before processing or after processing A) Before processing B) After processing to rice

- Can you mention the amount of paddy that you sold without processing?

……………………………………………………………………………

- Can you mention amount of paddy that you sold after processing in form of rice?

……………………………………………………………………………

- Do you understand importance of adding value to your crops? A) Yes B) No

- How do you sell your produce? A) in the farm soon after harvesting B) in the farm before harvesting C) In the warehouse individually D) In the warehouse collectively E) Other way of selling, mention

- Had you had any idea of having a community project for value addition in Kamwene village? A) Yes B) No

- If you establish rice milling machine in the village, does the village community have people who will be able to use modern machines A) Yes B)No

- Is there any development partner, NGO or any civil society that has shown interest in supporting the village community to establish rice milling machine? A) Yes B) No

- Do you think that by introducing rice milling machine project in Kamwene village will increase market for your rice? A) Yes B) No

- If the answer is yes, then mention type of rice market which can be reached by your rice after milling.

………………………………………………………………………………………

Do you think that establishing rice milling machine in Kamwene village will contribute in reducing poverty in Kamwene village? A) Yes B) No

- If yes, please mention how it will contribute in reducing poverty in Kamwene village

………………………………………………………………………………………

- If yes, please mention ways that you think that the village community can raise fund for establishing this project I) ……………………………………………

II)………………………………………III………………………………

IV)…………………………………………V)……………………………

- Where do you get service for milling your rice? A) In a village community milling machine B) In a private milling machine within the village C) In a private milling machine outside the village D) Other machines, please mention

- Are there other organizations which are working in the village which you think that they can host the project? A) Yes B) No

- Do you think the village community has enough confidence and trust to this organization? A) Yes B) No

- If the paddy processing machine will be established, do you think the village community will participate in managing the project? A) Yes B) No

- Mention the role of hosting organization to the value addition project ……………………………………………………………………………………

- Mention the role of shareholders and the local government ……………………………………………………………………………………

- Are there farmer’s groups/organizations in Kamwene village? A) Yes B) No

- If the answer is yes, then what kind of groups/ organizations are they? A) Informal groups B) Formal groups registered in the Ministry of Home affairs C) Formal groups registered in the district level by Registrar for societies D) Other forms of registration.  Mention

- Are you a member of farmers’ organizations? A) Yes B) No

- If yes what benefit do you get by being a member of Farmers’ organization?

………………………………………………………………………………………Do you think that your group leaders will be able to manage this rice value addition project? A) Yes B) No

- If the answer is no, then kindly mention who do you think that he/she will be able to manage the project on behalf of the village community? ...................................................................................................................................................................................................................................................................................................................................................................................................

- Do you know that you can own the village community project by buying shares?

- Yes B) No.

- If the answer is yes, are you willing to buy shares in the village community project for rice value addition? A) Yes B) No

- If no, please give reason why don’t you like to buy shares ………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

Appendix II: Letter

# Footnotes

Alliance for a Green Revolution in Africa

Tanzania Mercantile Exchange

# Text boxes

VILLAGE GENERAL ASSEMBLY (AGM)

VILLAGE COUNCIL

VILLAGE CHAIRPERSON

Forestry And Natural Resources Committee

Economic Committee

VEO

Social Welfare Committee

Finance and Planning Committee