POULTRY HUSBANDRY TRAINING TO IMPROVE INDIGENOUS CHICKEN PRODUCTION BY SAFINA AND SHALOM WOMEN GROUPS IN ARUSHA MUNICIPALITY

EMMANUEL SINDIYO

A DISSERTATION SUBMITTED IN PARTIAL FULFILLMENT OF REQUIREMENTS FOR THE MASTER IN COMMUNITY ECONOMIC DEVELOPMENT OF THE OPEN UNIVERSITY OF TANZANIA

2011

# CERTIFICATION

I, the undersigned, Dr Leonard Fweja, certify that I have read and hereby recommend this dissertation for acceptance by the Open University of Tanzania in partial fulfillment of the requirement for the degree of Master in Community Economic Development (MCED).

…………………………….

Dr.Leonard Fweja

Date…………………………

# COPYRIGHT

“No part of this project may be reproduced, stored in any retrieval system, or transmitted in any form by any means, electronic, mechanical, photocopying, recording or otherwise without prior written permission of the author or the  Open University of Tanzania in that behalf”.

# DECLARATION

I declare that this is my own original work, and that it has not been submitted and will not be presented for a similar degree  or any other award in any other University.

Emmanuel Sindiyo

……………………….

Date

# DEDICATION

This work is dedicated to my wife Veronica, my children Sarafina and Ndavukai, my Mother Salome and to all those who strive for the development of the poor communities.

# ACKNOWLEDGEMENT

The output of this work could not be possible without the valuable contribution of many people. Specifically I would like to thank the following for their immense support and encouragement; Dr. S,Onditi, Mrs Dello, and Mr Kitumbo my project supervisor for his committed professional guidance and advice throughout the course of the study, Dr Leonard Fweja, Arusha municipal council  for their cooperation towards the completion of this work. Generally I would like to extend my appreciation and thanks to the instructors and staff of Community Economic Development Program and my fellow CED students. Special thanks to my wife Veronica and my children (Sarafina and Ndavukai) for the support they have accorded me during the whole period of study.

# ABSTRACT

The project was hosted by CBOs called SAFINA and SHALOM women groups found in Engutoto Ward, in Arusha Municipality, Arusha Region. The project report consists of the following areas; Different methodology used in collecting data, Assessment, implementation, monitoring and evaluation. Data collected were analyzed using SPSS computer software program. Prioritizations of the problem were done by using Pair wise ranking. The major identified problems were poor skills on indigenous chicken husbandry among poultry keepers which lead to poor nutrition, poor housing system and high mortality rates due to existence of different poultry killer diseases in the area.  The project implementation have focus on one major area of training on better animal husbandry practices, in which 60 members for Safina and Shalom women groups were equipped with skills in poultry husbandry. The findings for the completed enter versions observed during the monitoring and evaluation showed that there is improvement in egg production, due to the improvement of nutrition, disease control, egg production among poultry keepers increased relative to time before the project, baby chicks motility decreased drastically. Generally this project aimed at strengthening the SAFINA and SHALOM women groups and Engutoto community at large through selected areas of capacity building (training) in order to hasten achievement of the desired benefits, which are primarily vested in increased income and food security.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENT	vi

ABSTRACT	vii

TABLE OF CONTENTS	viii

ABBREVIATIONS	xiii

LIST OF TABLES	xiv

LIST OF APPENDICES	xv

CHAPTER ONE	1

PARTICIPATORY NEEDS ASSESSMENT	1

1.0 General Introduction	1

1.1 Engutoto ward profile	1

1.1.1 Location and size	1

1.1. 2 Administration	2

1.1.3 Population	2

1.1.4 Economic activities	2

1.1.5 Social services	3

1.1.6 Vegetation	3

1.1.7 Ethnicity	3

1.2 Community need assessment	3

1.2.1 Objective	4

1. 2. 2 Research Methodologies	4

1.3 Identified problem	9

1.4 Conclusion	9

CHAPTER TWO	9

PROBLEM IDENTIFICATION	9

2.0 Background to Research problem	9

2.1 Problem statement.	9

2.1.1 Project description;	9

2.2.1 Target Community:	9

2.2.2 Stakeholders	9

2.2.3 Project goal	9

2.2.4 Project Objectives	9

2.3 Host organization	9

2.3.1 Organization structure	9

2.3.2 Role of coordinator (CED student) will be responsible for	9

2.3.3 Role of the CBOs	9

CHAPTER THREE	9

LITERATURE REVIEW	9

3.0 Introduction.	9

3.1 Theoretical literature review.	9

3.1.1 Poultry production as a tool for poverty reduction.	9

3.1.2 Management system	9

3.1.3 Problems related to poultry production	9

3.1.4 Strategy for family poultry development	9

3.1.4.1 Disease control	9

3:2 Empirical Review	9

3:2:1 Poultry industry in Tanzania	9

3.2.1.2 Marketing of poultry products	9

3.2.2 Case study; Senegal	9

3.3 Policy Review	9

3.3.1 Women, Agriculture and Rural Development	9

3.3.2 Agricultural and Livestock Policy 1997	9

3.3.3 Agricultural Sector Development Strategy 2001	9

3.3.4 Sera Ya Taifa Ya Uwezeshaji Wa Wananchi Kiuchumi 2004 (Community Development Policy)	9

3.3.5 Community Development Policy 1996	9

3.3.6 The National Strategy for Growth and Reduction of Poverty. (NSGRP) or (MKUKUTA)	9

3.3.7 The Tanzania Development Vision 2025	9

3.3.8 Summary of Policy Review	9

CHAPTER FOUR	9

IMPLEMENTATION	9

4.0 Introduction	9

4.1 Project Products and output	9

4.2 Project Planning	9

4.2.1 Project Implementation Plan	9

4.2.3 Staffing Pattern	9

4.3 Project Implementation	9

4.3.1 Project implementation process	9

4.2.4 Project budget	9

CHAPTER FIVE	9

PROJECT PARTICIPATORY MONITORING, EVALUTION AND SUSTAINABILITY	9

5 Introductions	9

5.1 Participatory Monitoring	9

Monitoring of Objectives	9

5.1.1. Monitoring information system	9

5.1.1.4 Aggregating information	9

5.1.2 Participatory monitoring Methods	9

5. 1. 3 Participatory monitoring plan	9

5.1.4 Actual Monitoring results	9

5.2 Participatory Evaluation	9

5.2.1 Performance Indicators	9

5.2.2 Participatory Evaluation Methods	9

5.2.6 Actual monitoring results	9

5.2.6.1 Impact indicators	9

5.2.3.3 Intermediate results	9

5.3Sustainability	9

5.3.1 Sustainability Plans	9

5.3.2 Economic and Financial Sustainability	9

5.3.3 Political Sustainability	9

5.3.4 Institutional Sustainability	9

CHAPTER SIX	9

CONCLUSIONS AND RECOMMENDATIONS	9

6.1 Conclusion	9

6.2 Recommendations	9

REFERENCES	9

APPENDICES	9

# ABBREVIATIONS

AIDS               	Acquire Immune Deficiency Syndrome

ASDP                    	Agriculture Sector Development Programme

BRAC                      	Building Economy across Communities

CBO                       	Community Base Organization

CED                        	Community Economic Development

CEDPA                  	Center for Development and Population Activities

CNA                       	Community Need Assessment

CULUFUFIA          	Committee’s Lutte pour la Findele Faim.

DADPS                  	District Agriculture Development plan

GDP                         	Growth Development product

HIV                         	Human infectious deficiency virus

IGA                       	Income Generating Activity

ISRA                         	Senegalese Institute of Agriculture Research

NGO                      	Non Governmental Organization

O&OD                  	Opportunity and Obstacles to Development

PRA                        	 Participatory rural appraisal

SDA                         	Seventh day Assembly

SMES                     	Small medium Enterprise

SPSS                     	Statistical package for social science

# WADP                   	Ward Agriculture Development Plan

# LIST OF TABLES

Table 1: Education status of respondents	9

Table 2:shows different economic activities of community members.	9

Table 3: Types of livestock.	9

Table 4: Common killer diseases of poultry	9

Table 5:Pair wise ranking of the identified community problems	9

Table 6:Stake holder’s analysis	9

Table 7:Project logical framework	9

Table 8:Project implementation plan	9

Table 9:Inputs	9

Table 10 :Project Budget	9

Table11 Project implementation Ghatt chart	9

Table 12 Participatory monitoring Plan	9

Table.13 Three categories of indicators	9

Table14. Evaluation summary Table	9

# LIST OF APPENDICES

Appendix 1: Guiding Questions for the CNA Focus Group (Swahili version)	9

Appendix 2: Questioner (Swahili version)	9

Appendix 3: Poultry keeper daily record form (Swahili version)	9

# CHAPTER ONE

# PARTICIPATORY NEEDS ASSESSMENT

## 1.0 General Introduction

Participatory needs assessment has long been an important community development tool. It identifies unmet needs in the community; provide evidence for support through various interventions. It is both a process and a method. As a process, it can build leadership, group cohesion, and a sense of local involvement in the community as a method, needs assessment is a tool that helps a community plan for and implements strategies in development interventions.	The purpose of conducting the community needs assessment was to identify areas of concern and major issues which the Engutoto Ward community as well as the CBO wish to address. The information was gathered through focus group discussion, survey, records reviews and observation. The information was gathered and analyzed for the major problem identification. Action was taken for designing means to improve the household income through capacity building in poultry production.

# 1.1 Engutoto ward profile

The name of the ward where participatory assessment took place is Engutoto which is a Maasai name meaning sacred place.

# 1.1.1 Location and size

Engutoto Ward is one among seventeen (17) Wards of Arusha Municipal council. It lies between Longitudes 34.5 º – 38˚ degree East and Latitudes 2˚- 6 ˚ south. The ward headquarters lies 6 Km South East   from clock tower along Njiro road. The Ward is situated in Themi division, Arusha district in Arusha region. It has an area of 15 squares

kilometer (1500ha) and is bordered by Lemara and Terat ward in the Western part, Themi Ward in the Northern part and Arusha rural in the Eastern part and southern part.

### 1.1. 2 Administration

There are 6 administrative streets namely Block C1, Block C2, Block F, Block J, Block H and Block D.

### 1.1.3 Population

Engutoto Ward is one of the fastest growing Wards in Arusha Municipality and has a population of 5069 people, a growth rate of 5.4 % (2002 population census), and 1299 household.

### 1.1.4 Economic activities

Major economic activity for people of this area is poultry keeping as well as vegetable production. They keep 952 Cows, 377 sheep, 85 goats, 150 pigs, 10085 indigenous chicken, and 140 tacky. Large part of this area people depend on seasonal rains and during the dry seasons irrigation is practiced mainly in Block C1.The sources of income for the residents who depends on agriculture are the sale of milk, vegetables, eggs and live chicken. Eighty percent (80%) of people who are engaged in agriculture are poultry keepers of these 90% are women. Household income is mainly spent on buying clothes, children books, and paying school fees. Most of the food in the Ward is purchased from the market. The extra food is brought from central market, Kilombero within municipality, and Tengeru market which is located in Arumeru district.  The months when people experience shortage of food are January to April. The farm produce are obtained through irrigation along river Kijenge. The rain fed crops such as maize and beans are planted in small plots in the lower lands. The difference in wealth is not big, relatively when compared to other parts of the Municipality. Very few houses in the area are temporarily built with mud mixed with cow dang. The livestock keeping economy has been continuously affected by decrease of size of the land frequent occurrence of long droughts that make some of the keepers who keep indigenous cattle to migrate to other part of the country like Kilindi in Tanga region searching for pasture and water, this social behavior of keeping large number of cattle has undergoes a natural death due to urbanization.

### 1.1.5 Social services

The Ward has 6 Primary school and 5 kindergarten, one secondary school and 3 private dispensaries and several feeder roads which are roughs road.

### 1.1.6 Vegetation

Three natural vegetation zones can be identified as follows: wooded grassland, bushed grassland and open grassland, all of which cover most of the southern part.  Agriculture forms patches of different cropping patterns. Geological distribution of soil varieties includes red clay loams soil, black cotton soil (clay), and sandy loam.

### 1.1.7 Ethnicity

The main ethnic group of Engutoto community is the agro-pastoral namely Waarusha who forms the largest part of the local population, others are Wasambaa, Waangaza, Wazigua, Wapare, Warangi, Wagogo, Wachaga, Wahaya, Wakamba, Waluguru ,and Waadzabe.

### 1.2 Community need assessment

The concept of community needs assessment connotes a process by which an assessment of the current situation in the community is undertaken, value-based judgments regarding the preferred or desired situation are reached, and some determination of the priority status of local needs is made.

### 1.2.1 Objective

The main objective of this study was to examine the needs of poultry keepers in Engutoto Ward.

#### 1.2.1.1 Specific objectives

- To identify major problem facing poultry production in Engutoto Ward

- To rank the identified problems based on priority

#### 1.2.1.2. Research question

- What are the problems of poultry production Engutoto Ward?

- What is the most pressing problem?

### 1. 2. 2 Research Methodologies

#### 1.2.2.1 Target population

The community here referred to as target population was identified through Arusha municipal council Department of Agriculture and Cooperative that works with several communities in enabling them to achieve their objectives. The selection of the Engutoto ward was based on a visit to the area of operation after consultation with Ward management. The visit revealed that the ward is suitable for this research. Two meetings were conducted with ward executive officers and their streets chair persons to solicit political will.

#### 1.2.2.2 Research design

Longitudinal surveys design in which data are collected over a period of time was used in the current study, particularly a Cohort design. By using this design a group is studied over time though the people in a group may vary. This method was, particularly, useful in ascertaining the specific problems in poultry business, their needs and their sense of ownership.  Both qualitative and quantitative methods were used to enrich the study, and to allow the collection of detailed information from the respondents in their social context. Quantitative methods are, "methods such as surveys and experiments that record variation in social life in terms of categories that vary in amount. Data treated as quantitative are either numbers or attributes that can be ordered in terms of magnitude". This method was selected because the researcher wanted to establish the magnitude of the problem facing poultry production in terms of numbers. On the other hand qualitative methods include participants' observation, intensive interviewing and focus groups discussions that are designated to capture social life as participants experience other than in categories predetermined by the researcher. A qualitative research design was selected because it is a systematic process of discovering social interactions and understanding how they interrelate and influence their environment.

#### 1.2.2.3 Sampling and sample size

Two sampling methods namely simple random sampling  were used. The sample was thus selected randomly from two poultry keeping women groups within Engutoto Ward. The sampling size was 40 out of 62 members of the two groups. Out of forty sampled members 28 were randomly sampled and 12 were accidental sampled while doing home visits with ward extension staff in different communities. Interviews or observations were made when people were available. This method best suited while doing home visits because most of the people visited were doing different activities such as farming and others. Home visits were always done without prior communication with the families to be visited. This was purposely done because the researcher wanted to assess how families take care of their chicken. Prior-communication with the families to be visited could distort the reality because some family members would prepare a good /bad atmosphere to impress the team.

#### 1.2.2.4 Data collection methods

#### 1.2.2.4.1 Secondary data collection

This was done as an exploratory phase of the Community Needs Assessment. It assisted in getting initial ideas of the existing situation and hence formed the foundation of the CAN checklist .Literature review was done in order to gather some information about poultry projects. The literature sources consulted for this study included documents from Arusha Municipal council-Department of Agriculture Livestock and cooperatives. United Nations documents on  food security, national  policies, documents on poultry production as a tool for poverty reduction, documents from bureau of statistics, reports from different partners and other books tackling poultry production issues in different communities. Other sources were the internet and Microsoft encyclopedias.

#### 1.2.2.4.2 Primary data collection

This entails the actual field work for data collection in which several methods were used.

#### 1.2.2.4.2.1 Questionnaires

Questionnaires were designed in order to obtain specific information about the condition of poultry production in Engutoto Ward. The administered questionnaires had different types of question which focused on economic, social, Health and environmental issues. The questionnaire also aimed at gathering information on problems facing poultry production in the area, land availability in relation to type and number of livestock kept, sense of ownership, entrepreneurship skills and knowledge on poultry production.

#### 1.2.2.4.2.2 Observation

Observation was one of the ways used by the researcher all the time of the research process in the study area, in order to collect data. This method focused much on conversations, non-verbal communication, general behavior of respondents and the environment in general. In other words, the researcher was able to come in touch with the reality of poultry keepers in these communities. This method was chosen purposefully to compliment other methods, and especially, interviews. In addition to that in some circumstances people would shy off from interviews, and therefore, observation seemed the best data collection tool. Through observation, the researcher aimed at gathering more information on the conditions, facilities and services available.

###### 1.2.2.4.2.3 Focus group discussion

Focus group discussion was done in three groups each consisting of 10 individual respondents.  The group composed of 10 community members. A focus group guide was prepared in order to enable the researcher to gather specific information from the participants.

#### 1.2.2.5 Reliability of Data

- Information provided was measured by comparing information's of respondents among the member group and the physical observation method used to ascertain the reliability of the respondents.

- After analyzing data the information obtained have been critically viewed to test its validity and truthfulness of the data obtained from the respondents.

- The data gathered have been compared with the documented findings of other similar project carried within the country and elsewhere in the world.

- The survey objectives were clearly defined to all stakeholders and the feedback questions showed that they understood clearly the objectives.

- Questions for both questionnaires and interviews were designed to reflect the need of the survey and were tested before and modified where it seemed necessary.

#### 1.2.2.6 Validity of the data

- Information gathered during needs assessment have been used as baseline source of information. In order to validate the data gathered, some other documents/literatures were reviewed on the same topic.

- There has been adequate description and methods to establish reliability.

#### 1.2.3.4 Data analysis methods

Data analysis means, "...tallying and averaging responses, looking at their relationships, and comparing them...” Both qualitative and quantitative data analysis methods were employed. Qualitative analysis involves presenting text or narrative data. Quantitative data analysis involved the use of scales of measurement and descriptive statistics which was done by using SPSS version 16.

##### 1.2.3.4.1 CAN findings

##### 1.2.3.4.2 Education level

Results in Table 1 shows the education level of respondents involved in poultry keeping. The largest proportion of this community (65%) has the basic education, that is, primary level education and about quarter (23%) of the total sample have secondary level education. Less than 10% have tertiary level education and there is still a significant level of illiteracy within the community (6%). The findings generally show that, the community is still illiterate and the education level implies the involvement of the majority of community members in informal activities but with limited know-how.

Table 1: Education status of respondents

| Education level | Frequency (y) | percentage | Valid percentage | Cumulative percentage |
| --- | --- | --- | --- | --- |
| Primary education | 26 | 65 | 65 | 65 |
| Secondary education | 10 | 23 | 23 | 88 |
| Informal Education | 2 | 6 | 6 | 94 |
| Post secondary | 2 | 6 | 6 | 100 |
| Total | 40 | 100 | 100 |  |

Source: Field Survey Findings, 2011

##### 1.2.3.4.2 Economic activities

Result in Table 2 shows different economic activities of respondent. The largest proportional of the community (60%) keep livestock as their income generating activities and about a quarter (27%) practice mix farming that is keeping livestock and practicing horticulture. About 10% of them practice horticulture and only 3% of this community are doing other economic activities which is not agriculture related. The finding generally shows that majority of this community depend much on livestock keeping and therefore more resources should be allocated for the development of this sector.

Table 2:shows different economic activities of community members.

| Type of activity | Frequency | Percentage | Valid percentage | Commutative percentage |
| --- | --- | --- | --- | --- |
| Livestock keeping | 24 | 60 | 60 | 60 |
| Livestock keeping and horticulture | 11 | 27 | 27 | 87 |
| Horticulture | 4 | 10 | 10 | 97 |
| Non Agricultural activities | 1 | 3 | 3 | 100.0 |
| Total | 40 | 100.0 | 100.0 |  |

Source: Field Survey Findings, 2011

###### 2.3.4.2.1 Types of livestock

Result in Table 3 shows different types of livestock kept by this community. Majority of the respondent (71%) keep indigenous chicken and about (24%) keep ruminants that is 12% dairy cows and another 12% keep goats. Few of them (5%) keep rabbits. The finding generally shows that poultry industry is a sensitive and area of more attention by this community relative to others.

Table 3: Types of livestock.

| Type of livestock | Frequency | Percentage | Valid percentage | Commutative percentage |
| --- | --- | --- | --- | --- |
| Dairy cows | 5 | 12 | 12 | 12 |
| Dairy Goats | 5 | 12 | 12 | 24 |
| Rabbit | 2 | 5 | 5 | 29 |
| Indigenous Chicken | 28 | 71 | 71 | 100.0 |
| Total | 40 | 100.0 | 100.0 |  |

Source: Field Survey Findings, 2011

###### 1.2.3.4.1.2. Common killer diseases;

The common killer diseases of poultry in the study area are presented in Table 4. The largest proportional of the respondent (60%), reported New castle (Kideri) as the most dangerous killer disease of poultry. Less than 50% are killed by eye infection and flue (20% flue, 20% eye infection). The magnitude of the problem implies poultry keepers lose their capital {poultry) due to these major killer diseases.

Table 4: Common killer diseases of poultry

| Type of disease | Frequency | Percentage | Valid percentage | Commutative percentage |
| --- | --- | --- | --- | --- |
| Eye Infection | 8 | 20 | 20 | 20 |
| New castle Disease | 24 | 60 | 60 | 80 |
| Flue | 8 | 20 | 20 | 100 |
| Total | 40 | 100.0 | 100.0 |  |

Source: Field Survey Findings, 2011

## 1.3 Identified problem

Four problems were identified by the community members as summarized in Table 5. Of the four identified problems based on the pair-wise ranking which involved community members it was revealed that inadequate education in indigenous chicken husbandry was the most pressing problem which underlies poor poultry production. Other problems are lack of entrepreneurship skills, existence of poultry diseases and poor nutrition.

## 1.4 Conclusion

This chapter has explored on the community Needs Assessment Survey which was conducted in Engutoto Ward, Arusha Municipality. The assessment shows that indigenous chicken keeping is the main income generating activity for women in Engutoto ward and the major identified problem that faces their project is lack of skills on indigenous chicken husbandry.

Table 5:Pair wise ranking of the identified community problems

| Identified problem | In adequate skills on poultry husbandry | In adequate education on entrepreneur ship skills | Existence of poultry diseases | Poor nutrition | Score | ranking |
| --- | --- | --- | --- | --- | --- | --- |
| In adequate skills on indigenous chicken husbandry |  | In adequate skills on indigenous chicken husbandry | In adequate skills on indigenous chicken husbandry | In adequate skills on indigenous chicken husbandry | 7 | 1 |
| Poor nutrition | Skills on poultry husbandry |  | poor nutrition | In adequate skills on indigenous chicken husbandry | 3 | 2 |
| Existence of poultry diseases | In adequate skills on indigenous chicken husbandry | Ed on entrepreneurship skills |  | poor nutrition | 2 | 3 |
| In adequate education on entrepreneur ship skills | In adequate skills on indigenous chicken husbandry | Poor nutrition | Existence of poultry diseases |  | 0 | 4 |

Source: Field Survey Findings, 2011

# CHAPTER TWO

# PROBLEM IDENTIFICATION

## 2.0 Background to Research problem

This chapter focuses on problem identification based on Community Needs Assessment (Group PRA) which was carried out in November 2010. It was from these results that the group members agreed that lack of skills in indigenous chicken husbandry was the main problem they were facing in their project. Lack of husbandry skills could lead to failure to poor feeding and general management including record keeping and housing system. It was from these findings that it was deemed important to impart appropriate techniques/skills on the members to alleviate the situation.

## 2.1 Problem statement.

Poultry husbandry can make a commercially profitable business and a home to be self sufficiency provided the indigenous chicken keepers are well skilled with husbandry techniques. Though Engutoto Ward community is highly dependent on indigenous chicken keeping for its livelihood, the business has been facing a lot of problems which include high mortality rates, poor housing and nutrition all leading to poor egg and meat production. The underlying root cause of this is poor husbandry skills which were also identified as the most pressing problem by community members (Table 1) which has existed for quite some time without being addressed.

The current proposed project thus aims at equipping indigenous chicken keepers with poultry husbandry skills to sustain their business and improve their livelihood through improved food security and income generation.

# 2.1.1 Project description;

The purpose of our project is to collaborate with Safina and Shalom women groups members to start initiatives by organizing ourselves and allocate time for  training so that to acquire skills  in indigenous chicken husbandry and practice  them to get better results.

### 2.2.1 Target Community:

The project serves two women groups (safina and shalom).

## 2.2.2 Stakeholders

The community in collaboration with the researcher identified key stakeholders those who play significant role in community development who are: Timber mill, Ward Advisory Committee, BRAC foundation, Seventh day Dispensaries and animal inputs shops. All these organization play a great role in its area of operation to contribute to the community sustainable development goals. The following is the summary of their role in the communities.

Table 6:Stake holder’s analysis

| Name of stakeholder group/organization | Role in the project |
| --- | --- |
| SAFINA AND SHALOAM WOMEN GROUP | -Beneficiary of the project –They will offer time, ideas, physical and manpower |
| ARUSHA MUNICIPAL COUNCIL | -Provide funds and 1 staff who will train the group members on feeds and feeds formulation. |
| BRAC FOUNDATION | -Technical support on disease and disease control, they support also some New castle vaccine |
| CED STUDENT | -Coordinating, project writing; consolidate community idea for the benefit of the Project, participatory planning monitoring and evaluation. |
| ENGUTOTO WARD(ward executive officer) | -Security and administrative support |
| TIMBER MILL | -Provide timber services to the community Member group procure some timber from this miller |
| SEVENTH DAY DISPENSARY | -Provide Health services to the member group The fact that it is the only Dispensary which is very near to them. |
| ANIMAL INPUT SHOPS | -sell animal feeds and veterinary drugs to the community |
| SHOPS AND KIOSK | Purchase poultry and poultry products(eggs, live chicken for meat) |

### 2.2.3 Project goal

The majority of community members particularly women are involved in poultry keeping as their main economic activity. However the business has been doing poorly because of the ignorance in poultry rearing. This is reflected by poor nutrition, frequent occurrence of diseases which have been killing a lot of chicken and other husbandry related problem. To address this situation the current project goal is to train community members about indigenous chicken husbandry to equip them with the necessary skills for successfully undertaking the business. This will ensure proper husbandry practices and thus lower the poultry mortality, improve the general poultry husbandry, improve productivity and hence their income.

### 2.2.4 Project Objectives

Overall objective

The overall objective is to equip poultry farmers with the general husbandry skills

Specific objectives

- To train 60 members of Safina and Shalom groups on indigenous chicken nutrition by February 2011.

- To train 60 members of Safina and Shalom groups on indigenous chicken disease control and prevention by March 2011.

- To train 60 members of Safina and Shalom groups on the procedures for the management of poultry as indigenous and crossbreeds chicken by June 2011.

## 2.3 Host organization

The host organization for this project re the two community based organizations (CBO) that is, Safina and Shalom Women groups, the two groups were selected so that to get a reasonable number of women who are performing daily duties in indigenous chicken production. The groups were established in February 2009 and are in the final process of registration. These organizations have the same Vision, Mission and Organization structures each group have 30 members each member run her own indigenous chicken poultry  project at their back yard. Their social capital, cohesiveness and willingness to learn are their greatest asset. The group leadership mastery of the groups dynamics and was able to motivate the members to desired goals. These groups drew support from Arusha municipal council department of Agriculture and livestock development.

### 2.3.1 Organization structure

The structure shows the group office bearers who were elected in 2009 and according to group’s constitutional handout the new leaders would be elected in 3 years time. The general assembly is the annual member meeting and according to constitution the assembly would meet either at the end of the year or beginning of the next year.

Below are general roles and responsibility at each level

I. General assembly

To discuss all issues arise from monthly group meetings

Approve new members who are joining the group

Approve funds to be used for the development of member group’s projects

Discuss displine matters when arise

Conduct and monitor election when due

II.Chair person

Supervise day to day activities of the group

Organize minute’s reports prior to general assembly

Link group members with service providers within the ward and outside

Conduct assessment and nominate new comers and submit their names to the general assembly meeting for approval

III. Executive secretary

Support chairperson in all matters within a group

She is responsible in preparing meeting minutes monthly

Keep group records

IV.Treasure

Keep financial record of the group

Prepare financial reports and submit to chair person for monthly meeting

Manage creditors and debtors within the group

Help in preparation of annual budget, collection of funds and its management

Vision

Group members with a growing and sustainable economy.

Mission Statement

Safina and Shalom group mission is to generate employment for increasing income and providing services and benefit the health safety and welfare of the group members.

SWOT analysis

Strength

Presence of land for agriculture, Experienced farmers in traditional farming, Well defined organization structure, Presence of farmer groups, Farmers are eager to learn, Presence of indigenous chicken, Improved infrastructure, Adequate labor force, Presence of development spirit built among group members.

Weakness

Lack of correct and update statistics, High illiteracy rate among member group,Poverty,Poor farming practices, Lack of skills in poultry production, Lack of entrepreneurial skills among members.

Opportunities

Adequate labor force within the area, Proximity to town market, Abundant streams and furrows for irrigation in the upper lands, Farmers eager to learn and adopt, Existence of financial credit institutions near to the ward, Connection to farmer’s forum-MVIWATA,Existence of NGOs , Committed leadership.

Threats

Rapid population increase, Urban expansion into farm land, pest and diseases, Soil erosion & gullies, Agro pricing mechanism, HIV/AIDS and other pandemic, Culture and taboos, Policy changes, Unfavorable terms of credit, Drought.

### 2.3.2 Role of coordinator (CED student) will be responsible for

Making sure the project activities are implemented as according to the annual plan, budget approved. Preparing monthly, quarterly, semi-annual and annual progressive and financial reports, Controlling the efficiency and effective use of the finances, Organize and network so as to solicit other sources of fund in order to interview other un-reached areas of the community need, supervising group activities through collaborating with group treasurer and group committee, preparing and presenting progress report of the project in the evaluation meetings which involves all stakeholders, any other duty as may be directed by his immediate supervisor.

### 2.3.3 Role of the CBOs

Act as main implementers of the project, advice community to join the group and solicit funds from donors.

# CHAPTER THREE

### LITERATURE REVIEW

## 3.0 Introduction.

Literature Review is the body of text that aims to review the critical points of current knowledge including substantive findings as well as theoretical and methodological contributions to a particular topic. The function of a scientific literature review is primarily to collect and examine the state of current knowledge in a field by examining the work of scholars and researchers whose work have been recognized as valuable.  Ultimately, a well researched and written literature review accomplishes three goals.  These are; establish context for your work by showing what has been done in the area Exposes the gap in current knowledge shows your supervisors that you have done your research. This chapter will provide theoretical, empirical literature review and policy review on poultry project.

## 3.1 Theoretical literature review.

### 3.1.1 Poultry production as a tool for poverty reduction.

Gueye, 1998 describes that poverty, is both a cause and a consequence of inability to cope with shocks. The poor are often considered more vulnerable to shocks because of the assumed lack of diversification in their income and/or asset portfolio. In low income countries of Sub-Saharan Africa this vulnerability of the poor to various shocks is considered to be of most importance for policy targeting. In the limited livelihoods diversification that poor households tend to have livestock that constitutes an important source of income and in general comprises the most important asset to them. Free range local chicken production is the one of which its  numbers in Africa are increasing annually despite the threat of diseases such as Newcastle, Fowl typhoid and other problems such as poor management, endo-parasites and vermin attack. Boki (2000) estimated the free range local chicken numbers in 1995 at 26 million, while for Kenya,  estimated them to be 22 million for 1997.Also evidence shows that most consumers prefer free range local chicken than commercial ones derived from imported flocks and that free-range local chicken production fetch premium prices. For example, in Dar es Salaam, an indigenous chicken egg is sold at TShs 300 while that of a layer at between TShs 80 and TShs 100 and such eggs are plentiful in the streets Boki(2000). Small scale poultry production systems either in the form of small semi- or fully scavenging household flocks or a slightly larger more intensive units have developed in a large number of developing countries around the world as a source of livelihood support for the rural poor. There is also growing evidence to demonstrate the role of small scale poultry in enhancing the food and nutrition security of the poorest households and in the promotion of gender equality.In many developing countries, poultry production is based mainly on traditional extensive poultry production systems (Sonaiya et al., 1998). All over the developing world these low input/low output husbandry systems have been a traditional component of small farms for centuries and are assumed to continue for the foreseeable future. It estimated that 80 percent of the poultry population is found in traditional family-based poultry production systems, which contribute up to 90 percent of poultry products in some countries. Approximately 20 percent of the protein consumed in developing countries originates from poultry (i.e. meat and eggs). Yet, despite the importance of family poultry, relatively few field programmes have been initiated to improve the output.

Family poultry is an integrated component of nearly all rural, many peri-urban and some urban households and provides valuable protein and generates extra cash. All ethnic groups tend to be involved in family poultry production. Women, assisted in some cases by children, as they are the main owners and managers of family poultry. For instance, according to Guèye (1998), more than 85% of rural families in sub-Saharan Africa keep one or more species of poultry, and more than 70% of chicken owners are women.

### 3.1.2 Management system

Four management sub-systems have been described by Bessei (1987) and Sonaiya (1990). There are the free-range system or traditional village system, the backyard (family or subsistence) system, the semi-intensive system and the intensive husbandry system. The two first types are the most commonly practised in rural Africa Gueye (2000). There is no doubt that adoption of one or more management sub-system(s) is largely determined by the availability of resources and inputs i.e. housing, cages, feed, drugs and time. Also, these management sub-system(s) frequently overlap, thus, free range is sometimes coupled with feed supplementation, backyard with night confinement but without feeding; standard poultry cages in confined space, etc.

### 3.1.3 Problems related to poultry production

The most striking problem in relation to poultry production is the high mortality.

Mortality rates may be as high as 80-90% within the first year after hatching. Traditionally, Newcastle disease is believed to be the most devastating disease in free-range systems and the main course of the high mortality (Katule etal, 1990) However, many other factors affect the efficiency of poultry production either directly or indirectly. These include the genetic constitution of the host, nutrition (or malnutrition), environment, management, other diseases and societal pressures that can interact in multiple ways influencing the ultimate productivity level, the overall mortality rate and the quality of the final product. Successful poultry production also includes the possibility of obtaining loans for further investments and improvements of the production. In village production only small loans are needed, but they are mostly impossible for the producers to get, poultry production has the potential to become a considerable business. In particular, it is unique among the livestock productions in respect to gender, as females often take care of these animals (Fattah, 1999).

### 3.1.4 Strategy for family poultry development

To improve family productivity, and move from backyard to semi-intensive/commercial poultry production, a number of important constraints have to be overcome (Guèye, 2000).

### 3.1.4.1 Disease control

Newcastle disease (ND) constitutes the most serious epizootic poultry disease throughout the world, particularly in developing countries. No progress has been made in controlling ND in free ranging village flocks, which represent more than 80 percent of the total poultry population. For example, several surveys in Africa showed high rates of seropositivity in the absence of vaccination. In developing countries, ND occurs every year and kills on an average 70-80 percent of the unvaccinated village hens. It is very difficult to organize vaccination campaigns covering free-range birds and the main constraints are: the difficulty of grouping together an adequate (large) number of birds in order to obtain an efficient vaccination rate; birds of various ages are usually raised together; and the need to maintain, at all stages, an efficient cold chain for proper vaccine conservation. Furthermore the large number of farmers involved implies the need for considerable budgets (vaccines costs, transportation, refrigeration equipment, etc.) and makes actual vaccination programmes difficult to accomplish. In fact, planned vaccination programmes using existing commercial vaccines to control ND in village poultry have been successful, but the need for large labor and technical inputs has limited their efficiency. It should be kept in mind that, besides the vaccination, other general approaches can be used to control ND: hygiene, slaughter of infected birds and selection for resistance to the disease or for a better immunological response. Moreover, ND does not represent the only disease affecting family poultry. Consequently, the following activities are recommended: Epidemiological surveys at a regional level should be conducted in order to propose appropriate and low cost vaccination schemes. Based on the survey results, appropriate vaccination programmes have to be established. Training and use of perverts, preferably women, to undertake vaccination at group level.

#### 3.1.4.2 Protection against various predators

Predators such as snakes, rats, dogs, cats, foxes, raccoons, birds of prey represent the main causes of losses, especially in young birds. Human beings can also represent another important predator for adult birds! Prevention can be contemplated through the following measures: Proper housing that should be constructed using locally available materials. Predators should be trapped, hunted or repelled by specific plants. For example, in Nigeria, sliced garlic (Allium sativum) is placed around poultry houses to keep off snakes.

#### 3.1.4.3 Feeding

Careful attention should be given to ensuring adequate feed resources, which represent 60 to 80 percent of the economic inputs in the commercial poultry sector. It is, therefore, not advisable to develop a wholly grain-based feeding system. The recommended policy is to identify and use locally available feed resources to formulate diets that are as balanced as possible. Research capacities must be strengthened to develop strategies to optimize locally available feed. Both conventional and alternative feed resources that are readily available to smallholder farmers should be identified. Shrub leaves (Leucaena sp., Calliandra sp., Sesbania sp., etc.), aquatic plants (Azolla sp., water hyacinths, etc.), insects (termites), fruits (palm-oil fruit, papaya, guava, etc.), small animals (e.g. snails, earthworms), etc. can all be used as poultry feed. These products are rich in protein as well as vitamins and minerals and are all appropriate for supplementing diets of scavenging poultry. All these products, and the list is far from being exhaustive, are available in some parts of a country and during certain periods of the year; however, people must be skilled in using them properly. This implies the need for extension officers and farmers to be trained in the use of these alternative feed resources.

#### 3.1.4.4 Family poultry farmers' organizations

Organizing family farmers is not an easy task. There are several reasons. Flock sizes are small and birds are maintained with minimal land, labor and capital inputs. That means that farmers generally consider family poultry as secondary occupation compared with other activities in agriculture, trade, etc. Nevertheless, it is essential to: develop producers groups which will: allow the group members to have easier access to inputs: feed supplementation, improved birds, drugs and vaccines, technical advice, etc., and facilitate access to credit, training, transportation and marketing of poultry products encourage educated people to initiate poultry farming as a secondary occupation, conducted at family level using medium-sized flocks, and develop associated activities like market gardening that can utilize poultry manure and help to reduce or remove household waste and pests.

#### 3.1.4. 5 Genetic improvement

Indigenous or local breeds are generally raised in family poultry production systems. These birds are usually selected for their hardiness and sometimes for meat production, but not for egg production. Hens are thus poor layers; however they are good hatchers, except for guinea hens. When farmers contemplate to adopt a more intensive poultry production system, they are eager to purchase more productive birds. There is a need to find the best method to provide them with such birds and the options are: to supply hybrid strains which means the presence of well managed hatchery facilities and (grand) parent stock, or to supply purebred breeds which allow the farmer to renew his flock and to remain independent from external suppliers. Unfortunately purebred breeds are more and more difficult to purchase and produce less than hybrids. However, poor hatching is commonly observed from hatcheries in many developing countries, especially in sub-Saharan Africa. Also, regular imports of hybrid parent stock must be carefully planned because usually there are many obstacles to overcome, e.g. purchase of importing licenses, obtaining hard currency, adequate shipment and transportation facilities, customs clearance and ensuring excellent conditions for the reception of birds, etc. Smallholder farmers cannot afford to carry out these operations themselves, while government structures have proved unreliable and the private sector does not seem really interested. However, some solutions have proved to be efficient: Joint-ventures with multinational companies interested to distribute their own products, Farmers Organizations that are able to provide their members with all necessary inputs, including imported birds .It is also possible to import less productive purebred and robust breeds for distribution to farmers, and allow them to conduct their own genetic improvement. However, many of these operations, like cock exchange programmes in the past have failed, essentially because there was a lack of proper and continuous monitoring and exotic birds did not survive under the harsh conditions prevailing in many developing countries. Therefore, it is recommended that indigenous stocks be studied and preserved.

#### 3:1:4:6 Marketing facilities

Poultry products in most developing countries, especially in Africa, are still expensive. The marketing system is generally informal and poorly developed. Unlike eggs and poultry meat from commercial birds derived from imported stocks, consumers generally prefer those from indigenous stocks. The existence of a local market offering good sales opportunities and adequate transport facilities are obvious prerequisites for family poultry development. As most consumers with the greater purchasing power live in cities, intensification of poultry production should be initiated in peri-urban areas or, at least, in areas having a good road network.

#### 3.1.4.7 Training and management

Technical skills need to be considered at both farmer and extension levels. Training is essential for both farmers and extension officers in the following areas: disease control, housing and equipment, feeding, genetic improvement and marketing. A basic knowledge in specific features of poultry anatomy/physiology is also important to understand the basis of the above topics. Housing and management could be improved through appropriate farmer training, preferably conducted on-farm. Local craftsmen could be trained to manufacture small equipment, like feeders, drinkers, etc.

## 3:2 Empirical Review

### 3:2:1 Poultry industry in Tanzania

The poultry industry in Tanzania comprises commercial poultry production with broilers and layers, and the traditional poultry production, which is sometimes called the scavenging or scratcher production, made up of various types and sizes of birds. The total number of poultry as estimated in the 1994/95 sample census of agriculture was about 30 million. Poultry production together with other small livestock contributes 5.4% to the total GDP. Poultry are the most evenly distributed in Tanzania because (Kibari Boki, 2000).They are not affected by tsetse flies which limits other stock like cattle; They are accepted by most religious groups (unlike pork which is not taken by Muslims);They multiply very fast; They are easy to dispose of (unlike cattle which if slaughtered for family use, need storage or refrigeration); They are easy to market and one gets money which can be used for other purposes; Poultry manure can be used as raw material for feed formulations, fed directly to fish, poultry manure is important for fertilizing soils and commonly used in gardens etc; and Poultry meat and eggs are good sources of protein.

#### 3.2. 1.1 Traditional poultry production.

Traditional or indigenous chickens are the most numerous of the domesticated chickens. According to the sample census of agriculture 1994/95 there was 26,385,506 indigenous

Chickens which supply 100% of the poultry meat and eggs in rural areas and 20% of the poultry meat and eggs consumed in urban areas (Kvan Velune, 1987). These birds are believed to have a low genetic potential for production but have the ability to survive under harsh conditions (scratch and scavenge to obtain their feed, poor housing, poor husbandry including disease control). They are normally kept in the backyard or in the house, let out in the morning and locked in during the night. The average carcass weight is between 0.6 and 1.2 kilogram. Egg production is between 40 and 60 eggs per annum. All these birds are kept by smallholder farmers with flock sizes ranging from 10 to 30 birds per household.  Efforts to improve the production and productivity of the indigenous chickens through upgrading started in 1937 when exotic breeds were introduced. In 1943, other upgrading programmes were initiated using cockerels imported from South Africa. The cockerels were reared for 10 weeks and sold to farmers. In 1982, the Food and Agricultural Organization (FAO) agreed to finance a programme for rural poultry. In 1986, an up-grading programme used imported Rhode Island Red and Barred Plymouth Rocks and sold them to farmers as a package to include males and females in several stations. The chicks were normally reared up to 10 weeks. At farmers’ level the pure breeds were let to mix with the indigenous birds and mate randomly. This approach had

the following advantages:

The pure breeds could multiply under village conditions and act as a source of pure breeds to other farmers and also they could produce more meat and eggs than the indigenous birds;

- Pure indigenous birds will continue to be multiplied through crossing;

- Several crosses will be produced which will produce more meat and eggs; and

- There will be no need to introduce incubators at village level, as indigenous chickens will continue brooding. This programme stopped in 1989 when the FAO funding stopped. There has not been any follow-up on the actual field performance due to financial constraints. In 1998/99, a diversification programme of the Special Programme on Food production to improve household food security started to improve small stock including poultry. In this programme improvement of rural chicken is done through disease control particularly vaccination against Newcastle disease, proper housing, feeding, etc. in the regions of Morogoro and Dodoma.

### 3.2.1.2 Marketing of poultry products

According to (Mozi, 2003), Tanzania is a very big country with very poor infrastructure (roads, telecommunication). Movement of products from one place to another is therefore a major problem. Similarly, marketing of poultry and poultry products in urban, peri-urban, and rural areas is a problem. Commercial poultry farmers for layers or broilers are disorganized and there is no proper marketing. A producer sells their products (eggs or live broilers) to consumers directly or through middlemen. It is worth noting that Tanzanians prefer to buy live chickens and slaughter at home; dressed and refrigerated meat is not commonly preferred. In rural areas, indigenous chickens are bought by middlemen who later transport them to market places or sell to urban consumers. Farmers also sell eggs and live poultry at local markets. In the village, households do slaughter their own chicken as well as consume some of the eggs, leaving the rest for hatching.

### 3.2.2 Case study; Senegal

A unique collaboration between the Network for Smallholder Poultry Development, a Danish NGO, Bicycles for Senegal, and the Senegalese farmers’ association, COLUFIFA (Comité de Lutte pour la Fin dela Faim) resulted in a highly successful pilot poultry project in seven villages in Casamance in Southern Senegal. As an immediate output of the project after 1.5 year the number of chickens has increased significantly, and, more important, the women have experienced more self-confidence and a higher social standing in their community. Now more than 200 women are involved in smallholder poultry activities, and numbers chickens and women involved are growing by the day. The beneficiaries are among the poorest of the poor, and they have been selected through a participative process in each target village. Besides increasing the income of the families, the project also aims at empowering the women and strengthening the capacity of their organization. Women received technical training (housing, feeding, health, and general management of the poultry) in order to be able to generate a small income from semi-scavenging poultry. After an introduction to savings, credit and marketing, they get access to a small credit of up to about 55 USD each. Avery important part of the project is the organization of the women. The 30 beneficiaries per village are divided into small groups of 5 in each with social collateral for the credit, and they meet once a week to discuss the problems encountered in the management of the chickens. A Farmer Field School approach is being used. The project is implemented by COLUFIFA, which has contracted local partners to undertake the training, the credit and the veterinary assistance. Besides, COLUFIFA has engaged in collaboration with the Senegalese Institute of Agricultural Research (ISRA) in Dakar (Riis etal.).

### 3.3 Policy Review

### 3.3.1 Women, Agriculture and Rural Development

According to the Fact Sheet Tanzania by FAO, 1995, a new agricultural policy which was inaugurated in January 1997 was the result of four main reasons: the merger of agriculture and livestock policies; changes due to economic policy transformation; initiation of a new land policy that advocates changing land use patterns; and emphasis on environmental management and protection.

### 3.3.2 Agricultural and Livestock Policy 1997

According to Agricultural and Livestock Policy 1997, in the short and long term goal agriculture will continue to play a major role in the national economy. The policy deploys the need of review and analyses its sector performance with the view to identifying and removing constrain that prevent from making maximum contribution. The policy shows the key economics areas which are highly contributed by agriculture, this include country growth domestic product (GDP), export earning and employments in which the agriculture sector accounts for 60% and 84% respectively.

#### 3.3.2.1 The Poultry Industry in Tanzania

The poultry industry in Tanzania is guided by the poultry policy of the year 2002, which insists on promotion of indigenous poultry breeding and development of the traditional flocks so as to exploit their production potential. The poultry industry in Tanzania is categorized according to the type of production as traditional and commercial production systems. The traditional system is the largest contributing to more than 50% of the flock, supplying most of the poultry meat and eggs consumed in rural and about 20% in urban areas. The common indigenous chicken types include Kuchi, Kishingo, Sukuma, Kinyavu and Kiduchu. Poultry kept in the traditional system offers the potential for a relatively quick increase in productivity through the introduction of improved husbandry practices, technical support services, diseases control and breeding. Commercial poultry production is mostly practiced in urban and peril urban areas where they are confined. Productivity levels in the commercial poultry production system, which produces most of the poultry meat and eggs for urban consumers, are constrained by disease, poor quality feeds and weak enforcement of hatchery regulations. The policy objective is to increase quantity and improve quality of poultry and its products to satisfy domestic demand, increase export and promote sustainable poultry production. The policy further stipulates that development of traditional flocks and indigenous poultry breeding shall be promoted.

### 3.3.3 Agricultural Sector Development Strategy 2001

According to national Agricultural Sector Development Strategy 2001(ASDS), it highlighted some of the agricultural sector challenges which include low productivity, poor coordination and limited capacity, underdeveloped supporting facilities, erosion of the natural resource base, in appropriate technology, dependency on rain fed agriculture and access to food markets. The strategy indicated the possibility of the country to increase agriculture products such wheat and rice as the means to replace imports and expand food and livestock exports to neighbor countries. The strategic (ASDS) document puts forward the need of increase private sector participation and agriculture development in general by creating the favorable climate for commercial activities. The government aims at devising appropriate investment incentives for agriculture sector harmonize and publicize the agricultural sector legislation and that of collaborating sectors; provide legal empowerment for stakeholders to control commodity boards; legalize and promote cross-border trade; streamline procedures for legal access to land and undertake land demarcation and surveys in agricultural investment zones.

### 3.3.4 Sera Ya Taifa Ya Uwezeshaji Wa Wananchi Kiuchumi 2004 (Community Development Policy)

According to Sera Ya Taifa Ya Uwezeshaji Wa Wananchi Kiuchumi 2004, (Community Development Policy), the land was stated as ineffectively utilized to enable the citizen to fully participate in economic development. For this reason the Government will utilize the land by enabling her citizen to increase their income and access share through land in order to actively involve in economic development. The strategies to be used include developing infrastructure in arable land so that it will be used for agriculture production. Also to develop infrastructure which will accommodate agriculture, livestock, business and other economic development activities? The Government also intends to enable the farmers and other land users to access the credits through land.

### 3.3.5 Community Development Policy 1996

Community Development Policy, 1996, aims at enabling Tanzanians to bring about their own development by working to improve production so that they may have increased income which will enable communities to build a better life through self reliance and use of locally available resources. It acknowledges this approach as the major way to eradicate poverty. The policy focusing areas include eradicate poverty through involving those responsible for bringing about community development by advising and training individual families and households, encouraging groups or cooperative productive activities. It also focus on responding to and meeting the need of special groups of women, children and youth in order to reduce their work load, strengthen family income generating projects and enable them to participate in decisions and ownership of family property.

### 3.3.6 The National Strategy for Growth and Reduction of Poverty. (NSGRP) or (MKUKUTA)

MKUKUTA (Mkakati wa kukuza Uchumi na Kupunguza Umaskini Tanzania) was approved by the cabinet of Tanzania in February 2005 for implementation over five years. MKUKUTA says that "the small and medium scale enterprises (SMEs) lack Financing; technical and managerial skills; infrastructure; market information; and contacts with external markets. Rural areas lack road networks and telecommunications hence constraints markets, foreign and domestic trade, employment and restricts access to social services. The strategy identifies three clusters one of them is growth and reduction of income poverty; this cluster supports objectives of the poultry project. The cluster focuses on scaling up investments towards modernizing small, medium and large scale agricultural enterprises, promoting off-form activities including Small and Medium size Enterprises with emphasis on agro-processing, and promoting more sustainable use of natural resources for the benefit of poor communities. The strategy gives attention to trade, services and markets, infrastructure, and creating conducive environment to attract private investments. Internationally, the project objectives go in line with the millennium Development Goals - goal 1 eradicates extreme poverty and hunger.

- Reduce by half the proportion of people living on less than a dollar a day.

- Reduce by half the proportion of people who suffer from hunger.

### 3.3.7 The Tanzania Development Vision 2025

The vision come to being after the realization that, the country need to develop itself in all areas in order to be active participants as the nation in a global development world characterized with advance technology, high productivity, modern and efficient transportation and communication infrastructure. The Development vision objectives include achieving quality and good life for all; good governance and the rule of law; and building a strong and resilient economy that can effectively withstand global competition. The national development vision deploys the intent of being people centered. It consider the national development as fact in which wealth are created and distributed freely from inequalities and all forms of social and political relations which inhibits empowerment and effective democratic and popular participation of all social groups in society. The government committed to create the situation so as to foster economic transformation from a low productivity agricultural economy to a semi-industrialized one and highly productive agricultural activities which are affectively integrated and buttressed by supportive industrial and service activities in the urban and rural areas.

### 3.3.8 Summary of Policy Review

Due to the supportive policy on the agriculture and livestock the SAFINA and SHALOM WOMEN members and the whole community of Engutoto ward are in the position to access and utilize the opportunity for poverty alleviation through the implementation of income generating activities in agriculture and livestock. Unless there are viable ways of introducing appropriate technology and approach to improve and run income generating activities on agricultural and livestock, the situation may worsen in the future for SAFINA and SHALOM women group and  Engutoto community as whole. Due to the fact that income generating activities are practical and proved to work in different parts of the world, then small groups for women at Engutoto community and Engutoto Ward in particular will be able to run their income generating activities for agriculture, livestock and other small business for poverty alleviation.

# CHAPTER FOUR

# IMPLEMENTATION

## 4.0 Introduction

Implementation means carrying out what has been planned. In implementing this project implementation plan was followed as guidance. The plan consisted of objectives with corresponding activities, timeframe, and resources needed and responsible persons. The plan which guided the implementation was developed in which financial, material resources and human resources were inevitable for the successful implementation of the project. Project budget was contributed by the author, community members and Arusha Municipal council.

## 4.1 Project Products and output

The projects main products and outputs are as follows

- Improved skills to poultry husbandry.

- Improved skills in poultry nutrition.

- Improved skills in poultry diseases and diseases control.

- Increased productivity

- Increased income

- Improved wellbeing

## 4.2 Project Planning

Project planning is the central component in the project development process. The project planning involved the following major steps: Identifying activities, sequencing activities, developing timeframe for activities. And assigning responsibilities for carrying out the activities lastly but not list is assessing facilities equipments and service needed.

Identifying Activities

Identifying project activities is the most important step in the project-planning phase. Time and effort invested in this specific step guaranteed the success achieved. Identification project activities were carried out in a participatory way by involving all the CBO members basing on the project objectives and taking into consideration the resource and constraints.

Sequencing activities

After having identified the activities then they were sorted out as some of them had to be completed before others source of the activities had to conducted concurrently with others. Hence sequencing them was imperative.

Time frame.

After identifying and sequencing activities of the project, the next task was to determine the duration of the activity by determining the activity start date completion date.

Assigning responsibilities.

Assigning Responsibilities for different activities to specific individuals was done in a systematic manner involving all the CBO members. The criteria for assignment of the tasks were the individuals’ possessed skills and the demands of the activity.

Facilities, Equipments, Materials and Services.

Carrying out activities of project requires various kinds of facilities, equipments materials and services. The communities’ members have agreed collectively to determine the facilities and services needed for each activity in the project.

Preparation of the Budget

Preparation of budget is critical in project planning. A budget is generally a statement of income and expenditure. In community development projects budgets can take many forces. In certain projects, priority is given to preparing an estimate of expenditure for project activities, because the money will be provided by a funding agency or a development organization Gajanayake (1993) However in this particular project the funder where CED student, Arusha Municipal council under ASDP-Program and CBO members.

Table 7:Project logical framework

| Narrative Summary | Indicators | Means of Verification | Assumption /Risks |
| --- | --- | --- | --- |
| GOAL Income at house hold level improved through poultry husbandry training to improve indigenous chicken production | The targeted members of Safina and Shalom Women groups are enjoying good production (eggs, meat) of indigenous chicken and earn reasonable income. | Progress report Poultry keepers daily report | Community is willing to adopt new techniques in indigenous chicken production |
| Objective 1 Sixty(60) members for Safina and Shalom women group trained on poultry nutrition by March 2011 | Number of group members for Safina and Shalom Women group practicing principles of poultry nutrition i.e, feed formulation and feeding Increase in egg production | Poultry keepers daily reports Group report | Political will from leaders is guaranteed |
| Objectives 2 Sixty(60) members of Safina and Shalom women groups trained on disease control and prevention by February 2011 | Decrease in baby chicks mortality rates | Poultry keepers daily reports Group report | Political will from leaders is guaranteed |
| Objective3 Sixty(60)members of Safina and Shalom women groups trained on management of poultry as indigenous and cross breeds chicken by April 2011 | Number of cross breeds chicken Number of improved chicken houses | Poultry keepers daily reports Group report | No change of climatic conditions |
| Output 1: Poor production of indigenous chicken due to poor nutrition is minimized Main Activities to Output 1 1.1 Training on local available resources as feed ingradradients 1.2 Theoretical training on composition of cost effective feed formulation utilizing locally raw material. | Output 1: At list every member group formulate their own poultry feed. | Poultry keepers record Group report |  |
| Output 2 Community awareness of preventive and curative measures in dealing with poultry diseases. Main Activities to Output 2 1.1Theoretical training on the types and signes of common poultry diseases 2.1Training on importance of vaccination | Output 2 60 members trained on poultry disease and disease control. At list 60% decrease of baby chicks mortality at age of three At list 95% of the members practice vaccination against New Castle diseases. |  | Existence of Close supervision of livestock department. |
| Output 3 Safina and shalom women groups members have Skills on management of poultry as indigenous chicken Main activities to Output 3 1.1Training on production systems 1.2Training on local breeds and their performances under different management systems 1.3Training on baby chick management 1.4Training on general hygienic measures 1.5 Conducting training on breeds selection and breeding program | Output 3 At list 60% of member group have improve chicken houses suitable for indigenous chicken. At list 40% of safina and Shalom women groups have procurer improved indigenous cockerels to crossbreed with the local breeds. | Poultry keepers record Monitoring report |  |

Source: Project design 2011

### 4.2.1 Project Implementation Plan

Table 8 Project implementation plan

| Specific objective | Activities | Project month | Resources Needed | Person responsible |
| --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |
| 1.To train 60 members for Safina and Shalom women groups on poultry nutrition by February 2011 | Preparation of training manuals Training on available feed resources and feed ingredients | v | v |  |  |  |  |  |  |  |  |  |  | Stationaries,resource person Feed resources | CED student, project, ward extension officer |
|  | Theoretical training on poultry nutrition Determining the nutritional value of locally produced raw materials suitable for use in feed production |  |  | v | v |  |  |  |  |  |  |  |  | Stationaries,tea and refreshment | CED student, ward extension officer |
|  | Training on composition of cost effective feed formulas utilizing locally produced raw materials |  |  |  | v |  |  |  |  |  |  |  |  | Animal feeds | CED student, Ward extension officer |
|  | Training on feeding and feeding regime |  |  |  | v | v |  |  |  |  |  |  |  | Resource person,stationaries, beam balance/weigh scale, | CED student |

| 2.To train 60 members of Safina and Shalom groups on disease control and prevention by February 2011 | Activities | Project month | Resources Needed | Person responsible |
| --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |
|  | Preparation of learning materials/Notes /venue |  | v |  |  |  |  |  |  |  |  |  |  | Stationaries,resource person, funds | CED student,BRAC foundation |
|  | Theoretical training on the types and signs of common poultry diseases |  |  |  | V |  |  |  |  |  |  |  |  | Stationaries,tea and refreshment funds | CED student,BRAC foundation, ward extension officer |
|  | Training on the control and prevention of diseases |  |  |  | V |  |  |  |  |  |  |  |  | Transport | CED student,BRAC foundation, and ward extension officer |
|  | Training on the importance of vaccination. |  |  |  | V | V | V | V |  |  |  |  |  | Resource person, vaccine | BRAC and CED student, ward extension officer |
| 3.To train Sixty (60) members of Safina and Shalom groups on the procedures for the management of poultry as indigenous and cross breeds chicken by April 2011 | Preparation of learning materials/Notes /venue |  |  | v |  |  |  |  |  |  |  |  |  | Stationaries,resource person | CED student, project |
|  | Training on basic requirements for poultry housing |  |  | v | V |  |  |  |  |  |  |  |  | Stationaries,tea and refreshment | Project committee CED student, ward extension officer |

Table 9:Inputs

| SPECIFIC OBJECTIVES | ACTIVITY | INPUT | UNITY MEASURE | NUMBER OF UNITS | UNIT COST |
| --- | --- | --- | --- | --- | --- |
| 1.To train 60 members for Safina and Shalom women group on poultry nutrition by March 2011 | Preparation of training manual | petrol | lts | 10 | 2,000 |
|  |  | note books | each | 60 | 1,000 |
|  |  | refreshments | pack | 60 | 2,000 |
|  |  | extra duty allowance | Personal days | 2 | 10000 |
|  | Training on available resources and feed ingredients | counter books | each | 60 | 2,500 |
|  |  | bal pen | dozen | 3 | 5,000 |
|  |  | refreshments | pack | 60 | 2,000 |
|  |  | Facilitator allowance | man days | 2 | 10,000 |
|  |  | photocopies | each | 120 | 50 |
|  | Theoretical training on poultry nutrition and determination of nutritional value | Petrol | lts | 10 | 2,000 |
|  |  | flip chart | each | 2 | 7,000 |
|  |  | Extra duty | Personal days | 5 | 10,000 |
|  |  | Cotton seed cake | Kg | 5 | 10,000 |
|  |  | Fish meal | Kg | 10 | 700 |
|  |  | Mineral salt | Kg | 10 | 600 |
|  |  | Leaf meal | Kg | 2 | 500 |
|  |  | Maize bran | kg | 50 | 450 |
|  |  | Sun flower cake | kg | 15 | 600 |
|  | Training on compositio | Petrol | lts | 10 | 2,000 |
|  |  | flip chart | each | 2 | 7,000 |
|  |  | Extra duty | Personal days | 5 | 10,000 |
|  |  | Fish meal | Kg | 10 | 700 |
|  |  | Mineral salt | Kg | 10 | 600 |
|  |  | Leaf meal | Kg | 2 | 500 |
|  | locally raw material suitable for feed production | Maize bran | kg | 50 | 450 |
|  |  | Sun flower cake | Kg | 15 | 600 |
| 2.To train 60 members of Safina and Shalom groups on disease control and prevention by February 2011 | Preparation of learning material/notes and venue | Stationeries Extra duty allowance | Pack Man days | 1 2 | 25,000 10,000 |
|  | Theoretical training on the types and signs of common poultry diseases | refreshments | pack | 60 | 2,000 |
|  |  | facilitator | man days | 2 | 10,000 |
|  |  | photocopies | each | 120 | 50 |
|  |  | petrol | lts | 10 | 2,000 |
|  |  | flip chart | Each | 2 | 7,000 |
|  | Training on the control and prevention of livestock | bal pen | dozen | 3 | 5,000 |
|  |  | refreshments | Pack | 60 | 2,000 |
|  |  | facilitator | man-day’s | 2 | 10,000 |
|  |  | photocopies | Each | 120 | 50 |
|  |  | petrol | Lts | 10 | 2,000 |
|  | diseases | flip chart | Each | 2 | 7,000 |
|  | Training on importance of vaccination | Stationeries New castle vaccine | Pack vials | 1 10 | 25,000 6000 |

| 3.To train 60 members of Safina and Shalom groups on the procedures for the management of poultry as indigenous and cross breeds chicken by April 2011 | Training on basic requirements for poultry housing | bal pen | dozen | 3 | 5,000 |
| --- | --- | --- | --- | --- | --- |
|  |  | refreshments | Pack | 60 | 2,000 |
|  |  | Facilitator allowance | man days | 2 | 10,000 |
|  |  | photocopies | Each | 120 | 50 |
|  |  | Petrol | Lts | 10 | 2,000 |
|  |  | Colored pictures | Each | 12 | 3000 |
|  | Training on conducting breeding programe | stationeries | pack | 1 | 25,000 |
|  |  | Facilitator allowance | Personal days | 2 | 20000 |
|  |  | Tea | person | 60 | 2500 |
|  | Training on production systems ,local breeds and per romance under different | stationeries | pack | 1 | 25,000 |
|  |  | Extra duty allowance | Personal days | 2 | 10,000 |
|  | Training on baby chicks management | In boxes | Each | 1 | 150,000 |
|  |  | Celing board | Pc | 1 | 7500 |
|  |  | Saw dust | bag | 1 | 1200 |

Source: Project budgeting 2011

### 4.2.3 Staffing Pattern

#### 4.2.3.1 Staffing Plan

Implementation of the project lies upon the CBO members, assisted by the CED student. All together were participating fully in implementing the project.

#### 4.2.3.2 Training Needs

All CBO members performing daily duties are scheduled to be trained in poultry husbandry

## 4.3 Project Implementation

The life cycle of a community development project consists of three major phases: Planning, implementation and evaluation. Implementation means carrying out what has been planned. Among the major activities in project implementation are securing community participation, coordination of activities, monitoring and taking care of contingency situation. Constant coordination has been done to prevent duplication of activities, to promote efficiency and to reduce costs. Monitoring was carried out for checking whether the work is proceeding according to the plan, and in case of shortcomings to take stock of the situation and effect the necessary correction actions.

### 4.3.1 Project implementation process

The project implementation had one major implementation area namely training on indigenous chicken improvement for the CBO members.

Training was done to all 60 members of the two CBOs. The members were trained on indigenous husbandry; the training was based on scientific ways of indigenous rearing, poultry diseases and disease control, indigenous chicken nutrition, breeds and breeding.

### 4.2.4 Project budget

Table 10 :Project Budget

| SPECIFIC OBJECTIVES | ACTIVITY | INPUT | UNITY MEASURE | NUMBER OF UNITS | UNIT COST | TOTAL COST |
| --- | --- | --- | --- | --- | --- | --- |
| 1.To train 60 members for Safina and Shalom women group on poultry nutrition by March 2011 | Preparation of training manual | petrol | lts | 10 | 2,000 | 20,000 |
|  |  | note books | each | 60 | 1,000 | 60,000 |
|  |  | refreshments | pack | 60 | 2,000 | 120,000 |
|  |  | extra duty allowance | Personal days | 2 | 10000 | 20,000 |
|  | Training on available resources and feed ingredients | counter books | each | 60 | 2,500 | 150,000 |
|  |  | bal pen | dozen | 3 | 5,000 | 15,000 |
|  |  | refreshments | pack | 60 | 2,000 | 120,000 |
|  |  | Facilitator allowance | man days | 2 | 10,000 | 200,000 |
|  |  | photocopies | each | 120 | 50 | 6,000 |
|  | Theoretical training on poultry nutrition and determination of nutritional value | Petrol | lts | 10 | 2,000 | 2,000 |
|  |  | flip chart | each | 2 | 7,000 | 14,000 |
|  |  | Extra duty | Personal days | 5 | 10,000 | 50,000 |
|  |  | Cotton seed cake | Kg | 5 | 10,000 | 50,000 |
|  |  | Fish meal | Kg | 10 | 700 | 7000 |
|  |  | Mineral salt | Kg | 10 | 600 | 6000 |
|  |  | Leaf meal | Kg | 2 | 500 | 1000 |
|  |  | Maize bran | kg | 50 | 450 | 205,00 |
|  |  | Sun flower cake | kg | 15 | 600 | 9000 |
|  | Training on composition of cost effective feed | Petrol | lts | 10 | 2,000 | 2,000 |
|  |  | flip chart | each | 2 | 7,000 | 14,000 |
|  |  | Extra duty | Personal days | 5 | 10,000 | 50,000 |
|  | formula utilizing locally raw material suitable for feed production | Cotton seed cake | Kg | 5 | 10,000 | 50,000 |
|  |  | Fish meal | Kg | 10 | 700 | 7000 |
|  |  | Mineral salt | Kg | 10 | 600 | 6000 |
|  |  | Leaf meal | Kg | 2 | 500 | 1000 |
|  |  | Maize bran | kg | 50 | 450 | 205,00 |
|  |  | Sun flower cake | kg | 15 | 600 | 9000 |
|  |  |  |  |  | Subtotal (1) | 989,000 |
| 2.To train 60 members of Safina and Shalom groups on disease control and | Preparation of learning material/notes and venue | Stationeries Extra duty allowance | Pack Man days | 1 2 | 25,000 10,000 | 25,000 20,000 |
|  | Theoretical training on | refreshments | pack | 60 | 2,000 | 120,000 |
| prevention by February 2011 | the types and signs of common poultry diseases | facilitator | man days | 2 | 10,000 | 200,000 |
|  |  | photocopies | each | 120 | 50 | 6,000 |
|  |  | petrol | lts | 10 | 2,000 | 20,000 |
|  |  | flip chart | Each | 2 | 7,000 | 14,000 |
|  | Training on the control and prevention of livestock diseases | bal pen | dozen | 3 | 5,000 | 15,000 |
|  |  | refreshments | Pack | 60 | 2,000 | 120,000 |
|  |  | facilitator | man-day’s | 2 | 10,000 | 200,000 |
|  |  | photocopies | Each | 120 | 50 | 6,000 |
|  |  | petrol | Lts | 10 | 2,000 | 20,000 |
|  |  | flip chart | Each | 2 | 7,000 | 14,000 |
|  | Training on importance of vaccination | Stationeries New castle vaccine | Pack vials | 1 10 | 25,000 6000 | 25,000 60,000 |
|  |  |  |  |  | Sub total | 865,000 |
| 3.To train 60 members of Safina and Shalom groups on the procedures for the management of poultry as indigenous and cross breeds chicken by April 2011 | Training on basic requirements for poultry housing | bal pen | dozen | 3 | 5,000 | 15,000 |
|  |  | refreshments | Pack | 60 | 2,000 | 120,000 |
|  |  | Facilitator allowance | man days | 2 | 10,000 | 200,000 |
|  |  | photocopies | Each | 120 | 50 | 6,000 |
|  |  | Petrol | Lts | 10 | 2,000 | 20,000 |
|  |  | Colored pictures | Each | 12 | 3000 | 36000 |
|  | Training on conducting breeding | stationeries | pack | 1 | 25,000 | 25,000 |
|  | program | Facilitator allowance | Personal days | 2 | 20000 | 40000 |
|  |  | Tea | person | 60 | 2500 | 150,000 |
|  | Training on production systems ,local breeds and per romance under different systems | stationeries | pack | 1 | 25,000 | 25,000 |
|  |  | Extra duty allowance | Personal days | 2 | 10,000 | 20,000 |
|  | Training on baby chicks management | In boxes | Each | 1 | 150,000 | 150,000 |
|  |  | Ceiling board | Pc | 1 | 7500 | 7500 |
|  |  | Saw dust | bag | 1 | 1200 | 1200 |
|  |  |  |  |  | Sub total | 815,700 |
|  |  |  |  |  | Grand total | 2,669,700 |

:

#### 4.3.1.1 Accomplishment of the Goals and Objectives

The members of the CBO now are practice skills in indigenous chicken production. The municipal residents prefer indigenous poultry so accessibility to a reliable and sustainable market for the poultry project products is available. Members of these CBOs are able to diagnose diseases which affect their poultry and therefore they carry out initial treatments measures, they also identify eggs for brooding and carry out breeding programme.

4:3:2.Project implementation Ghatt chart

A Gantt chart is a type of bar chart that illustrates a project schedule. Gantt charts

illustrate the start and finish dates of the terminal elements and summary elements of a project. Terminal elements and summary elements comprise the work breakdown structure of the project. Gantt charts can be used to show current Schedule status using percent-complete shadings and a vertical

.

Table11 Project implementation Ghatt chart

| ID No. | Activity | Duration | 2010 | 2011 | resources | Responsible person |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | sept | oct | nov | Dec | Jan | Febr | Mar | Apr | May | Jun | Jul | Aug | Sep |  |  |
| 1. | Problem identification Community identification | 2 months |  |  |  |  |  |  |  |  |  |  |  |  |  | Stationaries,Fuel,fafunds | CED student, Ward executive officer |
|  | Pleminary visits to the Engutoto wards community members. | 1 month |  |  |  |  |  |  |  |  |  |  |  |  |  | Fuel,stationeries,funds | CED student |
|  | Community needs assessment (Problem identification) | 2 months |  |  |  |  |  |  |  |  |  |  |  |  |  | Stationaries,tea and refreshment | CED student, Ward extension officer |
| 2. | Project designing and planning | 1 month |  |  |  |  |  |  |  |  |  |  |  |  |  | Stationaries,tea | Identified community members,CED student |
|  | identification of training needs, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | identification of training resources, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | mobilization of resources, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | preparation of training materials, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | identification of training venue |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. | Project implementation | 4months |  |  |  |  |  |  |  |  |  |  |  |  |  | Stationaries,facilitators allowances, animal feeds,poultry,building and construction materials, fuel | CED student, Safina and Shalom Women groups |
|  | Conducting training on poultry nutrition feed regime, feed and feed formulation, cost effective feed formula. | 1 month |  |  |  |  |  |  |  |  |  |  |  |  |  | Facilitator allowance, animal feeds | BRAC foundation,CED student |
|  | Conducting training on disease control and prevention | 2 month |  |  |  |  |  |  |  |  |  |  |  |  |  | Stationeries | BRAC foundation,CED student, project committee members |
|  | Training on importance of vaccination | 1 month |  |  |  |  |  |  |  |  |  |  |  |  |  | New castle vaccine, facilitator ,fuel | BRAC foundation |
|  | Training on production systems ,local breeds and performance under different systems | 1 month |  |  |  |  |  |  |  |  |  |  |  |  |  | stationaries,facilitator, | CED student |
|  | Training on basic requirements for poultry housing | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | Stationaries,facilitaor,fuel,brooder making materials | CED student |
|  | Training on baby chicks management | 1month |  |  |  |  |  |  |  |  |  |  |  |  |  | In boxes Ceiling board Sisal Twine, Saw Dust | CED student,SAFINA and SHALOAM group members, |
|  | Participatory monitoring & evaluation | continuous |  |  |  |  |  |  |  |  |  |  |  |  |  | Transport cost,stationaries | CED student,SAFINA and SHALOAM group members, member from BRAC foundation |
|  | Project report writing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Stationeries, photocopying cost. |  |

Source: Project planning

# CHAPTER FIVE

# PROJECT PARTICIPATORY MONITORING, EVALUTION AND SUSTAINABILITY

# 5 Introductions

This chapter highlights on the monitoring and evaluation process of the project. At the end of the quoter the format is used to compare the planned with the actual achievement and evaluate them. In this study monitoring of project activities was done to assess whether the project activities were conducted as planned and also to assess if the available recourses were used efficiently during the project implementation. Monitoring provides the management with current situation, identify the implementation problems and find solutions, discover trends and pattern, keep project activities on schedule, measure progress towards achievement of project objectives. It help to formulate revise future goals and objectives and finally make decisions about human, financial and material resources.

## 5.1 Participatory Monitoring

Monitoring is the regular observation and recording of activities taking place in a project or programme. It is a process of routinely gathering information on all aspects of the project. It involves in giving feedback about the progress of the project to the donors, implementers and beneficiaries of the project. Boerma define monitoring as a systematic and continuous process of collecting and analyzing information about the progress of a programme (Boerma J.T. 1991) .According to CEDPA 1994 monitoring is the process of routinely gathering information on all aspects of the project. Participatory Monitoring and Evaluation (M&E) is a collaborative process that involves Stakeholders at different levels working together to assess a project or policy, and take any Corrective action required. The direct beneficiaries of the project play an active role in monitoring; they maintain records at the community level, analyses progress and use this information to make decisions about project implementation. Monitoring is usually conducted as an ongoing activity throughout the life of a project. The Monitoring was conducted regularly through reports to access the project progress in line to planned activities and keep the project on schedule.

## Monitoring of Objectives

- Determining whether the inputs in the project are adding value.

- Ensuring all activities are carried out properly by the right people and in time;

- Determining whether the way the project is carried out is in line to with the plans.

- Analyzing the situation whether there is occurring challenges in the project implementation and finding solutions.

### 5.1.1. Monitoring information system

The following are important issues in monitoring information system.

#### 5.1.1.1 Recording information

Maintaining records is the first step in developing a monitoring system. Unless there is a regular update on key activities and selected indicators, it is not possible to build a monitoring system. The following issues were considered during the design data recording system; Unit of analysis information was collected at the individual level.

#### 5.1 .1.2 Maintaining of the record

The mechanism employed for monitoring included, the use of attendance sheets to every

meetings conducted. Normally leaders record their names in every meeting or during consultations. Likewise in trainings all participants sign the attendance sheets. Follow up on the agreed activities is made by both the group members. During monitoring, the issue of time was a bit a challenge since most of the group participants were reluctant with time (not observing time during meetings). The training has taken into consideration the fact that other participants they have lower inability of understanding and internalizing the training materials. There are 60 active member groups, but only 52 were able to follow training to the end. The community members are so integrated to each other in such a way that the funerals, celebrations, and festival affect plans and group schedule. For instance the planning training was postponed because of the funerals. Also the training on feed formulation had fewer participants compared to other trainings since other went for the funeral. Since most of the implementation take place at the community level data recording starts in the community.

The author in collaboration with group leaders was given responsibility for data collection and recording. The group members were provided with note books and dairy to record their own information. The dairy was used to record observations, problems encountered, questions, concerns, suggestions and anything related to poultry project. Project coordinator (author) was his responsibility of collecting the information which will be analyzed at the end.

#### 5.1.1.3 How often information was gathered

At community level individuals were collecting data daily while at project level data were monthly collected from the individuals the fact that these groups is used to meet once in a month.

### 5.1.1.4 Aggregating information

Data aggregation refers to compiling all of the information on various indicators and activities from all of the households and communities where the project is implemented. Since the project coordinator (author) visit individuals every month the coordinator use the same format with that at community level, the information was aggregated in such a manner that it is easy to understand and use the data. Data aggregated every month since the group members used to meet every month. The information is used by both stake holders i.e. the group community, Arusha municipal council and the CBOs.

### 5.1.2 Participatory monitoring Methods

Monitoring was conducted on monthly basis through different methods such as reviewing of reports and records, focus group discussion, checklist, project visit and observation.  The monitoring were carried out for the planned activities which include training on feed formulation, disease and disease vaccination, baby chicks rearing, housing system, breeding, feeding regime.

#### 5.1.2.1 Methods

The project used Participatory Rural Appraisal (PRA). In these methods, both the inductive and deductive methods are applied and conclusions drawn. Observation, description, personal study, interview, etc. are put to a qualitative test. Through observation, qualitative observation of events takes place. Through the description and interview method, the experience, emotions and the reactions of the subjects are listened to like a story and certain conclusions drawn on the basis of their narration. In respect of implemented activity 52 member groups for Safina and shaloam where able to follow, training from the beginning to the end, also 60 members were observed to feed their chicken with good formulated diet, only 42 member groups where able to construct good poultry houses.

### 5. 1. 3 Participatory monitoring plan

The table below summarizes the monitoring plans as per goal, objectives, activities, indicators, data sources, tool applied to collect data, person responsible and the time frame.

### 5.1.4 Actual Monitoring results

The actual monitoring plans carried out during the implementation of the project included:

- Data recording.

- Case studies.

- Interpretation of the action plan.

## 5.2 Participatory Evaluation

According to CEDPA (1994), Participatory evaluation refers to the process of evaluation where all project partners, community participants and project staff are involved. In participatory evaluation, all key decisions regulating the evaluation are made by the project partners. These include;

- Timing, when to carry out the evaluation.

- Process, indicators and analysis.

- Sharing and reporting and using the findings.

The purpose of this evaluation was but not limited to see whether the objectives have been achieved in relation to planned activities, to find out the effectiveness of the project, that is, to assess the extent to which things were done as per project plans. Furthermore evaluation was used to inform what to be done in the future as the result of experience and the work which have been done. Two evaluations (Formative and Summative) were conducted within the designated period to the project. Evaluation of the project success was done in reference to the planned schedule and activities.

Table 12 Participatory monitoring Plan

| Plan Objectives | Work plan activities | Monitoring objective | Objective verifiable Indicators | Importance of monitoring | Monitoring information | Person responsible | TIME FRAME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.To train 60 members for Safina and Shalom women group on poultry nutrition by February 2011 | Preparation of training manual | To have training manual in place | Number of training manual | Having a training tool | Training manual and report | CED student ,consultants | 1rst week of January |
|  | Training on available resources and feed ingredients | To have farmers who can able to identify resources and feeds ingredients | Number of group members trained | Having farmers who are able to identify feed resources | Training report | CED student ,consultants | 2nd week of January |
|  | Theoretical training on poultry nutrition and determination of nutritional value | Improved poultry diet | Number of group members trained | Having poultry with good nutrition status | Training report, on farmer record | CED student ,consultants | 3rd week of January |
| 2.To train 60 members of Safina and Shalom groups on disease control and prevention by March 2011 | Preparation of learning material | To have training manual in place | Number of group members trained | Having a training tool | Training manual & report | CED students Consultant | 1st week of March |
|  | Theoretical training on types and signs of common poultry | To have reduction of mortality rate. | Number of people trained. | Having less mortality rate | Training report | BRAC –foundation and CED students | 2nd week of March |
|  | disease |  |  |  |  |  |  |
|  | Training on the control and prevention of livestock diseases. | To have reduction of mortality rate. | Number of people trained. | Having less mortality rate | Training report | BRAC –foundation and CED students | 2nd week of March |
|  | Training on importance of vaccination | To have vaccination program | Number of people trained | Having less mortality rate | Training report | BRAC-foundation and CED student | 3nd week of March |
| 3.To train 60 members of Safina and Shalom groups on the procedures for the management of poultry as indigenous and cross breeds chicken by April 2011 | Training on basic requirements for poultry housing | To have good poultry houses | Number of people trained | Having good poultry houses | Training report | CED student | Firs 2 weeks of April |
|  | Training on conducting breeding program, and baby chicks management | To have breeding program And well baby chicks management skills | Number of people trained | Breeding program in place | Training report | CED student | Last 2 weeks of April |

Source: Project monitoring and evaluation, 2011

### 5.2.1 Performance Indicators

Indicators are quantitative or qualitative criteria for success that enable one to measure or assess achievement of project objective. Feuerstein (1986) distinguished nine common types of indicators which includes its availability, relevance, accessibility, utilization, coverage, quality, effort, efficient and impact. Indicators are also defined as a specific, observable, and measurable characteristic or change that shows the progress a program is making toward achieving a specified outcome. Indicators to measure the success of the objectives were designed from the project inceptions. The indicators were put into three categories, which include input, output and impact indicators. The indictors were developed in such a way that, it measure changes that can be linked to the project undertaken. The indictors are also defined as a specific, observable, and measurable characteristic or change that shows the progress a program is making toward achieving a specified outcome. Appropriate to measure what is important as well as qualitative and quantitative change. The indicators are targeted in terms of quality, quantity and timing. Input indicators such training, funds used, hand out distributed, consultation meeting were done to Safina and Shalom women Groups. The impact of the training was increase in poultry production, existence of poultry project, proper use of management skills acquired (breeding skills, baby chicks rearing, vaccination and housing system.

In a process of implementing capacity building project several indicators were evidenced.

- Input indicators

A total amount of Tanzania shillings 2,669,700/= were spent in the implementation of capacity building project to date which include facilitation of training sessions, cost of practical materials such as animal feeds,stationeries,tea and refreshment, payment of facilitator allowance and fuel.

- Output indicators

Sixty members of safina and shaloam women group were trained and all of them have started practicing the acquired knowledge in different levels.

- Impact indicators

The target impact was to increase income of the group members and Engutoto community at large, and this will be seen in the future.

Table.13 Three categories of indicators

| Objectives | Input indicators | Outcome indictor | Impact indicator |
| --- | --- | --- | --- |
| 1.To train 60 members for Safina and Shalom women group on poultry nutrition by February 2011 | Number of training conducted Type of training conducted Funds used | Number of people with skills on poultry husbandry, People involved | Income of safina and shalom women groups increased. |
| 2.To train 60 members of Safina and Shalom groups on disease control and prevention by March 2011 | Number of training conducted Availability of Hand out Funds used | Number of people practicing technology Number of people with skills on poultry husbandry, People involved Decrease in mortality Increase in egg production per chicken | Income of safina and shalom women groups increased. |
| 3.To train 60 members of Safina and Shalom groups on the procedures for the management of poultry as indigenous and cross breeds chicken by June 2011 | Number of training conducted Number of hand out distributed Funds used Number of improved chicken houses | Number of people with skills in poultry husbandry, People involved Decrease in mortality Increase in egg and meat production per chicken | Income of safina and shalom women groups increased. |

### 5.2.2 Participatory Evaluation Methods

Participatory Rural Appraisal method was applied by the CED team.  This method enabled assessment of  the impact of the exercise to the  local community (including the community members of all age and gender groups, NGO staff, private sector, the poor and the illiterate) to generate and analyze data relating to their own situations. This method entailed the street development committee to extract and analyze the data and make recommendations to the women group and the street at large and district Council and the host organization. Impact is not yet to be realized but indications show that capacity building on poultry production made a mark and has contributed to the improvement of production status in the community. Also there is clear relationship between no good chicken house and economic capability. During monitoring the following indicators were observed; Sixty members of safina and Shaloam group were able to follow training on poultry nutrition, 52 were able to follow training on disease and disease control, and 53 members did participate fully in the breeding and housing management session, also the training manual were prepared and member group were able to follow during training sessions. The monitoring team obseverved that there is some improvement in egg production, population increase of poultry was also observed. We fail to observe impact indicators as was planed i.e. (income of Safina and shaloam women group increased).

Table14. Evaluation summary Table

| Evaluation question | Objective | Activity | Direct Indicators | Indirect Indicators | Source of Data | Evaluator |
| --- | --- | --- | --- | --- | --- | --- |
| 1.was the project goal and objectives archieved? 2. What other things both positive and negative | Sixty members for safina and shalom women group trained on poultry nutrition by February 2011 | Training on available resources and feed ingredients | CBO members, community leaders participation in the project planning, implementation, monitoring and evaluation Monthly & annual Financial reports Quarterly and annual Narrative reports | Eagerness to attend the training and the attitude of the Community ownership of this development project | Farmer’s records. Training reports | CED team |
|  |  | Theoretical training on poultry nutrition and determination of nutritional value |  |  |  |  |
|  | 2.sixty members of Safina and Shalom groups trained on disease control and prevention | Evaluate and recommend accordingly | Evaluation reports | Good impact to the community | Farmer’s records. Training reports | As above |
|  |  | Theoretical training on types and signs of common poultry disease | CBO members, community leaders participation in the project planning, implementation, monitoring and evaluation Monthly & annual Financial reports Quarterly and annual Narrative reports | Income of Group members and whole entire community increased Proper implementation of the project Good impact to the community | Farmer’s records. Training reports |  |
|  | by March 2011 | Training on the control and prevention of livestock diseases. | CBO members, community leaders participation in the project planning, implementation, monitoring and evaluation Monthly & annual Financial reports |  | Farmer’s records. Training reports | CED team |
|  | 3.Sixty members of Safina and Shalom groups trained on the procedures for the management of poultry as indigenous and cross breeds chicken by April 2011 | Training on basic requirements for poultry housing Training on conducting breeding program | CBO members, community leaders participation in the project planning, implementation, monitoring and evaluation Monthly & annual Financial reports Quarterly and annual Narrative reports | Income of Group members and whole entire community increased Proper implementation of the project Good impact to the community | Farmer’s records. Training reports | CED team |

Source. Field evaluation report 2011

#### 5.2.3.1 Sampling

Purposive sampling method was used as always proved to be useful. In this sampling, also known as judgmental sampling, person who, in judgment about some appropriate characteristics required of the sample members, is relevant to the research topic and easily available to him was chosen. In this technique, some variables are given importance and represent the universe but the selection of units is deliberate and based on prior judgment. Cross sectional sampling in which representatives .from all groups are selected randomly .for instance women 30 member group (15 from shalom group and 15 from Safina) filled evaluation forms by help if their children.

#### 5.2.3.2 Evaluation of reliability and validity

The validity and reliability of the data collected was checked by using Triangulation type of participatory research method. This is a method of crosschecking qualitative information whereby the information collected in different ways and from different sources and people, by using different tools are made sure that they are reliable and unbiased. Triangulation counteracts the tendency on the part of qualitative methods to be subjective, unrepresentative and impressionistic. Therefore information gathered from interviews was crosschecked by focus group discussion and structured forms and sometimes way round.  Filled forms by selected women were crosschecked during group meeting in which individuals were called and asked some questions to clarify the answers. Most the questions were to put numbers, answers yes or no to make life easy for responders.

### 5.2.6 Actual monitoring results

Owing to the nature of project and the fact that it is only five months into its implementation certain activities have not been accomplished and as such there is nothing to report in those areas. Impact indicators have not been measured; the report focuses monitoring indicators.

### 5.2.6.1 Impact indicators

By the end of project, income of Safina and Shalom women groups improved. Data has not been collected to measure changes in the income at the household level. Since the project has been running for only six months and impact is expected to be observed in 12 month time.

### 5.2.3.3 Intermediate results

Objective 1.By the end of February 2011, Safina and Shalom women group would have trained on poultry nutrition,

In February a training attended by 60 of the 60 members was held. The women were given skills in poultry nutrition and encouraged to formulate their own poultry feeds using locally available resources. The training was conducted by CED student assisted by ward extension officer. During evaluation we found that farmers records shows an average increase of eggs production relative higher compare to that time before the project.  Refers figure 3 bellow.

Fig 1.Average egg production

Source:Field repport, 2011

Objective 2 By the end of March 2011, 60 members of Safina and Shalom women group trained on sign of different poultry disease and disease control.

In March 2011 training on poultry disease and disease control was attended by 52 of the 60 members of Safina and Shalom women group, trained members were encouraged to undertake control measure for poultry diseases, we observe that group members are vaccinating their chicken against New castle disease, poultry keepers records shows that there is a sharp decrease of baby chicks mortality. Figure 4, shows  chicks motality before and after the project.There is high proportional of death(720 chicks) at age of 3 month before the project relative to 100 after implementation of the project.In general the result implies that motarlity rate has significantly  decreased.

Fig2.Mortality rate of chicks

Source; Field report 2011

Also we manage to trace number of member group who are vaccinating their chicken Figure 5 show respondent who vaccinate their chicken before and after project. In general respondents who vaccinated their chicken has increased from 15 before the project to 30 respondents after project. It implies poultry keepers have started to practice principles of disease and disease control by carrying out vaccination.

Fig 3. Number of respondents who vaccinate their chicken

Source.Field repport, 2011

Objective 3: By the end of June 2011, Safina and shalom women groups were trained on poultry breeding as indigenous and cross breeds. In the mid of June 53 of 60 members of safina and shalom women groups trained on indigenous chicken breeds and its selection, group members have appreciate the training and poultry keepers records shows that 35 members of Safina and Shalom have procured improved cockerels from Oljavutian women group at Sokon 1 Ward to crossbreed their chicken Also field report shows that there is less population of improved crossbreed’s chicken which has started to reproduce.

Since the project has been running for only six months and the planned breeding training has taken place in three month ago, but also the Filial 1 generation take more time of about six to 9 months to give offspring.

## Sustainability

Australian Agency for International Development 2000, Sustainability is referred as a characteristic of a process or state that can be maintained at a certain level indefinitely. The project is rooted in the community. It is the community members' initiative through participatory process which led to the existence of the project. The most needed things for the project sustainability is clarity and ownership of goal to the groups' members. So far the group leaders as well as their members are on the top in implementation of the programme to attain the goal. Currently the author will continue to collaborate with group leaders for more encouragement on transparency and accountability. The groups have a potential to network and collaborate with other groups and associations for experience and best practice sharing.

### 5.3.1 Sustainability Plans

There are concrete steps considered to ensure the sustainability of the project: First step was, developed clear stipulated goal of the project to both Arusha Municipal council extension staff and groups members at Engutoto Ward. The second step was, building capacity of leaders in leadership skills and group dynamic hence they will be able to enhance mutual understanding among the group members. Third step is the development of the annual operation plan and operational plan acts as the guide and map toward the goal achievement.

This means, internal and external resources will be geared to the accomplishment of what was stipulated in their strategic plan. The group changes, study visits are among the key areas during training as the mechanism to update and equipped group's members with ability to review their plans accordingly.

### 5.3.2 Economic and Financial Sustainability

The act of contributing funds themselves the group contributed funds through monthly pelages as well through fundraising within their community towards their project is the evidence element of ownership. Unlike the previous time of waiting for donors to propose and lead development initiatives, the group has the base on where to start and progress forward.

### 5.3.3 Political Sustainability

Tanzania has been experiencing and still experiencing both social and political peace. Community leaders such as street chair person, street executive officer and ward executive officer were well involved from the project inceptions and throughout implementations process. To avoid tensions among the existing political parties within the ward. The project is in line with the key reforms that the government is pursuing with donor community support such as the macroeconomic and structural Reform. The project fit well within the slogan of KILIMO KWANZA which is now a drive force within the economical development of Tanzania.

### 5.3.4 Institutional Sustainability

The Arusha municipal council organization has been in front line to ensure what was initiated is coming into reality. As mentioned earlier, the Arusha municipal council organization is still operation within that community hence they will work hand in hands with groups for goal accomplishment. District agriculture development project coordinator and BRAC foundation were part and parcel in all training conducted to groups' members at Engutoto Ward. The trained groups leaders and members as per evaluation are aware and capable to lead their members to attain their goals. With the real and enthusiastic prevailing, Safina women group and Shalom will become a centre of learning for both Arusha Municipal Council organization and other groups within Engutoto Ward community. Hence it will inspire and attract group leaders and Arusha Municipal council staff.

# CHAPTER SIX

# CONCLUSIONS AND RECOMMENDATIONS

6.0 Introduction

This chapter resent the conclusion and recommendations of the study and project undertaken in Engutoto community.

## 6.1 Conclusion

The training project on poultry husbandry improvement has made a great impact to both the SAFINA and SHALOM women group and Engutoto community at Large and to the author. The community itself are proud of coming out from darkness after several training conducted. Apart from the experience, the author learned a lot in terms of conducting the community needs assessment, prioritize and develop a problem, implement, monitor and evaluate the community base project. Based on the study and coordination of the developed project, it was realized that, Income improvement at the household level requires careful study, analysis as well as proper continuous capacity building for the poultry project. In peri urban set up were people are oriented and acquainted with different activities it is importance to have a quality capacity building on proper means of running, otherwise it may take long time than anticipated for benefits realization. Basing on the evaluation conducted to the project at Engutoto ward, it shows that, with a guide community members are capable in developing and implementing their own plans. Though at the low level, the study also reveal that community members are willing and potential in contributing financially towards the implementation of their plans. In order for development to be sustainable, it requires not only means but also advocacy for social and economic issues within the community and other stakeholders such as NGOs, civil societies and the government in large.

## 6.2 Recommendations

The topics covered during training have enabled the groups in Engutoto Ward to run their poultry project in a sustainable way. There should be a constant capacity building in relation to any launched project for its sustainability. It is clear that, mobilizing community members to form group for project is one thing and capacity training for skills and means to overcome the challenges is another thing. Both mobilization and training has vital role to contribute for proper management and running of the income generation activities. Improper initiation of the project within the community will not only result in resource waste but also time, energy and moral of the community members will be affected. It will create disaster hence act as the fall block to any innovation. It is good to all community practitioners to make a thorough community assessment needs and ensure that the community members have bought the ideas before embark to any intervention or project initiations. Challenges are not constant neither static hence group formed within the community they must ensure quality time for reflection and learning from one another to rectify or make a remedy to any emerging problem before it is too late to intervene. There is a need to motivate and facilitate knowledge transfer by study tours, Nanenane exhibition and interaction with other parties or agencies for learning purpose and project sustainability.  Livestock and farming are the major interventions which attract investment and exploration in peri urban society. The author suggests that, communities should be motivated and encouraged to join through groups hence initiate and launch appropriate project within their locality. The project should not be limited to livestock and agriculture but also business should be employed for household income improvement. Poverty cannot be eliminated by one method yet CED approach is vital since it gives the community members the opportunity to participate through ideas, contributions, design, implementation, monitoring and evaluation of their community

based project.

# REFERENCES

Aparna .S. (2000). A brief Guide on How to Conduct a Needs Assessment.Apa American

Psychological Association, USA.

Bessei. (1987).Poultry management systems, the how manual for field staff in sub Sahara

Africa .Econ Dev News, Volume 2 Issue 2, pp 8

Boki.J. (2000). Poultry industry in Tanzania with emphasis on small scale rural poultry

Production, world poultry science, vol.16, No.17, 10-13.

Centre for Development & Population Activities [CEDPA] (1994). Project Design for

Program Managers. The CEDPA Training Manual Series. Volume II

FAO (1995).Women, Agriculture and Rural Development. Fact sheet Tanzania.

Fattah.K.A. (1999).Poultry as a tool in Poverty Eradication and Promotion of Gender Equality’. World poultry science, 1999, Vol.25 No.03, p369

Fink, Arlene et al (2001). How to Conduct Surveys: A Step-by-Step Guide, London: The

International Professional Publishers, 1985.Agers.

Guey’e, E, F. (2000). Implementation of Social Economical Empowerment Project.

World Poultry, vol.16, No.10, 14-17.

Katule, A, M. (2002).Production of local chickens under village management condition.

World Poultry. vol.22, No.10, 6-9

Kvan, Velune (1987), traditional poultry keeping in Northern Ghana. World Poultry.

vol.16, No.65, 23.

NSGRP (2005). Growing out of Poverty, A Plain Language Guide to Tanzania's

National Strategy for Growth and Reduction of Poverty

Mozi etal, (2003). Marketing of free range local chicken in Morogoro and Kilosa urban

Markets, Tanzania.FAO

http://www.fao/ag12againfo/proiects/en/pplpi/proiecdocs.html-03/04/2011

Peace Corps (2002). A Community Economic Development (CED) Training Guide for

Peace Corps Volunteers. ICE No. M0069.

Riise (2000). Strategies for developing family poultry production at village level,

Experience from West Africa FAO.

http://www.fao/ag1againfo/proiects/en/pplpi/proiect docs.html-02-06-2011

Sanaiya, E.B. (1990).Rural poultry production system in Tanzania, Presentation done

in Africa Conference 1998.

Stewart, P. (2003). Real Community Economic Development.  N.Y.B.G, New York

The World Bank Group. (2003).Empowering Rural Producer Organizations. Women

Livestock Manager in the third World, Tools and Techniques, the World Bank Washington DC.

UNICEF, 2000 TNZ: The Review of UNICEF-supported Women Economic

Activities (WEA). (1996). Community Development Policy, Ministry of Community Development.

URT (1997).Agriculture and Livestock Policy, Ministry of Agriculture and Cooperative,

Dar es   Salaam.

URT (2001). Agricultural Sector Development Strategy. The United Republic of

Tanzania.

URT (2004).Sera Ya Taifa Ya Uwezeshaji Wa Wananchi Kiuchumi, Jamuhuri ya

Muungano wa Tanzania

URT (2006).Livestock policy, Ministry of Livestock, the united republic of Tanzania.

# APPENDICES

Appendix 1: Guiding Questions for the CNA Focus Group (Swahili version)

1. Je umewahi kupata mafunzo yeyote juu ya ufugaji wa kuku?

2. Taja changamoto ambazo hukabiliana nayo katika ufugaji wa kuku?

3. Je umewahi kuwapatia kuku chanjo yeyote?

4. Taja kiasi cha uzalishaji wa mayai kwa kuku mpaka anapo tamia?

5. Je ni vyakula gani vinapatikana nyumbani kwako kwaajili ya ufugaji wa kuku?

6.umewahi kuchanganya chakula cha kuku peke yako/

7.Je ni aina gani wa kuku wa asili unayo fuga?

8.Je kitu gani kifanyike ili uweze kuboresha ufugaji wako?

Appendix 2: Questioner (Swahili version)

1. Je unashughulika na shughuli ipi ya kiuchumi kati ya hizi?(chagua moja)

  - kilimo cha mboga

  - ufugaji na kilimo cha mboga

  - ufugaji

2. Je unajishuhulisha na ufugaji gani kati ya hizi.

- Ufugaji wa kuku

- Ufugaji wa sungura

- Ufugaji wa ng’ombe wa maziwa

- Ufugaji wa mbuzi wa maziwa

3. Taja aina ya magonjwa yanayo ua kuku kwa wingi katika mazingira yako ya ufugaji.

- ……………………………….

- ……………………………….

- ……………………………….

- ………………………………..

3. Je ni idadi gani ya kuku unaofuga (chagua moja katika yafuatayo)

- 5 hadi 10

- 10 hadi 50

- 50 hadi 100

- 100 kuendelea

4. Katika ufugaji taja aina ya ufugaji ambao unaona ukifanya utaweza kujikwamua kiuchumi katika mazingira unayoishi sasa(weka alama ya vyema mbele ya jibu)

- Kuku

- Mbuzi wa maziwa

- ng’ombe wa maziwa

5. Je huduma ya afya ya mifugo inapatikana katika mazingira yako

- Ndiyo

- Hapana

6. Je huduma za kijamii Kama Barabara,Hospitali,shule na  maji zimeridhisha kwa kiwango gani

- Inatosheleza

- inatosheleza kiasi

- Inatosheleza sana

- Huduma ni duni sana

7. Taja vyanzo vitatu vya mapato unayotegemea

(i)…………………………………

(ii)…………………………………

(iii)…………………………………….

7. Je unauza mazao yako ya kuku (kuku,mayai,mbolea) Katika Jamii yako?

8. Je unafikiri Kiasi cha Ardhi ulichonacho inakutosheleza kuendeshea maisha yako ya kila siku?

- Ndiyo

- Hapana

9. Taja misaada unayopata kutoka kwa wadau wa maendeleo katika uendeshaji wa shughuli zako za Kiuchumi

(i)………………………………………….

(ii)………………………………………….

(iii)………………………………………….

10. Nani kati ya wadau wafuatao ndio watoa huduma katika jamii yenu?

- Serekali

- kanisa

- Msikiti

- Watu binafsi

Appendix 3: Poultry keeper daily record form (Swahili version)

Jina la mfugaji………………….

Mtaa……………………………………….

| Tarehe | Idadi ya kuku waliop-o | Uzalishajio wa mayaikwa siku | Matibabu/huduma | Vifo | Mauzo |
| --- | --- | --- | --- | --- | --- |
|  | Wadogo | Mtamba | wanaotaga | Vifaranga | wanaotamia | majogoo |  |  |  | kuku | mayai | Mbolea(kg) | maelezo |

# Text boxes

1. GENERAL ASSEMBLY (Annual meeting)

2.   Chair person

3. Executive secretary

4.    Treasurer