IMPROVED INCOME OF TUSHIRIKIANE WOMEN GROUP THROUGH SOAP MAKING IN NGULYATI VILLAGE, BARIADI DISTRICT

MARIA ADOLF KIMONGE

A DISSERTATION SUBMITTED IN PARTIAL FULFILMENT FOR THE REQUIREMENTS OF THE DEGREEE OF MASTER OF COMMUNITY ECONOMIC DEVELOPMENT OF THE OPEN UNIVERSITY OF TANZANIA

2019

# CERTIFICATION

The undersigned certifies that has read and hereby recommend for the acceptance by the Open University of Tanzania (OUT) a project entitled; “Improved Income of Tushirikiane Women Group through soap making  in Ngulyati Village, Bariadi District”, in partial fulfillment of the requirements for the Master degree of Community Economic Development of the Open University of Tanzania.

…………………………………..

Prof. Deus Ngaruko

(Supervisor)

......................................

Date

COPYRIGHT

No any part of this dissertation may be replicated, distributed in any form or by any means, in full or in part, with the exception of citation in research studies, without written permission of Directorate of postgraduate studies on behalf of the author and Open University of Tanzania.

# DECLARATION

I, Maria Adolf Kimonge, do hereby declares that this dissertation is my own original work and it has not been presented and will not be submitted to any other university for a similar or any other degree award.

……………..………..………….

Signature

…………………….………..

Date

# DEDICATION

This work is dedicated to the special people that touched my life in one way another that has granted positive impact in my entire carrier studies, special thanks goes to my beloved Parents my Mr and Mrs Adolf Kimonge, my beloved daughters Violet and Vivienne, my relatives, friends in heart and anybody that have not mentioned for their support are highly appreciated.

# ACKNOWLEDGEMENTS

I would like to thanks Almighty God father for giving strength, and courage to accomplish my studies, trusting without God nothing could be possible it not just my understanding, energetic and my power could take all this happen than God`s desires make all things possible.

Also I sincerely thank all people who devoted their time to assist and contributed to the fulfillment and accomplishment of this research work. Heartfelt cheers should go to my course coordinator Dr. Harrieth Mtae and my supervisor Professor Deus Ngaruko for being kind and mostly supportive leading me in all steps of this work as my Supervisor. More less, my extra-ordinary thanks goes to the management, academic staff, support staff and the whole community of the Open University of Tanzania Shinyanga and Mwanza campus and all campuses  starting with the Vice chancellor/ Rector Prof. Deus Ngaruko for his good fatherly guidance to the OUT administrative machinery that enables our academic ball to keep on rolling smoothly, without forgetting various OUT directorates and heads of departments who co-works with him to assure that we reach our academic excellence.

I cannot forget my family who permits me, support me financial and prayed to take this endeavor, among them are my beloved father Mr. Adolf Kimonge and my lovely mother Bertha Simon Mauki, for their lovely formation and upbringing to this moment. I am indebted to my lovely daughters for the patient and prayers during my studies they couldn’t be isolated despite of the time I being away and busy for studies, brothers and sisters  who accompanied me very close in all my studies materially and morally. Their support has been a green light to me and academic star who always was showing me the way. All I thank you and it is only God who can reward you back.

# ABSTRACT

This project report has resulted from the Participatory Needs Assessment which was done in Ngulyati village, Bariadi District, to identify the needs of Tushirikiane Women group and the project which they can implement as a way to deal with the identified need. The study findings note that the community is experiencing income poverty to the extent of failing to accommodate for their daily basic needs. As a solution to the problem, the community decided to start soap making project. The group members and stakeholders contributed money to make a starting capital. Various literature have shown that efforts to combat poverty and the room provided by various policies have not been able to pull many Tanzanians especially rural women out of income poverty. Through working with the host organization and other stakeholders, the community formed and registered a group namely Tushirikiane Women group, opened a bank account, and has started producing and selling soap. Daily monitoring of the project activities was conducted by using participatory methods including the participatory Rural Appraisal (PRA) and Beneficiary Assessment (BA). The project promises to be sustainable because the community has shown commitment to work with other stakeholders in implementing the project. The advanced recommendations include close involvement of community development and trade officers in order to nurture the group all production activities in order to maximize profit. It is further recommended that other groups of similar nature can emulate the same path to improve their income and reduce household poverty.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENTS	vi

ABSTRACT	viii

TABLE OF CONTENTS	ix

LIST OF TABLES	xiv

LIST OF FIGURES	xv

LIST OF ABBREVIATIONS	xvi

CHAPTER ONE	1

PARTICIPATORY NEEDS ASSESSMENT	1

1.1	Background Information	1

1.2	Community Profile	3

1.2.1	Demographic Features	3

1.2.2	Ethnicity	3

1.2.3	Economic Activities	4

1.2.4	Social Services	4

1.3	Community Needs Assessment (CNA)	5

1.3.1	Objectives of the Community Needs Assessment (CNA)	6

1.3.1.1	General Objective	6

1.3.1.2	Specific Objectives	6

1.3.2	Research Questions	7

1.3.3	Research Methodology	7

1.3.3 	Types and Sources of Data	7

1.3.4 	Sources of Data	8

1.3.5	Research Design	9

1.4	CNA Findings	12

1.4.1	Demographic and Socio Economic Characteristics of Respondents	12

1.4.2	Economic Activities in Ngulyati Village	16

1.4.3	Community Needs for Women from Poor Households in Ngulyati             Village	17

1.4.4	Selection of Suitable Community Economic Project	18

1.5	Needs Prioritization and Leveling	19

1.5.1	Selection of Community Project	21

1.6	Conclusion	23

CHAPTER TWO	24

PROBLEM IDENTIFICATION	24

2.1 	Background to Research Problem	24

2.2 	Problem Statement	26

2.3 	Project Description	27

2.3.1 	Target Community	27

2.3.2 	Stakeholders	28

2.3.3 	Project Goal	28

2.3.4 	Project Objectives	29

2.4 	Host Organization	30

2.4.1 	Vision of the Host Organization	30

2.4.2 	Mission of the Host Organization	30

2.4.3 	Ngulyati Village Council Organization Structure	31

2.4.4 	Host Organization’s Strength, Weakness, Opportunities and                   Challenges Analysis	31

2.4.5 	The Role of the Host Organization	32

2.4.6 	The Role of CED Student	33

CHAPTER THREE	34

LITERATURE REVIEW	34

3.1 	Introduction	34

3.2 	Definition of Concepts	34

3.2.1 	Poverty	34

3.2.2 	Absolute Poverty	34

3.2.3 	Relative Poverty	35

3.2.4 	Income Poverty	35

3.2.5 	Poor Household	35

3.2.6 	Development	35

3.2.7 	Conditional Cash Transfer	35

3.3 	Theoretical Literature Review	36

3.3.1	Income Poverty in the World and Tanzania	36

3.3.2 	Efforts by Tanzania to Curb Income Poverty	37

3.4.1 	Soap Making and Production	38

3.4.2 	Requirements for Soap Production	38

3.4.3 	Soap Marketing	39

3.5 	Policy Review	39

3.5.1 	Community Development Policy 1996	39

3.5.2 	National Economic Empowerment Policy	40

3.5.3	Tanzania Development Vision 2025	40

3.5	Literature Review Summary	41

CHAPTER FOUR	42

PROJECT IMPLEMENTATION	42

4.1 	Introduction	42

4.2 	Project Outputs and Activities	42

4.3 	Project Products	44

4.4 	Project Planning	44

4.4.1 	Implementation Plan	44

4.4.2 	Inputs	49

4.4.3 	Staffing Pattern	49

4.4.4 	Project Budget	50

4.5 	Project Implementation	53

4.5.1 	Project Implementation Report	53

PTER FIVE	58

PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	58

5.1 	Introduction	58

5.2 	Participatory Monitoring	58

5.2.1 	Monitoring Information System	59

5.2.2 	Participatory Monitoring Methods used in the Monitoring of the                Project	61

5.2.3 	Participatory Monitoring Plan	61

5.3 	Participatory Evaluation	63

5.3.1 	Performance Indicators	63

5.3.2 	Participatory Evaluation Methods	65

5.3.3 	Project Evaluation Summary	65

5.4 	Project Sustainability	68

5.4.1 	Strategies for Project Sustainability	68

5.4.2 	Project Sustainability Assessment	69

5.4.3 	Financial Sustainability	69

5.4.4 	Institutional Sustainability	69

5.4.5 	Political Sustainability	70

CHAPTER SIX	71

CONCLUSION AND RECOMMENDATION	71

6.1 	Introduction	71

6.2 	Conclusion	71

6.3 	Recommendations	74

REFERENCES	76

APPENDICES	78

# LIST OF TABLES

Table 1.1: Sample Size	11

Table 1.2: Age Distribution of Respondents	13

Table 1.3: Respondents' Size of Household	14

Table 1.4: Education Level of Respondents	15

Table 1.5: Respondents Occupation	15

Table 1.6: Respondents' Income Distribution	16

Table 1.6: Community Needs Ranking Matrix	20

Table 1.7: Pair wise Ranking of proposed Community Projects	22

Table 2.1: Stakeholders Analysis Matrix	29

Table 2.2: SWOC Analysis of Host Organization	32

Table 4.1: Project Outputs and Activities	43

Table 4.2: Project Implementation Plan	45

Table 4.3: The Logical Framework of the Project	47

Table 4.4: Staff Pattern	50

Table.4.5: Project Budget	51

Table 4.6: Project Implementation Report	55

Table 4.7: Project Implementation Ghannt Chat	56

Table 5.1: Monitoring Information System	60

Table 5.2: Project Monitoring Plan	62

Table 5.3: Project Performance Indicators	64

Table 5.4: Project Evaluation Summary	66

# LIST OF FIGURES

Figure 1.1: Distribution of Economic Activities in Ngulyati Village	17

Figure 1.2: Community Needs	18

Figure 1.3: Community Economic Projects	19

Figure 1.4: A Researcher with Respondents during Identification and                              Ranking Needs and Identification of a Project	20

Figure 2.1: Ngulyati Village Organization Structure	31

Figure 4.1: CED Student with VEO, and Project Beneficiaries as they Display Their First Products in their Office	53

Figure 4.2: CED Student with VEO, Community Development Officer                              and Project Beneficiaries during Liquid Soap Making	54

# LIST OF ABBREVIATIONS

BA	Beneficiaries Assessment

CBO	Community Based Organization

CCT	Conditional Cash Transfer

CED	Community Economic Development

CNA	Community Needs Assessment

DC	District Council

DCDO	District Community Development Officer

FGD	Focus Group Discussion

HBS	Household Budget Survey

IGA	Income Generating Activities

LGA	Local Government Authority

MCED	Master of Community Economic Development

MDG	Millennium Development Goals

MIS	Management Information System

MKUKUTA	Mkakatiwakukuzauchuminakupunguzaumasikini Tanzania

MKUZA	MkakatiwakukuzaUchumi Zanzibar

NBS	National Bureau of Statistics

NMB	National Microfinance Bank

NPES	National Poverty Eradication Strategy

NSGRP	National Strategy for Growth and Reduction of Poverty

PRA	Participatory Rural Appraisal

PRSP	Poverty Reduction Strategy Paper

PSSN	Productive Social Safety Net

SPSS	Statistical Package for Social Science

SWOC	Strength, Weaknesses, Opportunities and Challenges

TASAF	Tanzania Social Action Fund

TZS	Tanzanian Shillings

URT	United Republic of Tanzania

USD	United States Dollar

VEO	Village Executive Officer

WB	World Bank

# CHAPTER ONE

# PARTICIPATORY NEEDS ASSESSMENT

## Background Information

The Tanzania Household Budget Survey (2011/2012) (NBS, 2014) clearly puts it forward that approximately 81% of the poor people in Tanzania live in rural areas where income poverty is very widespread. The survey further depicts that almost 34% of the rural population in Tanzania mainland is deeper in poverty further away from the basic needs poverty line which is estimated to be 28.2% for the whole Tanzania mainland. According to (URT, 2013), it is estimated that almost 12 million Tanzanian people are still poor and more than 10 million citizens in rural areas most of whom are women and children live in extreme poverty.

Due to extreme income poverty in rural areas, most of the people experience lack of access to quality education, health care services, insufficient housing, water and sanitation services and proper nutrition.  The (World Bank, 2016)says that effects of poverty are worse in child headed, and women headed households which have limited access to productive assets especially agricultural land. The situation of income poverty as experienced by many rural people, requires  for constant interventions on poverty reduction and economic growth through social safety net programs, improvement of agricultural and transportation systems, reduction of population growth, and improvement of access to social services notably education, health, water and sanitation and housing.

For so many years, Tanzania as any other developing African countries has been implementing several poverty reduction strategies and programs some of which directly aim at improving community livelihood and social service delivery. Some of the strategies implemented in Tanzania from the year 2000 include Mpango wa Kupunguza Umaskini na Kukuza Uchumi Tanzania (MKUKUTA1&2) in mainland, Mpango wa Kukuza Uchumi Zanzibar (MKUZA) in Zanzibar, United Nations Millennium Development Goals (MDGs) and Tanzania National Development Vision 2025. Also, for the past six years from the year 2012, Tanzania has been implementing a national wide Productive Social Safety Net (PSSN) implemented through Tanzania Social Action Fund (TASAF).

Through this country wide program, the most vulnerable and income poor households are identified (targeted) and enrolled to receive a bi-monthly Conditional Cash Transfer (CCT) for the purpose of increasing their household income and economic opportunity while adding up their consumption of health and education services (URT, 2013). Despite the efforts made by the government and other stakeholders in fighting against poverty, various reports still depict a big portion of populations living in abject poverty hence calling for more efforts from the government, Non-Government organizations (NGO) and the community itself.

Through this chapter, we will reviewthe basic information on the community under study and will illustrate howParticipatory Community Needs Assessment was used as a tool through which the community needs were identified and ranked in a participatory manner by involving the community. Through participatory needs assessment, all community members had equal opportunity to participate in identifying their needs and rank them starting with the most burning need and deciding on which one should be addressed first. Finally, the chapter presents the analyzed study findings and the suggestions on the available alternative projects through which the need will be dealt with.

## Community Profile

The study will involve a community of women from very poor households which are TASAF program beneficiaries, and they receive bi-monthly Conditional Cash Transfer (CCT) in Ngulyati Village, Ngulyati ward in Bariadi District. These women are from very poor households with very low income levelsand limited access to basic needs like decent housing, quality health services, nutrition, education, clean water, sanitation services and decent clothes. Ngulyati village is located about 37Kilometres along from Bariadi town which is the headquarters of Bariadi District and Simiyu Region as well.

### Demographic Features

Ngulyati village has a total of 372 households out of which 97 households are enrolled to benefit from the Productive Social Safety Net (PSSN) which is a government program implemented by TASAF. According to the current updated village register presented by the Village Executive Officer (Ngulyati Village Annual Community development report, 2018), Ngulyati village has a population of 3409 people whereby among them 1535 are women and while 1486 are men. However, only 2161 people equal to 63% of the total population can directly engage in productive activities while the rest are children and aged old people.

### Ethnicity

The inhabitants of Ngulyati village are basically the Sukuma who are the indigenouspeople of the area. Most of the people in Ngulyati village are Christians of the Roman Catholic religion and very few Muslims and Pagans.  The Sukuma are culturally known for hardworking and almost all religions preach the importance of working hard and advocates for loving each other and working together in combating against poverty. In view of that cultural background and religious teachings, it is anticipated that the community members in Ngulyati Village will similarly work together in identifying the needs and implementing the project that will increase their income.

### Economic Activities

There are two major economic activities that are carried out in the village namely agriculture and animal keeping; and very few people engage in petty business like kiosk and food vending. Agriculture employs about 93% of the population in the village whereby the major crops include cotton, maize, rice, sunflower, potatoes, millet and sorghum.  The livestock kept include cows, goats, sheep and poultry. As presented by (NBS, 2014), the households are likely to be poor if they are dependent on the sale of food and cash crops or earning a living from natural products. On the contrary, households tend to be non-poor when they become part of the formal sector and receiving wages or business income. The community in Ngulyati village needs to change from relying on crop sales and start engaging in income generating activities in order to get rid of income poverty.

### Social Services

Ngulyati Village as any other village in Bariadi District, has basic social services mainly primary education, health, water and spiritual services. The village has one primary school, one dispensary and various religious institutions dominated by the Roman Catholic. The village has no piped water and most of the people get water from the shallow wells and the nearby dam which provide water for both livestock and people’s domestic use throughout the year. As regards to market services, the village has an auction place where every Friday people gather to sell and buy various products including livestock, crops and domestic consumables.

The village electrified with power from Tanzania Electric Service Company (TANESCO). The village has a passable road throughout the year which is periodically maintained by Tanzania Rural Roads Agency (TARURA). The road connects the village with Bariadi town which is the capital of Simiyu Region and Magu town in Mwanza Region. The availability of these services especially the auction place, electrical power and passable roads guarantees marketability of the products which will be produced by the community.

## Community Needs Assessment (CNA)

Community Needs Assessment (CNA) refers to the systematic process of collection and analysis of information which is used to guide resource allocation decisions with a view to discovering and identifying goods and services the community is lacking in relation to the generally accepted standards, and for which there exists some consensus as to the community’s responsibility for their provision (The United Way of America, 2012). Also, (McKillip, 2007) defined CNA as a process of “ordering and prioritization of community needs.” Therefore Community Needs Assessment is a way of gathering data about a community’s opinions, needs, challenges, and assets used to determine which project(s) will meet the real needs of the community.

Community Needs Assessment (CNA) was conducted in Ngulyati village, Bariadi District to identify the needs of poor women from households which were enrolled in  TASAF program (community) and look at available solutions and income generation initiatives through which their needs could be curbed. This community is part of poor households who are currently enrolled in TASAF program to receive bi-monthly Conditional Cash Transfer (CCT).The program focuses on economic enhancement of enrolled households and children development by ensuring that they access education and health services. The study also assessed opportunities and challenges to implement the project, market and capacity building gaps as well as the strength and weakness (SWOT) the host organization.

### Objectives of the Community Needs Assessment (CNA)

#### General Objective

The general objective of the assessment was to gather data on the needs of women from the households which are registered in TASAF program in Ngulyati village in Bariadi District and identify available economic options for community intervention.

#### Specific Objectives

The Specific objectives of the assessment include the following;

- To describe social economic and demographic characteristics of women from TASAF beneficiary households in Ngulyati village

- To assess the available economic activities implemented in Ngulyati Village

- To identify the community needs among women from TASAF beneficiary households in Ngulyati village

- To identify the most viable project to mitigate the community need identified by the women from TASAF beneficiary households in Ngulyati village

### Research Questions

The study seeks to get answers for the following research questions;

- What are social economic and demographic characteristics of women from TASAF beneficiary households in Ngulyati village?

- What are the major economic activities in Ngulyati Village?

- What are the main community needs among women from TASAF beneficiary households in Ngulyati village?

- What is the most viable project to mitigate the community need identified by the community of women from TASAF beneficiary households in Ngulyati village?

### Research Methodology

Research Methodology section describes the design of the study on increased income of Tushirikiane Women group soap making in Ngulyati village. This part of the documentgives description of the study population, the sample and sample size and sampling techniques. In this section, we also look at the methods of data collection and how the collected data were processed, analyzedand presented.

# 1.3.3 Types and Sources of Data

# 1.3.3.1 Primary and Secondary Data

The researcher use both primary and secondary data collection during the study. Either primary data were collected at the community (Tushirikiane women group) who are the TASAF enrolled beneficiaries in Ngulyati village, group leaders, village leaders and other stakeholders.

# 1.3.3.2 Secondary Data

These type of data collection were used by researcher from published and unpublished documents from TASAF program documents, village reports, TASAF management information System (MIS), and National Bureau of statistics (NBS), Community development documents

# 1.3.4 Sources of Data

1.3.4.1 Interview

Personal interview was conducted to collect information from the key informants including the village leaders, community development officer and trade officer and TASAF coordinator to get the information that used to complement the data collection using questionnaires.

1.3.4.2 Questionnaire

This type of data collection was applied to collect data from 33 respondents who were the household women from TASAF beneficiaries at Ngulyati village in Bariadi district so as to get the real situation of the study. About 33 respondents who were administered with questionnaires form key respondents who have given the clear situation of income status in the community.

1.3.4.3 Focus Group Discussion

Focus group discussions method were used to collect information from the community where by respondents were divided into 3 groups with equal group size to discuss pre – determined questions derived from the research questions especially on identifying and ranking their needs and how to overcome  them.

### Research Design

This study was descriptive and participatory in nature.Throughout the process, it involved the community (women from TASAF beneficiary households),Ngulyati village leaders and other stakeholders in getting the answers for the identified research questions. Data collection methods for primary data included survey questionnaires and interviews. Questionnaires were used to collect data from women from TASAF households who are the main respondents. Interview was used to collect information from key informants including Community Development Officer, trade officer, and village government leaders. The use of these data collection methods ensured high level of participation and involvement of thecommunity in identifying and ranking the community needs and suggesting the most appropriate project. Secondary data were obtained from TASAF program documents, village reports, TASAF Management Information System (MIS), and National Bureau of Statistics (NBS). While the major technique is the questionnaire, other techniques of data collection like interview, Focus Group discussion (FGD), and observation were used to get information that was used to complement the data collected by using the questionnaire.

### 1.3.6.1 Sampling Techniques

The sampling frame for this study had 97 individuals which is the total population of women from TASAF beneficiary households which receive bi-monthly cash transfers in Ngulyati Village. The probability sampling (simple random sampling and systematic sampling) was used in selection of the respondents, whereby it facilitated the researcher not to be biased in selection of the respondents at population size. However non probability sampling (Purposive sampling) was also used to select key informants.  From this population, random sampling technique was applied to get 33 respondents which is equivalent to 34% whereby every member had an equal chance to participate in the study. Due to homogeneity of the population, there was no need of having a very big sample as it would not have different responses from the 34%. However, only nine women were conveniently selected to participate directly in project implementation. Selection of the group to participate in the project implementation considered readiness of the member to contribute money, physical fitness and availability to participate, willingness to join the group and past experience in income generating activities.

1.3.6.2 Sample Size

The sample size of the study was 33 respondents that were picked out of 97 total population of the community the women households beneficiaries enrolled by TASAF at Ngulyati village in Bariadi district.  In addition with 2 village leaders, 1 community development officer, 1 trade officer and 2 TASAF officers that make the total population of 39 respondents. So the researched had a total of 39 respondents as a sample size

In getting the sample size of 39 respondents the following formula was applied

n =    		N

1 +N(e)2

N=total population, n=sample size, and e = rescission (error) source: Yamane (1967)

The breakdown of this sample size is as illustrated in the table below;

# Table 1.1: Sample Size

| Category | Sample size |
| --- | --- |
| Community household women enrolled by TASAF program | 33 |
| Village leaders | 2 |
| Ward Community development officer | 1 |
| District trade officer | 1 |
| TASAF officers | 2 |
| TOTAL | 39 |

Source: Field study 2018

#### Data Collection Methods

Collection of primary data was directly done from main respondents who are the women from households which are enrolled in TASAF program in Ngulyati village. Data were collected by using the prepared questionnaire as a main tool (annexed). Administration of the questionnaires wasdone by two competent data collectors who were led by the researcher to collect data from the sample group of 33 respondents. Together with the questionnaire which was used as the main tool of data collection, interviews to Key Informants and Focus Group Discussion (FGD) were used whereby participants were divided into 3 groups with equal group size to discuss on pre determined questions derived from the research questions especially on identifying and raking their needs and how to overcome them. The checklist which was prepared to guide the discussion and help the researcher to verify data (triangulation) collected by using questionnaire is annexed.

#### Data Analysis Methods

The collected data were manually edited, coded and entered in SPSS for analysis to provide frequencies and percentages (descriptive statistics for interpretation) regarding the socio-economic characteristics of respondents namely age, education level, occupation and income. Microsoft excel was also used to calculate percentages of respondents’ reactions towards the available economic activities, community needs and selection of income generating activities.

#### Data Presentation

The analyzed data were presented through tables of frequency and percentages to depict and verify the information provided by respondents.   Prioritization of community needs and community interventions ranking were also presented in tables and figures to show the gathered information.

## CNA Findings

This section of the document presents the analysis and discussion of the data whichwere collected from 33 randomly sampled women from 97 households who are enrolled in TASAF in Ngulyati village in Bariadi District. The data also show the ranking of the needs and prioritization of appropriate community project to be implemented. The analysis, presentation and discussion were done to answer the research questions and the stated objectives of this study.

### Demographic and Socio Economic Characteristics of Respondents

Under this section of the report, the discussion is on the age distribution, family size, education level, occupation and monthly income of the respondents. It is also important to know that the study involved women only, so apparently there was no reason to analyze and discuss sex distribution of respondents.

#### Age

From Table 1.2, the data show that about 51.5% of women from TASAF beneficiary households in Ngulyati village have the age ranging between 46 to 60 years. The table also shows that almost 81.8% of the respondentsare aged between 31 to 60 years old. The implication of these data is, that these women are still young and energetic involve in production activities especially agriculture and business. Due to poverty within the community, and poor access to quality food and health services; the data suggest that very few of them just about only 6% can live above 60 years. This age is below 64years which is the average life expectancy for Tanzanian females (World Health Rankings, 2017). Involvement of this community in productive activities may ensure them with the capacity to afford basic needs like quality food, medical services and quality housing and hence live longer.

# Table 1.2: Age Distribution of Respondents

|  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | 18-30 | 4 | 12.1 | 12.1 | 12.1 |
|  | 31-45 | 10 | 30.3 | 30.3 | 42.4 |
|  | 46-60 | 17 | 51.5 | 51.5 | 93.9 |
|  | Above 60 | 2 | 6.1 | 6.1 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2018)

#### Household Composition

The Table 1.3 indicated that out of 33 respondents, about 51.5% have households with 4 to 5 members most of whom areyoung children going to school. The respondents noted through focus group discussions that most of these children are grandchildren to these women as their real parents go to town to search for jobs after completion of either primary or secondary school. This implies that these old people have to cater for all domestic requirements especially school and health requirements; food and clothing for themselves and for the dependents.

There are a significant number of households with 2 to 3 members as it is to those with more than 5 members, which is 24.2% for each category of age bracket. Engagement of these women in income generating activities will result into relatively stable incomes that would strengthen their economic capacity to meet household workload especially nutritious food, health, shelter and clothes.

# Table 1.3: Respondents' Size of Household

|  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | 2-3 | 8 | 24.2 | 24.2 | 24.2 |
|  | 4-5 | 17 | 51.5 | 51.5 | 75.8 |
|  | Above 5 | 8 | 24.2 | 24.2 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2018)

#### Education Level

The table indicated 1.4 illustrates the incidence of poverty is normally linked with the education level of head and other members in the household. A big number of the respondents, equivalent to 63.6 % had completed primary school while the rest 36.4% never went to school. There was nobody who went beyond primary education level. This may probably explain partly why they belong in the poorest class in the society. Direct involvement of the community in income generating activities will lead them into acquiring some money to pay for education of their children which will eventually help to disconnect this poverty cycle.

# Table 1.4: Education Level of Respondents

|  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | Primary | 21 | 63.6 | 63.6 | 63.6 |
|  | None | 12 | 36.4 | 36.4 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2018)

#### Occupation

During the study the findings illustrate that about 51.5% of the respondents are casual laborers who work for others to earn a living, 42.4 get their earnings from farming while only 6.1 % engage in petty business as indicated in table 1.5 of the report. All respondents are unskilled labor and they are normally employed as part time casual laborers in farms in the same village or neighboring villages.  Even those respondents who make 42.4% who earn a living through farming disclosed through focus group discussion that they don’t own any piece of land but they hire during farming season. It is obvious that the community with this nature of occupation has to join forces and be capacitated to establish their own income generating activities so that they can diversify their inputs and increase their income.

# Table 1.5: Respondents Occupation

|  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | Farming | 14 | 42.4 | 42.4 | 42.4 |
|  | Petty business | 2 | 6.1 | 6.1 | 48.5 |
|  | Casual labour | 17 | 51.5 | 51.5 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2018)

#### Income Distribution

As shown in Table 1.6, the study majority of respondents equivalent to 72.7% earn between TZS 31,000 to TZS 40,000 per month while about 15.2% earn less than TZS 30,000 per month and the rest, equivalent to 12% earn between TZS 41,000 and TZS 50,000 per month. However, it should be noted that this income includes an average of TZS 20,000 per household from TASAF every month depending on the demographic characteristics of the household. The income distribution of this type justifies the need for this community to organize themselves into productive groups and engage in income generating activities so that they can become economically stable even after phasing out of TASAF cash transfer. Through FGD, the respondents confirmed their readiness and willingness to use the money obtained from TASAF as startup capital for various activities which would ensure constant flow of income.

# Table 1.6: Respondents' Income Distribution

|  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | Bellow 30,000 | 5 | 15.2 | 15.2 | 15.2 |
|  | 31,000-40,000 | 24 | 72.7 | 72.7 | 87.9 |
|  | 41,000-50,000 | 4 | 12.1 | 12.1 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2018)

### Economic Activities in Ngulyati Village

As shown in Figure 1.1, the study indicates the presence of two major economic activities that are carried out in the village namely agriculture (crop production) by 49% and animal keeping 46%. The major crops include cotton, maize, rice, sunflower, potatoes, millet and sorghum. The study also show that about 95% of the people in the village are engaged in both crop farming and animal keeping and very few about 4% engage in petty business like kiosk and food vending.  Other economic activities which are only 1% include construction services and transportation of both goods and people from the village to Bariadi town or Mwanza city and vice versa. As noted earlier in section 1.4.1.4 above, approximately 52% of women from poor households are engaged in these economic activities only through offering casual labour. This community of women does not own the means of production especially land.

# Figure 1.1: Distribution of Economic Activities in Ngulyati Village

Source: Field data (2018)

### Community Needs for Women from Poor Households in Ngulyati Village

The CNA has revealed that the community in Ngulyati village has a number of needs. The identified needs include improved household income, capital to establish business, entrepreneurship training and market linkages for agricultural products. The respondents were required to identify only one need which they consider a major one. As shown by Figure 1.2, improved household income has emerged the first need by scoring 49% followed by business capital 21%, entrepreneurship training 18% and lastly market linkages for agricultural products which has scored 12%. Generally speaking, the community needs to improve their standard of living by enhancing their daily earning. These community needs are interlinked. Improved household income can only be realized through income generating activities which require capital and various trainings, coaching and market linkages. Therefore, any income generating activity which will be established by the group will help to curb the identified needs by incorporating these components within the project.

# Figure 1.2: Community Needs

Source: Field data (2018)

### Selection of Suitable Community Economic Project

As shown by Figure 1.3, the respondents were asked to select only one income generating activity among the given options, which they consider appropriate in their environment. Out of 33, about 12 respondents which is equivalent to 36% mentioned soap making while 8 respondents equivalent to 24% chose poultry. Tie and dye project was proposed by 6 respondents equivalent to  18%, cotton farming 4 respondents equivalent to 12% and finally pottery 3 respondents equivalent to 9%.

# Figure 1.3: Community Economic Projects

Source: Field data (2018)

## Needs Prioritization and Leveling

Naturally, the community has always a lot of needs and challenges as they struggle to earn a living and improve their lives. There is no way of doing away with those needs and challenges. However, the community needs have to identified and prioritized in order to determine which one to start with by considering the available resources and opportunities. The CNA has revealed that the community in Ngulyati village has a number of needs. The identified needs include improved household income, capital to establish business, entrepreneurship training and market linkages for agricultural products. Generally speaking, the community needs to improve their standard of living by enhancing their daily earning. In order to arrange the community needs as to which community issue to be addressed first, the pair wise ranking matrix was used as shown in Table 1.6 and the Figure 1.4.

# Figure 1.4: A Researcher with Respondents during Identification and Ranking Needs and Identification of a Project

# Table 1.6: Community Needs Ranking Matrix

| Community Needs | Business Capital | Entrepreneurship training | Markets linkage for agricultural products | Improved household income | Points | Rank |
| --- | --- | --- | --- | --- | --- | --- |
| Business Capital |  | Capital | Capital | Improved income | 2 | 2 |
| Entrepreneurship training |  |  | Entrepreneurship training | Improved income | 1 | 3 |
| Markets linkage for agricultural products |  |  |  | Improved income | 0 | 4 |
| Improved household income |  |  |  |  | 3 | 1 |

Source: Field data 2018

# As shown in Table 1.6, the community identified four needs as follows:

- Capital to establish business

- Entrepreneurship training

- Markets linkage for agricultural products and

- Improved household income

Through needs ranking process, the prioritization matrix clearlyshow that improved household income ranksthe first with a total ofthree points, followed by business capital with 2 points, then entrepreneurship training with only one point and lastly markets linkage for agricultural products without any score. It is clearly seen that the main need for this community is improved household income. The second need in the rank is capital to facilitate establishment of income generating activity, which is also closely linked with the first need because availability of financial capital will facilitate establishment of business through which the community will improve their household income.

### Selection of Community Project

The community has agreed that their common need which should be attended firs is to improve their household income. Therefore, the community had to identify and prioritize through pair wise ranking the most appropriate project as shown in table 7 bellow. The proposed and ranked projects include the following;

- Poultry

- Tie and dye (Batiki making)

- Pottery (pots making)

- Soap making

- Cotton farming

# Table 1.7: Pair wise Ranking of proposed Community Projects

| Projects | Poultry | Tie and dye | Cotton farming | Pottery | Soap making | Points | Rank |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Poultry |  | Poultry | Poultry | Poultry | Soap making | 3 | 2 |
| Tie and dye |  |  | Tie and dye | Tie and dye | Soap making | 2 | 3 |
| Cotton Farming |  |  |  | Cotton farming | Soap making | 1 | 4 |
| Pottery |  |  |  |  | Soap making | 0 | 5 |
| Soap making |  |  |  |  |  | 4 | 1 |

Source: Researcher, 2018

From Table 1.7, the community ranked soap making project as their first option followed by poultry, the tie and dye, cotton farming and finally pottery. Through focus group discussion, the respondents mentioned a number of reasons behind their selection of soap making ahead of other options. The reasons include small capital required for raw materials, market availability especially schools and health facilities, no complicated skills required and previous experience of some members. The community members also raised their startup capital amounting to TZS 100,000 by mobilizing a contribution from each member after receiving TASAF payment.

The community further agreed on to work together by forming a group that has to bear a name, written constitution and the group to be registered by the registrar at the District Council. Registration of the community group is important because it ensures legal status of the group and it defines the roles and responsibilities as well as benefits of each member of the group.

## Conclusion

The Community Needs Assessment (CNA) has helped the researcher to identify in details the information that has been analyzed to provide answers to research questions which were generated from the research objectives. The presented study findings show that most of women from TASAF beneficiary households are casual laborers with very low income yet with big domestic workloadand responsibilities. The population size in theirhouseholds go up to the average of 5 members most of whom are children who have education and medication needs. The community has decided to form and register a group through which they will implement soap making project which will contribute in improving their income.

# CHAPTER TWO

# PROBLEM IDENTIFICATION

## 2.1 Background to Research Problem

The meaning of poverty is very complex as it differs according to contexts, from one country to another and from one community to the other and even from household to household. There are also varying types and degrees of poverty, taking a wider perspective, poverty can be referred to as "the state of being extremely poor" and is understood by many to mean the lack of basic necessities as; food, water, shelter, healthcare, and basic education. Regardless of any definition we may opt to take, the fact remains that the level of poverty in Tanzania is high especially among the rural population who still depend on poorly mechanized agriculture and petty trade.

According to the recent study; Tanzania: Poverty, Growth, and Public Transfers (World Bank, 2011), the impact of economic growth on consumption (by income group) has been relatively equal, excluding the highest 10 percent whose consumption rose more than average and the lowest 10 percent of the population who became worse off. Using the 2011/12 Household Budget Survey data (NBS, 2014), the estimated Basic Needs Poverty Line is 36,482 TZS per adult equivalent per month, and Food Poverty Line is 26,085 TZS per adult equivalent per month.

The Government of the United Republic of Tanzania (World Bank, 2016), has been implementing various poverty reduction programs so that the most vulnerable people can take benefit from economic growth. From the year 2012, the Government has been implementing the Productive Social Safety Net (PSSN) through which the most vulnerable households get a bi-monthly cash transfer to facilitate them with ability to afford basic requirements especially education and health costs. Despite economic growth trends, approximately 10% of the poorest Tanzanian households require permanent support as they experience high levels of income poverty,  food insecurity; poor social indicators (e.g., malnutrition, diseases and ignorance).

The study findings (NBS, 2014) shows that the funds obtained from TASAF have helped the households to increase their familyincome. However, due to the nature of household requirements, theirincomebases are so weak to the extent that getting substantial amount of money to take care of themselves and that of their children and grandchildren is still questionable. As revealed by the CNA, most of the women from the benefitting households are old and they are left with grandchildren whose parents go to nearby towns of Lamadi, Magu, Bariadi and Mwanza seeking for employment. Other problems as obtained during participatory needs assessment include lack of working capital, inadequate entrepreneurship skills, lack of access to information on production and market linkages.

Through a Community Participatory Assessment, the community identified various opportunities within their village including favorable weather condition for agricultural activities, availability of institutions like schools, dispensaries, presence of a big market (auction place) in the village and presence of community development officer who can always guide the group in daily operations. Another big opportunity is the presence of TASAF program that provides them with cash which they can use as capital to establish an income generation project. Through CNA, the community identified the available economic activity options including poultry, tie and dye (Batiki), cotton farming as well as soap making. Finally, the community reconciled that they need to organize themselves into a registered group and establish soap making project through which they will increase their income.

## 2.2 Problem Statement

The Government of Tanzania has been implementing policies, strategies and programs aimed at stimulating economic growth and reducing income poverty among Tanzanian population. One of the most recent program is the Productive Social Safety Net (PSSN), which is implemented by TASAF by  disbursing cash to the identified most vulnerable households. For about six years from the inception of this program, achievements have been recorded in economic growth among various benefiting households. However, income poverty is still widespread among those households which are extremely vulnerable. The CNA findings in the first chapter of this document have revealed that about 72.7 % of the women in those households in Ngulyati village have a monthly average income ranging between Tshs. 31,000 to Tshs. 40,000 most of which is obtained from TASAF. This income ranges from Tshs. 1,000 to Tshs. 1,300 per day which very far below from the poverty line.

Apart from producing for their own requirements, the study has shown that these women have additional responsibility to produce food, pay education and health costs for grandchildren who are left behind by their parents who have moved to towns. The cash obtained from TASAF cannot suffice to cater for these growing households demands. The CNA findings have revealed that the community has the ability to save very little cash which once put together could be used as capital for soap making project which will give them more income on top of other sources of income.

## 2.3 Project Description

The project is the ‘Increased income of Tushirikiane women group through soap making project in Ngulyati Village, Bariadi District’, which was implemented by a group of nine (9) whose households are enrolled in TASAF program in Ngulyati Village, Bariadi District in Simiyu Region. This group named Tushirikiane used their small saving from the funds they get from TASAF as a starting capital to buy materials and make liquid soap as a way to increase their income and reduce household poverty.

Through this project, it is anticipated that part of the problems identified in chapter one will be addressed as they are all associated with low household income.  The project was executed by the small group of 9women under the general supervision of the group leaders who were elected as per group constitution. The village government provided overall group and project leadership and management. Bariadi District Council as a major stakeholder in this project, providedstaff namely the community development officer and trade officer who provided coaching on group formation, constitution writing and general knowledge on business making.  The project activities started in August 2018 and it will be a continuous implementation with the vision to scale up by diversifying into other products.

### 2.3.1 Target Community

The project was implemented by the group of 9 women selected from TASAF beneficiary households in Ngulyati village in Bariadi District, Simiyu Region. This group is responsible on day to day operations of the project. The village has a total of 97women from the households which are enrolled in TASAF whereby 33 participated by providing data for this study. Implementation and daily operation of soap making project involved only 9 members who have been purposively selected by considering their age, ability to contribute funds and willingness to join a group and work together. The study revealed that for the project to succeed, the group should be formally organized with written constitution, leadership, formal name and a bank account. These groups were assisted by the village leadership, MCED student and the District Community Development Officer (DCDO) to formalize the group.

### 2.3.2 Stakeholders

Various stakeholders contributed for successful implementation of the project. The main stakeholder is Bariadi District Council, whereby the Community Development Officer, TASAF coordinator and Trade Officer provided various technical supports depending on their specialities. Another important stakeholder is the village government which provided general guidance and organised all correspondences between the group and the experts who are based at the district headquarters. The stakeholder matrix is presented in Table 2.1.

### 2.3.3 Project Goal

The project goal is to improve the income of the community of women from household who are TASAF beneficiaries, through production and selling soap by November 2018. Increased household income will contribute to poverty reduction among the group members hence increase their capacity to afford households’ basic needs including shelter, food, clothing, education and medication.

# Table 2.1: Stakeholders Analysis Matrix

| Stakeholder | Stakeholder role | Stakeholder expectation |
| --- | --- | --- |
| Bariadi District Council | Provision of technical expertise through community development officer and Trade officer | The group will follow technical expertise provided |
| Ngulyati Village leadership | Provision of general leadership and coordination of all correspondences between the group and the experts at district level | The group will respect the village leadership and correspondences will be channeled through the village office |
| Members of Tushirikiane group | Mobilize resources, follow experts’ guidance and make and soap | Resources will be mobilized and soap will made by considering technical guidance |
| Community Development Officer | Group mobilization and facilitation of constitution writing, group registration and opening bank account | The group will be organized to write a constitution, group registration and opening bank account |
| TASAF coordinator | Provision of data regarding the households and encouraging them to save money for project capital | The group will follow the advice to save money for project capital |
| Trade officer | Advising and linking the group with markets | The group will get reliable market for produced soap |
| Researcher (MCED student) | Conduct research through CNA, training on soap making, oversee and document all project activities | CNA findings will be shared with stakeholders, documentation will be also done to improve project implementation |

Source: Field data 2018

### 2.3.4 Project Objectives

#### 2.3.4.1 General Objective

The project general objective was to increase income of women from poor households which are TASAF beneficiaries in Ngulyati Village through Soap making by November 2018.

#### 2.3.4.2 Specific Objectives

- To build capacity to  9 Tushirikiane group members on soap making  by the end of September 2018

- To acquire premises for soap processing and display of products by end of October 2018

- To procure soap making materials by end of October 2018

- To facilitate  community group formation registration by November 2018

## 2.4 Host Organization

The project was hosted by Ngulyati Village  Council which is responsible for day to day administration and management of all issues regarding social and economic development in the village under supervision of the Village chairperson who is  elected by citizens and the Village Executive Officer (VEO) who is a government employee . The village leadership provided a temporary office for the group and coordinatedall correspondences and activities of other stakeholders towards achievement of project objectives.

### 2.4.1 Vision of the Host Organization

Provide the best services in facilitating the members of the villagein using the available social and economic resources to enhance their social economic development.

### 2.4.2 Mission of the Host Organization

Ngulyati village aims at becoming a role model in provision of socioeconomic services to the community members to ensure that people have decent life and they live in peace and harmony.

### 2.4.3 Ngulyati Village Council Organization Structure

The Village Council has been vested with power to oversee day to day responsibilities of the village government. The village council has the following organization structure.

# Figure 2.1: Ngulyati Village Organization Structure

Source: Bariadi DC (2013)

### 2.4.4 Host Organization’s Strength, Weakness, Opportunities and Challenges (SWOC) Analysis

The purpose of the SWOC analysis is to portray detailed information of Ngulyati Village Council regarding the available opportunities which will help during the implementation of the soap making project. The analysis also determines strengths of the organization, weaknesses and challenges facing the organization and how they could influence the project implementation. Strengths and weaknesses are internal variables while Opportunities and Challenges are external variables. The SWOC of Ngulyati Village Council, which the host organization for this project was identified and is presented in the following Table.

# Table 2.2: SWOC Analysis of Host Organization

| SN | STRENGTH | WEAKNESS | OPPORTUNITY | CHALLENGE |
| --- | --- | --- | --- | --- |
| 1 | Highly committed and active village leadership | Some committee members are missing | Leadership has experience in supervising similar community groups and projects | Only VEO has a monthly salary, other members of the village council are not paid |
| 2 | Availability of permanent village office premises | So many activities taking place within the premise | The office is very close to Ngulyati market, easy for customers to access products and services | There is no electricity |
| 3 | Presence of community development officer | She has 5 villages to serve | she lives in Ngulyati Village and she is around most of the time | Sometimes she is not available when she goes to attend other villages |
| 4 | VEO is the permanent government employee | He is sometimes very busy with LGA activities | Most of time he is available | Limited Time for close supervision of the project |

Source: Research findings (2018)

### 2.4.5 The Role of the Host Organization

- To sensitize the community on group formation project implementation

- To ensure proper administrative activities throughout the project life

- To bridge between the community and other stakeholders

- To organize trainings required by the community in implementing the project

- To participate in project products marketing

- To provide office premises for the group to perform their duties

- To ensure the project tools and documents, and products are safe

- To collaborate with MCED student to  participate in mobilizing the resources required in project implementation

- To ensure the project sustainability

### 2.4.6 The Role of CED Student

The main role of CED student’s is to ensure that the planned interventions are successfully implemented as per work plan. The student will also do the following;

- Community sensitization on the importance of soap making project as source of income to the group.

- To participate in mobilization of resource required to facilitate project implementation

- To consult different facilitators especially community development officer, trade officer and other resource persons so that they can offer their skills to the community

- To facilitate project documentation and reporting

# CHAPTER THREE

# LITERATURE REVIEW

## 3.1 Introduction

This chapter presents both theoretical and empirical literature by authors who have written on poverty alleviation and soap production projects. The chapter presents the status of income poverty globally and in Tanzania and the efforts employed to address it. It also presents various Income Generating Activities implemented in Tanzania as a way to reduce income poverty. Through this chapter, Soap production as one of Income Generating Activities (IGA) is previewed by basing on its production requirements, specifications, types, branding and marketing.  Empirical literature review looks at the real experience on soap production in Tanzania and Bariadi District in particular and how it has contributed in combating income poverty especially among women. The last part of the chapter reviews the existing policies in Tanzania and how they contribute in soap making as one of income generation initiatives.

## 3.2 Definition of Concepts

### 3.2.1 Poverty

Poverty is referred to as a state of deprivation and prohibitive of decent life by failure to meet basic needs (URT, 2007) including food, shelter and clothes. Poverty is normally categorized into absolute poverty and relative poverty.

### 3.2.2 Absolute Poverty

Absolute poverty is defined by (URT, 2007) as the complete inability of a person or household to attain minimum standards of living, especially basic necessities like food, clothes and shelter. It is a situation of being unable to meet the minimum levels of income, food, clothing, healthcare, shelter and other essentials (Todaro, 2012).

### 3.2.3 Relative Poverty

Relative poverty is the state of wellbeing which is normally assessed by comparing people within the same society (URT, 2005). Poverty can further be classified into income and non-income poverty. However, income poverty is said to exacerbate other categories of poverty.

### 3.2.4 Income Poverty

Income poverty refers to the situation whereby the individual or household’s income is below the established poverty line, such that one cannot afford basic needs notably food, shelter and clothes (UNDP, 2011).

### 3.2.5 Poor Household

A poor household refers to the household which are characterized by severe deprivation of basic human needs like food, safe water, sanitation facilities, health services, shelter, education and access to information (UNDP, 2011).

### 3.2.6 Development

Development is a process of improving the quality of all humans’ life in capacities by raising people’s level of living, self-esteem, and freedom (Todaro, 2012)

### 3.2.7 Conditional Cash Transfer

These are programs that transfer cash generally to poor households on the conditions that those households make pre specified investments in the capital of their children (Fiszbein, 2009). They are programs with primary objective of alleviating poverty by supporting an immediate additional income for the poor (Britto, 2006).

## 3.3 Theoretical Literature Review

### 3.3.1 Income Poverty in the World and Tanzania

It is estimated that in 2013, about 767 million people which is equivalent to 10.7% of the world’s population lived under the international poverty line compared to 12.4 % in 2012. This progress was mainly driven by East Asia and Pacific notably China and Indonesia and South Asia notably India where number of poor people have significantly reduced. The (World Bank, 2016) report further shows that almost half of the extreme poor still live in Sub-Saharan Africa with about 389 million people living on less than USD 1.90 a day in 2013, a vast of whom live in rural areas relying on poorly mechanized  agricultural sector.

Income poverty is said to affect the rural population whose majority depend on subsistence agriculture by using inferior farm implements and poor tools. The income of rural households is mainly below the established poverty line, which is the amount of income required to satisfy basic needs. The results from (NBS, 2014) reveal that, income poverty was experienced by about 75.4 percent of Tanzanians who were currently employed in agricultural and fishery occupations with 87.6 percent of them living in rural areas. According to the current World Bank report (World Bank, 2016), the international poverty line is USD 1.90 which is equivalent to TZS 4,180.

The same report depicts that Tanzania in particular maintained stable economic growth between 2004 and 2014 with the average of 6.5% per year. During that period, extreme poverty declined from 11.7% to 9.7 %. As the report (World Bank, 2016) puts it, despite this decline in poverty, access to good schools, healthcare, electricity, safe water and other critical services remains elusive for many people, often determined by socioeconomic status, gender, ethnicity, and geography. Moreover, for those who have been able to move out of poverty, progress is often temporary: economic shocks, food insecurity and climate change threaten to rob them of their hard-won gains and force them back into poverty.

### 3.3.2 Efforts by Tanzania to Curb Income Poverty

Fighting against poverty has been a permanent agenda in the history of Tanzania. A number of strategies were put in place to eradicate poverty and increase economic growth. With reference to just a few of them, the Tanzania Development Vision 2025 designed in 1999, the National Poverty Eradication Strategy (NPES) designed in 1998 and Poverty Reduction Strategy Paper (PRSP) designed in 2000, set the goal of eradicating abject poverty by 2025. The review of PRSP guided formulation of the National Strategy for Growth and Reduction of Poverty (NSGRP or MKUKUTA). These second generation of PRS generated a strong agenda, aiming at sustaining broad-based growth whilst emphasizing equity and good governance. The MKUKUTA strategy has been the guiding frameworks for growth and poverty reduction in Tanzania.

Other current poverty reduction initiatives include the investment in human capital by providing free basic education to all, and employment creation through promotion of industrial sector, transport infrastructure and agricultural development including horticulture expansion. The government of Tanzania is also implementing a conditional cash transfer to identified poor households, for the purpose of raising their income and conditional stipends based on school enrollment and attendance as well as consumption of health services.  The obtained income can be used by the households to invest in other sustainable IGA notably small business, livestock keeping and crop farming in order to stabilize the income (Evans, 2013).

3.4 Empirical Literature Review

### 3.4.1 Soap Making and Production

As put by (Horowitz, 2013), Soap is a universal product that can be found in all homes, canteen, laundries, hotels and toilets. Soaps are used every day for washing and bathing hence justifying its constant demand due to its important role of the product in daily human life. Soap products can be bar soaps, liquid soaps and detergents with different scent, color and packaging. Soap production industry is among growing sectors of the economy in developing countries including Tanzania and they generate millions of money annually from small scale, medium scale and big soap producers. The industry produces direct and indirect employment opportunities. Soap products range from toilet soaps, bathing soaps, baby soaps, body wash soaps, hand wash, dish washer, cloth washing soaps, car wash soaps, and detergents. All these products can be in the form of bar, foam or liquid and are produced in different fragrance.

#### 3.4.2 Requirements for Soap Production

The equipment needed for soap making include soap making machine, heat resistance plastic or stainless steel pitcher with lid, big stainless steel or plastic spoon, stainless steel measuring spoons, measuring cups, small beakers, stick blender, soap moulds, soap pot, rubber spatulas, large stainless steel or plastic ladle, protective goggles, protective rubber hand gloves, quick reading and accurate thermometer (Horowitz, 2013). Other materials include lye solutions, oils, additives for coloring, packaging materials and fragrances. To be effective and competitive, there must be adequate space, distribution networking, good marketing skills and customer care services.

#### 3.4.3 Soap Marketing

There are wide range of available customers for soaps and detergents. Market and customer research must be thoroughly done to identify the demand and potential groups of people and organizations and the quality and quantity they may require. Customers may include individuals, hotels, restaurants and canteens, schools, government offices, mothers with babies, cleaning organizations, car washers, dispensaries and laundry owners.

## 3.5 Policy Review

### 3.5.1 Community Development Policy 1996

The government of Tanzania prepared the Community development policy (URT , 1996) to enable Tanzanians to bring about their own development by using locally available resources to improve production so that they may have increased income which will enable communities to build a better life through self reliance. It acknowledges the approach of involving the community especially through groups as the major way to eradicate poverty. Implementation of soap making project in Ngulyati village has also applied the same approach whereby a community has formed a group of nine women who decided working together for the purpose of increasing their income.

# 3.5.2 National Economic Empowerment Policy

Closely linked with the community development policy is the National Economic Empowerment Policy (URT, 2004) that intends to address all economic empowerment needs of the individual citizens of Tanzania and local companies in which Tanzania citizens hold not less than fifty percent of the shares. The Policy takes on board farmers, livestock keepers, fishermen, employees, traders as well as other groups of individuals in various economic activities. It is envisaged that, by the year 2025, a large segment of the national economy will be owned by Tanzanians. This process will embrace all Tanzanians by availing equal opportunities to all groups to develop them, particularly the rural poor like the members of Tushirikiane Women group in Ngulyati village who decided to start soap making project.

### 3.5.3Tanzania Development Vision 2025

The vision 2025 was prepared to guide the country in developing itself towards  active participation as the in global development characterized with advanced technology, high productivity, modern and efficient transportation and communication infrastructure. The development vision objective include achieving standard and good life for all citizens, good governance, rule of law and building a strong and resilient economy that can effectively withstand global competition (NBS, 2014). The vision 2015 acts as a roadmap through which the government continues to speed up the economic transformation from low productivity agriculture to a semi –industrialized economy. Transformations aim also at highly productive agricultural activities which are effectively integrated and strengthened by supportive industrial and service activities in the rural and urban setting.

## 3.5Literature Review Summary

From the reviewed literature, it is evident that many Tanzanians especially those living in the rural areas are still very poor. As most of the literature have revealed, poverty mostly affects the unemployed youth and women especially the those living in the rural areas. The contribution of the majority of Tanzanian citizens in the economy remains to be limited by lack of capital, limited knowledge, experience and skills, inappropriate mindset towards development and challenges associated with access to various opportunities provided in development policies. Other challenges facing the rural poor include lack of reliable markets and inability to penetrate competitive markets for their products. The information obtained in the reviewed literature regarding poverty is quite similar to that obtained during CNA as presented in the first chapter of this document. CNA findings also revealed that the women from poor households in Ngulyati Village in Bariadi District are mainly faced by income poverty and lack of capital to start their income generating activities.

Through various policy frameworks, the Government of Tanzania has created a platform through which all citizens are encouraged to participate in different economic activities depending on one’s interest, skills, capital, geographical location and available resources. It is from this opportunity that the community of nine women from the households which benefit from TASAF in Ngulyati village have decided raise their income by establishing Soap making project.

# CHAPTER FOUR

# PROJECT IMPLEMENTATION

## 4.1 Introduction

Project implementation requires harmonization of various activities and coordination of various institutions and stakeholders to ensure the project goals are realized. In this Chapter looked at the summary of all phases of project implementation including activity planning, project products and outputs analysis, required project resources, responsible persons for each activity, and the duration of time required to accomplish the project activities. The chapter also presents the project implementation report that highlights all important project activities implemented and the end project results achieved. The content of this chapter is very important as it merges the wishes obtained in the first chapter and the information obtained from literature review into practical reality. This chapter translates the project objectives presented in the second chapter of this document into practicable project activities to produce physical project products and outputs.

## 4.2 Project Outputs and Activities

This project had various outputs including the Community Needs Assessment report, trained group members on soap making, obtained tools for soap production and written constitution and the registered group. Others include the income of group members through soap production. As of now, the general goal of the project cannot be assessed because soap production is at the initial stage. An assessment on the rise of income among community members will be after several rounds of soap sales.  In order to achieve the project objectives and outputs, several activities were planned as presented in table4.1. All project activities have been successfully implemented and outputs achieved as anticipated.

# Table 4.1: Project Outputs and Activities

| OBJECTIVES | OUTPUTS | ACTIVITIES |
| --- | --- | --- |
| To train 9 Tushirikiane group members on soap making, packaging, by the end of September 2018 | Community Needs Assessment report | Conduct CNA (data collection, processing and analysis) |
|  |  | Write CNA report |
|  | 9 Group members trained on soap making and packaging | Make preparations for training |
|  |  | Conduct raining on soap production, packaging and marketing |
| To acquire premises for soap making and office by end of October 2018 | 2 rooms (1 for Soap factory and 1 for Office) | Mobilize funds to cover premises hiring costs |
|  |  | Hire two rooms |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition |
|  |  | Purchase materials and detergents and for soap production |
|  | 50lts of Liquid soap | Make soaps |
|  |  | Sell soaps and keep sales record |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared registration certificate | Prepare group constitution |
|  |  | Submit application package to Bariadi District Council Director for registration |
|  | Group Bank Account | Mobilize funds to open bank account |
|  |  | Submit application package to the bank for opening bank account |

Source: Researcher, 2018

In order to achieve the project objectives and outputs, several activities were planned as shown in Table 4.1. Many project activities have been successfully implemented and outputs achieved. Soap production has just started at small scale and t is expected to grow slowly as the group gets experience and reliable markets.

## 4.3 Project Products

The major project products are bar and liquid soap which are produced by Tushirikiane group. Other products include CNA report, training report on soap making, purchased production tools, group constitution, group registration certificate and a document bearing group bank details.

## 4.4 Project Planning

Project planning is the main component in the project development process. This component comprised of identifying the project objectives and outputs, scheduling the activities in logical sequence, identifying responsible persons for each activity, identifying resources needed and budget required. Planning tools including the project Implementation Plan, project budget, Logical Framework and Ghannt chart were prepared.

### 4.4.1 Implementation Plan

Implementation plan was prepared to guide implementation of the project. The plan indicated the activities to be executed, required resources, time frame and responsible person. Implementation of activities started timely by involving and consulting various stakeholders, especially the Community Development Officer on CBO formation and trade officer for technical inputs regarding soap making. Execution of the project activities followed the plan shown in table 4.2 and the Logic Framework shown in Table 4.3 respectively.

# Table 4.2: Project Implementation Plan

| OBJECTIVES | OUTPUTS | ACTIVITIES | PROJECT MONTHS | RESOURCES | RESPONSIBLE |
| --- | --- | --- | --- | --- | --- |
|  |  |  | AUG 2018 | SEPT 2018 | OCT 2018 | NOV 2018 |  |  |
| To train 9Tushirikiane group members on soap production, packaging, by the end of September 2018 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) |  |  |  |  | Personnel, Stationery and transport | VEO, CED student, Tushirikiane group |
|  |  | Write CNA report |  |  |  |  | Stationery , time, personnel | CED student |
|  | 9 Group members trained on soap making and packaging | Make preparations for training |  |  |  |  | Stationery, | CED student, VEO, FTushirikiane group, CDO |
|  |  | Conduct raining on soap production, packaging and marketing skills |  |  |  |  | Stationery, Meals, personnel and money | CED student, Trade Officer, Tushirikiane group, VEO |
| To acquire premises for soap making and office by end of October 2018 | 2 rooms (1 for Soap factory and 1 for Office) | Mobilize funds to cover premises hiring costs |  |  |  |  | Money, time, personnel | CED student, VEO, Tushirikiane group, CDO |
|  |  | Hire two rooms |  |  |  |  | Money, time, personnel | CED student, Tushirikiane group leaders, |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition |  |  |  |  | Human, Funds | CED student, VEO, Tushirikiane |
|  |  | Purchase materials and detergents and for soap production |  |  |  |  | Human, production tools, time | CED student, Tushirikiane group |
|  | 50lts of Liquid soap | Make soaps |  |  |  |  | Packaging materials, human, tools and detergents | CED student, Tushirikiane group |
|  |  | Sell soaps and keep sales record |  |  |  |  | Human, stationery | Tushirikiane group, VEO |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared and registration certificate obtained | Prepare group constitution |  |  |  |  | Stationery, Meals | CED student, VEO, Tushirikiane group, CDO |
|  |  | Submit application package to Municipal Director for registration |  |  |  |  | Transport costs, meals, personnel | CED student, VEO, Tushirikiane group leaders, CDO |
|  |  | Submit application package to for registration |  |  |  |  | Personnel, time, meals, transport costs | CED student, VEO, Tushirikiane group |
|  | Open Group Savings Bank Account | Fundraise to open bank account |  |  |  |  | Meals, time, personel | CED student, VEO, community, CDO |
|  |  | Submit application package to the bank to open Bank account |  |  |  |  | Funds to open bank account | CED student, VEO, ommunity leaders, |

Source: researcher, 2018

# Table 4.3: The Logical Framework of the Project

| Hierarchy of Objectives | Objectively Verifiable Indicators (OVIs) | Means of verification (MOV) | Assumptions |
| --- | --- | --- | --- |
| Objective 1: To train 9Tushirikiane group members on soap production, packaging, by the end of September 2018 |
| 1.2 Write CNA report |  |  |  |
| 2.1Make preparation for training | 15 community members attended training | Training report List of attendane | The participants will attend and follow instructions |
| 2.2 Conduct training on soap making and packaging |  |  |  |
| Objective 2: To acquire premises for soap making and office by end of October 2018 |
| Output 1: 2 rooms (1 for Soap factory and 1 for Office) | Hiring contract | soap factory and office | the premises will be available under one roof |
| Activities under outputs of objective 2 |  |  |  |
| 1.1 Mobilize funds to cover hiring costs | Funds mobilized | Cash and list of contributors | Willingness to contribute |
| 2.1 Hire office and factory/ production place for soap production | Soap factory and office obtained | structures and lease documents | The premises will be obtained |
| Objective 3: To procure soap making materials by end of October 2018 |
| Output 1: 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Tools purchased | List of purchased tools and detergents | Procurement will made as planned |
| Output 2: 50lts of Liquid soap | Soap produced and records kept | Production records | Production records will be kept accurately |
| Activities under outputs of objective 3 |  |  |  |
| 1.1Mobilize resources for tools acquisition | Amount of funds mobilised | List of contributors and amount contributed | Willingness of stakeholders to contribute |
| 1.2 Purchase materials and detergents and for soap production | List of materials and detergents procured | List of materials and detergents procured | Procurement will made as planned |
| Objective 4: To facilitate preparation of constitution, group registration and opening Bank account by November 2018 |
| Output 1. Constitution prepared and certificate obtained | Group registration is complete | Registration certificate | Certificate will be available on time |
| Output 2. Open Group Savings Bank Account | Bank Account has been opened | Bank account documents (Account details) | The group will meet the criteria |
| Activities under outputs of objective 3 |
| 1.1 Prepare group constitution | Group constitution prepared | Constitution | The CDO will guide the group in making a good constitution |
| 1.2 Submit application package to Council Director for registration | Application submitted and registration obtained | Registration certificate | Registration process will not take long |
| 2.1 Fundraise to open Bank Account | Funds mobilized | Amount of money collected and used to open Bank Account | Willingness of stakeholders to contribute |
| 2.2 Submit application package to the bank for bank account | Documents submitted and Bank Account opened | Bank Account details | The group will meet the criteria |

Source: researcher, 2018

### 4.4.2 Inputs

Various inputs were mobilized and used during implementation of this project. These include human resource, financial resources and material inputs and time. Human resources basically included Ngulyati Village leaders, community development Officer, trade officer, MCED student and the community members who provided their physical labor for daily execution of the project. Financial inputs are major resources which facilitated capacity building, transportation, and acquisition of project materials, group registration and opening bank account.

The details on the financial inputs are provided in section 4.4.4 of this document. Material inputs include time, office premises which was provided by the host organization and the vehicle provided by LGA to facilitate transport to the field. The MCED student provided technical inputs to ensure community participation during needs identification, selection of a project as well as project planning, management and documentation.

### 4.4.3 Staffing Pattern

The project is implemented by a group of 9 women from TASAF beneficiary households in Ngulyati Village. The activities were implemented under direct supervision of group leaders who normally got directives from village council leaders, Community Development Officer, trade officer and CED student. The group leaders include elected chairperson, secretary, treasurer who have the role of leading their fellow group members as specified in table 14. Management and coordination of project activities was done by the Village Council which is the host organization. The project has no paid staff because the nature of business does not involve paid employment.

# Table 4.4: Staff Pattern

| Position | Roles |
| --- | --- |
| Village Council Leaders | Overall management and coordination of activities and correspondences |
| Group Chairperson | Supervision of other group members, call for meetings and ensure all activities are implemented by considering the guidelines provided by Village leaders and other stakeholders |
| Group secretary | Keep group records and project documents, writing meeting minutes |
| Group treasurer | Keep records on income and expenditure; Collect and bank money from members contributions and other sources |
| Group members | Participation in all project activities for their own benefit |

Source: researcher, 2018

### 4.4.4 Project Budget

The project budget was TZS 1,731,000 that was mobilized from various contributors including the host organization, the Councilor for Ngulyati ward, CED student and beneficiaries. Estimation of project costs was done in collaboration between MCED student, community leaders, Community development officer and the project committee members who were chosen from the village council. The developed project budget is indicated in Table 4.5 as follows;

# Table.4.5: Project Budget

| OBJECTIVES | OUTPUTS | ACTIVITIES | RESOURCES | QUANTITY | UNIT COST | TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
| To train 9 Tushirikiane group member on soap production, packaging, by the end of September 2018 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | Personnel | 4persons | 15,000 | 60,000 |
|  |  |  | Stationery | Lumpsum | 30,000 | 30,000 |
|  |  |  | Transport | 4people | 15,000 | 60,000 |
|  |  | Write CNA report | Stationery | Lumpsum | 20,000 | 20,000 |
|  | 9 Group members trained on soap making and packaging | Make preparations for training | Stationery | Lumpsum | 60,000 | 60,000 |
|  |  | Conduct raining on soap production, packaging and marketing skills | Meals | 20 persons | 5,000 | 100,000 |
|  |  |  | Small buckets | 6 | 4,000 | 24,000 |
|  |  |  | Big buckets | 2 | 8,000 | 16,000 |
|  |  |  | Gloves | 10 pairs | 4000 | 40,000 |
|  |  |  | Colour | 500mls | 3000 | 3000 |
|  |  |  | Moulder | 1 | 40,000 | 40,000 |
|  |  |  | Sulpohonic | 2kg | 8000 | 16,000 |
|  |  |  | Caustic | 20Lts | 4,000 | 80,000 |
|  |  |  | Table | 1pc | 50,000 | 50,000 |
|  |  |  | Chair | 10 | 14,000 | 140,000 |
|  |  |  | Perfume | 1 Lt | 10,000 | 10,000 |
|  |  |  | Palm oil | 5Lts | 8,000 | 40,000 |
|  |  |  | Personnel allowance | 2 people | 25,000 | 50,000 |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition | Personnel | 3 | 15,000 | 45,000 |
|  |  | Purchase detergents and moulds for soap production | Colours | 1500mls | 15,000 | 15,000 |
|  |  |  | Caustic | 20Lts | 4,000 | 80,000 |
|  |  |  | Sulphonic | 4kgs | 8,000 | 32,000 |
|  |  |  | Perfume | 2Lts | 10,000 | 20,000 |
|  |  |  | Palm oil | 10Lts | 8,000 | 80,000 |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared and certificate obtained | Prepare group constitution and application | Stationery (printing and binding) | Lump sum | 30,000 | 30,000 |
|  |  |  | Meals | 18 people | 5,000 | 90,000 |
|  |  | Submit application package to Council Director for registration | Transport | 4 Persons | 5,000 | 20,000 |
|  |  |  | Meals | 4 persons | 5,000 | 20,000 |
|  |  |  | Personnel |  |  |  |
|  | Open Group Savings Bank Account | Fundraise to open bank account | Meals | 4 people | 5,000 | 20,000 |
|  |  |  | Transport costs | 4 people | 5,000 | 20,000 |
|  |  | Submit application package to the bank to open Bank account | Funds to open Bank Account | Lumpsum | 30,000 | 30,000 |
| TOTAL |  |  |  |  |  | 1,731,000 |

Source: researcher, 2018

## 4.5 Project Implementation

### 4.5.1 Project Implementation Report

The implementation of the project started in August 2018 as illustrated in the project implementation plan, and it clearly followed the sequenced order of activities that resulted into realization of project objectives. The MCED student in collaboration with the community development officer, trade officer and host organization, participated in all stages to ensure that there is smooth take off, and regular monitoring of all project activities. Implementation of project activities involved all identified stakeholders, each performing specified tasks. Implementation started by conducting CNA through which community needs were identified, project selected and the community to implement the project identified. There followed capacity building to the community on how to effectively implement the project. Thereafter, required tools were identified and bought.

# Figure 4.1: CED Student with VEO, and Project Beneficiaries as they Display Their First Products in their Office

The group of beneficiaries was registered into a CBO namely TUSHIRIKIANE with registration number CD/BRD/CBO’S NO. 775with a bank account number 30510018404 held at NMBBariadi Branch. Apart from soap production, the group has a vision of operating a credit and savings project in future. The detailed analysis of implemented activities and the current status are shown in the Table 4.6.

# Figure 4.2: CED Student with VEO, Community Development Officer and Project Beneficiaries during Liquid Soap Making

# Table 4.6: Project Implementation Report

| OBJECTIVES | OUTPUTS | ACTIVITIES | IMPLEMENTATION STATUS | REASONS FOR DEVIATION |
| --- | --- | --- | --- | --- |
| To train 9 Tushirikiane group member on soap production, packaging, by the end of August 2018 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | CNA completed | NA |
|  |  | Write CNA report | CNA report written | NA |
|  | 9 Group members trained on soap making and packaging | Make preparations for training | Preparations completed | NA |
|  |  | Conduct raining on soap production, packaging and marketing skills | Training was successfully done | NA |
| To acquire premises for soap making and office by end of October 2018 | 2 rooms (1 for Soap factory and 1 for Office) | Mobilize funds to cover premises hiring costs | Funds obtained | NA |
|  |  | Hire two rooms | Rooms obtained | NA |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition | Funds obtained | NA |
|  |  | Purchase materials and detergents and for soap production | Soap production started | NA |
|  | 50lts of Liquid soap | Make soaps |  |  |
|  |  | Sell soaps and keep sales record | Selling is on progress and sales records are kept | NA |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared and certificate obtained | Prepare group constitution and application | Constitution completed | NA |
|  |  | Submit application package to Council Director for registration | Certificate obtained | NA |
|  | Open Group Savings Bank Account | Fundraise to open bank account | Funds obtained | NA |
|  |  | Submit application package to the bank to open Bank account | Bank account obtained | NA |

Source: researcher, 2018

# Table 4.7: Project Implementation Ghannt Chat

| OBJECTIVES | OUTPUTS | ACTIVITIES | PROJECT MONTHS |
| --- | --- | --- | --- |
|  |  |  | AUG 2018 | SEPT 2018 | OCT 2018 | NOV 2018 |
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |
| To train 9Tushirikiane group member on soap production, packaging, by the end of September 2018 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Write CNA report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 9 Group members trained on soap making and packaging | Make preparations for training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conduct raining on soap production, packaging and marketing skills |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To acquire premises for soap making and office by end of October 2018 | 2 rooms (1 for Soap factory and 1 for Office) | Mobilize funds to cover premises hiring costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Hire two rooms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Purchase materials and detergents and for soap production |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 50lts of Liquid soap | Make soaps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Sell soaps and keep sales record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared and certificate obtained | Prepare group constitution and application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Submit application package to Council Director for registration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Open Group Savings Bank Account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Fundraise to open bank account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Submit application package to the bank to open Bank account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# PTER FIVE

# PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

## 5.1 Introduction

Participatory monitoring and evaluation is a process of involving all identified stakeholders of the project in all implementation stages including project planning, daily implementation of activities and finally assessment of the project towards achieving the goal. Involving the stakeholders makes them fully own the project and increases the chance of sustainability. This chapter provides discussion on participatory monitoring, evaluation and sustainability. It looks at how the community and various stakeholders used resources to facilitate day to day implementation of project activities towards achieving the desired project objectives. Through this chapter we will also look at how the project has succeeded to achieve the expected objectives and analyze durability and continuity of the project.

## 5.2 Participatory Monitoring

Monitoring is the process of regularly collecting information concerning the project. The collected information is normally used to assess the prevailing situation and discover trends and patterns. The project managers use the collected data to identify challenges and find solutions, keep project activities on schedule and measure progress towards achieving objectives. The information can further be used to inform decisions on human, financial and material resources and formulating or revising goals and objectives.  For the case of soap production in Ngulyati village, the community members participated fully from inception and daily implementation of activities in order to realize the predetermined objectives. Leaders from host organization and extension officers took part in daily monitoring of activities including capacity building, land and tools acquisition, farm preparation, transplantation and management and finally formal registration of a group into a CBO.

### 5.2.1 Monitoring Information System

The collected data were analyzed to generate analytical information which is used by stakeholders in making various decisions. Information was collected mainly through observation and meeting discussions with the community during regular field visits. Records were kept by MCED student and the community secretary. The collected data were on whether the activities are implemented as per schedule, inputs are available and if there are gaps and obstacles and the ways to address them.

Some of important information  regarding soap making project was on the number of trained community members, tools acquisition process, inventory of tools, records on collected funds and how they were spent, stakeholders, activity schedule, quantity of soap produced and sold and documentation on group registration and bank details. In order to keep records, the community has a book which is kept by secretary who is responsible for recording all information on project progress.

# Table 5.1: Monitoring Information System

| SN | Categories of information and activities | Elements to be monitored | Records to be kept | Who is collecting information | Who is the user of information | How to use information | Decision to be made and output to be achieved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Work Plan activities | Implementation of planned activities, activity timing, and availability of resources to facilitate implementation of activities | Work plans and their implementation status | Secretary and VEO | Project management team | Identifying the activities to be implemented; identifying the implementation gaps and make decisions | Re-planning, assess resources required and decide on how to access them |
| 2 | Cost and expenditure | Financial resources required, how to access them and how income and expenditure records are kept | Income and expenditure | Treasurer and VEO | Project management team and project beneficiaries | Assess adherence to project budget and Identifying financial gaps, | Decide on how to adhere to the budget and how to access more financial resources |
| 3 | Staff and supervision | Number of required staff, qualification and roles | Qualification and performance for each role | Chairperson Secretary and VEO | Project management team and project beneficiaries | Assess on the performance of roles for each position | Determine the performance gaps and plan how to fix them |
| 4 | Other inputs | Other required inputs which were not planned before | List of required additional inputs | Chairperson Secretary and VEO | Project management team and project beneficiaries | Assess the necessity of having emerging inputs and the available alternatives | Plan on how to get the inputs (if they are necessary) use the available inputs effectively |

Source: researcher, 2018

### 5.2.2 Participatory Monitoring Methods used in the Monitoring of the Project

Monitoring allows project implementers and supervisors to record progress of planned activities. In monitoring soap making project in Ngulyati village various methods were used but mostly we used Participatory Rural Appraisal (PRA), Beneficiaries Assessment (BA) and Participatory community needs assessment through which the community and other stakeholders shared their knowledge and experience regarding the project management. Regular meetings were conducted for planning and progress monitoring of the project. On call follow-ups were used by Community Development Officer (CDO) especially to record progress made during preparation of group constitution which was required for group registration and opening of bank account.

### 5.2.3 Participatory Monitoring Plan

The monitoring plan was prepared to guide the project monitoring exercise. It guides the stakeholders on the nature of information to collect, the indicators, the tools to use and the source of data in relation to the outputs and project objectives. It further specifies the timeframe within which monitoring will be done and the responsible person.

# Table 5.2: Project Monitoring Plan

| OBJECTIVES | OUTPUTS | ACTIVITIES | INDICATORS | DATA SOURCE |
| --- | --- | --- | --- | --- |
| To train 9 Tushirikiane group member on soap production, packaging, by the end of September2018 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | Community Needs Identified | CNA report |
|  |  | Write CNA report | Community Needs Identified | CNA report |
|  | 9 Group members trained on soap making and packaging | Make preparations for training | Identified venue, stationeries | Project progress report |
|  |  | Conduct raining on soap production, packaging and marketing skills | Attendance list of participants | Training report |
| To acquire premises for soap making and office by end of October 2018 | 2 rooms (1 for Soap factory and 1 for Office) | Mobilize funds to cover premises hiring costs | Cash collected | Project progress report |
|  |  | Hire two rooms | Contract | Project progress report |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition | Resources mobilised | Project progress report |
|  |  | Purchase materials and detergents and for soap production | Materials purchased | Project progress report |
|  | 50lts of Liquid soap | Make soaps | Soap made | Project progress report |
|  |  | Sell soaps and keep sales record | Sales | Project progress report |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared and certificate obtained | Prepare group constitution and application | Constitution prepared | Project progress report |
|  |  | Submit application package to Councill Director for registration | Application submitted and certificate obtained | Project progress report |
|  | Open Group Savings Bank Account | Fundraise to open bank account | Funds obtained | Project progress report |
|  |  | Submit application package to the bank to open Bank account | Application submitted and bank account opened | Project progress report |

Source: researcher, 2018

## 5.3 Participatory Evaluation

Participatory Project Evaluation is a systematic process of involving the community and stakeholders in investigating the significance or value of the project and determines whether the predetermined goal and objectives have been achieved. Through evaluation, the stakeholders get to know what was actually achieved, what was not achieved and why, what was learned and what else can be improved in order to enhance future performance. Evaluation forms part of management process consisting of planning, implementation and evaluation, each following the other in unbroken cycle until completion of the project and starting the other.

Evaluation is normally done with reference to the indicators which measure the achievement or failure of the project. For the case of soap making project in Ngulyati village, the project beneficiaries were involved in conducting participatory community needs assessment and identification of the project. While all objectives have been achieved, final evaluation will be done later after several sales of soap to assess the achievement of the project goal.

### 5.3.1 Performance Indicators

Performance indicators for soap making in Ngulyati village were categorized into input indicators, output indicators and impact indicators and they are qualitative and quantitative. Input indicators include time (number of man days), amount of money spent and other resources used while output indicators include number of community members trained, and the tools purchased.  Output indicators also include the quantity of soap to be made and sold, and the amount of money to be generated out of saleof the products. Finally, output indicator looks at the group registration certificate and bank details to prove that the group was formalized. Impact indicator for this project is the improved life standard as a result of improved income which will be obtained from sales of project products.

# Table 5.3: Project Performance Indicators

| Objectives | Outputs | Activities | Inputs Required | Performance Indicators |
| --- | --- | --- | --- | --- |
| To train 9 Tushirikiane group member on soap production, packaging, by the end of August 2018 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | Vehicle, Fuel, Personnel, Stationery, Time | CNA report |
|  |  | Prepare CNA report | Personnel, Time, Stationery | CNA report |
|  | 9 Group members trained on soap making and packaging | Make preparations for training | Stationery, time, personnel | Training materials, availability of Venue and facilitator |
|  |  | Conduct raining on soap production, packaging and marketing skills | Human, time, stationery, meals and refreshment | Training report and list of inputs |
| To acquire premises for soap making and office by end of October 2018 | 2 rooms (1 for Soap factory and 1 for Office) | Mobilize funds to cover premises hiring costs | Cash | Amount of cash |
|  |  | Hire two rooms | Cash, time, human | Hired premises |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition | Human, time, tools, cash | Amount of cash to purchase tools |
|  |  | Purchase materials and detergents and for soap production | Cash, time, human | List of purchased tools |
|  | 50lts of Liquid soap | Make soaps | Human, time, materials | Production records |
|  |  | Sell soaps and keep sales record | Human, time, tools | Soap sales records |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared and certificate obtained | Prepare group constitution and application | Human, stationery, time, food | Group Constitution |
|  |  | Submit application to council Director for registration | Human, time, transport cost, food, Time, Human | Application package submitted to DED |
|  |  | Obtain group office | Human, time | Office obtained |
|  | Open Group Bank Account | Mobilize TZS 30,000 funds to open bank account | Human, time, communication cost | TZS 30,000 mobilized to open bank account |
|  |  | Submit application package to the Bank for bank account | Human, time, transport cost, food | Application package submitted to the Bank |

Source: researcher, 2018

### 5.3.2 Participatory Evaluation Methods

This project had three objectives namely, to train 9 Tushirikiane group members on soap production and packaging by the end of August 2018, to start Soap production by end of October 2018 and to facilitate preparation of constitution, group registration and opening Bank account by November 2018.All project activities for all objectives have been completed.  As noted earlier on, evaluation of this project has not been done, it will be done at a later stage after several rounds of sales of the products to assess the progress towards achieving the project goal.

Evaluation will be done by the beneficiaries in collaboration with other stakeholders who will us Beneficiaries Assessment (BA) approach and Participatory Rural Appraisal (PRA). A checklist with predetermined questions will be used to interrogate the direct beneficiaries so that they can give their views on how the project has achieved the outputs, objectives, and goal and sustainability factors.

### 5.3.3 Project Evaluation Summary

The project evaluation summary provides achievement of the project based on the predetermined goal, objectives, outputs, activities performance indicators and expected outcome. All activities have been completed and objectives achieved. Generally for the finished activities, we have witnessed strong commitment of the project beneficiaries and stakeholders from inception of the project up to the stage of implementation. All completed activities were implemented and finished as per implementation plan.  The last evaluation which will be done later will provide a clear assessment on the extent to which the goal has been achieved.

# Table 5.4: Project Evaluation Summary

| Objectives | Outputs | Activities | Performance Indicators | Expected Outcome | Actual Outcome | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| To train 9 TushirikianeWomen group member on soap production, packaging, by the end of August 2018 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | CNA report | The community Needs Identified | The community needs were identified | Completed |
|  |  | Prepare CNA report | CNA report | The community Needs recorded | Community Needs were recorded and project identified | Completed |
|  | 9 Group members trained on soap making and packaging | Make preparations for training | Training materials, availability of Venue and facilitator | Training materials, Venue and facilitator obtained | Training materials, Venue and facilitator obtained | Completed |
|  |  | Conduct raining on soap production, packaging and marketing skills | Training report and list of inputs | 9 members of Tushirikiane group aware of ways of soap making and packaging | 9 members of Tushirikiane group aware of ways of soap making and packaging | Completed |
| To acquire premises for soap making and office by end of October 2018 | 2 rooms (1 for Soap factory and 1 for Office) | Mobilize funds to cover premises hiring costs | Amount of cash | Funds obtained | Funds obtained and used to hire premises | Completed |
|  |  | Hire two rooms | Contract for office hiring | Premises hired | Premises used in project activities | Completed |
| To procure soap making materials by end of October 2018 | 8 mixing buckets, 10 pairs of gloves, 1 molder, 1 wooden table, 500 ml colour, 2kgs sulphonic, 20Lts caustic and glycerin | Mobilize resources for tools acquisition | Amount of collected resources | Funds collected | Funds collected | Completed |
|  |  | Purchase materials and detergents and for soap production | Purchased tools and detergents | Materials purchased | Materials purchased | Completed |
|  | 50lts of Liquid soap | Make soaps | Quantity of soap made | 50lts of Liquid soap made | 50lts of Liquid soap made | Completed |
|  |  | Sell soaps and keep sales record | Amount of soap sold | 50Lts of liquid soap sold | 50Lts of liquid soap sold | Completed |
| To facilitate preparation of constitution, group registration and opening Bank account by November 2018 | Constitution prepared and certificate obtained | Prepare group constitution | Group Constitution | Group constitution prepared | Group constitution prepared | Completed |
|  |  | Submit application to council Director for group registration | Application package submitted to DED | Group registration certificate obtained | Group registration certificate obtained | Completed |
|  | Open Group Bank Account | Mobilize TZS 30,000 funds to open bank account | TZS 30,000 mobilized to open bank account | TZS 30,000 paid to the bank as an account opening balance | TZS 30,000 paid to the bank as an account opening balance | Completed |
|  |  | Submit application package to the Bank for bank account | Application package submitted to the Bank | Bank account opened | Bank account opened and operational | Completed |

Source: researcher, 2018

## 5.4 Project Sustainability

Sustainability of the project is assessed by looking at the factors which will facilitate the project to maintain its operations and benefits to beneficiaries even after withdrawal of funders.  We will look at the strategies in place and ability of the community to run the project and develop other income generating activities in future by using internal resources. In order to ensure sustainability, the CED student maintained the use of participatory approach in all stages from project identification, implementation, monitoring and evaluation. This approach has empowered the community members such that they can run the project with very minimal dependency from external support.

### 5.4.1 Strategies for Project Sustainability

There are various strategies for sustainability of soap making project in Ngulyati village. The strategies included involvement of project beneficiaries from CNA, resource mobilization, project implementation and monitoring of activities. Another strategy is involvement of community development officer and trade officers who instill skills into the group and capacity building in terms of production and management skills. In terms of financial sustainability, community members agreed to make contribution at every TASAF payment and keep that money for future expansion of operations.

Furthermore, the use of self-prepared constitution to guide daily group management, involvement of the village council as host organization and formalization of the community into a registered CBO with a bank account are very important strategies to ensure the group and the project are sustainable.

### 5.4.2 Project Sustainability Assessment

Sustainability assessment of the project is part of evaluation process which is expected to be done after completion of all project activities in August 2018. However, some indicators of sustainability were assessed at the beginning and during the course of implementation. Early indicators include commitment of the community members to work together with other stakeholders to identify the project, follow instructions provided by extension officers and willingness to contribute money for project operations. The economic sustainability of the project will be assessed at a more mature stage of a project.

### 5.4.3 Financial Sustainability

The project was implemented by nine women from households which normally get bi-monthly cash transfer from PSSN. From this cash, the members agreed to make a collective saving by contributing some money which was used to run the project and will still be used to expand project operations as specified in the group constitution. Other funds will be obtained from soap sales and they will be kept in the opened bank account and re invested as per their constitution.

### 5.4.4 Institutional Sustainability

It is anticipated that this group will abide to the articles of their self-prepared constitution and they will proceed to work under supervision of Ngulyati Village Council which is a permanent institution in the government structure. Also as noted during reviewing the policies, the project has a government support through various policies. By formalizing the group, it is obvious that the group members can access any support from the government and other Non-Government Organizations. The established CBO will be able to access soft loans and other capacity building opportunities including trainings on various income generating activities and business.

### 5.4.5 Political Sustainability

The project is supported by various government policies and it is being implemented in a politically healthy environment. The project has full political support from ward and village leaders who even contributed towards its establishment. It is anticipated that political leaders will proceed supporting the group and their project; and they will sensitize the community to establish similar projects through which the household incomes will be improved.

# CHAPTER SIX

# CONCLUSION AND RECOMMENDATION

## 6.1 Introduction

This chapter is an overview of the whole process from project identification through Participatory Community Needs Assessment, project implementation, monitoring and project evaluation. It discusses key issues identified in CNA, Literature review, the reasons for selecting the project, project implementation report, participatory monitoring, evaluation and sustainability. Furthermore, the chapter presents the recommendations to the community and host organization who may wish to implement similar projects. We will also discuss other unplanned occurrences which affected the project. In a nutshell, this chapter is a summary of what has been covered in all previous chapters.

## 6.2 Conclusion

Through the conducted participatory Community Needs Assessment (CNA), it was found that the outstanding challenge of community in Ngulyati village is low income. This community is made of very limited income earners but yet with high domestic workloads and household responsibilities. These women are mostly old and their families have up to 5 members on average, most of whom are children who have high requirements for education, medication and nutrition.

In order to raise their income, these women decided to form a CBO through which they implemented soap making project in Ngulyati village. The choice of soapmaking project considered various opportunities as reveled through the Community Participatory Assessment. Some of the reasons behind the choice include presence of a big market (auction place) in the village and presence of trade officer and community development officer who provide technical support. The presence of ongoing PSSN operations is yet another opportunity that influenced the project because the community got cash from the program and used part of it as startup capital.

Theoretical and empirical literature review was done to gather the existing knowledge and experience on poverty reduction, income generation and soap making activities. The gathered knowledge added value in implementing soap making in Ngulyati Village. Available policies on poverty reduction, women empowerment policy, community development policy and the Vision 2025 were also reviewed to assess on how the policy framework can affect the project. Generally, the literature shows that apart from continuous efforts to combat poverty, many Tanzanians especially women are still poor. The policy framework gives room for groups of disadvantaged people especially women and youth to engage themselves in income generating activities depending on their choices and ability. The information obtained in the reviewed literature regarding poverty is quite similar to that obtained during CNA as presented in the first chapter of this document and has greatly contributed towards successful implementation of the project.

Implementation of the project was directly done by 9 selected members under supervision of elected CBO leaders and coordination of Ngulyati village council which is the host organization.The project aimed at capacity building to the community on how best to make and sell soap, starting soap making and finally facilitate the community to form registered CBO with a constitution and bank account. In order to facilitate implementation of the objectives, the District Council as a major stakeholder provided ancommunity development officer and trade officer who offered all necessary guidance in various aspects regarding group formation and registration, soap making and marketing.

Implementation of the project started in August 2018 and followed the Implementation plan. The group of beneficiaries was registered into a CBO namely TUSHIRIKIANE with registration number CD/BRD/CBOS NO.775with a bank account number 30510018404 held at NMB Bariadi Branch. Apart from soap making, the group has a vision of operating a credit and savings project in future as specified in their constitution.

Monitoring of project activities was done by using participatory methods including the participatory Rural Appraisal (PRA) and Beneficiary Assessment (BA). The community members participated fully from inception and daily implementation of activities in order to realize the predetermined project objectives. The CED student in collaboration with leaders from host organization and extension officers took part in daily monitoring of activities including capacity building, tools acquisition, soap making and packaging, preparation of constitution and finally formal registration of a group into a CBO.

Some indicators of project sustainability were assessed at the beginning and during the course of implementation. Early indicators that are evident include financial sustainability, institutional sustainability and political sustainability. The community has demonstrated commitment to work together with other stakeholders to identify the project, follow instructions provided by experts and willingness to contribute money for project operations. The host organization with a lot of political support from the village and ward level is taking a leading role in coordinating all project activities. Also, having a group constitution, bank account and registering the group as a CBO is yet another vivid indicator of institutional sustainability. Other sustainability indicators have not revealed themselves at this stage and they will be recorded after final evaluation of the project.The economic sustainability of the project will only be measured later to assess the economic contribution towards improvement of beneficiaries’’ life and continuity of production.

## 6.3 Recommendations

It is hereby recommended that the host organization, Community Development officer and the Trade Officer keep close supervision in order to support the group and its operations by providing daily couching. The community still needs continuous practical guidance especially on producing quality soap, branding, packaging and marketing. The group also needs more training on financial and project management as well as conflict resolution to avoid group disintegration. Performance of this project should be taken as a lesson for other disadvantaged groups of women and youth groups around and outside the area who can be mobilized to follow the same path to save money, form and register groups and come up with any income generating project of their choice through which they will improve their income and reduce household poverty.

It is further recommended that future projects should use participatory approaches such us PRA and BA as they have proved to be strong tools of involving people in working together in the project identification, project implementation, monitoring and evaluation of project. The use of such approaches increases the chance of project ownership and sustainability because they allow the community to come up with real needs and appropriate solutions. Experience from implementation of soap production project has proved that the community and other stakeholders are ready to work and contribute both materially and financially provided that things are transparent.

# REFERENCES

Britto, S. F. (2006). Poverty in Focus. Brazil: United Nations development Programme.

Evans D. K. & Hausladen, S. (2013). Community Based Cash Transfers in Tanzania: Results from a randomized trial. Washington DC: World Bank.

Fiszbein, S. N. (2009). Conditional Cash Transfer. Washngton DC: The World Bank.

McKillip, M. (2007). Mechanical harvesting of Sweet Cherries resource. Washington DC: American Society of Agriculture Engineers.

NBS, (2014). Household Budget Survey 2011/2012 Main Report, Dar es Salaam: URT.

NBS, (2014). Tanzania Conditional Cash Transfer (CCT) Impact Evaluation: Final Report. Dar es Salaam.

The United Way of America, (2012). World Urbanization prospects the 2001 revision, New York: United Nations.

Todaro, S. C. (2012). Economic Development, Washington DC: Pearson.

UNDP, (2011). HUMAN DEVELOPMENT REPORT. London: Oxford University Press.

URT, (1996). Community Development Policy. Dar es salaam.

URT, (2004). National Economic Empowerment Policy. Dar Es Salaam.

URT, (2005). Poverty and Human Development Report, Research and analysis. Dar es Salaam: Mkuki na Nyota Publishers.

URT, (2007). Poverty and Human Development Report, Research and analysis. Dar es Salaam: Ministry of Planning, Economy and Empowerment.

URT, (2013). Productive Social Safety Net (PSSN) OPERATION MANUAL, Dar es Salaam, Tanzania.

World Bank, (2016). Poverty and Shared Prosperity: Taking on Inequality, Washington DC: World Bank Group.

World Bank, (2011). Poverty, Growth and Public Transfers. Washington DC: World Bank.

# APPENDICES

# Appendix 1: 	Questionnaire

QUESTIONNAIRE TO BE ADMINISTERED TO RESPONDENTS

Ward:_______________________________                Village_________________________

Distance in km to district HQ:__________

Date of Interview:___________________

Questionnaire  number___________

Name of Interviewer	Tel No:………………………………………….

| No | a) Age | b) Size of household | c) Education Level | d) Occupation/ source of income | e)Income per month in Tsh |
| --- | --- | --- | --- | --- | --- |
| 1 | 18 – 30 31 – 45 46 – 60 Above 60 | 1 2-3 4-5 Above 5 | Primary education Secondary education Higher education None | Farming Livestock keeping Petty business Casual Labor others | Below 30,000 31,000-40,000 41,000-50,000 51,000-60,000 Above 60,000 |

Objective 1: Socio economic and demographic Characteristics of the respondents

2) Household composition and population

| Age group | Number of household member |
| --- | --- |
| 1. Adults (≥18 years) |  |
| 2. Children (11-18 years) |  |
| 3.Children (<10years |  |
| Total |  |

Objective 2: Economic activities in Ngulyati village

3) What are economic activities taking place in Ngulyati village (mention a least three)

- ………………ii…………………..iii……………………….

Objective 3: Challenges and Needs for women from TASAF beneficiary households in Ngulyati village

4) Choose one among the following needs of the women in your village (choose the most pressing)

|  | Need | Tick |
| --- | --- | --- |
| 1 | Business Start up capital |  |
| 2 | Improved household income |  |
| 5 | Market linkages for agricultural products |  |
| 6 | Entrepreneurship training |  |

Objective 4: identification of an economic project

5) Which project do you think is good for you to implement and improve your income? (According to your experience and environment)….Tick once against your choice

| No | Project (Income generating activity) | Tick |
| --- | --- | --- |
| 1 | Poultry |  |
| 2 | Tie and dye |  |
| 3 | Cotton farming |  |
| 4 | Soap making |  |
| 5 | Goat/ sheep keeping |  |

6) Why do you think that project is suitable for you (Refer your choice above)

| No | Reason | Tick only three |
| --- | --- | --- |
| 1 | Favorable weather condition |  |
| 2 | Availability of river/ ponds/wells for irrigation |  |
| 3 | Less diseases attacking plants/ animals |  |
| 4 | Soil fertility |  |
| 5 | Market availability |  |
| 6 | Easy to produce |  |
| 7 | Availability of Skills and experience |  |
| 8 | Requires small capital and running costs |  |
| 9 | Others (mention) |  |

7) Are you ready to join others and work together in an organized group? Yes_______No__________

8) Do you have any suggestion/ comment?_________________________________

# Appendix 2: Focus Group Discussion Checklist

- What are the needs of the poor women in your village (Ngulyati)

- How can the needs you have mentioned be addressed?

- Which project do you think is good for you to implement and improve your income?

- Why do you think the project you have mentioned is suitable for you

# Appendix 3: Registration Certificate for Tushirikiane Group in Ngulyati village

# Appendix 4: Tushirikiane Bank Account details

Appendix 5: Registered constitution for Tushirikiane Group in Ngulyati village

# Text boxes

VILLAGE COUNCIL

VILLAGE CHAIRPERSON

SECURITY COMMITTEE

ENVIRONMENTAL COMMITTEE

COMMUNITY DEVELOPMENT COMITTEE

FINANCE COMMITTEE

VILLAGE EXECUTIVE OFFICER