ESTABLISHMENT OF LIQUID SOAP MAKING PROJECT TO IMPROVE INCOME OF JITHAMINI GROUP IN GONGOLAMBOTO WARD IN ILALA MUNICIPALITY, DAR ES SALAAM

VIOLET ONESMO KILUVIA

A DISSERTATION SUBMITTED IN PARTIAL FULFILLMENT OF THE REQUIREMENTS FOR THE DEGREE OF MASTER OF COMMUNITY ECONOMIC DEVELOPMENT (MCED)

DEPARTMENT OF COMMUNITY ECONOMIC DEVELOPMENT

OF THE OPEN UNIVERSITY OF TANZANIA

2021

# CERTIFICATION

The undersigned certifies that has read and hereby recommend for the acceptance by the Open University of Tanzania (OUT) a project entitled; “Establishment of Liquid Soap Making Project to Improve Income of Jithamini Group in Gongolamboto Ward in Ilala Municipality, Dar es Salaam”, in partial fulfillment of the requirements for the degree of Master of Community Economic Development of the Open University of Tanzania.

…………………………………..

Dr. Felician Mutasa

(Supervisor)

...........................................

Date

COPYRIGHT

No any part of this dissertation may be replicated, distributed in any form or by any means, in full or in part, with the exception of citation in research studies, without written permission of Directorate of postgraduate studies on behalf of the author and Open University of Tanzania.

# DECLARATION

I, Violet Onesmo Kiluvia, declare that, the work presented in this dissertation is original. It has never been presented to any other University or Institution for the same purpose. Where other people’s works have been used, references have been provided. It is in this regard that I declare this work as originally done by the researcher. It is hereby presented in partial fulfillment of the requirements for the award of Masters Degree in Community Economic Development (MCED) of the Open University of Tanzania.

……………..………..………….

Signature

…………………….………..

Date

# DEDICATION

This work is dedicated to my beloved husband Mr. Steven J. Motta, my children Davis and Derick; all relatives and friends for their tireless efforts and encouragements throughout my studies.

Thank you!

# ACKNOWLEDGEMENTS

I sincerely thank the heavenly God for giving me good health, encouragement and passion which helped me to accomplish my studies. Special appreciation goes to my supervisor Dr. Mutasa for his tireless efforts, constructive ideas and proper guidance which   enabled me to write this dissertation; and to my work mates Johari and Zuwena who always encouraged and motivated me throughout the study.  I also extend my heartfelt thanks Mr. Salmin, my immediate supervisor for allowing me to pursue my Masters studies. All instructors at the Open University of Tanzania particularly the CED department deserve special thanks for imparting knowledge and skills to me in a serious tone.

I appreciate the support provided by Jithamini group and the host organization that provided me with constructive information, adequate cooperation and moral support during data collection and project implementation. Many congratulations to The Open University of Tanzania for running this very important course as it has been an eye opener and more practical to me as a student and to the community which has managed to establish liquid soap production project.

Lastly, this research report is a result of different people whose contribution can’t be underestimated but yet they can’t be mentioned all on this page, but I extend my heartfelt gratitude to all.

# ABSTRACT

This project report is a result of the Participatory Needs Assessment which was conducted in Gongolamboto Ward, Ilala Municipality, to identify the needs of widows who are engaged in small and informal business. The study applied descriptive research design under which both qualitative and quantitative approach was employed. The researcher employed simple random sampling and purposive sampling techniques to get respondents. Data were collected from a sample of 33 respondents using primary and secondary sources. The reviewed literatures have clearly shown that despite the government’s efforts to combat poverty and the avenue provided in various policy documents have not been able to pull many Tanzanians especially women out of income poverty. The assessment found that the community, as any other widows of the same status in Tanzania is experiencing income poverty to the extent of failing to afford basic needs for themselves and their dependents. The group members and other stakeholders including the researcher, contributed money which was used as a starting capital of the project. Sustainability of the project is assured because the community has shown commitment to own and work with other stakeholders in implementing the project. The recommendations put forward include close involvement of government extension officers especially community development and trade officers in in order to nurture the group in all production activities in order to maximize profit. It is also recommended that other groups with similar composition and characteristics should learn from Jithamini group in order to improve their income and reduce household poverty.

Keywords: Absolute Poverty, Poverty, Relative Poverty, Income Poverty.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENTS	vi

ABSTRACT	vii

TABLE OF CONTENTS	viii

LIST OF TABLES	xiii

LIST OF FIGURES	xiv

LIST OF ABBREVIATIONS	xv

CHAPTER ONE	1

PARTICIPATORY NEEDS ASSESSMENT	1

1.1	Background Information	1

1.2	Community Profile	3

1.2.1	Demographic Features	4

1.2.2	Ethnicity	4

1.2.3	Economic Activities	5

1.2.4	Social Services	5

1.3	Community Needs Assessment	6

1.3.1	Objectives of the Community Needs Assessment	7

1.3.1.1	General Objective	7

1.3.1.2	Specific Objectives	7

1.3.2	Research Questions	7

1.3.3	Research Methodology	8

1.3.3.1	Research Design	8

1.3.3.2	Sampling Techniques	9

1.3.3.3	Data Collection Methods	10

1.3.3.4	Data Analysis Methods	10

1.3.3.5	Data Presentation	10

1.4	CNA Findings	11

1.4.1	Demographic and Socio Economic Characteristics of Respondents	11

1.4.1.1	Respondents’ Age Distribution	11

1.4.1.2	Respondents’ Household Composition	12

1.4.1.3	Education Level of Respondents	13

1.4.1.4	Occupation of Respondents	14

1.4.1.5	Income Distribution	15

1.4.2	Community Needs	17

1.5	Needs Prioritization and Leveling	17

1.5.1 	Selection of Community Project	18

1.6 	Conclusion	20

CHAPTER TWO	21

PROBLEM IDENTIFICATION	21

2.1	Background to Research Problem	21

2.2	Problem Statement	22

2.3 	Project Description	23

2.2.1	Target Community	24

2.2.2	Stakeholders	25

2.2.3 	Project Goal	26

2.2.3.1 	Project Objectives	26

2.2.3.2 	General Objective of the Project	26

2.2.3.3 	Specific Objectives of the Project	26

2.3 	Host Organization	26

2.3.1 	Vision of the Host Organization	27

2.3.2 	Mission of the Host Organization	27

2.3.3 	Gongolamboto Ward Development Council Organization Structure	27

2.2.4 	Host Organization’s Strength, Weakness, Opportunities and                   Challenges (SWOC) Analysis	28

2.3.5 	The Role of the Host Organization	29

2.3.6 	The Role of the Student	29

CHAPTER THREE	31

LITERATURE REVIEW	31

3.1 	Overview	31

3.2 	Definition of Concepts	31

3.3 	Theoretical Literature Review	32

3.3.1 	Sociological Theory of Entrepreneurship	33

3.3.2 	Economic Theory of Entrepreneurship	33

3.4 	Empirical Literature Review	35

3.4.1 	Income Poverty in the World and Tanzania	35

3.4.2 	Efforts by Tanzania to Curb Income Poverty	36

3.4.3 	Soap making and Production	37

3.4.3.1 	Requirements for Soap Production	37

3.4.3.2	Soap Marketing	38

3.5 	Policy Review	38

3.5.1 	Community Development Policy 1996	38

3.5.3	Tanzania Development Vision 2025	39

3.6 	Literature Review Summary	39

CHAPTER FOUR	41

PROJECT IMPLEMENTATION	41

4.1 	Overview	41

4.2 	Project Outputs and Activities	41

4.3 	Project Products	42

4.4 	Project Planning	42

4.4.1 	Implementation Plan	42

4.4.2 	Inputs	47

4.4.3 	Staffing Pattern	47

4.4.4 	Project Budget	49

4.5 	Project Implementation	51

4.5.1 	Project Implementation Report	51

CHAPTER FIVE	55

PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	55

5.1 	Overview	55

5.2 	Participatory Monitoring	55

5.2.1 	Monitoring Information System	56

5.2.2 	Participatory Monitoring Methods	58

5.2.3 	Participatory Project Monitoring Plan	58

5.3 	Participatory Project Evaluation	60

5.3.1 	Project Performance Indicators	60

5.3.2 	Participatory Evaluation Methods	62

5.3.3 	Project Evaluation Summary	63

5.4 	Project Sustainability	65

5.4.1 	Strategies for Project Sustainability	65

5.4.2 	Project Sustainability Assessment	66

5.4.3 	Financial Sustainability	66

5.4.4 	Institutional Sustainability	66

5.4.5 	Political Sustainability	67

CHAPTER SIX	68

CONCLUSION AND RECOMMENDATIONS	68

6.1 	Introduction	68

6.2 	Conclusion	68

6.3 	Recommendations	71

REFERENCES	73

APPENDICES	75

# LIST OF TABLES

Table 1.1: Age Distribution of Respondents	12

Table 1.2: Respondents' Size of Household	13

Table 2.1: Stakeholders Analysis Matrix	25

Table 2.2: SWOC Analysis of the Host Organization	28

Table 4.1: Project Implementation Plan	43

Table 4.2: The Logical Framework of the Project	45

Table 4.3: Staff Pattern	48

Table 4.5: Project Implementation Report	53

Table 4.6: Project Implementation Ghannt Chat	54

Table 5.4: Project Evaluation Summary	64

Table 5.1: Monitoring Information System	57

Table 5.2: Project Monitoring Plan	59

Table 5.3: Project Performance Indicators	61

Table 5.4: Project Evaluation Summary	64

# LIST OF FIGURES

Figure 1.1: Education Level of Respondents	13

Figure 1.2: Respondents Occupation	14

Figure 1.3: Respondents' Income Distribution	16

Figure 1.1 Gongolamboto Ward Organization Structure	27

# LIST OF ABBREVIATIONS

BA	Beneficiaries Assessment

CBO	Community Based Organization

CCT	Conditional Cash Transfer

CED	Community Economic Development

CNA	Community Needs Assessment

DC	District Council

DCDO	District Community Development Officer

FGD	Focus Group Discussion

HBS	Household Budget Survey

IGA	Income Generating Activities

LGA	Local Government Authority

MCED	Master of Community Economic Development

MDG	Millennium Development Goals

MIS	Management Information System

MKUKUTA	Mkakatiwakukuzauchuminakupunguzaumasikini Tanzania

MKUZA	MkakatiwakukuzaUchumi Zanzibar

NBS	National Bureau of Statistics

NMB	National Microfinance Bank

NPES	National Poverty Eradication Strategy

NSGRP	National Strategy for Growth and Reduction of Poverty

PRA	Participatory Rural Appraisal

PRSP	Poverty Reduction Strategy Paper

PSSN	Productive Social Safety Net

SPSS	Statistical Package for Social Science

SWOC	Strength, Weaknesses, Opportunities and Challenges

TASAF	Tanzania Social Action Fund

TZS	Tanzanian Shillings

URT	United Republic of Tanzania

USD	United States Dollar

WEO	Ward Executive Officer

WB	World Bank

# CHAPTER ONE

# PARTICIPATORY NEEDS ASSESSMENT

## Background Information

The Tanzania Household Budget Survey (2017/2018) (NBS, 2019)indicates  that approximately 33% of the households are headed by women most of whom are facing legislative and financial barriers as well as gender norms that impede their full participation in economic and social development. The same report (ibid), says that although women account for 70% of the total food produced, they still face challenges such as lack of access to financial credit and skills development and high rates of domestic violence.

Tanzanian women are still experiencing severe discrimination in both laws and practices. It is clarified in the Household Budget survey (2017/2018) that the customary law of 1963 prohibits women, widows and daughters from inheriting land. This makes the law one of major bottle necks for the women to engage in business that would effectively improve their income.  According to the Household Budget survey (2017/2018) (NBS, 2019), about 3% of Tanzanian poor people live in Dar essalaam and it has doubled from 1.5% in 2012. It is further stated in the survey that about 27.4% of women headed households are poor as while only 26% of male headed households are poor.

Due to extreme income poverty affecting women headed households, they always experience lack of access to quality education, health care services, sufficient housing, water and sanitation services and proper nutrition.  This is affirmed by the (World Bank, 2016)which says that effects of poverty are worse in child headed, and women headed households which have limited access to productive assets especially agricultural land. The World Bank (ibid) suggests that the situation of income poverty as experienced by many people, requires  for constant interventions on poverty reduction and economic growth through social safety net programs, improvement of agricultural and transportation systems, reduction of population growth, and improvement of access to social services notably education, health, water and sanitation and housing.

In order to reduce poverty in the country, Tanzania as any other developing countries in Africa has been implementing a series of poverty reduction strategies and programs to improve food and nonfood production, community livelihood and social service delivery. Some of the strategies implemented in Tanzania from the year 2000 include the National Strategy for Growth and Reduction of Poverty (MKUKUTA1&2) in mainland, Zanzibar strategy for Growth and Reduction of Poverty (MKUZA) in Zanzibar, United Nations Millennium Development Goals (MDGs) and Tanzania National Development Vision 2025, the first five year National Development Plan 2011/12- 2015/16, the second five year National Development Plan 2016/17-2020/21.

For the same purpose of reducing the effects of poverty, Tanzania is implementing regional and international commitments like East Africa Community Vision 2050, Africa Development Agenda 2063 and the Global Agenda 2030 on Sustainable Development Goals. For the past eight years since the year 2012, the government of Tanzania in collaboration with other Development Partners has been implementing a national wide Productive Social Safety Net (PSSN) to support the most vulnerable and income poor households through provision of a bi-monthly Conditional Cash Transfer (CCT) for the purpose of increasing their household income and economic opportunity while adding up their consumption of health and education services (URT, 2013). Despite the efforts of the government and other stakeholders in fighting against poverty, various reports are still showing a big part of populations living below poverty line hence calling for more efforts from the government, Non-Government organizations (NGO) and the community itself.

Through this chapter, we reviewed the basic information on the community under study and illustrated how Participatory Community Needs Assessment was applied as a tool to identify and rank the community needs by involving the community. Through the participatory needs assessment, we were able to understand the community, their needs, priorities, available opportunities and resources as well as identification of potential stakeholders.  Through participatory needs assessment, all identified community members had equal opportunity to participate in identifying their needs and rank them starting with the most burning need and deciding on which one should be addressed first. Finally, the chapter presents the analyzed study findings and the suggestions on the available alternative projects through which the needs will be addressed.

## Community Profile

The study involved a community of widows from very poor households who are also engaged in small business and informal undertakings in Gongolamboto Ward, Ilala Municipality. These women are from very poor households with relatively low income levels and very limited access to basic needs like decent housing, quality health services, nutrition, education, clean water, sanitation services and decent clothes.  Gongolambotois one of the administrative wards of Ilala Municipality of the Dar es Salaam Region. The ward is located some 21 Kilometresin the Western part of the city and consists of four (4) sub wards namely Guluka Kwalala, Ulongoni A, Ulongoni B and Gongolamboto.

### Demographic Features

According to the 2012 census (NBS, 2012) GongolambotoWard had a population of 57,312 people out of which 27,927 were males and 29,385 were females. According to anecdotal data obtained from the office of the Ward Executive Officer, there are about 126 widows in Gongolamboto Ward out of whom 74 are known for their engagement in small business for the purpose of raising their income.

### Ethnicity

Gongolamboto Ward is basically an urban setting with very complex mixture of inhabitants from all parts of Tanzania. However, the Zaramo are slightly higher in numbers as compared to other tribes like the Sukuma, Chagga, Mwera, Ngindo, Makonde, Luguru, Pogoro, and others. Most of the people in Gongolamboto Ward as it is in the whole of Ilala Municipality, are Muslims and few Christians and Pagans.  These ethnic characteristics of the inhabitants show that the community is a combination of people from various parts of Tanzania with various backgrounds and experiences with a Tanzanian spirit of loving each other and hardworking in fighting poverty. It was therefore anticipated that the identified community members in Gongolamboto Ward will similarly work together in identifying the needs and implementing the project that will increase their income.

### Economic Activities

As in other urban areas, there are various economic activities taking place in Gongolamboto. The economic activities range from urban horticulture, poultry, bricks making, quarrying, transportation, arts and entertainment, hair dressing,   and other people engage in petty business like kiosk and food vending. As presented by (NBS, 2014), the households are likely to be poor if they are dependent on informal sector like sale of food and cash crops or earning a living from natural products. On the contrary, households tend to be non-poor when they become part of the formal sector and receiving wages or business income. The community in GongolambotoWard especially the poor widows have to be supported so that they can diversify their income generating activities in order to get rid of income poverty.

### Social Services

Gongolamboto Ward in Ilala Municipality, has all basic social services mainly primary education, health, water, transport, power and spiritual services. There are6 public and 4 private primary schools, 3 public and 2 private secondary schools, and one private university namely Kampala International University. Part of the ward is well connected to piped water such that most of the houses have running water. However, some parts have no piped water such that people get water from their self-made shallow wells.

The ward is electrified with power from Tanzania Electric Service Company (TANESCO), and it has good road networks both tarmac roads and rough roads passable throughout the year which are periodically maintained by Tanzania National Roads Agency (TANROADS) and Tanzania Rural Roads Agency (TARURA). The availability of these social services especially, electrical power and passable roads guarantees marketability of the products which will be produced by the community.

## Community Needs Assessment

Community Needs Assessment (CNA) is defined as systematic process of collecting and analyzing information which is used to guide resource allocation decisions with a view to discover and identify goods and services the community is lacking in relation to the generally accepted standards, and for which there exists some consensus as to the community’s responsibility for their provision (The United Way of America, 2012). Also, (McKillip, 2007) definesCNA as a process of “ordering and prioritization of community needs.” Therefore Community Needs Assessment is a way of gathering data about a community’s opinions, needs, challenges, and assets used to determine which project(s) will meet the real needs of the community.

Community Needs Assessment(CNA)was conducted in Gongolamboto Ward, Ilala Municipality to identify the needs of poor widows (community) and look at possible project and income generation initiatives through which their needs could be solved. This community is part of poor households which are headed by women but the focus was on only those who have an informal and relatively small income generating activity like Kioski, hair dressing saloon, food vending, genge, tailoring, fish frying, selling vegetables and fruits so that they can diversify their opportunities by establishing another community managed project . The study also assessed opportunities and challenges to implement the project, market and capacity building gaps as well as the strength and weakness (SWOT) the host organization.

### Objectives of the Community Needs Assessment

#### General Objective

The general objective of the study was to collect data on the needs of poor widows who also have small business undertaking in Gongolamboto Ward in Ilala Municipality and identify available economic options for community managed interventions.

#### Specific Objectives

The Specific objectives of the study were as follows;

- To describe social economic and demographic characteristics of  widows who have small business in Gongolamboto Ward

- To assess the available economic activities implemented in Gongolamboto Ward

- To identify the community needs among widows who also have small business in Gongolamboto Ward

- To identify the most feasible project to mitigate the community needs as  identified by the widows who also have small business in Gongolamboto Ward

### Research Questions

The study seeks to get answers for the following research questions;

- What are social economic and demographic characteristics of widows who have small business in Gongolamboto Ward?

- What are the major economic activities in Gongolamboto Ward?

- What are the main community needs among widows who also have small business in Gongolamboto Ward?

- What is the most feasible project to mitigate the community needs as identified by the widows who also have small business in Gongolamboto Ward?

### Research Methodology

This section of Research Methodology describes the design of the study through which the research questions will be answered. It describes the study population, the sampling frame, sample size and sampling techniques. In this section, we also discuss the data collection methods and how the collected data were processed, analyzed and presented.

#### Research Design

This assessment was both descriptive and participatory study in nature because throughout the research, there was involvement of community (widows), Gongolamboto Ward leaders and other identified stakeholders in getting the answers for the predetermined research questions. The methods for primary data collection included survey questionnaires, interviews and observation. Questionnaires were used to collect data from widows who are the main respondents. Interview was only used to gather information from key informants including Trade officer, cooperatives officer, Community Development Officer, and Ward Government leaders. The use of these data collection methods ensured high level of participation and involvement of the community in identifying and ranking the community needs and selecting the project.

Secondary data were collected from various documents including ward development reports and National Bureau of Statistics (NBS). While the major data collection technique was the questionnaire, other used techniques like interview, Focus Group discussion (FGD), and observation were used to get information that were used to complement the data collected by using the questionnaire.

#### Sampling Techniques

The sampling frame for this study was 74 poor widows which is the total population of widows who also do small business in Gongolamboto Ward. Although the ward has more widows, the focus of this study was put to only those who at least have a small business, excluding those with no any business and those with relatively big business. Purposive sampling technique was applied to get the list and details of 74 widows with predetermined criteria. The list of known widows who run small business was provided by the Community Development Officer who is based in Gongolamboto Ward. From this sampling frame, the researcher applied random sampling technique to get only 33 respondents which is equivalent to 44.5%of the total population whereby every widow owning a small business in Gongolamboto Ward had an equal chance to participate in the research.

However, after completion of the study only ten widows out of those 33 who participated in the study were conveniently selected and agreed to participate directly in project implementation. Selection of the widows to join the group that would participate in the project implementation considered various factors like readiness of the member work with others in the group, readiness and ability to contribute money for startup capital and group registration, ability to work and availability to participate with others.

#### Data Collection Methods

Primary data was directly collected from 33 main respondents who are the widows who also own small business in Gongolamboto Ward. The data was collected by using the prepared questionnaire as main tool. The questionnaires were administered by two competent data collectors who were trained and led by the researcher to collect data from the sample group of 33 respondents. Apart from the questionnaire which was the main tool of data collection, interviews to Key Informants and Focus Group Discussion (FGD) were used whereby respondents were divided into 3 equally sized groups to discuss and come with answers for the questions derived from the research questions. FGD was used to get detailed information on identifying and raking their needs and how to overcome them by selecting the project. The checklist which was prepared to guide the discussion and help the researcher to verify data (triangulation) collected by using questionnaire is annexed.

#### Data Analysis Methods

The collected data were manually edited, coded and analyzed byusing the Statistical Package for Social Sciences (SPSS) and Microsoft excel to provide frequencies and percentages (descriptive statistics for interpretation) regarding the socio-economic characteristics of respondents like age, education level, occupation and income.

#### Data Presentation

The analyzed data were presented in form of tables of frequency and percentages to show and validate the information provided by respondents. Prioritization of community needs and ranking of community interventions were also presented in tables and figures.

## CNA Findings

This section of the document gives the analysis and discussions regarding the data which were gathered from 33respondents who were randomly sampled from 74 widows who also own informal and small business in Gongolamboto Ward in Ilala Municipality. The ranking of the community needs as well as prioritization and selection of viable project to be implemented by the community is also presented in this chapter. The data analysis, presentation and discussion were done to provide answers for the research questions and the given objectives of this study.

### Demographic and Socio Economic Characteristics of Respondents

This part of the document presents the discussion on the respondents’ age distribution, family size, education level, occupation, economic activities and monthly income. As it has been noted from the beginning, this study involved widows only, therefore there was no reason to collect, analyze and discuss data on sex distribution of respondents.

#### Respondents’ Age Distribution

As shown in Table 1.1 bellow, the collected data show clearly that about 51.5% of widows who also small business in Gongolamboto Ward dare aged between 46 to 60 years. From the same table we also see that about 81.8% of the respondents have the age ranging between 31 to 60 years old. These data about the age of respondents imply that these widows are still youthful and have energy to involve in economic activities which could improve the livelihood of their households. Probably due to poverty experienced by this community, and poor access to quality food and inadequate access to health services; the data suggest that very few of them just 2 out of 33 respondents which is equivalent to 6% can live above 60 years. This age is slightly below 64years which is the pronounced average life expectancy for Tanzanian females (World Health Rankings, 2017). Enhancement and involvement of these widows in income generating activities would lead into improving their financial capacity to afford basic needs like nutritious food, Medical services and housing and hence add their chances to live longer.

# Table 1.1: Age Distribution of Respondents

| Age bracket | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | 18-30 | 4 | 12.1 | 12.1 | 12.1 |
|  | 31-45 | 10 | 30.3 | 30.3 | 42.4 |
|  | 46-60 | 17 | 51.5 | 51.5 | 93.9 |
|  | Above 60 | 2 | 6.1 | 6.1 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2020)

#### Respondents’ Household Composition

The collected dada depicts that about 17 out of 33 respondents which is equivalent to 51.5% have households with 4 to 5 members. During FGDs we also noted that apart from the head of the family, most household members areyoung children who are still at schoolsin various stages. This implies that these widows whoare breadwinners have to find money to cover for all domestic requirements especially those related to school and health services; food, housing and clothing. Also the data show a substantial number of respondents whose households have 2 to 3 members as it is to those with more than 5 members, which is 24.2% for each group. Engagement of these women in income generating activities will result into relatively stable incomes that would strengthen their economic capacity to meet household consumption requirements

# Table 1.2: Respondents' Size of Household

| Household size | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | 2-3 | 8 | 24.2 | 24.2 | 24.2 |
|  | 4-5 | 17 | 51.5 | 51.5 | 75.8 |
|  | Above 5 | 8 | 24.2 | 24.2 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field Data (2020)

#### Education Level of Respondents

The level of poverty is normally associated with the education level of head and other members in the household. Out of 33 respondents, about 19respondents equivalent to 56 % had completed primary school while 11 respondents equivalent to 33% had completed Ordinary level secondary school.

# Figure 1.1: Education Level of Respondents

Source: Field Data (2020)

Also, 3 respondents never equivalent to 9% never went to school. There was nobody who reported to have gone beyond ordinary Secondary school. This probably explains partly why this community is one of poor classes in the society. Expansion and diversification of business would lead them into obtaining some money to pay for education of their children and other household members so that they can ultimately disconnect this poverty cycle.

#### Occupation of Respondents

As noted from the beginning of this chapter, the study participants are those widows from poor households who have small business in Gongolamboto Ward. Therefore, it is obvious that all respondents are engaged in various entrepreneurial activities. The study findings as illustrated in chart 1.4 below, show that the biggest potion of respondents, about 22% of are engaged in food vending alias mama ntilie.The data further show that about 18% of the respondents earn their income from selling small vendor shops of green vegetables, fruits and spices.

# Figure 1.2: Respondents Occupation

Source: Field data (2020)

Other economic activities done by widows in Gongolamboto Ward include small scale agriculture (vegetables and poultry) 15%, Kiosk (15%), Tailoring (12%), hair dressing saloon (12%) and fish frying (6%).All respondents have no specific skills and they never got any training in business and entrepreneurship. The community with this nature can be encouraged to proceed with their ventures and also be facilitated to join forces to establish a community managed project that will increase their income.

#### Income Distribution

As illustrated in chart 1.5 below, the majority about 10 out of 33 respondents equivalent to 30% earn between TZS 151,000 to TZS 200,000 per month while about 24% earn about TZS 201,000to 250,000 per month. Only 6% of respondents reported to earn more than TZS 300,000 per month while about 3% earn less than TZS 50,000 per month. According to the 2018 Household Budget Survey, the daily cost of the food poverty line is TZS 1,109.53 per adult equivalent or TZS 33,748per adult per month while the basic needs poverty line adds an allowance for basic non-food necessities to the food poverty line such as clothes, transportation, housing, education and health is equivalent or TZS 49,320 per adult per month.

From the collected data, it shows that more than 97% of respondents earn above both the food poverty line and the basic poverty line. However, due to their households’ composition, whereby most of the households have an average of 5 members, their incomes are very mean to cater for all family requirements. There is a justifiable need to facilitate the community as they organize themselves into productive groups and engage in income generating activities so that they can become economically stable. Through FGD, the respondents confirmed that the income obtained from their small business is not sufficient to cater for household requirements. One respondent said,

“My husband died five years ago, I live with three children and three adults who are my relatives who all depend on me. Iam not employed….we all depend on this small business…I have to pay for food, rent for both residence and business premise, clothes, transport, electricity bills, water bills, medication etc…”.

According to this statement which was supported by almost all respondents during the discussion, it is obvious that the community needs to diversify the sources of income in order to meet the needs. The respondents also showed willingness to form and register a Community Based Organization (CBO) and to contribute some money obtained from their business as startup capital for a project which would ensure constant flow of income.

# Figure 1.3: Respondents' Income Distribution

Source: Field Data (2020)

### Community Needs

Though FGDs, the responds in groups of 11 respondents each were asked to identify their needs by considering the challenges facing them, their personal experiences and the available resources. The challenges which were identified include limited household income, lack of capital to expand business, lack of entrepreneurship skills, lack of reliable markets for their products and services.

As shown in table 1.3, the community identified four major needs as listed below:

- Capital to expand business

- Entrepreneurship training

- Reliable markets for their products and

- Improved household income

## Needs Prioritization and Leveling

Table 1.3: Community Needs Ranking Matrix

| Community Needs | Capital to expand Business | Entrepreneurship training | Reliable Markets for products | Improved Household income | Points | Rank |
| --- | --- | --- | --- | --- | --- | --- |
| Capital to expand Business |  | Capital to expand business | Capital to expand business | Improved HH income | 4 | 2 |
| Entrepreneurship training | Capital to expand business |  | Entrepreneurship training | Improved HH income | 2 | 3 |
| Reliable markets forproducts | Capital to expand business | Entrepreneurship training |  | Improved HH income | 0 | 4 |
| Improved household income | Improved household income | Improved household income | Improved household income |  | 6 | 1 |

Source: Field Data 2020

Normally, the community has always a long list of needs and challenges as they struggle every day to make a living and improve their livelihood. Although it is not possible to meet all the needs and solve all challenges, it is important for the community to identify and prioritize their needs in order to determine which one to start with by considering the available resources and opportunities. When we look at the identified community needs altogether, we can generally speak that the community needs to improve their members’ standards of living by improving their daily income. The researcher used pair wise ranking matrix in order to arrange the community needs in hierarchy showing which need to be addressed first and which one should be the lastas shown in table 1.3.

Through needs ranking process, the prioritization matrix clearly show that improved household income ranks the first with a total of six points, followed by capital to expand business with 4 points, then entrepreneurship training with only 2 points and lastly reliable markets for their products without any score. It is clearly shown that the main need for this community is improved household income.

### 1.5.1 Selection of Community Project

The community has agreed that their common need to be addressed first is to improve their household income. During FGDs, respondents were asked to discuss and come up with three viable community managed projects which can be implemented to improve the household income. The three listed projects were ranked in pair wise ranking method to get the most appropriate project as shown in table 7 bellow. The proposed and ranked projects are as follows;

- Local chicken rearing (Poultry)

- Tie and dye (Batiki making)

- Liquid Soap making

Table 1.4: Pair wise Ranking of proposed Community Projects

| Projects | Poultry | Tie and dye (Batiki) | Liquid Soap making | Points | Rank |
| --- | --- | --- | --- | --- | --- |
| Poultry |  | Poultry | Liquid Soap making | 2 | 2 |
| Tie and dye | Poultry |  | Liquid Soap making | 0 | 3 |
| Liquid Soap making | Liquid Soap making | Liquid soap making |  | 4 | 1 |

Source: Researcher, 2020

From table 1.4, liquid soap making was ranked the first with 4 scores followed with 2 scores and lastly tie and die with no score. Through focus group discussion, the respondents mentioned a number of reasons for their selecting liquid soap making ahead of other options. The reasons include small capital required for raw materials, reliable market availability especially the nearby institutions like schools and health facilities; and lastly no complex skills required.

The community further agreed on to work together by forming a voluntary membership group that has to bear a name, written constitution and the group to be registered by the CBO registrar at the Municipal Council. By considering voluntarism, ability to work with others in a group and willingness to contribute an initial capital; ten widows were selected to form Jithamini group which implement the liquid soap project. Registering the community group is important because it gives legal identity of the group and it defines the roles and responsibilities as well as benefits of each affiliate of the group.

## 1.6 Conclusion

Through the Participatory Needs Assessment, the researcher was able to collect information that has been analyzed to provide answers to research questions which were generated from the objectives of CNA. The research findings depicted that most of widows who also own petty business in Gongolamboto ward have very low income but yet they have big domestic workload and responsibilities. The widows’ households ‘population size go up to the average of 4 members most of whom are children going to schools who have education and health related requirements.

Although all widows under study are involved in small business, the research shows that they are still poor and want to improve their household incomes by expanding their ventures and diversify by establishing a community managed project. In that note, the community has decided to form and register a Community Based Organization through which they will implement liquid soap making project.

# CHAPTER TWO

# PROBLEM IDENTIFICATION

## Background to Research Problem

The concept of poverty is very multifaceted as its meaning differs depending on contexts, from one country to another and from one community to the other or even from household to household. According to (World Bank, 2011), poverty can be referred to as "the state of being extremely poor" and is understood by many to mean the lack of basic necessities such as food, water, shelter, healthcare, and basic education. Regardless of any definition we may opt to take, the fact remains that the level of poverty in Tanzania is high especially among non-employed women who depend on an informal petty business.

Poverty can also be understood by looking at two measurements namely food poverty line and Basic Needs Poverty line. The 2017/18 Household Budget Survey (NBS, 2019), defines food poverty line as the level at which households total spending is used to meet their needs for food. This is also known as extreme poverty line. The same survey defines Basic Needs Poverty as an aggregation measure of poverty that takes into accounts both the food and non-food requirements. In that account, the currentBasic Needs Poverty Line is TZS 49,320 per adult equivalent per month, and Food Poverty Line is TZS 33,748per adult equivalent per month.

The Government of the United Republic of Tanzania (World Bank, 2016), has been implementing various poverty reduction programs which have helped the most vulnerable people in taking benefits from economic growth. For example according to the HBS 2017/18, the food and basic needs poverty lines have increased from TZS 26,085 and36,482 in 2011-12 to TZS 33,748 and 49, 320 in 2017-18 respectively. However, despite the reduction of poverty incidences in Tanzania, approximately 8% of Tanzanian households are extremely poor as they fall below food poverty line (NBS, 2019 and require permanent support. As revealed by the CNA, the community’s main need is to raise income to meet the household requirements. Other problems as obtained during Participatory Needs Assessment include capital to expand business, entrepreneurship skills, and reliable market for their products.

Through a Community Participatory Assessment, the community identified various opportunities for business within their ward including availability of institutions like the University, primary and secondary schools, dispensaries, presence of electricity, presence of government extension officers like community development officer and trade officer who can always give guidance to the group in daily operations. The CAN has also identified various economic activity options including poultry, tie and dye (Batiki), as well as soap making. Finally, the community reconciled that they need to organize themselves into a registered group and establish liquid soap making project through which they will increase their income.

## Problem Statement

The Government of Tanzania has been implementing policies, strategies and programs aimed at stimulating economic growth and reducing income poverty among Tanzanian population. One of the most recent and current government poverty reduction program is the Productive Social Safety Net (PSSN), which is implemented by TASAF by disbursing cash to the identified most vulnerable households. For about 8 years from the inception of this program, achievements have been recorded in economic growth among various benefiting households. However, according to (NBS, 2017) income poverty is still widespread among those households which are extremely vulnerable. The CNA findings have revealed that about 3 % of the widows in Gongolamboto Ward have a monthly average income of less than TZS. 50,000 while the majority i.e. 30% earn between TZS 201,000 to TZS 250,000.This income was not sufficient to cater for households’ requirements as the study has shown that these widows have additional responsibilities to buy food, pay for education, transport, rent, utility bills, clothing and health costs for their dependents.

## 2.3 Project Description

The project is the ‘Establishment of liquid soap making project to improve income of widows of Gongolamboto Ward in Ilala Municipality, Dar es salaam”, which was implemented by Jithamini group with (10) members who are widows running their small business. This CBO named Jithamini group used the members ‘contributions as a starting capital to buy materials and make liquid soap as a way to increase their income and reduce household poverty.

It was expected that successful implementation of this project would assist the group members to solve part of the challenges identified in chapter one as they are all associated with low household income.  Daily implementation of the project was done by the small group of 10Jithamini group members under supervision of selected group leaders as per their constitution. The Ward under the leadership of the Ward Executive Officer (WEO) provided the overall group and project coordination and management.

Ilala Municipality Council who is a major stakeholder in this project, provided technical skills through staff notably the Community Development Officer, Cooperatives Officer and Trade Officer who provided instructions on group formation, constitution writing, group registration, entrepreneurship skills and practical training on making and packaging liquid soap. The project activities started in June2020 and it will be a continuous implementation with the ambition to scale up by diversifying into other products in the future.

### Target Community

The project was directly implemented by the group of 10 widows who also have petty business like those selling fresh fruits and green vegetables alias vigenge, cooked food vendors alias mama ntilie, hair dressing saloon, fish frying, and tailoring; all based in Gongolamboto Ward in Ilala Municipality, Dar es salaam Region. It should be clearly understood that from the beginning we excluded widows who are employed in the formal sector, those who have relatively big business and those with no business at all.

These 10 widows who formed the Jithamini group were selected from 33 widows who participated in the CNA. As noted earlier on, selection of members considered the willingness of a person to join the group and work with others in a group setting, ability and willingness to contribute funds for capital, trustworthiness and acceptability to other members. For sustainability and legal identity of the group and the project, the business was formally organized with written constitution, elected leadership, formal name (Jithamini group) and a bank account.

### Stakeholders

The project had various stakeholders who contributed towards its successful implementation. The main stakeholder is Ilala Municipality Council, which offered technical skills and guidance through the Community Development Officer, Cooperatives and Trade Officer who provided various technical support basing on their fields. Another important stakeholder is the Ward Government which provided general guidance and organised all correspondences between the group and the experts who are based at the Municipal headquarters. The stakeholder matrix is presented in table 2.1 as follows;

# Table 2.1: Stakeholders Analysis Matrix

| Stakeholder | Stakeholder’s role | Stakeholder’s expectation |
| --- | --- | --- |
| Ilala Municipality Council | Provision of technical expertise through Community Development Officer, Cooperatives Officer and Trade officer | The group will follow technical expertise provided, and will operate as per legal framework |
| Gongolamboto Ward leadership | Provision of general leadership and coordination of all correspondences between the group and the officers at Municipal level and the Bank | The group will respect the Ward leadership and all correspondences will be channeled through the Ward office |
| Members of Jithamini group | Follow experts’ guidance, write constitution, elect leaders, Mobilize funds for capital, open bank account and make and sell liquid soap | Experts’ guidance will be followed, Funds will be mobilized and liquid soap will made and sold |
| Community Development Officer | Group mobilization and facilitation of constitution writing, group registration and opening bank account | The group will be organized to write a constitution, group registration and opening bank account |
| Trade officer | Advising and linking the group with markets and provide entrepreneurship skills to the group | The group will follow entrepreneurship training and will get reliable market for produced soap |
| Researcher | Conduct Participatory Needs Assessment, training on liquid soap making, oversee and document all project activities | Participatory Needs Assessment will inform the project implementation. Training will be done and documentation will be also done to improve project implementation |

Source: Field data 2020

### 2.2.3 Project Goal

The main goal of the project was to improve the household income of the community of widows who run informal and small business in Gongolamboto Ward, through production and selling liquid soap by the end of October2020.  Increased income at household level ensure the ability to afford basic needs including decent shelter, nutritious food, clothing, and quality education and health services.

### 2.2.3.1 Project Objectives

#### 2.2.3.2 General Objective of the Project

The project general objective was to increase income of poor widows who have small business undertakings in Gongolamboto Ward through making and selling Liquid Soap by end of October2020.

#### 2.2.3.3 Specific Objectives of the Project

- To build capacity of10members of Jithamini group on liquid soap making and packaging by the end of September2020

- To start liquid Soap making and selling by the mid of October2020

- To facilitate  formation of Community Based Organization by the end of October2020

## 2.3 Host Organization

The host for the project was the Ward Development Committee (WDC)of Gongolamboto Ward which is responsible for day to day administration and management of all issues regarding social and economic development in the ward. The WDC is under supervision of the Ward Councilor who is a political personnel elected by the wananchi, and the Ward Executive Officer (WEO) who is a government employee. The ward leadership provided a temporary office for the CBO and coordinated all correspondences and activities of other stakeholders towards achievement of project objectives.

### 2.3.1 Vision of the Host Organization

Provide the best services in facilitating the wananchi in Gongolamboto by using the available social and economic resources to enhance their social economic development.

### 2.3.2 Mission of the Host Organization

Gongolamboto Ward Development Council aims at becoming a role model in provision of socioeconomic services to the wananchi to ensure that they have decent life and they live in peace and harmony.

### 2.3.3 Gongolamboto Ward Development Council Organization Structure

# Figure 2.1:Gongolamboto Ward Organization Structure

Source: Gongolamboto Ward Office (2014)

The Village Council has been vested with power to oversee day to day responsibilities of the village government. The village council has the following organization structure.

### 2.2.4 Host Organization’s Strength, Weakness, Opportunities and Challenges (SWOC) Analysis

# Table 2.2: SWOC Analysis of the Host Organization

| SN | Strengths | Weaknesses | Opportunities | Challenges |
| --- | --- | --- | --- | --- |
| 1 | Highly committed Wardleadership and active committees | Some committee members are missing | Leadership has experience in overseeingCBOs and projects of similar nature | Only WEO and other government employees have monthly salaries, other members of the WDC are not paid |
| 2 | Availability of permanent office premises | So many activities taking place within office the premises | The office is very accessible and close to the highway bus stop, easy for customers to access products and services | There is no piped water |
| 3 | Presence of community development officer at ward level | She has so many groups to attend | The CDO is available and around most of the time | Sometimes he is not available when he goes to attend other outreach responsibilities |

Source: Research Findings (2020)

The organization’s SWOC analysis was done to portray detailed information of Gongolamboto Ward Council regarding the available opportunities which would help during the implementation of the liquid soap making project. The analysis also depicted strengths of the organization, weaknesses and challenges facing the organization and how they could affect the project implementation. Strengths and weaknesses are internal variables while Opportunities and Challenges are external variables. The SWOC of Gongolamboto Ward Council, which the host organization for this project was identified as presented in following table 2.2

### 2.3.5 The Role of the Host Organization

- To sensitize the community on group formation project implementation

- To make sure there is proper administrative activities throughout the project life

- To link the community and other stakeholders

- To organize trainings required by the community in implementing the project

- To participate in project products marketing (market linkage)

- To provide office premises for the group to perform their duties

- To ensure the project tools and documents, and products are well kept

- To collaborate with the researcher in mobilizing the resources required in project implementation

- To work with the researcher in facilitating the formalization of the CBO and opening bank account

- To ensure the project sustainability

### 2.3.6 The Role of the Student

The main role of the student is to ensure that the planned project activities are successfully executed as per schedule. The researcher was also responsible for the following;

- To conduct community sensitization on the importance of liquid soap making project as source of income to the group members.

- To participate in mobilization of resource required to facilitate project implementation.

- To ensure that the community has all the required skills in implementing the project

- To collaborate with other stakeholders in facilitating constitution writing, registration and opening bank account for the group

- To facilitate project documentation and reporting

# CHAPTER THREE

# LITERATURE REVIEW

## 3.1 Overview

Through this chapter we discuss both theoretical and empirical literature by authors who have written on poverty alleviation and soap production projects. The chapter presents the status of income poverty globally and in Tanzania and the efforts employed to address it. It also presents various Income Generating Activities implemented in Tanzania as a way to reduce income poverty. Through this chapter, Liquid Soap production as one of Income Generating Activities (IGA) is previewed by basing on its production requirements, specifications, types, branding and marketing.  Empirical literature review looks at the real experience on liquid soap production in Tanzania and Ilala Municipality in particular and how it has contributed in combating income poverty especially among women. The last part of the chapter reviews the existing policy framework in Tanzania and how it has contributed in raising the income of the poor populations especially women.

## 3.2 Definition of Concepts

### 3.2.1 Poverty

Poverty is referred to as a state of deprivation and prohibitive of decent life by failure to meet basic needs (URT, 2007) including food, shelter and clothes. Poverty is normally categorized into absolute poverty and relative poverty.

### 3.2.2 Absolute Poverty

Absolute poverty is defined by (URT, 2007) as the complete inability of a person or household to attain minimum standards of living, especially basic necessities like food, clothes and shelter. It is a situation of being unable to meet the minimum levels of income, food, clothing, healthcare, shelter and other essentials (Todaro, 2012).

### 3.2.3 Relative Poverty

Relative poverty is the state of wellbeing which is normally assessed by comparing people within the same society (URT, 2005). Poverty can further be classified into income and non-income poverty. However, income poverty is said to exacerbate other categories of poverty.

### 3.2.4 Income Poverty

Income poverty refers to the situation whereby the individual or household’s income is below the established poverty line, such that one cannot afford basic needs notably food, shelter and clothes.

### 3.2.5 Poor Household

A poor household refers to the household which are characterized by severe deprivation of basic human needs like food, safe water, sanitation facilities, health services, shelter, education and access to information (UNDP, 2011).

### 3.2.6 Development

Development is a process of improving the quality of all humans’ life in capacities by raising peoples’ level of living, self-esteem, and freedom (Todaro, 2012)

## 3.3 Theoretical Literature Review

For the purpose of this report and by considering that our community is a group of women who are also entrepreneurs, we were guided by various entrepreneurship theories. The entrepreneurship theories which were cited are categorized into Sociological, economical and psychological as follows;

### 3.3.1 Sociological Theory of Entrepreneurship

According to (Landstrom, 1998), the sociological theory of entrepreneurship focuses on the social context or the society in which entrepreneurial activities take place. As asserted by (Reynolds, 1991) there are four social contexts that relate to entrepreneurial opportunities. The first one is social networks where the emphasis is put on building social relationships and bonds that promote trust and faith with the people.

The second context involves analyzing the life situations, characteristic and background of individuals who have decided to become entrepreneurs. The third context is ethnic identification which puts emphasis onOne’s sociological background as one of the decisive “push” factors to become or not to become an entrepreneur. The fourth and last social context is called population ecology which considers environmental factors as important factors for business to survive. The environment factors referred to under this context include the political system, religious system, the government policies, customers, employees and competitors.

### 3.3.2 Economic Theory of Entrepreneurship

According to Modigliani, (1998) the economic theory of entrepreneurship explains that there are factors which accelerate the behavior of savings and expenditure. He mentions the factors as the level of income earned and the age factor of an Entrepreneur. The theory assumes that people (entrepreneurs) with high income are likely to save than those with meager income and people in their middle age are likely to make savings as compared to young people. The theory concludes that Deference we see in consumption and savings are partly the product of age and income differences.

3.3.3 Psychological Theory of Entrepreneurship

The psychological theories of entrepreneurship emphasize on the individual characteristics that define entrepreneurship. They are two types of psychological theories namely locus of control theory and the Need for achievement theory.

- Locus of Control theory

Rotter (1966) defines Locus of Control as an individual’s inner perception about the underlying main causes of events in his/her life. In this context the entrepreneur’s success or failure is determined by his/her own perception, abilities and external support. Individuals with internal locus of control believe that they are able to control life events by their own efforts, while those individuals with an external locus of control believe that life's events are the result of external factors, such as chance, luck or fate.

- Need for Achievement Theory

### The need for achievement theory by McClelland (1961) asserts that naturally all human beings have a desire to succeed, accomplish, excel or achieve. Entrepreneurs are driven by this desire to achieve, succeed and excel.

# 3.4 Empirical Literature Review

### 3.4.1 Income Poverty in the World and Tanzania

It is estimated that in 2013, about 767 million people which is equivalent to 10.7% of the world’s population lived under the international poverty line compared to 12.4 % in 2012. This progress was mainly driven by East Asia and Pacific notably China and Indonesia and South Asia notably India where number of poor people have significantly reduced. The (World Bank, 2016) report further shows that almost half of the extreme poor still live in Sub-Saharan Africa with about 389 million people living on less than USD 1.90 a day in 2013, a vast of whom live in rural areas relying on poorly mechanized  agricultural sector.

Income poverty is said to affect the rural population whose majority depend on subsistence agriculture by using inferior farm implements and poor tools. The income of rural households is mainly below the established poverty line, which is the amount of income required to satisfy basic needs. The results from (NBS, 2014) reveal that, income poverty was experienced by about 75.4 percent of Tanzanians who were currently employed in agricultural and fishery occupations with 87.6 percent of them living in rural areas. According to the current World Bank report (World Bank, 2016), the international poverty line is USD 1.90 which is equivalent to TZS 4,180.

The same report depicts that Tanzania in particular maintained stable economic growth between 2004 and 2014 with the average of 6.5% per year. During that period, extreme poverty declined from 11.7% to 9.7 %. As the report (World Bank, 2016) puts it, despite this decline in poverty, access to good schools, healthcare, electricity, safe water and other critical services remains elusive for many people, often determined by socioeconomic status, gender, ethnicity, and geography. Moreover, for those who have been able to move out of poverty, progress is often temporary: economic shocks, food insecurity and climate change threaten to rob them of their hard-won gains and force them back into poverty.

### 3.4.2 Efforts by Tanzania to Curb Income Poverty

Fighting against poverty has been a permanent agenda in the history of Tanzania. A number of strategies were put in place to eradicate poverty and increase economic growth. With reference to just a few of them, the Tanzania Development Vision 2025 designed in 1999, the National Poverty Eradication Strategy (NPES) designed in 1998 and Poverty Reduction Strategy Paper (PRSP) designed in 2000, set the goal of eradicating abject poverty by 2025. The review of PRSP guided formulation of the National Strategy for Growth and Reduction of Poverty (NSGRP or MKUKUTA). These second generation of PRS generated a strong agenda, aiming at sustaining broad-based growth whilst emphasizing equity and good governance. The MKUKUTA strategy has been the guiding frameworks for growth and poverty reduction in Tanzania.

Other current poverty reduction initiatives include the investment in human capital by providing free basic education to all, and employment creation through promotion of industrial sector, transport infrastructure and agricultural development including horticulture expansion. The government of Tanzania is also implementing a conditional cash transfer to identified poor households, for the purpose of raising their income and conditional stipends based on school enrollment and attendance as well as consumption of health services.  The obtained income can be used by the households to invest in other sustainable IGA notably small business, livestock keeping and crop farming in order to stabilize the income (Evans D.K, Hausladen S, 2013).

### 3.4.3 Soap making and Production

Soap is a universal product that can be found in all homes, canteen, laundries, hotels and toilets. Soaps are used every day for washing and bathing hence justifying its constant demand due to its important role of the product in daily human life. Soap products can be bar soaps, liquid soaps and detergents with different scent, color and packaging. Soap production industry is among growing sectors of the economy in developing countries including Tanzania and they generate millions of money annually from small scale, medium scale and big soap producers. The industry produces direct and indirect employment opportunities. Soap products range from toilet soaps, bathing soaps, baby soaps, body wash soaps, hand wash, dish washer, cloth washing soaps, car wash soaps, and detergents. All these products can be in the form of bar, foam or liquid and are produced in different fragrance.

#### 3.4.3.1 Requirements for Soap Production

The equipment needed for soap making include soap making machine, heat resistance plastic or stainless steel pitcher with lid, big stainless steel or plastic spoon, stainless steel measuring spoons, measuring cups, small beakers, stick blender, soap molds, soap pot, rubber spatulas, large stainless steel or plastic ladle, protective goggles, protective rubber hand gloves, quick reading and accurate thermometer. Other materials include lye solutions, oils, additives for coloring, packaging materials and fragrances. To be effective and competitive, there must be adequate space, distribution networking, good marketing skills and customer care services.

#### 3.4.3.2Soap Marketing

There are wide range of available customers for soaps and detergents. Market and customer research must be thoroughly done to identify the demand and potential groups of people and organizations and the quality and quantity they may require. Customers may include individuals, hotels, restaurants and canteens, schools, government offices, mothers with babies, cleaning organizations, car washers, dispensaries and laundry owners.

## 3.5 Policy Review

### 3.5.1 Community Development Policy 1996

The government of Tanzania prepared the Community development policy (URT , 1996) to enable Tanzanians to bring about their own development by using locally available resources to improve production so that they may have increased income which will enable communities to build a better life through self-reliance. It acknowledges the approach of involving the community especially through groups as the major way to eradicate poverty. Implementation of soap making project in Gongolamboto Ward has also applied the same approach whereby a community has formed a group of nine women who decided working together for the purpose of increasing their income.

3.5.2 National Economic Empowerment Policy

Closely linked with the community development policy is the National Economic Empowerment Policy (URT, 2004) that intends to address all economic empowerment needs of the individual citizens of Tanzania and local companies in which Tanzania citizens hold not less than fifty percent of the shares. The Policy takes on board farmers, livestock keepers, fishermen, employees, traders as well as other groups of individuals in various economic activities. It is envisaged that, by the year 2025, a large segment of the national economy will be owned by Tanzanians. This process will embrace all Tanzanians by availing equal opportunities to all groups to develop them, particularly the rural poor like the members of Jithamini group in Gongolamboto Ward who decided to start liquid soap making project.

### 3.5.3Tanzania Development Vision 2025

The vision 2025 was prepared to guide the country in developing itself towards  active participation as the in global development characterized with advanced technology, high productivity, modern and efficient transportation and communication infrastructure. The development vision objective include achieving standard and good life for all citizens, good governance, rule of law and building a strong and resilient economy that can effectively withstand global competition (NBS, 2014). The vision 2015 acts as a roadmap through which the government continues to speed up the economic transformation from low productivity agriculture to a semi –industrialized economy. Transformations aim also at highly productive agricultural activities which are effectively integrated and strengthened by supportive industrial and service activities in the rural and urban setting.

## 3.6 Literature Review Summary

From the reviewed literature, it is evident that many Tanzanians especially those living in the rural areas are still very poor. As most of the literature have revealed, poverty mostly affects the unemployed youth and women especially those living in the rural areas. The contribution of the majority of Tanzanian citizens in the economy remains to be limited by lack of capital, limited knowledge, experience and skills, inappropriate mindset towards development and challenges associated with access to various opportunities provided in development policies. Other challenges facing the rural poor include lack of reliable markets and inability to penetrate competitive markets for their products. The information obtained in the reviewed literature regarding poverty is quite similar to that obtained during CNA as presented in the first chapter of this document.

CNA findings also revealed that the women from poor households in Gongolamboto Ward in Ilala Municipality are mainly faced by income poverty and lack of capital to start their income generating activities. Through various policy frameworks, the Government of Tanzania has created a platform through which all citizens are encouraged to participate in different economic activities depending on one’s interest, skills, capital, geographical location and available resources.

# CHAPTER FOUR

# PROJECT IMPLEMENTATION

## 4.1 Overview

Successful implementation of the project entails coordination of various activities and harmonization of all interested institutions and stakeholders to ensure that the project goals and objectives are achieved. In this Chapter we also discuss the phases of project implementation including activity planning, project products and outputs analysis, required resources, responsible persons for each project activity, and the time required to finish the project activities.

The project implementation report that highlights all important project activities implemented and the end project results achieved are also covered in this part. The content of this chapter is very important as it merges the wishes obtained in the first chapter and the information obtained from literature review into practical reality realized during the project implementation. It is through this chapter that we translate the project objectives presented in the second chapter of this report into attainable project activities to produce physical project products and outputs.

## 4.2 Project Outputs and Activities

Implementation of this project involved various outputs including the Community Needs Assessment report, trained group members on liquid soap making and entrepreneurship skills, tools for liquid soap production and written constitution and the registered CBO. Other project outputs may include the income raised by the group through selling liquid soap. Currently, we cannot assess achievement of the general goal of the project because production is still at the initial stage such that no big profit has been realised so far. An assessment regarding the rise of income among community members will be done after several rounds of liquid soap production and sales.

## 4.3 Project Products

The main project product is liquid soap which are produced by Jithamini group. However, throughout this project there are other products which include CNA report, training report on liquid soap making, purchased soap production tools, the written group constitution, group registration certificate and a document bearing group bank account information.

## 4.4 Project Planning

Project planning is the main component in the project development process which comprises identification of the project objectives and outputs, scheduling the activities in logical sequence, identifying responsible persons for each activity, identifying resources needed and budget required to implement all activities. For planning purposes of this project, the project Implementation Plan, project budget, Logical Framework and Grant chart were prepared.

### 4.4.1 Implementation Plan

An activity implementation plan was prepared to guide the implementation of the project. The implementation plan specified the activities to be implemented, the required resources, the time frame and responsible persons for each obligation. Implementation of activities started by involving and consulting various stakeholders, especially the Host Organization for provision of temporary office and workshop, the Community Development Officer on CBO formation and preparation

of constitution and finally the Trade officer for technical inputs regarding liquid soap making and marketing. Implementation of the project activities followed the plan shown in table 4.1 and the Logic Framework shown in Table 4.2 respectively.

# Table 4.1: Project Implementation Plan

| Objectives | Outputs | Activities | Project Months | Resources | Responsible |
| --- | --- | --- | --- | --- | --- |
|  |  |  | JULY 2020 | AUG 2020 | SEP 2020 | OCT 2020 |  |  |
| To build capacity of 10 members of Jithamini group members on liquid soap production and packaging, by September 2020 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) |  |  |  |  | Personnel, Stationery and transport | WEO, Researcher, Jithamini group members |
|  |  | Write CNA report |  |  |  |  | Stationery , time, personnel | Researcher |
|  | 10 members of Jithamini group trained on liquid soap making, packaging and marketing skills | Make preparations for training |  |  |  |  | Stationery, Venue | Researcher, WEO, Jithamini group Members, Trade Officer |
|  |  | Conduct one day training on liquid soap production, packaging and marketing skills |  |  |  |  | Stationery, Meals, personnel and money | Researcher, Trade Officer, Jithamini group, WEO |
| To start liquid soap production by October 2020 | Tools for soap production purchased | Mobilize funds for purchasing the tools |  |  |  |  | Money, time, personnel | Researcher, WEO, Jithamini group, CDO |
|  |  | Purchase detergents required liquid soap production |  |  |  |  | Money, time, human | Researcher, Jithamini group leaders, |
|  | Soap production started | Obtain workshop and office for the group production |  |  |  |  | Time, Human, Funds | Researcher, WEO, Jithamini group |
|  |  | Make liquid soaps |  |  |  |  | Human, production tools, time | Researcher, Jithamini group |
|  |  | Sell liquid soap and keep sales record |  |  |  |  | Soap packaging materials, transport costs | Researcher, WEO, Jithamini group members, Trade Officer |
| To facilitate formation of Community Based Organization (CBO) by October 2020 | Group constitution written and registration certificate acquired | Write group constitution |  |  |  |  | Stationery, Meals | Researcher, WEO, Jithamini group, CDO |
|  |  | Submit to IlalaMunicipal Director the application for registration |  |  |  |  | Transport costs, meals, human | Researcher, WEO, Jithamini group leaders, CDO |
|  | Open Jithamini Group Savings Bank Account | Mobilize funds foropening savings bank account |  |  |  |  | Meals, time, human | Researcher, WEO, Jithamini group leaders, CDO |
|  |  | Submit to the Bank manager the application to open Bank Account |  |  |  |  | Funds to open savings bank account for Jithamini group | Researcher, WEO, Jithamini group leaders, |

Source: Researcher, 2020

# Table 4.2: The Logical Framework of the Project

| Hierarchy of Objectives | Objectively Verifiable Indicators (OVIs) | Means of verification (MOV) | Assumptions |
| --- | --- | --- | --- |
| Goal: To increase household income of Jithamini group members in Gongolamboto Ward through production and selling of liquid soap byOctober2020. | Change in household Income forJithamini group members | Sales records Survey reports | Sales records are correct and available Members will not hide their household income |
| Objective 1: To build capacity of 10 members of Jithamini group on liquid soap making and packaging by the end of September 2020 |
| Output 1: Community Needs Assessment (CNA) Report | Community Needs and suitable projects identified | CNA report | The researchwasbe done as per standard procedures The respondents will provide genuine responses |
| Output 2: 10 members of Jithamini group trained on liquid soap making and packaging | 10 members of Jithamini group have skills to make, package and sell liquid soap | Training report and photos | All 10 members attend and follow the training |
| Activities under outputs of objective 1 |
| 1.1 Conduct CAN | Community Needs and suitable projects identified | The written CNA/ research report | The study will follow all procedures The community will provide genuine answers |
| 1.2 Write CNA report |  |  |  |
| 2.1Make training preparation | 10 members of Jithamini group attended the training | Training report Training attendance list | The participants will attend and follow the training |
| 2.2 Train participants on liquid soap making and packaging |  |  |  |
| Objective 2: To start liquid Soap making and selling by October2020 |
| Output 1: Tools for liquid soap production acquired | The tools of production in place | List of procured project tools | Tools purchasedfollowing the given specifications |
| Output 2: Liquid Soap making started | Liquid soap making workshop is in place | Liquid Soap making workshop | The community will follow and understand the instruction provided by trainers |
| Activities under outputs of objective 2 |

| Hierarchy of Objectives | Objectively Verifiable Indicators (OVIs) | Means of verification (MOV) | Assumptions |
| --- | --- | --- | --- |
| 1.1 Mobilize funds to purchase tools | Funds mobilized | Collected funds and list of contributors with their respective amounts | Readiness to support the project |
| 1.2 Purchase materials and detergents for soap liquid production | Purchased Tools and detergents | List of procured items | Materials and detergents procured as per specification |
| 2.1 Acquire office and workshop production place for liquid soap production | Office and Workshop for liquid Soap making acquired | Office and workshop spaces | The office and workshop spaces obtained |
| 2.2 Produce liquid soaps | Liquid soap produced | Liquid soap production records | Production will made as planned |
| 2.3 Sell liquid soap and keep sales data | All Soap produced sold and sales datakept | Sales records (Quantity and amount of money recorded) | The quality of soap will be good and buyers will be available |
| Objective 3: To facilitate formation and registration of Community Based Organization (CBO) by October 2020 |
| Output 1. Group Constitution written and registered by the Municipal Council | Group registration is complete | Written Constitution and Registration certificate | Certificate will be available on time |
| Output 2. Open Bank Account for the group | Savings Bank Account for the group has been opened | Bank Account details available | The CBO is eligible for registration |
| Activities under outputs of objective 3 |
| 1.1 Write group constitution | Group constitution prepared | Constitution | The CDO will guide the group in making a good constitution |
| 1.2 Submit to Municipal Council the application for registration | Application submitted and registration obtained | Registration certificate | Registration process will not take long |
| 2.1 Mobilize funds to open Group Savings Bank Account | Funds mobilized | Amount of money collected and used to open Bank Account | Willingness of stakeholders to support the group financially |
| 2.2 Submit to the bank the application for Group bank account | Bank Account opened | Bank Account details | The group is eligible for opening bank account |

Source: researcher, (2021)

### 4.4.2 Inputs

Implementation of this project used various resources which were mobilized and utilized. These include financial resources, material inputs, human resource, and the whole time spent from planning up to completion of the project. Financial resources are major inputs which facilitated training, transportation, and purchase of project materials, CBO registration and opening bank account. Human resources mainly include Gongolamboto Ward leaders, Community Development Officer, trade officer, Researcher and the community members who provided their physical labor for daily implementation of the project.

The detailed financial resources which were used are provided in section 4.4.4 of this report. Material inputs include the time spent, office and workshop premises which were provided by the host organization. The researcher in collaboration with the Community Development Officer and Trade officer who provided technical inputs to ensure community participation during needs identification, selection of a project, training of group members as well as documentation.

### 4.4.3 Staffing Pattern

The project has no paid staff as it was directly implemented by a group of 10 widows under supervision of their elected leaders who normally collaborated with ward leaders, Community Development Officer, Trade officer and the researcher. The elected group leaders include the chairperson, secretary and treasurer who have the role of leading their fellow CBO members as illustrated in Table 4.3. Management and coordination of project activities was done by Ward Development Council which is the host organization.

# Table 4.3: Staff Pattern

| Position | Roles |
| --- | --- |
| Ward Development Council (WDC)under the WEO | Provision of guidance, coordination of activities and correspondences regarding the project |
| The Chairperson of Jithamini Group | Overall leader of other group members who calls for meetings and ensure implementation of all activities |
| The secretary of Jithamini group | Keep all project documents and taking meeting minutes |
| The treasurer of Jithamini group | Responsible for keeping records on project income and expenditure; Collect and take to bank all monies obtained from sales, members contributions and any other source |
| JithaminiGroup members | Participate in all project activities and meetings for their own advantage |

Source: Researcher, 2020

### 4.4.4 Project Budget

Table.4.4: Project Budget

| PROJECT OBJECTIVES | PROJECT OUTPUTS | PROJECT ACTIVITIES | RESOURCES/INPUTS | QUANTITY | UNIT COST | TOTAL IN TZS |
| --- | --- | --- | --- | --- | --- | --- |
| To build capacity of 10 members of Jithamini group on liquid soap making and packaging by the end of September 2020 | Community Needs Assessment (CNA) Report 10 members of Jithamini group trained on liquid soap making and packaging | Conduct CNA (data collection, processing and analysis) Write CNA report | Human | 3Persons | 30,000 | 90,000 |
|  |  |  | Stationeries | Lump sum | 50,000 | 50,000 |
|  |  |  | Transport | 3people | 25,000 | 75,000 |
|  |  |  | Stationeries | Lump sum | 45,000 | 45,000 |
|  |  | Make training preparations | Stationery | Lump sum | 50,000 | 50,000 |
|  |  | Train participants on liquid soap making, packaging and marketing skills | Lunch | 13 people | 7,000 | 91,000 |
|  |  |  | Buckets (10Lts) | 10 | 5,000 | 50,000 |
|  |  |  | Buckets (20Lts) | 5 | 9,000 | 45,000 |
|  |  |  | Hand gloves | 30 pairs | 5000 | 150,000 |
|  |  |  | Various liquid Colors | Assorted | 15,000 | 15,000 |
|  |  |  | Caustic soda | 10Lts | 5,000 | 50,000 |
|  |  |  | Workshop Table | 1pc | 55,000 | 55,000 |
|  |  |  | Workshop Chairs | 10 | 15,000 | 150,000 |
|  |  |  | Assorted Perfumes | 1 Lt | 10,000 | 10,000 |
|  |  |  | Palm oil | 10Lts | 8,000 | 80,000 |
|  |  |  | Trainers’ extra duty allowance | 2 people | 30,000 | 60,000 |
| To start liquid Soap making and selling by October 2020 | Tools for liquid soap production acquired | Mobilize funds to purchase production tools | Human | 2 | 15,000 | 30,000 |
|  |  |  | Communication | Lump sum | 20,000 | 20,000 |
|  |  | Purchase materials and detergents for soap liquid production | Hand gloves | 30 pairs | 5000 | 150,000 |
|  |  |  | Various liquid Colors | Assorted | 45,000 | 45,000 |
|  |  |  | Caustic soda | 10Lts | 5,000 | 50,000 |
|  |  |  | Assorted Perfumes | 5 Lt | 10,000 | 50,000 |
|  | Liquid Soap making started | Acquire office and workshop(production place) for liquid soap production | Office Room and workshop | 2 room hired at 50,000 @month for 6 months | 50,000 | 300,000 |
|  |  | Produce liquid soaps | Tools and detergents (already procured) | 0 | 0 | 0 |
|  |  | Sell liquid soap and maintain sales record | Liquid soap branded containers ( 5Lts and 1Lt) | 100 | 1000 | 100,000 |
|  |  |  | Transport costs during distribution | 2 | 25,000 | 50,000 |
| To facilitate formation and registration of Community Based Organization (CBO) by October 2020 | Group Constitution written and registered by the Municipal Council | Write group constitution | Stationery (printing and binding) | Lump sum | 20,000 | 20,000 |
|  |  |  | Lunch | 10 people | 5,000 | 50,000 |
|  |  | Submit to Municipal Council the application for registration | Transport | 4 Persons | 5,000 | 20,000 |
|  |  |  | Lunch | 4 persons | 5,000 | 20,000 |
|  | Savings Bank Account for the group has been opened | Mobilize funds to open Group Savings Bank Account | Meals | 4 people | 5,000 | 20,000 |
|  |  |  | Transport costs | 4 people | 5,000 | 20,000 |
|  |  | Submit to the bank the application for Group bank account | Funds to open Bank Account | Lumpsum | 50,000 | 50,000 |
|  |  |  | Transport costs | 4 people | 5,000 | 20,000 |
|  |  |  | Lunch | 4people | 5,000 | 20,000 |
| TOTAL | 2,101,000 |  |  |  |  |  |

Source:  Researcher, 2020

## 4.5 Project Implementation

### 4.5.1 Project Implementation Report

Execution of the project started in July2020by conducting the Participatory Needs Assessment as illustrated in the project implementation plan, and it followed the sequenced order of activities that resulted into realization of project objectives. The Researcher in collaboration with the host organization, community Development Officer, Trade Officer and the, participated in all stages to ensure that there is smooth take off, and regular monitoring of all project activities. Implementation of project activities involved all identified stakeholders, each performing specified tasks.

Implementation started by conducting a participatory CNA through which community needs were identified and prioritized through pairwise ranking method; theproject was selected and the community to implement the project was identified. There followed capacity building to the community on how to effectively implement the project. The training was conducted for two days at Gongolamboto Ward Office and it was facilitated by the Community Development Officer, Trade Officer, CED student and cooperatives officer. The covered topics include CBO formation, Constitution writing, Liquid Soap making, Entrepreneurship skills, Business record keeping, Business branding and marketing and report writing.

Prior the training, the facilitators developed a simple printed training materials which were simplified for easy consumption by the community. At the end of the training, the facilitators guided the community to identify and costing for all required materials and tools for making water soap in order to come up with the budget amounting to 2,101,000. Fundraising was done in order to get that required amount of fund whereby the community contributed TZS 50,000 each making a total of TZS 500,000.

The rest was contributed by CED student (1,000,000); WEO’s office (200,000); Ward Councilor (201,000) and the Municipal Community Development Officer (200,000). After mobilizing the required materials, the community made a total of 200 Lts of liquid soap which was packaged into branded 5Litres (30 pieces sold at 8,000 each) and 1 Lt (50 pieces sold at 2000 each). This was the first round of liquid soap production whereby the earnings from sales was TZS 340,000 and it was expected to increase in the next rounds as the group was getting production experience and market exposure.

The group of beneficiaries was registered into a CBO namely JITHAMINI GROUP with registration number IMC/GMT/IGA/163/2020with a bank account number 015C535835000held at CRDB  Banana Branch. Apart from liquid soap production, the group has a vision of operating a credit and savings project in future. The detailed analysis of implemented activities and the current status are shown in the Table 4.5.

# Table 4.5: Project Implementation Report

| Project Objectives | Project Outputs | Project Activities | Current Implementation Status | Reasons for Deviation |
| --- | --- | --- | --- | --- |
| To train 10Jithaminigroup member on soap production, packaging, by the end of August2020 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | CNA completed. Data were collected, processed and analyzed as shown in Chapter one of this report | NA |
|  |  | Write CNA report | CNA report written | NA |
|  | 10 Group members trained on soap making, branding and packaging | Make preparations for training | Preparations including preparation of simplified training manualwas done by CDO, Trade officer, Cooperatives Officer and CED student | NA |
|  |  | Conduct raining on soap production, packaging and marketing skills | Training was successfully done by CDO, Trade officer, Cooperatives Officer and CED student | NA |
| To start liquid soap production by October2020 | Tools for liquid soap production purchased | Mobilize funds for tools acquisition | a total of TZS 2,101,000 was collected from community contributions and other stakeholders | NA |
|  |  | Purchase detergents, and other tools for liquid soap production | Detergents, and tools were procured | NA |
|  | Liquid Soap production started | Obtain office and factory/ production place for soap production | The Office was obtained at Banana area in Gongolamboto ward | NA |
|  |  | Make liquid soap | 200 Lts of liquid Soap production was made (photos attached) | NA |
|  |  | Sell soap to buyers and keep sales record | Selling is on progress whereby the first round sales recorded TZS 340,000 | NA |
| To facilitate formation of Community Based Organization byOctober 2020 | Constitution prepared and certificate obtained | Prepare group constitution and application | Constitution completed and application package for registration submitted to Municipal Director | NA |
|  |  | Submit application package to Council Director for registration | Registration Certificate obtained (copy annexed) from the Municipal Director | NA |
|  | Open Group Savings Bank Account | Fundraise to open bank account | TZS 50,000 obtained for opening a savings bank account | NA |
|  |  | Submit application package to the bank to open Bank account | Savings Bank account number 015C535835000 held at CRDB Banana Branch. opened | NA |

Source: Researcher, 2020

| OBJECTIVES | OUTPUTS | ACTIVITIES | PROJECT MONTHS |
| --- | --- | --- | --- |
|  |  |  | JULY2020 | AUG 2020 | SEPT 2020 | OCT 2020 |
|  |  |  | W 1 | W 2 | W 3 | W 4 | W1 | W 2 | W3 | W 4 | W 1 | W2 | W3 | W 4 | W1 | W2 | W3 | W4 |
| To train 10Jithaminigroup member on soap production, packaging, by the end of September 2020 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Write CNA report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 Group members trained on liquid soap making and packaging | Make preparations for training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conduct raining on soap production, packaging and marketing skills |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To start soap production by October2020 | Tools for soap production purchased | Mobilize funds for tools acquisition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Purchase detergents, and other tools for soap production |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Soap production started | Obtain office and factory/ production place for soap production |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Make liquid soap |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Sell soap to buyers and keep sales record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To facilitate preparation of constitution, group registration and opening Bank account by October2020 | Constitution prepared and certificate obtained | Prepare group constitution and application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Submit application package to Council Director for registration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Open Group Savings Bank Account | Fundraise to open bank account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Submit application package to the bank to open Bank account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Table 4.6: Project Implementation Ghannt Chat

Source: Researcher, 2020

# CHAPTER FIVE

# PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

## 5.1 Overview

Participatory monitoring and evaluation involved all stakeholders who took part in all stages of project implementation from project planning, daily implementation of project activities and assessment of the project towards achieving the project main goal. Involving the stakeholders especially CBO members added to them the sense of owning the project and hence increased the chance of project sustainability. This chapter discusses on participatory monitoring, evaluation and sustainability of the project by looking at how the community and various stakeholders used resources to facilitate execution of project activities towards achieving the anticipated project objectives. Through this chapter we will also look at how the project has succeeded to achieve the expected objectives and analyze durability and sustainability of the project even after the CED researcher and other stakeholders leave the CBO alone.

## 5.2 Participatory Monitoring

The process of Monitoring involves regular collection of information concerning the physical and financial performance of the project. The collected information is normally used to assess the prevailing situation and discover trends and patterns and to identify available challenges and find solutions to the same, keep project activities on schedule and measure progress towards achieving the objectives. Further, the collected information can be used to inform decisions on human, financial and material resources and formulating or revising goals and objectives.  With regards to liquid soap production in Gongolamboto Ward, the community members participated fully in the whole project cycle from planning, implementation and monitoring of activities in order to realize the predetermined project objectives. The stakeholders especially leaders from host organization, Community Development Officer, Trade Officer and Cooperatives officer took part in daily monitoring of activities including capacity building, procurement of project tools, supervising initial CBO meetings and finally facilitating registration and opening a bank account for the CBO.

### 5.2.1 Monitoring Information System

The collected project data were analyzed to produce systematic information to guide the project implementers and stakeholders in making various decisions. Information was collected mainly through observation, review of minutes and directly discussing with the community during field visits to determine on whether the activities are implemented as per schedule, inputs are available and if there are gaps and obstacles and the ways to address them. The project performance records were kept by the CED researcher and the CBO secretary.

The important information  regarding liquid soap making project was on the number of trained group members, project tools acquisition process, inventory of project tools, records on all collected funds and their expenditure, project stakeholders, project activity schedule, quantity of liquid soap produced and sales; and documentation on group registration and bank details.

# Table 5.1: Monitoring Information System

| SN | Categories of information and activities | Elements to be monitored | Records to be kept | Who is collecting information | Who is the user of information | How to use information | Decision to be made and output to be achieved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project work Plan activities | Progress of Implementation of planned activities, activity schedule, and project resources | Project work plans and implementation reports | Group Secretary, CED Researcher and WEO | Project management team | Identifying which activities to be implemented and when to implement; identifying the implementation gaps and make decisions | Re-planning, assess resources required and decide on how to access them |
| 2 | Project cost and expenditure | Financial and non-financial resources collection and expenditure | Project Income and expenditure | Treasurer, CED Researcher and WEO | Project management team | Assess adherence to project budget and Identifying financial gaps, | Decide on how to adhere to the budget and how to access more financial resources |
| 3 | Project Staff and supervision | Number of required staff, qualification and roles | Qualification and performance for each role | CED Researcher, Chairperson Secretary and WEO | Project management team | Assess on the performance of roles for each position | Determine the performance gaps and plan how to fix them |
| 4 | Other inputs of the project | Other required inputs which were not planned before | List of required additional inputs | CED Researcher, Chairperson Secretary and WEO | Project management team | Assess the necessity of having emerging inputs and the available alternatives | Plan on how to get the new inputs and use the available inputs effectively |

Source: Researcher, 2020

### 5.2.2 Participatory Monitoring Methods

Participatory project monitoring allows project implementers and supervisors to collaboratively record the project implementation progress of planned project activities. During monitoring of liquid soap making project in Gongolamboto Ward, a number of methods were applied but the most  used one was the Participatory Rural Appraisal (PRA), Beneficiaries Assessment (BA) and Participatory community needs assessment by which the community and other stakeholders shared their knowledge and experience concerning the project management. We also conducted regular meetings with all stakeholders for the purpose of planning and monitoring of the project implementation progress. On call follow-ups were also used by CED researcher and Community Development Officer (CDO) especially to record progress and provide support during preparation of group constitution which was a big requirement for group registration and opening of bank account.

### 5.2.3 Participatory Project Monitoring Plan

The project monitoring plan was prepared to guide the project monitoring process. The Monitoring Plan guided the project stakeholders on the nature of information to be collected, the project indicators to look at, the project tools to be used and the source of data in relation to the outputs and project objectives. The monitoring plan also specifies the timeframe and duration within which monitoring had to be done and the responsible person for each task.

# Table 5.2: Project Monitoring Plan

| OBJECTIVES | OUTPUTS | ACTIVITIES | INDICATORS | DATA SOURCE | METHODS/TOOLS | RESPONSIBLE | TIME FRAME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To train 10 Jithamini group member on soap production, packaging, by the end of August2020 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | Community Needs Identified | CNA report | Review of CNA report | Researcher, WEO, Community | August2020 |
|  |  | Write CNA report | Community Needs Identified | CNA report | Review of CNA report | Researcher | August 2020 |
|  | 10 Group members trained on soap making and packaging | Make preparations for training | Identified venue, stationeries | Project progress report |  | Researcher, WEO, community, CDO | September2020 |
|  |  | Conduct raining on liquid soap production, packaging, branding and marketing skills | Attendance list of participants | Training report | Training | Researcher, Trade Officer, community, WEO | September2020 |
| To start liquid soap production by October2020 | Tools for Liquid soap production purchased | Mobilize funds for tools acquisition | Cash collected | Project progress report | Record of collected cash | Researcher, WEO, community, CDO | September2020 |
|  |  | Purchase detergents, and other tools for liquid soap production | List of purchased items | Project progress report | List of purchased tools | Researcher, WEO, community | October2020 |
|  | Liquid Soap production started | Obtain office and factory/ production place for liquid soap production | Factory place | Project progress report | Lease contract | Researcher, WEO, group leaders, CDO | October 2020 |
|  |  | Make liquid soaps | Produced soap | Project progress report | Production records | Researcher, WEO, community, | October2020 |
|  |  | Sell soap to buyers and keep sales record | Sales | Project progress report | Sales records | Researcher, WEO, community, | Oct2020 |
| To facilitate preparation of constitution, group registration and opening Bank account by October2020 | Constitution prepared and certificate obtained | Prepare group constitution and application | Constitution prepared | Project progress report | Constitution document | CED Researcher, WEO, community | October2020 |
|  |  | Submit application package to City Council Director for group registration | Application submitted and Registration certificate obtained | Project progress report | Group Registration certificate | CED Researcher, WEO, Jithamini | October 2020 |
|  | Open Group Savings Bank Account | Fundraise to open bank account | Funds obtained | Project progress report | List of contributors | Researcher, WEO, Officer, CDO, | October2020 |
|  |  | Submit application package to the bank to open Bank account | Application submitted and group bank account opened | Project progress report | Bank account details | CED Researcher, WEO, community leaders, | October2020 |

Source: Researcher, 2020

## 5.3 Participatory Project Evaluation

Participatory Project Evaluation is a systematic process of involving the community and stakeholders in studying the significance of the project and determines whether the anticipated goal and project objectives have been achieved. Through evaluation, the stakeholders get to know what was actually achieved, what was not achieved and why, what was learned and what should be improved in order to enhance future performance. Project evaluation is part of management process comprising of planning, implementation of planned activities and evaluation, each following the other in unbroken cycle until completion of the project and starting the other.

Project evaluation is best done by always referring back to the set indicators which measure the level of achievement of the project. During evaluation of liquid soap making project in Gongolamboto Ward, the community members who are also project beneficiaries were involved during conducting participatory community needs assessment and identification of the project. They were also involved in daily implementation and assessment of each activity. So far, allproject activities have been implemented and all objectives have been achieved. However, we cannot currently conclude attainment of the main goal because the final evaluation will be done later after several sales of produced liquid soap and distribution of income.

### 5.3.1 Project Performance Indicators

Project performance indicators for liquid soap making in Gongolamboto Ward were categorized into input indicators, output indicators and impact indicators and they are qualitative and quantitative. Input indicators include time (number of man days), amount of money spent and other resources used while output indicators include number of community members trained, and the project tools purchased.  Output indicators also include the quantity ofliquid soap production and sales, and the amount of money generated out of products sales. Finally, output indicators considers the group registration certificate and bank details to substantiate that the group was formalized. Impact indicator for this project is the improved life standard as a result of improved income which will be obtained from sales of project products.

# Table 5.3: Project Performance Indicators

| Objectives | Outputs | Activities | Inputs Required | Performance Indicators |
| --- | --- | --- | --- | --- |
| To train 10Jithaminigroup member on soap production, packaging, by the end of August 2020 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | Vehicle, Fuel, Personnel, Stationery, Time | CAN report |
|  |  | Prepare CNA report | Personnel, Time, Stationery | CAN report |
|  | 10 Group members trained on liquid soap making and packaging | Make preparations for training | Stationery, time, personnel | Training materials, availability of Venue and facilitator |
|  |  | Conduct raining on liquid soap production, packaging and marketing skills | Human, time, stationery, meals and refreshment | Training report and list of inputs |
| To start soap production by end of September 2020 | Tools of production purchased | Mobilize funds for tools acquisition | Cash | Amount of cash to purchase tools |
|  |  | Purchase detergents, and other tools for soap production | Cash, time, human | List of purchased project tools |
|  | Liquid Soap production started | Obtain office and factory/ production place for soap production | Human, time, tools, cash | Quantity of produced liquid soap |
|  |  | Make liquid soap | Human, time, tools | Quantity of liquid soap produced |
|  |  | Sell soap to buyers and keep sales record | Human, time, tools | Soap sales records |
| To facilitate preparation of constitution, group registration and opening Bank account by October2020 | Constitution prepared and certificate obtained | Prepare group constitution and application | Human, stationery, time, food | Group Constitution |
|  |  | Submit application to City council Director for registration | Human, time, transport cost, food, Time, Human | Application package submitted to DED |
|  |  | Obtain group office | Human, time | Office obtained |
|  | Open Group Bank Account | Mobilize TZS 30,000 funds to open bank account | Human, time, communication cost | TZS 30,000 mobilized to open bank account |
|  |  | Submit application package to the Bank for bank account | Human, time, transport cost, food | Application package submitted to the Bank |

Source: Researcher, 2020

### 5.3.2 Participatory Evaluation Methods

This project had three objectives namely, to train 10Jithaminigroup members on liquid soap production and packaging by the end of August 2020, to start liquid Soap production by end of September2020and to facilitate preparation of constitution, group registration and opening Bank account by October2020.All project activities for all objectives have been completed.  As noted earlier on, evaluation of this project has not been done, it will be done at a later stage after several rounds of sales of the products to assess the progress towards achieving the project goal.

Final evaluation will be done by the beneficiaries in collaboration with other stakeholders who will use the Beneficiaries Assessment (BA) approach and Participatory Rural Appraisal (PRA). A checklist with predetermined questions will be used to interrogate the direct beneficiaries so that they can give their views on how the project has achieved the outputs, objectives, and goal and sustainability factors.

### 5.3.3 Project Evaluation Summary

The project evaluation summary provides achievement of the project based on the stated goal, project objectives, project outputs, planned activities, performance indicators and expected outcome. All planned project activities have been completed and objectives achieved. Generally for the finished activities, we have witnessed strong commitment of the project beneficiaries and stakeholders from project planning up to the stage of implementation. All completed activities were implemented and finished as per activity implementation plan.  The last evaluation which will be done later will provide a clear assessment on the extent to which the goal has been achieved.

# Table 5.4: Project Evaluation Summary

| Objectives | Outputs | Activities | Performance Indicators | Expected Outcome | Actual Outcome | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| To train 10Jithaminigroup member on liquid soap production, packaging, by the end of August 2020 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) | CNA report | The community Needs Identified | The community needs were identified | Completed |
|  |  | Prepare CNA report | CNA report | The community Needs recorded | Community Needs were recorded and project identified | Completed |
|  | 10 Group members trained on liquid soap making and packaging | Make preparations for training | Training materials, availability of Venue and facilitator | Training materials, Venue and facilitator obtained | Training materials, Venue and facilitator obtained | Completed |
|  |  | Conduct training on liquid soap production, packaging and marketing skills | Training report and list of inputs | 10 members of Jithaminigroupcan make and package liquid soap | 10 members of Jithaminigroup aware of ways of soap making and packaging | Completed |
| To start liquid soap production by end of September2020 | Tools of production purchased | Mobilize funds for project tools acquisition | Amount of cash required for project tools | Funds obtained | Funds obtained and used to but tools | Completed |
|  |  | Purchase detergents, and other tools for soap production | List of purchased project tools | Project Tools acquired | Tools purchased and are used in project activities | Completed |
|  | Liquid Soap production started | Obtain office and factory/ production place for soap production | Contract for office hiring | Office hired/ obtained | Office hired and used for liquid soap production and display of products | Completed |
|  |  | Make liquid soap | Produced soap | Tools purchased | Tools used in soap making | Completed |
|  |  | Sell soap to buyers and keep sales record | Sales records | Soap sold and records kept | Liquid Soap sold and records kept | Completed |
| To facilitate preparation of constitution, group registration and opening Bank account by October2020 | Constitution prepared and certificate obtained | Prepare CBO constitution and application package | Constitution | Group constitution prepared | Group constitution prepared | Completed |
|  |  | Submit application to council Director for registration | Application package submitted to Municipal Director for registration | CBO registration certificate obtained | Group registration certificate obtained | Completed |
|  | Open Group Bank Account | Mobilize TZS 30,000 funds to open bank account | TZS 30,000 mobilized to open bank account | TZS 30,000 paid to the bank as an account opening balance | TZS 50,000 paid to the bank as an account opening balance | Completed |
|  |  | Submit application package to the Bank for bank account | Application package submitted to the Bank | Bank account opened | Bank account opened and operational | Completed |

Source: researcher, (2021)

## 5.4 Project Sustainability

Project sustainability is evaluated by looking at the factors which will facilitate the project to maintain its operations and benefits to beneficiaries even after withdrawal of sponsors.  We assess available the strategies and ability of the community to run the project and develop other income generating activities in future by using internal resources. In order to ensure sustainability, the CED Researcher maintained the use of participatory approach in all stages from project identification, implementation, monitoring and evaluation. This approach has empowered the community members such that they can run the project with very minimal dependency from external support.

### 5.4.1 Strategies for Project Sustainability

The community has put in place various strategies of sustainability for soap making project in Gongolamboto Ward. The strategies included involvement of project beneficiaries in all project stages from CNA, resource mobilization, project implementation and monitoring of project activities. Another strategy is involvement of the Community Development Officer, Cooperatives Officer and Trade Officer who are permanent government employees who instilled skills into the group and capacity building in terms of soap production and marketing skills.

In terms of financial sustainability, the community members willingly agreed to contribute the initial capital for their own project and will proceed with buying shares, taking loans and repaying as per constitution. Another strategy is the use of self-prepared constitution to guide daily group operations, involvement of the Ward Development Council which is a permanent government administrative structure as the host organization. Finally, another element of sustainability is viewed through formalization of the community into a registered CBO with a bank account which make it legally identifiable.

### 5.4.2 Project Sustainability Assessment

Sustainability assessment of the project is part of evaluation process which is expected to be done after completion of all project activities in November2020. However, some indicators of sustainability were assessed at the initial stage and during the course of implementation. The assessed initial indicators include the commitment demonstrated by the community members to work together with other stakeholders to identify the project basing on their needs, follow instructions provided by extension officers and willingness to contribute money for project operations. The economic sustainability of the project will be assessed at a more mature stage of a project.

### 5.4.3 Financial Sustainability

The project was implemented by ten widows who also do small business in Gongolamboto Ward. From their small savings, the members contributed some money which was used as a startup capital to run the project and will still be used to expand project operations as specified in the group constitution. Other funds will be obtained from liquid soap sales and they will be kept in the opened bank account and re invested in other income generating activities as per constitution.

### 5.4.4 Institutional Sustainability

It is anticipated that this group will abide to the articles of their self-prepared constitution and they will proceed to work under supervision of Gongolamboto Ward Development Council which is a permanent institution in the government structure. Also as noted during reviewing the policies, the project has a government support through various public policies. By formalizing and registering the CBO, it is obvious that the group is eligible for support from the government and other development partners. The established CBO will be able to access available loans and other capacity building opportunities including trainings on various income generating activities and business provided by the government and other development actors.

### 5.4.5 Political Sustainability

The project is implemented in a politically stable environment and is supported by various government structures from the Municipal Council to Ward Development Council and yet it is supported by various public policies. It is further expected that political leaders will continue offering their supporting the CBO and their project; and they will sensitize the rest of the community to establish similar projects through which the household incomes will be improved and contribute into the development of the country.

# CHAPTER SIX

# CONCLUSION AND RECOMMENDATIONS

## 6.1 Introduction

This chapter provides an overview of the whole process from project identification through Participatory Community Needs Assessment, project implementation, monitoring and finally, project evaluation. It discusses key issues which were identified during the CNA, Literature review, the reasons for selecting the implemented project, project implementation report, participatory monitoring, evaluation and sustainability. It also presents the recommendations to the community and other organizations which may wish to implement similar projects. Lastly, the chapter discusses other unplanned occurrences which affected the project. In a nutshell, this chapter is a summary of what has been covered in all previous chapters.

## 6.2 Conclusion

Through the conducted participatory Community Needs Assessment (CNA), it was found that the outstanding challenge of community in Gongolamboto Ward is low income especially amongst the widows. This community is made of very limited income earners but yet with high domestic workloads and household responsibilities, with the families of up to 5 members on average, most of whom are children who have highlyrequire education, health and nutrition services.

As a way to improve their household income, these women have been engaging themselves in various entrepreneurial activities. Through this project, they have been mobilized and decided to form a CBO namely Jithamini through which they implemented liquid soap making project in Gongolamboto Ward. The choice of liquid soap making project considered various available opportunities as reveled through the Community Participatory Assessment. Some of the reasons behind the choice of liquid soap project include presence of trade officer and community development officer who provide technical support as well as the market for the product.

Through theoretical and empirical literature review we gathered the existing knowledge and experience on poverty reduction initiatives, income generation and liquid soap making activities. The obtained knowledge has added value in implementing liquid soap making in Gongolamboto Ward in Ilala Municipality. The available policy framework on poverty reduction including the women empowerment policy, community development policy and the Vision 2025 were also reviewed to assess on how the government policies can affect the project. Generally, the reviewed literature reveled that apart from continuous efforts employed by the government and other development partners to combat poverty, many Tanzanians especially women are still experiencing income poverty.

The existing Tanzanian policy framework gives opportunity for communities of disadvantaged people especially women and youth to engage themselves in income generating activities depending on their choices and ability to implement such projects. The information obtained in the reviewed literature regarding poverty is quite similar to that obtained during CNA as presented in the first chapter of this document and has significantly contributed towards successful implementation of the project.

Implementation of the liquid soap making project was directly done by 10 selected members under supervision of elected CBO leaders and coordination of Gongolamboto Ward council which is the host organization.The project aimed at capacity building to the community on how best to make and sell liquid soap, starting liquid soap making factory and finally facilitate the community to establish and register the legally acceptable CBO with a written constitution and bank account. In order to facilitate implementation of the objectives, the Municipal Council as a major stakeholder through the community development officer and trade officer who offered all necessary technical guidance in various aspects regarding CBO formation and registration, liquid soap making and product marketing.

Actual Implementation of the project commenced in August2020 and adhered to the established implementation plan. The group of beneficiaries was registered into a CBO namely JITHAMINI GROUP with registration number IMC/GMT/IGA/163/2020 with a bank account number 015C535835000 held at CRDB Banana Branch. Apart from liquid soap making, the group has a wide vision of operating a credit and savings project in future as specified in their constitution.

Monitoring of project activities was done by using participatory methods including the participatory Rural Appraisal (PRA) and Beneficiary Assessment (BA). The community members participated fully from inception and daily implementation of activities in order to realize the predetermined project objectives. The Researcher in collaboration with leaders from host organization and extension officers took part in daily monitoring of activities including capacity building, tools acquisition, soap making and packaging, preparation of constitution and finally formal registration of a group into a CBO.

Some indicators of project sustainability were assessed at the beginning and during the course of implementation. Early indicators that are evident include financial sustainability, institutional sustainability and political sustainability. The community has demonstrated commitment to work together with other stakeholders to identify the project, follow instructions provided by experts and willingness to contribute money for project operations. The host organization with a lot of political support from the village and ward level is taking a leading role in coordinating all project activities. Also, having a group constitution, bank account and registering the group as a CBO is yet another vivid indicator of institutional sustainability. Other sustainability indicators have not revealed themselves at this stage and they will be recorded after final evaluation of the project. The economic sustainability of the project will only be measured later to assess the economic contribution towards improvement of beneficiaries’’ life and continuity of production and selling of liquid soap.

## 6.3 Recommendations

It is hereby recommended that the host organization, Community Development officer, Cooperatives Officer and the Trade Officer keep close supervision in order to support the group and its operations by providing daily capacity building through couching, mentoring and market linkage. The community still needs continuous practical guidance especially on producing quality liquid soap, branding the products, packaging and marketing the products. The group also needs more training on business management, financial and project management as well as conflict resolution to avoid group disintegration. Performance of this project should be taken as a lesson for other disadvantaged groups of women and youth groups around and outside the area who can be mobilized to follow the same path to save money, form and register groups and come up with any income generating project of their choice through which they will improve their income and reduce household poverty.

It is further recommended that future projects should use participatory approaches such as PRA and BA as they have proved to be strong tools of involving people in working together in the project identification, project implementation, monitoring and evaluation of project. The use of such approaches increases the chance of project ownership and sustainability because they allow the community to come up with real needs and appropriate solutions. Experience from implementation of soap production project has proved that the community and other stakeholders are ready to work and contribute both materially and financially provided that things are transparent.

# REFERENCES

Britto, S. F. (2006). Poverty in Focus. Brazil: United Nations development Programme.

Evans D. K. & Hausladen, S. (2013). Community Based Cash Transfers in Tanzania: Results from a randomized trial. Washington DC: World Bank.

Fiszbein, S. N. (2009). Conditional Cash Transfer. Washngton DC: The World Bank.

McKillip, M. (2007). Mechanical harvesting of Sweet Cherries resource. Washington DC: American Society of Agriculture Engineers.

NBS, (2014). Household Budget Survey 2011/2012 Main Report. Dar es Salaam: URT.

NBS, (2014). Tanzania Conditional Cash Transfer (CCT) Impact Evaluation: Final Report. Dar es Salaam: NBS.

The United Way of America, (2012). World Urbanization prospects the 2001 revision. New York: United Nations.

Todaro, S. C. (2012). Economic Development. Washington DC: Pearson.

UNDP, (2011). HUMAN DEVELOPMENT REPORT. London: Oxford University Press.

URT, (1996). Community Development Policy. Dar es salaam: URT.

URT, (2004). National Economic Empowerment Policy. Dar Es Salaam: URT.

URT, (2005). Poverty and Human Development Report, Research and analysis. Dar es Salaam: Mkuki na Nyota Publishers.

URT, (2007). Poverty and Human Development Report, Research and analysis. Dar es Salaam: Ministry of Planning, Economy and Empowerment.

URT, (2013). Productive Social Safety Net (PSSN) OPERATION MANUAL. Dar es Salaam.

World Bank, (2011). Poverty, Growth and Public Transfers. Washington DC: World Bank.

World Bank, (2016). Poverty and Shared Prosperity: Taking on Inequality. Washington DC: World Bank Group.

# APPENDICES

# Appendix 1: 	Questionnaire

QUESTIONNAIRE TO BE ADMINISTERED TO RESPONDENTS

Region_______________________________

District____________________________

Ward:_______________________________                Village_________________________

Distance in km to district HQ:__________

Date of Interview:___________________

Questionaire number___________

Name of Interviewer	Tel No:………………………………………….

| No | a) Age | b) Size of household | c) Education Level | d) Occupation/ source of income | e)Income per month in Tsh |
| --- | --- | --- | --- | --- | --- |
| 1 | 18 – 30 31 – 45 46 – 60 Above 60 | 1 2-3 4-5 Above 5 | Primary education Secondary education Higher education None | Farming Livestock keeping Petty business Casual Labor others | Below 30,000 31,000-40,000 41,000-50,000 51,000-60,000 Above 60,000 |

SECTION A: socio economic and demographic Characteristics of the respondent

2) Household composition and population

| Age group | Number of household member |
| --- | --- |
| 1. Adults (≥18 years) |  |
| 2. Children (11-18 years) |  |
| 3.Children (<10years |  |
| Total |  |

SECTION B: Challenges and Needs for women from TASAF beneficiary households in Gongolamboto Ward

3) Rank the following challenges facing the widows in your village (1= least important, 5= most important)

| No | Challenge | Score |
| --- | --- | --- |
| 1 | Limited income |  |
| 2 | Land ownership |  |
| 3 | Drought |  |
| 4 | Domestic workload |  |
| 5 | Limited information on how to produce and market their products |  |
| 6 | Gender stereo typing |  |

4) Rank the following needs of the women in your village (1= least important, 5= most important)

| o | Need | Score |
| --- | --- | --- |
| 1 | Startup capital |  |
| 2 | Improved income |  |
| 3 | Land ownership |  |
| 4 | Reduced Domestic workload |  |
| 5 | Adequate information on how to produce and market their products |  |
| 6 | Gender empowerment |  |

SECTION C:

5) Which project do you think is good for you to implement and improve your income? (According to your experience and environment)….Tick once against your choice

| No | Project (Income generating activity) | Tick |
| --- | --- | --- |
| 1 | Poultry |  |
| 2 | Tie and dye |  |
| 3 | Cotton farming |  |
| 4 | Liquid Soap making |  |
| 5 | Goat/ sheep keeping |  |

6) Are you ready to join others and work together in an organized group? Yes_______No__________

7) Do you have any suggestion/ comment?_________________________________

# Appendix 2: Focus Group Discussion Checklist

- What are the needs of the poor Widows in your Ward (Gongolamboto)

- How can the needs you have mentioned be addressed?

- Which project do you think is good for you to implement and improve your income?

- Why do you think the project you have mentioned is suitable for you

# Appendix 3: Registration Certificate for Jithaminigroup in Gongolamboto Ward

# Appendix 4: Jithamini group Bank Account details

Appendix 5: Registered constitution for Jithaminigroup in Gongolamboto Ward

Figure 2: CED student (in black blouse and white skirt) with Jithamini Group Members during Training on Liquid Soap Making

Figure 3: Liquid Soap Product Made by Jithamini Group Already Packed for Sale

# Text boxes

WARD DEVELOPMENT COUNCIL (WDC)

WARD COUNCILOR

SECURITY COMMITTEE

SOCIAL WELFARE COMITTEE

ENVIRONMENTAL COMMITTEE

FINANCE COMMITTEE

WARD EXECUTIVE OFFICER