INCREASING ACCESS TO CREDIT FOR WOMEN THROUGH UPENDO NA AMANI VICOBA IN KILIMAHEWA, NACHINGWEA WARD RUANGWA DISTRICT

CHARLES DAMIAN TAMBA

A DISSERTATION SUBMITTED IN PARTIAL FULFILMENT OF THE REQUIREMENTS FOR THE DEGREEE OF MASTER OF COMMUNITY ECONOMIC DEVELOPMENT (MCED)

DEPARTMENT OF COMMUNITY ECONOMIC DEVELOPMENT

OF THE OPEN UNIVERSITY OF TANZANIA

2021

# CERTIFICATION

The undersigned certifies that he has read and hereby recommends for the acceptance by the Open University of Tanzania (OUT) a dissertation entitled; “Increasing women access to financial credit: The case of Upendo na Amani Village Community Bank in Kilimahewa Village at Nachingwea ward in Ruangwa District, in partial fulfilment of the requirements for the degree of Master of Community Economic Development of the Open University of Tanzania.

…………………………………..

Dr. Albert Memba

(Supervisor)

......................................

Date

# COPYRIGHT

No any part of this dissertation may be replicated, distributed in any form or by any means, in full or in part, with the exception of citation in research studies, without written permission of Directorate of postgraduate studies on behalf of the author and Open University of Tanzania.

# DECLARATION

I, Charles Damian Tamba, do hereby declare that this dissertation is my own original work and it has not been presented and will not be submitted to any other university for a similar or any other degree award.

……………..………..………….

Signature

…………………….………..

Date

# DEDICATION

This work is dedicated to my beloved wife, Majuto Hamisi Ungulu, and my beloved children, Maria faith Tamba and Yohanes Tamba.

Thank you!

# ACKNOWLEDGEMENTS

I am indebted to those who, in one way or another, have contributed to the successful completion of my studies and the writing of this dissertation. Since it is not possible to mention all of them, I would specifically wish to express my special gratitude to my supervisor, Dr. Albert Memba, for his guidance, encouragement and advice. His tolerance, wisdom, and commitment right from the beginning to the end have made this dissertation worthy reading.

I would also like to express my special thanks to my beloved wife, Majuto Hamisi Ungulu, and my beloved children, Maria faith Tamba and Yohanes Tamba, for encouraging me and creating a peaceful environment and supporting me throughout the study. I would like to thank my brother Joachim Damian Tamba for his assistance and encouragement from the beginning of my studies to the end. I also express my sincere thanks to the chairperson of the Amani na Upendo VICOBA women group of Kilimahewa village for the support they gave me during the period of my study.

I would like to further extend my sincere thanks to Ruangwa District Community Development Officer for allowing me to do my project in one of his income generating groups through Amani na Upendo group of Kilimahewa village. I would also like to thank the leaders of Ruangwa Organization for Poverty Alleviation (ROPA) for their assistance and cooperation during the contact of any field survey and data collection.

Finally, I would like to express my sincere thanks to MCED Coordinator Dr. Harrieth Mtae and all the instructors for their assistance and cooperation.

# ABSTRACT

This dissertation if the product of the Participatory Needs Assessment (PNA) that was done in Kilimahewa village, Ruangwa district, to identify the needs of Upendo na Amani group and identify ways of implementing it.  The study findings have shown that the community is having income poverty and lack of capital to finance their entrepreneurial ventures. The study has suggested for the establishment of a community managed savings and credit association as a solution to the problem.  Reviewed literature depicted that women were comparatively poor than men but they are likely to succeed fighting poverty through combined efforts especially formation of economic production groups. Although the Tanzanian policy framework avails opportunities and support for women growth, the policies have not been able to pull many rural women out of income poverty. Through working with the host organization and other stakeholders, the community formally formed and registered a group namely Upendo na Amani, opened a bank account, and has started savings through buying shares. Daily monitoring of the project activities was conducted by using participatory methods including the participatory Rural Appraisal (PRA) and Beneficiary Assessment (BA). The project promises to be sustainable because the community has put in place their constitution and has shown commitment to work with other stakeholders in implementing the project.

Keywords: Women, Financial, Community, Development, Credit.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENTS	vi

ABSTRACT	vii

TABLE OF CONTENTS	viii

LIST OF TABLES	xiii

LIST OF FIGURES	xiv

LIST OF ABBREVIATIONS	xv

CHAPTER ONE	1

PARTICIPATORY NEEDS ASSESSMENT	1

1.1	Background Information	1

1.2	Community Profile	2

1.2.1	Social - Economic Activities and Demographic Characteristics	2

1.2.2	Social Services	4

1.3	Community Needs Assessment	5

1.3.1	Objectives of the Community Needs Assessment	6

1.3.2	Research Questions	6

1.3.3	Research Methodology	7

1.4	Community Needs assessment Findings	10

1.4.1	Demographic and Socio Economic Characteristics of Respondents	10

1.4.2	Economic Activities Implemented by the Women Entrepreneurs	13

1.4.3	Community Need and Income Distribution	14

1.5	Community Needs Prioritization	15

1.6	Selection of Community Project	17

1.7	Conclusion	18

CHAPTER TWO	20

PROBLEM IDENTIFICATION	20

2.1 	Background to the research Problem	20

2.2	Problem Statement	21

2.3	Project Description	23

2.3.1	Target Community	25

2.3.2	Stakeholders	25

2.3.3	Project Goal	26

2.3.4	Project Objectives	27

2.4	Host Organization/CBO Profile	27

2.4.1	Vision of the Host Organization	28

2.4.2	Mission of the Host Organization	28

2.4.3	ROPA Organization Structure	28

2.4.5	The Role of CED Researcher	29

2.4.6	The Role of the Host Organization/CBO	30

CHAPTER THREE	31

LITERATURE REVIEW	31

3.1 	Introduction	31

3.2 	Definition of Concepts	31

3.2.2 	Gender	31

3.2.3 	Empowerment	31

3.2.4 	Entrepreneurship	32

3.2.5 	Women Economic Empowerment	32

3.2.6 	Village Community Bank	33

3.2.7 	Development	34

3.3 	Theoretical Literature Review	34

3.4 	Empirical Literature Review	35

3.4.1 	Women Entrepreneurship and Accessibility to Financial Credits	35

3.4.2 	Efforts by Tanzania to Empower Women	36

3.5 	Policy Review	37

3.5.1 	Women Development Policy1992	37

3.5.2 	Community Development Policy 1996	37

3.5.3 	National Economic Empowerment Policy	38

3.5.4 	Tanzania Development Vision 2025	38

3.6 	Literature Review Summary	39

CHAPTER FOUR	41

PROJECT IMPLEMENTATION	41

4.1 	Introduction	41

4.2 	Product and Outputs	41

4.3 	Project Planning	43

4.3.1 	Implementation Plan	43

4.3.2 	Inputs	47

4.3.3 	Staffing Pattern	48

4.3.4 	Project Budget	49

4.3.3 	Project Implementation	50

CHAPTER FIVE	55

PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	55

5.1 	Introduction	55

5.2 	Participatory Monitoring	55

5.2.1 	Monitoring Information System	56

5.2.2 	Participatory Monitoring Methods	58

5.2.3 	Participatory Monitoring Plan	58

5.3 	Participatory Evaluation	61

5.3.1 	Performance Indicators	61

5.3.2 	Participatory Evaluation Methods	63

5.3.3 	Project Evaluation Summary	64

5.3.4 	Lessons Learned During Project Implementation	66

5.4 	Project Sustainability	67

5.4.1 	Strategies for Project Sustainability	68

5.4.2 	Project Sustainability Assessment	68

5.4.3 	Financial Sustainability	69

5.4.4 	Institutional Sustainability	69

5.4.5 	Political Sustainability	70

CHAPTER SIX	71

CONCLUSIONS AND RECOMMENDATIONS	71

6.1 	Introduction	71

6.2 	Conclusion	71

6.3 	Recommendations	74

REFERENCES	76

APPENDIX	80

# LIST OF TABLES

Table 1.1: Respondents' Size of Household	12

Table 1.2: Respondents' Income Distribution	14

Table 1.3: Community Needs Ranking Matrix	16

Table 1.4: Pair Wise Ranking of Proposed Community Projects	17

Table 2.1: Stakeholders Analysis Matrix	26

Table 2.2: SWOT Analysis of the Host Organization	29

Table 4.1: Project Outputs and Activities	42

Table 4.2: Project Implementation Plan	44

Table 4.3: The Logical Framework of the Project	45

Table 4.4: Staff Pattern	48

Table 4.5: Project Budget	49

Table 4.6: Project Implementation Report	52

Table 4.7: Project Implementation Ghannt Chat	53

Table 5.1: Monitoring Information System	57

Table 5.2: Project Monitoring Plan	59

Table 5.3: Project Performance Indicators	62

Table 5.4: Project Evaluation Summary	65

# LIST OF FIGURES

Figure 1.1: 	Age Distribution of Respondents (N =33)	11

Figure 1.2: 	Education level of Respondents by Percentage	13

Figure 1.3: 	Respondents Occupation	14

Figure 1.4: 	A Researcher with Respondents during Identification and                 Ranking  Needs and Identification of a Project	15

Figure 2.1: 	ROPA Organization Structure	28

Figure 3.1: 	CED Researcher with Project Beneficiaries as they Proceed                        with Share Purchase and Loans Taking	51

Figure 3.2: 	CED Researcher with Beneficiaries during Project                          Implementation	51

# LIST OF ABBREVIATIONS

BA	Beneficiaries Assessment

CBO	Community Based Organization

CCT	Conditional Cash Transfer

CED	Community Economic Development

CNA	Community Needs Assessment

DC	District Council

DCDO	District Community Development Officer

FGD	Focus Group Discussion

HBS	Household Budget Survey

IGA	Income Generating Activities

LGA	Local Government Authority

MCED	Master of Community Economic Development

MDG	Millennium Development Goals

MKUKUTA	Mkakati wa kukuza uchumi na kupunguza umaskini Tanzania

MKUZA	Mkakati wa kukuza Uchumi Zanzibar

NBS	National Bureau of Statistics

NMB	National Microfinance Bank

NPES	National Poverty Eradication Strategy

NSGRP	National Strategy for Growth and Reduction of Poverty

PRA	Participatory Rural Appraisal

PRSP	Poverty Reduction Strategy Paper

PSSN	Productive Social Safety Net

SPSS	Statistical Package for Social Science

SWOC	Strength, Weaknesses, Opportunities and Challenges

TASAF	Tanzania Social Action Fund

TZS	Tanzanian Shillings

URT	United Republic of Tanzania

USD	United States Dollar

VEO	Village Executive Officer

VICOBA          Village Community Bank

VSLA               Village Savings and Loan Association

WB	World Bank

# CHAPTER ONE

# PARTICIPATORY NEEDS ASSESSMENT

## Background Information

The Tanzania Household Budget Survey (2011/2012) (NBS, 2014) clearly states that approximately 81% of the poor people in Tanzania live in rural areas where income poverty is very widespread. The survey further depicts that almost 34% of the rural population in Tanzania mainland is deeply affected by poverty further away from the basic needs poverty line which is estimated to be 28.2% for the whole Tanzania mainland. According to URT (2013), it is estimated that almost 12 million Tanzanians are still poor and more than 10 million citizens in rural areas, who are mostly women, live in extreme poverty.

As a result of extreme income poverty in rural areas, most of the people especially women experience lack of access to quality education, health care services, decent housing, proper nutrition and water and sanitation services.  The World Bank (2016) puts it clearly that effects of poverty are worse in child and women headed households that have limited access to productive assets especially agricultural land and financial capital to run business. The situation of income poverty as experienced by many women in rural areas requires constant poverty reduction struggles by the government, NGOs, social groups and individuals to improve production and economic growth.

Individual efforts to fight poverty displayed by many women include agriculture and entrepreneurial activities like petty trade, hair dressing, food vending, tailoring and embroidery. However, individual entrepreneurs are still facing a lot of challenges including lack of capital, lack of access to loans, lack of basic business skills, lack of markets and lack of exposure and experience. These challenges limit them from growing and they remain confined in the vicious cycle of low productivity and low access to resources.

## Community Profile

The study involved Upendo na Amani which is a group composed of twenty (20) women, who are unemployed in the formal sector but each of them having an entrepreneurial activity through which they earn incomes. These group members are involved in activities petty businesses like kiosks, food vending, fish frying, hair dressing, catering, stationery and decorations.  The group is found at Kilimahewa village in Nachingwea ward, Ruangwa district in Lindi Region.

## Social - Economic Activities and Demographic Characteristics

The main economic activities in Kilimahewa village include agriculture, which employs more than 90% of the population. Other economic activities include petty business, small scale mining, small industries, forest harvest and livestock keeping. Major food crops grown are maize, millet, rice, sweat potatoes, banana and cassava. Due to persisting low levels of income among the families, most of those uneducated populations are engaged in informal sector operating small scale businesses such as food vending, petty business, brick making, small scale mining, bodaboda, local bars, carpentry, masonry, pubs, tailoring, wine making, soap making, bakery etc.

The livestock kept in Kilimahewa village include cows, goats, sheep and poultry. As presented by NBS (2014), the households are likely to be poor if they are dependent on the sale of food and cash crops or earning a living from natural products. On the contrary, households tend to be non-poor when they become part of the formal sector and receiving wages or business own business. The community in Kilimahewa village, especially women, have to be facilitated to change from relying on crop sales and so that they can unite and engage in sustainable business activities in order to get rid of income poverty.

According to (NBS, 2012), Nachingwea ward has a total population of 8,142 people out of whom 3,769 are male and 4,373 are female and with the average household size of 3.4 persons. The residents of Nachingwea ward, and particularly Kilimahewa village, are Mwera who account for about 97% of the population while the remaining 3% is a mixture of other tribes who migrated to the area through intermarriages or other activities. The 3% of the population comprises of Makonde, Yao, Makua, Chagga, Ngindo, Matumbi, Maraba, Sukuma and the Haya.

The residents are still dominated by traditional and customary law; patriarchy system is very strong in the community, which is symbolically revealed during initiation ceremonies for young girls and boys who are being prepared to be mothers and fathers. The predominant religion is Islamic and the dominant type of marriage is mainly polygamous. The Mwera are culturally known for working together and they are hard workers. Since almost all religions preach the importance of working hard and advocate for loving each other and working together to fight poverty, it is anticipated that the cultural background and religious teachings in Kilimahewa influenced the group members to work together in identifying the needs and implementing the project that would increase their income.

## Social Services

Kilimahewa village, as any other village, is administered by Village Government Council under a leadership of the Village Executive Officer. There is one public primary school called Ruangwa and a private school called Wonder Kids pre and primary school.  The village has three nursery schools; namely, St. Thomas Aquinas nursery school, Careen nursery school, and Shalom nursery school. There is no Secondary school in the village but all children that qualify join Majaliwa Secondary School, which is located in the neighbour village of the same ward. Water supply in the whole ward of Nachingwea is still a problem since most parts are not connected to the piped water. Women and children buy bucket of water for between 200 and  500 TSHs.

The village enjoys full access of all major mobile networks such as TTCL, Tigo, Halotel, Vodacom and Airtel. Transport and transportation of product is not a problem since the village is close to the main road linking Lindi and Mtwara Regions and has a passable road network throughout the year which is periodically maintained by Tanzania Rural and Urban Roads Agency (TARURA). The village is connected to national power grid from Tanzania Electricity Supply Company (TANESCO) which supports most of the community to run small businesses like selling soft and hard drinks within the area. The main energy sources for cooking comprise of firewood, charcoal, kerosene and very few people use gas and electricity.

The village has one health centre that provides basic health services to the inhabitants. As regards to market services, the village has a place for auction where people meet on every Friday to sell and buy various products including livestock, crops and domestic consumables. The availability of these social services especially the auction place, electrical power and passable roads provide opportunity to the community to produce and transport their products to market places easily.

## Community Needs Assessment

According to Kosecoff (1985), Community Needs Assessment (CNA) is a method of collecting information from people about their ideas, feelings, plans, beliefs, and social, educational and financial backgrounds. To achieve that it usually takes the form of questionnaires, interviews and focus group discussion. However, other scholars, such as Borroughs (2011), define it as the process of identifying and discovering the needs of a target audience and it is instrumental method before planning. Therefore, CNA is an approach or method of collecting information from people that involves them to identify and assess their needs.

CNA for Kilimahewa Village was conducted in order to identify and assess needs and gaps in relation to the available resources, opportunities that can be utilized by women who are engaged in entrepreneurial activities. It was conducted in a participatory way to identify the real needs of the community and thereafter make interventions to address critical problems. The research findings were expected to be beneficial not only to the community but also to the researcher, Kilimahewa village Council, Ruangwa District Council and all development stakeholders. The participatory community needs assessment also assessed opportunities and challenges to implement the project, market and capacity building gaps as well as the strength and weakness (SWOT) of the host organization.

## Objectives of the Community Needs Assessment

The overall aim of the community needs assessment was to identify challenges facing women engaged in entrepreneurial activities in Kilimahewa village and find out the type of project which they can use to curb the challenges.

## Specific Objectives of CNA

The Specific objectives of the assessment included the following;

- To describe social economic and demographic characteristics of women entrepreneurs in Kilimahewa village

- To assess the major economic activities implemented by women entrepreneurs in Kilimahewa village

- To identify the community needs among women entrepreneurs in Kilimahewa village

- To identify the most viable project to mitigate the community needs identified by the women entrepreneurs in Kilimahewa village

## Research Questions

The study sought to get answers for the following research questions;

- What are social economic and demographic characteristics of women entrepreneurs in Kilimahewa village?

- Which major economic activities are implemented by women entrepreneurs in Kilimahewa Village?

- What are the main needs of women entrepreneurs in Kilimahewa village?

- What is the most viable project to mitigate the needs identified by the community of women entrepreneurs in Kilimahewa village?

## Research Methodology

## Research Design

Kothari (2004) explains research design as the procedure for collection and analysis of data in a manner that enables a researcher to come up with information relevant to study purpose. The study used both qualitative and quantitative research design to guide data collection and analysis. The data obtained were analyzed by using SPSS software.

This study was descriptive as it mainly described the characteristics of the respondents and their economic activities without necessarily explaining in details why and how those characteristics occurred. The study was also participatory in nature as it emphasized participation of the community throughout the process; it involved the community (women entrepreneurs), Kilimahewa village leaders, ROPA and other stakeholders in getting the answers for the pre-determined research questions and finally taking practical action towards identifying their needs. The methods for primary data collection included survey questionnaires and interviews. Questionnaires were used to collect data from the main respondents (community).

Interview was used to collect information from key informants including Community Development Officer, trade officer, and village government leaders. The use of these data collection methods ensured high level of participation and involvement of the community in identifying and ranking the community needs and suggesting the most appropriate project that would meet the needs. Secondary data were obtained from various documents including village reports, reports from the office of the District Executive Director and National Bureau of Statistics (NBS). While the major tool used for data collection was the questionnaire, other techniques of data collection like interview, Focus Group discussion (FGD), and observation were used to get information that was mainly used to complement the data collected by using the questionnaire.

## Sampling Techniques

The sampling frame for this study was 42 individuals, which is a total population of identified women entrepreneurs in Kilimahewa village whose names were provided by the village leadership. From that list, the researcher used simple random sampling technique to get a total of 33 main respondents which is equivalent to 78.5% of the total population. Random sampling was used by the researcher to ensure equal chance of being selected. The researcher used purposive non random sampling to identify Key Informants namely Village Chairperson, Village Executive officer, Community Development Officer, Trade Officer, Cooperative Officer and NMB Branch Manager, who were selected by considering their positions and relationship with the community.

The selected sample was highly representative because the selected sampling units had all general characteristics of the population and the researcher selected as many respondents as possible i.e. 78.5% to optimally reduce the sampling error. However, after the study that involved 33 main respondents, only twenty (20) women entrepreneurs were conveniently selected among them to participate directly in the project implementation, by forming Upendo na Amani group, attending trainings, writing constitution and establishing VICOBA. Selection of the group to participate in the project implementation considered readiness of the members to join other fellows to work together, willingness to contribute money, physical fitness and availability to participate in project activities, willingness to join the group and past experience in income generating activities.

## Data Collection Methods

Primary data were mainly collected by using the prepared questionnaire as a major tool. Primary data were directly collected from main respondents who are the women entrepreneurs in Kilimahewa village. Administration of the questionnaires was done by two competent data collectors who were familiarized with the tool before collecting data; it was led by CED student to collect data from the sampled group of 33 main respondents.

During Focus Group Discussion (FGD) respondents were divided into three groups with equal group size of 11 respondents to discuss and get answers for pre-determined questions developed from the research questions especially on identifying and raking their needs and identifying a project through which to overcome them. The checklist which was prepared to guide the discussion and help the researcher to verify data (triangulation) collected by using questionnaire is annexed. Together with the questionnaire which was used as the main tool of data collection, interviews were used to get supplementary information from Key Informants; namely, village government leaders, bank manager and district government leaders.

Review of documents mainly used by reading various existing documents at village, ward and district level. Such documents include area profile of the village, different missions ‘reports including joint development program in Ruangwa District.

## Data Analysis Methods

The collected data were manually edited, coded and entered in the Statistical Package for Social Sciences (SPSS) for analysis to provide frequencies and percentages (descriptive statistics for interpretation) regarding the socio-economic characteristics of respondents namely age, education level, occupation and income.

## Data Presentation

The analyzed data were presented through tables of frequency and percentages to portray and substantiate the information provided by respondents. Respondents’ choices through prioritization of community needs and community interventions ranking were also presented in tables and figures to show the collected information.

## Community Needs assessment Findings

This section of the document presents the analysis and discussion of the data which were collected from 33 randomly sampled women entrepreneurs from the population of women who are engaged in small business in Kilimahewa village. The collected information also shows the ranking of the needs and prioritization of appropriate community project to be implemented. The analysis, presentation and discussion were done to answer the research questions and the stated objectives of this study.

## Demographic and Socio Economic Characteristics of Respondents

Under this section of the report, the discussion is on the age distribution, family composition, education level, occupation and income of the respondents. It is also important to know that the study involved women only, so apparently there was no reason to analyze and discuss sex distribution of respondents.

## Age Distribution of Respondents

From chart 1.1, the data show that about 17 respondents out of 33, which is equivalent to 51.5% of the total sample, have the age ranging between 31 to 45 years. The table also shows that almost 96.9% of the respondents are below 60 years.  These data imply that these women entrepreneurs are still energetic and enthusiastic to work together as they participate in production activities. This also shows that they can get involved in business for a considerable long time.  The data also portray that it is only 3% of the population which is above 60 which may imply that when they grow above that age they withdraw from business due to lack of energy as they come close to the average life expectancy for Tanzanian females which is 64 years according to World Health Rankings (2017).

# Figure 1.1: Age Distribution of Respondents (N =33)

Source: Field data (2020)

## Household Composition

The study findings show that out of 33 respondents; 17 respondents (51.5%) have household size with 4 to 5 members most of whom are young children who are still attending school. The study shows a significant number of households with 2 to 3 members as it are to those with more than 5 members, which is 24.2% for each category of age bracket. This implies that these women need to have steady growth of income in order to be able to cater for school and health requirements; food and clothing for themselves and for the children. Engagement of these women in savings and credit associations will guarantee sustainable financing of their income generating activities that would strengthen their economic capacity to meet household workload especially nutritious food, health, shelter and clothes for themselves and children.

# Table 1.1: Respondents' Size of Household

|  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | 2-3 | 8 | 24.2 | 24.2 | 24.2 |
|  | 4-5 | 17 | 51.5 | 51.5 | 75.8 |
|  | Above 5 | 8 | 24.2 | 24.2 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2019)

## Education Level

The incidence of poverty is normally linked with the education level of head and other members in the household. The study shows that 14 respondents out of 33 (43%) had completed primary school, 11 respondents (33%) had completed ordinary level Secondary school, 4 respondents (12%) had a certificate, 2 had a degree and 2 never attended school. This may probably explain partly why they belong in the poor class in the society. Direct involvement of the community in income generating activities and ability to get soft loans from their VICOBA will lead them into acquiring some money to pay for education of their children which will eventually help to disconnect this poverty cycle.

# Figure 1.2: Education level of Respondents by Percentage

Source: Field data (2020)

## Economic Activities Implemented by the Women Entrepreneurs

The study findings show that out of 33 respondents who participated in the study, 10 women dealt with food vending, 9 dealt with hair dressing and beauty salon, and 8 engaged in tailoring and embroidery, while groceries and kiosks employed three women each.  During separate focus group discussions, all respondents had the view that their businesses attracted enough customers but all what they missed was capital to expand them to meet customer’s expectations.  They further disclosed that getting soft loans would help them to expand and diversify their ventures to get more profit. It is obvious that the community with this nature of occupation has to join forces and be capacitated to establish their own savings and loan association so that they can diversify their inputs and increase their income.

# Figure 1.3: Respondents Occupation

Source: Field data (2020)

## Community Need and Income Distribution

As shown in Table 1.4 the majority of respondents (72.7%) earn between TZS 300,000 to TZS 500,000 per month while about 15.2% earn between TZS 100,000- 300,000 per month and the rest (12%) earn above TZS 500,000 per month. The capital for business was solicited from family contributions and loans from friends. The income distribution of this type justifies the need for this community to organize themselves into productive groups through which they can mobilize funds and get loans and engage in income generating activities so that they can become economically stable. Through FGD, the respondents confirmed their readiness and willingness to use part of their monthly income to make monthly savings and get loans through VICOBA.

# Table 1.2: Respondents' Income Distribution

|  | Frequency | Percent | Valid Percent | Cumulative Percent |
| --- | --- | --- | --- | --- |
| Valid | 100,000- 300,000 | 5 | 15.2 | 15.2 | 15.2 |
|  | 300,001-500,000 | 24 | 72.7 | 72.7 | 87.9 |
|  | Above 500,000 | 4 | 12.1 | 12.1 | 100.0 |
|  | Total | 33 | 100.0 | 100.0 |  |

Source: Field data (2020)

## Community Needs Prioritization

The communities were given chance to identify and mention their needs. This was mainly done during FGD whereby individual respondents were pointing out the community need followed by the discussion on whether it should be recorded on the priority list paper or not. Through that process community needs were mentioned and listed on a piece of paper and the selected respondents were facilitated to rank them by considering the predefined criteria. The researcher applied Pair wise ranking technique by writing two competing needs on each piece of paper whereby the respondents were given chance to vote. For each paper, the highly voted need was picked and written in the prepared matrix as shown in Table 1.5.

The voting and selection of the community needs considered the available resources and opportunities. The identified needs included improved household income, capital to establish or extend business, entrepreneurship training and market linkages. In order to arrange the community needs as to which community issue to be addressed first, the pair wise ranking matrix was used as shown in Table 1.6 and the Figure 1.4.

# Figure 1.4: A Researcher with Respondents during Identification and Ranking Needs and Identification of a Project

# Table 1.3: Community Needs Ranking Matrix

| Community Needs | Business Capital | Entrepreneurship skills | Markets linkages | Improved Household income | Points | Rank |
| --- | --- | --- | --- | --- | --- | --- |
| Business Capital |  | Business Capital | Business Capital | Business Capital | 3 | 1 |
| Entrepreneurship skills |  |  | Entrepreneurship training | Improved household income | 1 | 3 |
| Market linkages |  |  |  | Improved household income | 0 | 4 |
| Improved household income |  |  |  |  | 2 | 2 |

Source: Field data 2020

As illustrated in Table 1.3 the identified four needs as follows:

- Capital to establish or extend business

- Entrepreneurship skills

- Market linkages for their products

- Improved household income

Through participatory needs ranking process, the prioritization matrix clearly shows that the community ranked capital as number one need because they needed it to establish or extend their businesses. Improved household income was ranked the second with 2 points, and then entrepreneurship training with only one point. The last was market linkages that had no score.  It is also obvious that by addressing the issue of capital, they will be automatically addressing the second need which is the improved household income. The two needs are closely linked because availability of financial capital will facilitate establishment of business through which the community will improve their household income.

## Selection of Community Project

The community agreed that their common need was capital to extend their business undertakings in order to improve their household income. Therefore, the community had to identify and prioritize through pair wise ranking the most appropriate project as shown in Table 1.4. The community was facilitated to list on a piece of paper the available and possible ways of raising resources for capital after which the common three were chosen. Later, the three proposed alternatives were arranged in pairs and the community was facilitated to vote against one alternative in each pair so as to get one that was highly voted.

The selected and ranked projects included the following;

- Get a bank loan

- Solicit funds from relatives/friends

- Form a community managed savings and credit association (VICOBA)

# Table 1.4: Pair Wise Ranking of Proposed Community Projects

| Projects | Get a bank loan | Solicit funds from relatives/ friends | Form VICOBA | Points | Rank |
| --- | --- | --- | --- | --- | --- |
| Get a bank loan |  | Solicit funds from relatives/friends | Form VICOBA | 0 | 3 |
| Solicit funds from relatives/friends |  |  | Form VICOBA | 1 | 2 |
| Form VICOBA |  |  |  | 2 | 1 |

Source: Researcher, (2020)

From Table 1.4 the formation of VICOBA was ranked number one followed by getting support from friends and family members and the last option was getting a bank loan. During focus group discussion, participants mentioned a number of reasons for them to establish VICOBA. Those reasons include the following;

- Establishment of VICOBA is a permanent and sustainable solution for the identified community need. Getting a bank loan or soliciting funds from relatives and friends would be just temporary solutions.

- VICOBA is a self-managed entity that will be controlled by the members (community) themselves.

- The amount of loans from VICOBA is determined by the amount invested by individual member through buying shares. This calls for more investment because the more the shares the bigger the loan (capital).

- The interest rates for VICOBA are relatively small as compared to those charged by the commercial banks.

- With the support from host organization, CED student, and community Development Officer, the community has the opportunity to be facilitated to establish VICOBA.

The community further agreed to move forward to work together by forming a VICOBA with the name of Upendo na Amani, wrote the constitution and later registered by the registrar at the District Council. Registration of the community group is important because it ensures legal status of the entity and it defines the roles and responsibilities as well as benefits of each member of the group.

## Conclusion

The findings have shown that about 72.7% of the respondents earn between TZS 300,001 to TZS 500,000 and about 51.5% have household size of 4 to 5 members, who are mostly young children who are still attending school. This is a relatively small income by considering the household size and composition. This calls for more efforts of mobilising themselves in having income generating activities through which they will raise monthly earnings.

The research findings show that 43% of the respondents had only completed primary school. This may imply that they do not have qualification to be employed in the salaried formal sector and they need to work hard in their entrepreneurial activities to make it possible to move from the poor section of the community. The research findings also show that more than 90% of respondents were below 60 years, which means they are still energetic, productive and have experience in doing business.

The Community Needs Assessment (CNA) has helped the researcher to identify in details the information that has been analyzed to provide answers to research questions which were generated from the research objectives. Based on the findings, the large number of respondents indicated that inadequate access to financial resources to establish or expand their business was still a problem. The community decided to establish Village Community Bank as an assured way to manage and sustain their needs by accessing soft loans to establish or expand business and improve their livelihood.

# CHAPTER TWO

# PROBLEM IDENTIFICATION

## 2.1 Background to the research Problem

Poverty is a very complex concept to define as it varies according to contexts, from one community to the other and from household to household. According to(UNDP, 2016), poverty is a multidimensional concept that seeks to measure levels of deprivation encountered by a person, household or community. Although most of the literature focuses on indicators of deprivation such as income, food, access to housing and so on, the choice of indicators to measure levels of deprivation can often be arbitrary and hence may not reflect a full-scale measure of unmet basic needs in different social contexts. Poverty is generally considered to be a measure of deprivation of the basic needs that a person, household or community requires for basic standard of living. These needs include shelter, resources, stable income, water and sanitation services, education and technology.

The government of Tanzania in collaboration with development partners has been adopting different policies and strategies to stimulate economic growth by supporting the rural poor farmers and entrepreneurs to reduce the economic and social challenges facing them. This part of the document has taken into consideration the results from situation analysis and identification of major problems facing small scale women entrepreneurs at Kilimahewa village and the available opportunities for them. Through this study, the list of priority needs was prepared and by use of pair wise matrix, they were prioritized to show which one is more affecting the community.

The CNA results depicted that women entrepreneurs in Kilimahewa village were facing income and non-income poverty hindering them to enjoy decent life and meet their basic needs. Lack of access to loans was identified as a major challenge facing women entrepreneurs in Kilimahewa village and through a pair wise ranking of alternative solutions, establishment of a community based savings and credit association, also known as Village Community Bank through which members will make financial savings, access soft loans and various trainings that would improve their undertakings. Through the established association, the members meet once in every month to make savings through buying shares which are given as loans to members at a small interest and they agree the repayment time.

## Problem Statement

Entrepreneurship is increasingly being recognized as an important driver of economic growth, productivity, innovation and employment, and it is widely accepted as a key aspect of economic dynamism (Ng`ariba, 2014). The role of entrepreneurship and entrepreneurial culture in economic and social development has often been underestimated. Over the years, it has become increasingly apparent that entrepreneurship indeed contributes to economic development. Nevertheless, men (ILO, 2006) owned significant numbers of enterprises. In other words, it was not common to see women-owned businesses worldwide especially in developing countries like Tanzania.

The proportion of women in Tanzania entering Micro and Small Enterprises (MSEs) sector has been increasing since 1991. Women accounted for about 35 per cent of informal enterprises (National Informal Sector, 1995). Women play a key role in the private sector as well as in the micro, small and medium enterprises (MSMEs) in Tanzania. The proportion of women owned enterprises (WOEs) is reported to have increased from 35 per cent in early 1990s (NISS, 1991) to 54.3 per cent in 2012. This amounted to 1.716 million WOEs, over 99 per cent of which are micro enterprises with fewer than five employees and almost three-quarters have only one employee.

The majority of women entrepreneurs are aged between 25 and 40 years, and have a low level of education. On one hand, these women entrepreneurs are a potential motor for the economy to generate jobs and reduce poverty. On the other hand, multiple obstacles continue to impede their capacity to start and grow businesses in sectors that generate quality jobs. Despite the fact that there have been various efforts by the government, donor agencies and NGOs in empowering women, still women face problems at the community level due to ignorance of their rights, low level of education and limited employment opportunities to mention but a few.

Why women continue to experience problems despite government NGOs and Donor agencies inputs continues to baffle researchers. This study aims, therefore, to address to the anomaly by improving the incomes of women entrepreneurs through of a community managed savings and loan association. As depicted by the conducted participatory Community Needs Assessment, small scale women entrepreneurs are facing limited access to loans that would be used to finance and expand their business. They also lack basic skills in entrepreneurship, financial management, record keeping and they have limited exposure and business experience. Through the same study, we noted that there was limited access to loans from banks like NMB and CRDB, which are available in the area. It was very difficult for small entrepreneurs who operate informally to access loans as they require collaterals like surveyed land, business license and immovable properties.

The community agreed to establish a community managed savings and credit association in Kilimahewa village to address some challenges notably limited access to loans to finance their businesses. Through this association, the community would address other challenges like skills gap in entrepreneurship, record keeping, business management and marketing.

## Project Description

The project is known as ‘increasing women access to financial credit: The case of Upendo na Amani Village Community Bank in Kilimahewa Village at Nachingwea Ward in Ruangwa District’, which was implemented by a group of twenty (20) women entrepreneurs who voluntarily agreed to join hands to establish a savings and credit association through which they will access soft loans at a reasonable interest. The main purpose of the project was to mobilize simple savings and provide soft loan facilities to members who are women entrepreneurs who find it very difficult to access formal financial services from the banks.

Apart from savings and loans, through this arrangement, members contribute small amount of money which act as self-insurance to members who get it back as a grant in case of any distress. The cycle of savings and lending activities will proceed for 12 months from May 2020 to April 2021 after which the accumulated savings and interests will be shared proportionally according to the amount saved by each member throughout the year. Each member has the passbook which is used to record her savings and loan payment.

The established association has a written constitution which is signed by each member to show agreement to the articles governing them. The constitution articulates how the association will be governed, conflict resolution, disciplinary procedures in case of misconduct, specifies how savings will be done and how loans will be accessed and the interest rate to be charged. There is management committee with five members; namely, Chairperson, Record keeper (secretary), cash box keeper (cashier), and two money counters. The committee members were elected by the general assembly comprising of all 20 members, each member having one vote.

The core activity of this association is to make financial savings through share purchase and provision of soft loans which are proportional to individual member’s savings. The member can buy between 1 and 5 shares for each meeting and the value of one share is TZS 10,000 to allow the poorest member to afford at least buying one share per meeting. In addition, TZS 5,000 is deposited in the social insurance fund that is always used to support the member in case of any social distress as specified in the constitution. Each member has equal right to borrow the amount of money which is equivalent to three times of her savings. The loan is returned with the interest of 10% in six months but in case the loan is not paid within the prescribed time, about 5% of the balance is charged per month.

General supervision of the project was done by the group leaders who were elected as per group constitution. The host organization, CED student and the village government provided overall group guidance and project leadership and management. Ruangwa District Council as a major stakeholder in this project supported the project by providing the community development officer and trade officer who coached them on VICOBA formation, constitution writing and facilitation of training on business management.  The district authority also facilitated the registration of VICOBA and opening a bank account. The project activities started in February 2020 by conducting a participatory study to identify the needs and alternative project, and it was completed in May 2020 by successfully establishing Upendo na Amani VICOBA whose activities will continue under guidance of the constitution.

### Target Community

The project was implemented by the group of 20 women selected among small scale entrepreneurs in Kilimahewa village in Ruangwa district. This group of 20 women is responsible for day to day operations and management of the project. The village has a total of about 40 women who are engaged in various entrepreneurial activities like tailoring, selling in small shops, food vending and hair dressing.  A total of 33 women participated in the study to provide data regarding the challenges (needs) facing them and the possible interventions. However, only 20 women were selected to form an association by considering their age, willingness to join group and ability to buy shares.

### Stakeholders

Various stakeholders participated to ensure successful implementation of the project. The main stakeholder is Ruangwa District Council, whereby the Community Development Officer and Trade Officer provided various technical supports depending on their specialties. Another important stakeholder is the village government which provided general guidance and organized all correspondences between the group and the experts who are based at the district headquarters. The stakeholder matrix is presented in Table 2.1.

# Table 2.1: Stakeholders Analysis Matrix

| Stakeholder | Stakeholder role | Expectations |
| --- | --- | --- |
| Ruangwa District Council | Provision of technical support through Trade officer and Community Development Officer | The group will follow the provided guidance |
| Kilimahewa Village leadership | Mobilize the community and provide general leadership | The group will respect the village leadership and maintain security and peace |
| ROPA | Hosting and coordination of the project | Provide venue for meetings and trainings, coordinate communication between the association and other stakeholders |
| Members of Upendo na Amani VICOBA | Main implementers of the project | Attend trainings, work together to write constitution and abide to it |
| Community Development Officer | Community mobilization, facilitation of constitution writing, registration and opening bank account | The group will follow procedures for group registration and opening bank account |
| Trade officer | Advising and training group members | The group members will follow trainings and advice |
| Researcher (MCED student) | Conduct research through CNA, training , oversee and document all project progress | Sharing CNA findings with stakeholders, documentation to improve project implementation. Ensure all activities are done and objectives met |

Source: Field data 2020

### Project Goal

The project goal is to increase savings and the ability of Upendo na Amani group members to access soft loans through establishment of VICOBA by the end of May 2020. Realization of the project goal would ensure improved welfare of women through an increased access to loans which they can use as capital to expand and diversify their business hence an increased capacity to afford households’ basic needs including shelter, food, clothing, education and medication.

### Project Objectives

#### General Objective

The project general objective was to improve the income of women entrepreneurs through formation of a community managed savings and loan association by May 2020.

#### Specific Objectives

- To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020

- To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020

- To start VICOBA Operation by May 2020

## Host Organization/CBO Profile

The project was hosted by ROPA which is an umbrella of small entrepreneurship groups in Ruangwa District, Lindi Region. ROPA was established in 2001 and registered in May 2003 with registration number SO.NO.11923 by 61 grassroots groups that are involved mainly in small scale entrepreneurship, policies, lobbying and advocacy environmental management and agriculture and livestock keeping as additional source of income to communities.  Since its formation, ROPA has worked to empower rural communities with various initiatives including training on; financial management and bookkeeping, management of revolving fund, lobbying and advocacy in child rights and responsibilities, entrepreneurship and environmental conservation.

### Vision of the Host Organization

ROPA’S vision is to empower poor communities in Ruangwa District to the level where they will be free, motivated and capable to participate meaningfully and effectively in the implementation of activities that add value to their quality of life politically, socially and economically in the micro and macro sector.

### Mission of the Host Organization

ROPA’s Mission is to support poor communities in Ruangwa District Council with gender perspective socially and economically by providing equal opportunities amongst organized initiatives of the poor, aimed at building their socio –economic base and areas that enhance the quality of their life.

### ROPA Organization Structure

The following is the organization structure of ROPA.

# Figure 2.1: ROPA Organization Structure

Source: ROPA organization profile (2018)

    - SWOT Analysis for ROPA

The purpose of the SWOT analysis is to portray detailed information of the host organization (ROPA) especially the available opportunities which will assist during the implementation of the project. The analysis also portrays strengths of the organization, weaknesses and challenges and how they could affect the project in the course of its implementation. The SWOT for ROPA, which is the host organization for this project was identified and is presented in the following table.

# Table 2.2: SWOT Analysis of the Host Organization

| No. | STRENGTH | WEAKNESS | OPPORTUNITIES | THREATS |
| --- | --- | --- | --- | --- |
| 1. | Strong and committed Leadership | Some committee members are missing | The organization has experience in supervising similar community groups and interventions | High political interference |
| 2 | Availability of permanent office premises | The office has so many users; a lot of activities | There is space for Upendo na Amani to convene their meetings | The office has no electrical power |
| 3 | Clear vision and mission | Some staff are volunteers who can leave at any time | Shared vision with the established VICOBA |  |
| 4 | Good working relationship with the local government | Majority of members are single hence no permanent settlement | The working experience will be used to support the project | Members are from one category (Teachers) |

Source: researcher, (2021)

### The Role of CED Researcher

The major role of CED researcher was to ensure that the project objectives ware achieved and the planned project interventions ware successfully implemented as per work plan. The researcher also did the following;

- Community sensitization on the importance of establishing community-based savings and loans association as a tool to support women entrepreneurs.

- To participate in resource mobilization to facilitate project implementation.

- To link between training facilitators especially community development officer, trade officer and other stakeholders

- To facilitate documentation of project progress

- To facilitate the trainings i.e. entrepreneurships training, financial management and record keeping training.

### The Role of the Host Organization/CBO

- To sensitize the community on group formation project implementation

- To ensure proper administrative activities throughout the project life

- To be a bridge between the community and other stakeholders

- To organize trainings required by the community in implementing the project

- To provide office premises for the group to perform their daily duties

- To ensure the project tools and documents, and products are safely kept

- To collaborate with MCED students to in mobilizing the resources required for project implementation

- To ensure the project sustainability

# CHAPTER THREE

## LITERATURE REVIEW

## 3.1 Introduction

In this chapter we reviewed both theoretical and empirical works on poverty alleviation through SMEs, Microfinance and formation of VICOBA as a means to women empowerment. Under this section, we will also review available literature on government policies related to poverty alleviation through women empowerment and involvement in economic activities.

## 3.2 Definition of Concepts

### 3.2.2 Gender

Gender refers to the roles and responsibilities of men and women that are created in our families, our societies and our cultures (UNESCO, 2003). The concept of gender also includes the expectations held about the characteristics, aptitudes and likely behaviour of both women and men (femininity and masculinity). Gender roles and expectations are learned. They can change over time and they vary within and between cultures.  According to UNESCO (2003) systems of social differentiation such as political status, class, ethnicity, physical and mental disability, age and more, modify gender roles.

### 3.2.3 Empowerment

According to the (International encyclopaedia, 1999) power means having the capacity and the means to direct one's life toward desired social, political and economic goals or status. Power means control over material assets, intellectual resource and ideology. Therefore, in simple words, empowerment is giving power. Power is the keyword of the term empowerment According to (Boserup, 1970) women empowerment enables women to take control of their own lives, set their own agenda, organize to help each other and make demands on the state for support and on the society itself for change’

### 3.2.4 Entrepreneurship

Entrepreneurship can be conceptualized as the discovery of opportunities and the subsequent creation of new economic activities, often via the creation of a new organization (Reynolds, 2005). Entrepreneurial behaviour means the ability to combine innovation, risk-taking and pro activeness (Miller, 1983). Also, Rajesh (2010) defines entrepreneurship as a process of creating something new with value by devoting necessary time and effort, assuming the accompanying financial, social risks and receiving the resulting rewards in terms of money and personal satisfaction and independence.

### 3.2.5 Women Economic Empowerment

Brandshow (2013) demonstrates that the most influential evidence on the importance of women to economic development has come from research used to support the World Bank’s ‘Gender Mainstreaming Strategy’ launched in 2001. That research highlighted that societies that discriminate by gender tend to experience less rapid economic growth and poverty reduction than societies that treat males and females more equally, and that social gender disparities produce economically inefficient outcomes (World Bank 2001a).

The primary pathways through which gender systems affect growth are by influencing the productivity of labour and the locative efficiency of the economy (World Bank 2002). In terms of productivity, for example, if the access of women farmers to productive inputs and human capital were on a par with men’s access, total agricultural output could increase by an estimated 6 to 20 percent. In terms of locative efficiency, while increases in household income are generally associated with reduced child mortality risks, the marginal impact is almost 20 times as large if the income is in the hands of the mother rather than the father (WBGDG 2003). It is important to note that while gender equality will help bring economic growth, economic growth will not necessarily bring gender equality. Advancing gender equality requires strengthening different dimensions of women’s autonomy:

Investment in the human capital, health and education, of women and girls is presented as a key way forward as witnessed by the MDGs. The logic is that ‘educated, healthy women are more able to engage in productive activities, find formal sector employment, earn higher incomes and enjoy greater returns to schooling than are uneducated women…’ (WBGDG 2003: 6). Educated women are more likely to invest in the education of their own children, and they are also more likely to have fewer children. Thus investment in human capital has positive short and longer term/inter-generational outcomes and is good for both productivity gains and lifting unsustainable population growth.

### 3.2.6 Village Community Bank

Village Community Bank (VICOBA) is a community managed banking model that started in West Africa and it is also known as Village Savings and Loan model. In Tanzania, the model was introduced by CARE International in Zanzibar and later spread in Tanzania Mainland where it was adopted and modified by Social Economic Development Initiative of Tanzania (SEDIT) in 2002 as VICOBA. The model is also known as Village Savings and Loan Associations (VSLAs) and they have been useful in poverty alleviation. In Asia, the model was useful in Bangladesh where the rural poor access credits through the Grameen Bank. In Tanzania like other African countries, VICOBA model has spread due to failure of Microfinance institutions to reach people especially in villages who need capital and credits to finance their Income Generating Activities.

### 3.2.7 Development

Development is defined as a process of improving the quality of all humans’ life in capacities by raising people’s level of living, self-esteem, and freedom (Todaro, 2012).

3.2.8 Microfinance

Microfinance is defined by (Robinson, 1998) as a development tool that grants or provides financial services and products like small loans, savings, micro-leasing, micro insurance and money transfer to assist the exceptionally poor in expanding or developing business.

## 3.3 Theoretical Literature Review

For the purpose of this report and by considering that our community is a group of women who are also entrepreneurs, we were guided by the Sociological theory of entrepreneurship. According to Landstrom (1998), the sociological theory of entrepreneurship focuses on the social context or the society in which entrepreneurial activities take place. As asserted by Reynolds (1991), there are four social contexts that relate to entrepreneurial opportunities. The first one is social networks where the emphasis is put on building social relationships and bonds that promote trust and faith with the people.

The second context involves analyzing the life situations, characteristic and background of individuals who have decided to become entrepreneurs. The third context is ethnic identification which puts emphasis on one’s sociological background as one of the decisive “push” factors to become or not to become an entrepreneur. The fourth and last social context is called population ecology which considers environmental factors as important factors for business to survive. The environmental factors referred to under this context include the political system, religious system, the government policies, customers, employees and competitors.

### 3.4 Empirical Literature Review

### 3.4.1 Women Entrepreneurship and Accessibility to Financial Credits

Makhlouf (2013) identified that the growth and success of women-owned businesses is one of the most profound changes in the business world today. He continued to assert that although women are an emerging big market force, many businesswomen are facing a lot of challenges in accessing credit to finance their business. Lack of access to financial credits is mentioned as one of constraints for women entrepreneurs. Despite challenges, women business owners are very interested in accessing credits and long term capital for their business growth needs. According to the Global Partnership for Financial Inclusion (GPFI) and IFC, women typically run small and informal firms in lower value-added sectors, which offer smaller returns to creditors, thus impeding their access to finance. Although microcredit can be useful in expanding financing options for the poor, especially women, it is not enough to meet the needs of SMEs. For women entrepreneurs to expand their businesses their financing needs exceed micro-credit ceilings.

In India, for instance, women remain inadequately covered by the banking system as they own only 27 per cent of the total deposit accounts in scheduled commercial banks and 14.3 per cent of the total value of deposits. Although the financing needs of women and women-owned enterprises are not radically different from the needs of men and men owned enterprises, women’s financial exclusion is higher due to a combination of factors (Das Barwa, 2015) Women’s status is entrenched in the patriarchal system, which confines them to a marginalized position at the bottom of the economic, social and political hierarchy. This leads financial institutions to exclude women from accessing finance as they are considered high-risk clients with limited resources to pay back the loans. Women’s low level of financial literacy combined with their time constraints prevent them from understanding the intricate process of applying for loans and having savings accounts. Consequently, they are trapped in the vicious circle of low income, low savings, poor access to credit and low returns on income (Das, Barwa, 2015).

### 3.4.2 Efforts by Tanzania to Empower Women

Fighting against poverty has been a permanent agenda in the history of post independent Tanzania, which has adopted a number of strategies to eradicate poverty and increase economic growth. The strategies include the Tanzania Development Vision 2025 of 1999, the National Poverty Eradication Strategy (NPES) of 1998 and Poverty Reduction Strategy Paper (PRSP) of 2000; all of which set the goal of eradicating abject poverty by 2025. The review of PRSP guided formulation of the National Strategy for Growth and Reduction of Poverty (NSGRP or MKUKUTA). The second generation of PRS brought a strong agenda, aiming at sustaining broad-based growth whilst emphasizing equity and good governance. Other current poverty reduction initiatives include the investment in human capital by providing free basic education to all, Conditional Cash Transfer to poor households implemented by TASAF, employment creation through promotion of industrial sector, improving the transport infrastructure, communication and agricultural development.

## 3.5 Policy Review

### 3.5.1 Women Development Policy1992

The Women Development Policy (URT, 1992) insists on the provision of more education and training opportunities to women in order to increase their skills and production abilities. The policy highlights the importance of training about business and administration to be provided to women, member of wards, district and village development councils. The policy calls for specific body of coordination, planning and evaluating implementation of women development plans to be established. Therefore, establishment of Upendo na Amani VICOBA is one of the policy implementation strategies which empower women to participate in bringing about their development.

### 3.5.2 Community Development Policy 1996

The government of the United Republic of Tanzania introduced the Community Development Policy (URT, 1996) to enable Tanzanians to bring about their own development by using locally available resources to improve production and increase income and build a better life through self-reliance. It emphasizes the involvement of the community, especially through formal groups and associations as the major way to eradicate poverty. Establishment of Upendo na Amani VICOBA applied the same approach whereby the community of entrepreneurs has formed a group of twenty women who decided to work together for the purpose of improving financial savings and access to soft loans.

# 3.5.3 National Economic Empowerment Policy

The National Economic Empowerment Policy (URT, 2004) is closely linked with the community development policy. The policy intends to address all economic empowerment requirements of the individual citizens of Tanzania and local companies in which Tanzania citizens hold not less than fifty percent of the shares. The Policy takes on board entrepreneurs, farmers, livestock keepers, fishermen, employees, traders as well as other groups of individuals in various economic activities. It is expected that, by the year 2025, a large segment of the national economy will be owned by Tanzanians. This process will embrace all Tanzanians by availing equal opportunities to all groups to develop them, particularly the rural poor like the members of Upendo na Amani VICOBA in Kilimahewa village who decided to establish a community managed savings and loan association.

### 3.5.4 Tanzania Development Vision 2025

The vision 2025 is a development strategy that was prepared to guide the country in developing herself towards  achieving development characterized by advanced technology, high productivity, modern and efficient transportation and communication infrastructure. The development vision 2025 objectives include achieving standard and quality life for all citizens, good governance, rule of law and building a strong and resilient economy that can effectively withstand global competition (NBS, 2014). The vision 2015 is a roadmap through which the government continues to speed up the economic transformation from low productivity agriculture to a semi-industrialized economy.

## 3.6 Literature Review Summary

The reviewed literature shows that many Tanzanians especially the unemployed women and youth living in the rural areas are still affected by poverty. The contribution of the majority of Tanzanian citizens in the economy remains to be limited by lack of capital, limited business knowledge, experience and skills, inappropriate mindset towards development and challenges associated with access to various opportunities provided in development policies. Other challenges facing the rural women entrepreneurs include limited access to financial credits, lack of reliable markets and inability to penetrate competitive markets for their products. The information obtained in the reviewed literature is not different from that obtained from CNA as presented in the first chapter of this document. The CNA findings also revealed that the women who are trying to enter entrepreneurship activities in Kilimahewa Village in Ruangwa district mainly face capital poverty and they lack access to loans because the bank interest rates are very high for them to afford.

The Government of Tanzania has created various policy frameworks that provide platforms through which all citizens are encouraged to participate in different income generating activities depending on their interest, skills, capital, geographical location and the available opportunities. Upendo na Amani community have decided to use the available opportunity to make an association through which they will be able to make financial savings and access soft loans at a very reasonable interest.

# CHAPTER FOUR

# PROJECT IMPLEMENTATION

## 4.1 Introduction

Project implementation requires harmonization of various activities and coordination of various institutions and stakeholders to ensure the project goals are realized. In this chapter, we will look at the summary of all phases of project implementation including activity planning, project products and outputs analysis, required project resources, responsible persons for each activity, and the duration of time required to accomplish the project activities.

The chapter also presents the project implementation report that highlights all important project activities implemented and the end project results achieved. This chapter is very important as it expresses what has been achieved in the project. This chapter translates the project objectives presented in the second chapter of this document into practicable project activities to produce physical project products and outputs.

## 4.2 Product and Outputs

This project had various outputs including the Community Needs Assessment report, trained group members VICOBA formation and management, entrepreneurship skills, record keeping; obtained tools, written constitution and the registered group.  Currently, the general goal of the project was not assessed because savings and loan provision is at the initial stage such that even repayment has not started. An assessment regarding the rise of income among community members will be done at the end of the cycle in April 2021. In order to achieve the project objectives and outputs, several activities were planned as presented in table 4.1. All project activities have been successfully implemented and outputs achieved as anticipated.

# Table 4.1: Project Outputs and Activities

| OBJECTIVES | OUTPUTS | ACTIVITIES |
| --- | --- | --- |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment report prepared | Conduct CNA (data collection, processing and analysis) |
|  |  | Write CNA report |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members |
|  |  | Make preparations for training (training materials and logistics) |
|  |  | Conduct three days training on the importance of savings, loans , entrepreneurship, record keeping and financial management |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 | Constitution prepared and registration certificate obtained | Conduct a one day preliminary meeting to agree on articles and election of leaders |
|  |  | Write, print, bind and sign the constitution |
|  |  | Submit request to DED for registration |
|  | Open Savings Bank Account | Fundraise to open bank account |
|  |  | Submit application package to the bank to open Bank account |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Purchase pass books, cash box, padlocks, ledgers and stamps |
|  | VICOBA operations started | Obtain office |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution |

Source: Researcher, 2020

## Project Products

The major project products include CNA report, training report on VICOBA establishment and management, purchased tools, group constitution, group registration certificate and a document bearing group bank details.

## 4.3 Project Planning

Project planning is the main component in the project development process. This component comprised of identifying the project objectives and outputs, scheduling the activities in logical sequence, identifying responsible persons for each activity, identifying resources needed and budget required. Planning tools including the project Implementation Plan, project budget, Logical Framework and Ghannt chart were prepared.

### 4.3.1 Implementation Plan

Implementation plan was prepared to guide implementation of the project. The plan indicated the activities to be executed, required resources, time frame and responsible person. Implementation of activities started timely by involving and consulting various stakeholders, especially the Community Development Officer on VICOBA formation and group dynamics; and trade officer for technical inputs regarding entrepreneurship skills. Execution of the project activities followed the plan shown in Table 4.2 and the Logic Framework shown in Table 4.3 respectively.

# Table 4.2: Project Implementation Plan

| Objectives | Outputs | Activities | Project Months | Resources |
| --- | --- | --- | --- | --- |
|  |  |  | Feb 2020 | Mar 2020 | Apr 2020 | May 2020 |  |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment (CNA) Report | Conduct CNA (data collection, processing and analysis) |  |  |  |  | Personnel, Stationery and transport |
|  |  | Write CNA report |  |  |  |  | Stationery, time, personnel |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting |  |  |  |  | Stationery, Public address system |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members |  |  |  |  | Time |
|  |  | Make preparations for training (training materials and logistics) |  |  |  |  | Human, time, funds |
|  |  | Conduct three days training on the importance of savings, loans , entrepreneurship, record keeping and financial management |  |  |  |  | Stationery, |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by December 2019 | Constitution prepared and registration certificate obtained | Write and sign constitution after approving the articles |  |  |  |  | Stationery, Meals |
|  |  | Write, print, bind and sign the constitution |  |  |  |  | Transport costs, meals, personnel |
|  |  | Submit application package to for registration |  |  |  |  | Personnel, time, meals, transport costs |
|  | Open Savings Bank Account | Fundraise to open bank account |  |  |  |  | Meals, time, personel |
|  |  | Submit application package to the bank to open Bank account |  |  |  |  | Funds to open bank account |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Mobilize resources for tools acquisition |  |  |  |  | Money, time, personnel |
|  |  | Purchase tools/ stationeries |  |  |  |  | Money, time, personell |
|  | VICOBA Operations started | Obtain office |  |  |  |  | Human, Funds |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution |  |  |  |  | Human, time |

Source: Researcher, 2020

# Table 4.3: The Logical Framework of the Project

| Hierarchy of Objectives | Objectively Verifiable Indicators (OVIs) | Means of verification (MOV) | Assumptions |
| --- | --- | --- | --- |
| Goal: To increase savings and the ability of Upendo na Amani group members to access soft loans through establishment of VICOBA by the end of May 2020. | The amount of savings The number of group members accessing loans The amount of loans issued to members | Individual member’s passbook Ledger book Bank statement VICOBA performance reports | Savings and loans records will be kept accurately Members will abide to the constitution in buying shares, accessing loans and repaying back |
| Objective 1: To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 |
| Output 1: Community Needs Assessment (CNA) Report | Community Needs and appropriate project identified | CNA report | The study will follow all procedures The community will provide genuine answers |
| Output 2: The Community is aware on the need to establish VICOBA | The community members readiness to establish VICOBA | Community awareness report | All members will attend and follow the awareness content |
| Output 3. 20 Upendo na Amani Group members trained on VICOBA establishment and management | Group member’s understanding of the procedure to establish and manage VICOBA | Training report | All 20 members will attend and follow the training content |
| Activities under outputs of objective 1 |
| 1.1 Conduct can | Community Needs and suitable projects identified | CNA report | The study will follow all procedures The community will provide genuine answers |
| 1.2 Write CNA report |  |  |  |
| 2.1Conduct community awareness meeting | 15 community members attended training | Awareness report List of attendance to the awareness meeting | The participants will attend and follow instructions |
| 3.1Identify 20 VICOBA members | 20 VICOBA members identified | List of identified members | 20 persons will be willing to join the group |
| 3.2Make preparations for training (training materials and logistics) | Training materials prepared and all logistics completed | Copies of training materials, training schedule and stationeries | All preparations will be completed timely |
| 3.3 Conduct three days training to 20 Upendo na Amani Group members on VICOBA establishment and management | 20 Upendo na Amani Group members have necessary knowledge on VICOBA establishment and management | Training report | The participants will attend and follow instructions |
| Objective 2: To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 |
| Output 1: Constitution prepared and registration certificate obtained | VICOBA registration is complete | Copy of constitution Registration Certificate | Registration process will not delay at any stage |
| Output 2: Savings Bank Account Opened | Bank Account has been opened | Operational bank account | Opening a bank account will not delay |
| Activities under outputs of objective 2 |
| 1.1 Conduct a one day preliminary meeting to agree on articles and election of leaders | Meeting conducted, agreed on articles and leaders selected | Minutes of the meeting | All members will attend the meeting and provide their constructive views |
| 1.2 Write, print, bind and sign the constitution | Constitution written, printed and signed | Copies of printed and signed constitution | Constitution preparation will consider the views of members and guidelines from the government |
| 1.3 Submit request to DED for registration and provision of certificate | Request of VICOBA registration submitted to DED and certificate obtained | Registration certificate | The registration procedure will not take long |
| 2.1 Fundraise to open bank account | Funds obtained to open bank account | Cash and list of contributors | People are willing to contribute |
| 2.2 Submit application package to the bank to open Bank account | Bank account opened | Bank account details | Opening a bank account will not take long |
| Objective 3: To start VICOBA Operation by May 2020 |
| Output 1: Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Tools purchased | List of procured tools and receipts | Tools will be purchased as per specifications |
| Output 2: VICOBA operations started | Operations started | Meetings conducted as per constitution | Meetings will be used to buy and sell shares, issue loans and repay loans as per constitution |
| Activities under outputs of objective 3 |
| 1.1 Mobilize funds for purchasing tools | Funds obtained | Cash and list of contributors | People are willing to contribute |
| 1.2 Purchase pass books, cash box, padlocks, ledgers and stamps | Tools purchased | List and receipts of purchased tools Purchased tools can be physically observed | Tools will be procured as per specifications |
| 2.1 Obtain office | Office obtained | Agreement | A suitable office will be available |
| 2.2 Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution | Meetings conducted for selling and buying shares, provision of loans and loan repayment | Pass books, ledger books and performance reports | Meetings will be conducted as mentioned in the constitution |

# Source: researcher, (2021)

### 4.3.2 Inputs

Various inputs were mobilized and used during implementation of this project. These include human resource, financial resources and material inputs and time. Human resources basically included Village leaders, community development Officer, trade officer, ROPA, MCED student and the community members who participated fully during project implementation. Financial inputs are major resources which facilitated capacity building, transportation, and acquisition of project materials, group registration and opening bank account.

The details on the financial inputs are provided in section 4.4.4 of this document. Material inputs include time, office premises which was provided by the host organization and the vehicle provided by LGA to facilitate transport to the field. The MCED student provided technical inputs to ensure community participation during needs identification, selection of a project as well as project planning, management and documentation.

### 4.3.3 Staffing Pattern

The project is implemented by a group of 20 women living at Kilimahewa village. The activities were implemented under direct supervision of group leaders who got directives from village council leaders, ROPA, Community Development Officer, trade officer and CED student. The group was under the leadership of elected chairperson, secretary, and treasurer.  Management and coordination of project activities was done by the ROPA which is the host organization. The project has no paid staff because the nature of business does not need salaried workers.

# Table 4.4: Staff Pattern

| Position | Roles |
| --- | --- |
| ROPA Leaders | Overall management and coordination of activities and correspondences |
| Chairperson | Supervision of other group members, call for meetings and ensure all activities are implemented by considering the guidelines provided by Village leaders and other stakeholders |
| Secretary | Keep group records and project documents, writing meeting minutes |
| Treasurer | Keep records on income and expenditure; Collect and bank money from members contributions and other sources |
| Group members | Participation in all project activities for their own benefit |

Source: researcher, 2020

### 4.3.4 Project Budget

The project budget was TZS 1,985,000 that was mobilized from various contributors including the host organization, the Ward Councillor, CED student and beneficiaries. Estimation of project costs was done in collaboration between MCED student, community leaders, community development officer and the project committee members who were chosen from the host organization. The developed project budget is indicated in Table 4.5.

# Table 4.5: Project Budget

| Objectives | Outputs | Activities | Resources | Quantity | Unit Cost | Total |
| --- | --- | --- | --- | --- | --- | --- |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment report prepared | Conduct CNA (data collection, processing and analysis) | Personnel | 4persons | 25,000 | 100,000 |
|  |  | Write CNA report | Stationery | Lump sum | 50,000 | 50,000 |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting | Transport | 2people | 15,000 | 30,000 |
|  |  |  | PA System | Lump sum | 50,000 | 50,000 |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members | Human | 0 | 0 | 0 |
|  |  | Make preparations for training (training materials and logistics) | Training materials | Lump Sum | 45,000 | 45,000 |
|  |  |  | Transport | 1 person | 20,000 | 20,000 |
|  |  | Conduct three days training on the importance of savings, loans , entrepreneurship, record keeping and financial management | Facilitators | 3 persons | 30,000 | 90,000 |
|  |  |  | Meals | 25persons | 10,000 per person per day for 3days | 750,000 |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 | Constitution prepared and registration certificate obtained | Conduct a one day preliminary meeting to agree on articles and election of leaders | Facilitators | 1 persons | 30,000 | 30,000 |
|  |  |  | Meals | 25 persons | 10,000 | 250,000 |
|  |  | Write, print, bind and sign the constitution | Persons | 2 persons for 5 days | 30,000 | 300,000 |
|  |  | Submit request to DED for registration | Transport | 2 persons | 15,000 | 30,000 |
|  | Open Savings Bank Account | Fundraise to open bank account | Funds | Lump sum | 50,000 | 50,000 |
|  |  | Submit application package to the bank to open Bank account | Transport | 2 persons | 15,000 | 30,000 |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Purchase pass books, cash box, padlocks, ledgers and stamps | Pass book | 20 | 3,000 | 60,000 |
|  |  |  | Ledger | 1 | 10,000 | 10,000 |
|  |  |  | Cashbox | 1 | 50,000 | 50,000 |
|  |  |  | Padlocks | 3 | 10,000 | 30,000 |
|  |  |  | Ink | 1 | 5000 | 5000 |
|  |  |  | Stamp | 1 | 5000 | 5000 |
|  | VICOBA operations started | Obtain office | Room | 0 | 0 | 0 |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution | 0 | 0 | 0 | 0 |
| TOTAL | 1,985,000 |

Source:  Researcher, 2020

## 4.3.3 Project Implementation

### 4.3.3.1 Project Implementation Report

The implementation of the project started in February 2020 as illustrated in the project implementation plan, and it clearly followed the sequenced order of activities that resulted into realization of project objectives. The MCED student in collaboration with the community development officer, trade officer and host organization, participated in all stages to ensure that there is smooth take off, and regular monitoring of all project activities. Implementation of project activities involved all identified stakeholders, each performing specified tasks. Implementation started by conducting CNA through which community needs were identified, project selected and the community

to implement the project identified. There followed capacity building to the community on how to effectively implement the project. Thereafter, required tools were identified and bought.

# Figure 3.1: CED Researcher with Project Beneficiaries as they Proceed with Share Purchase and Loans Taking

The formed VICOBA namely Upendo na Amani was registered with registration number HWR/MJ/UVK/2020/635with a bank account number 71110029964 held at NMB Ruangwa Branch. After formalization of the group, the community has a vision of diversifying in other projects in future. The detailed analysis of implemented activities and the current status are shown in the Table 4.6.

# Figure 3.2: CED Researcher with Beneficiaries during Project Implementation

# Table 4.6: Project Implementation Report

| Objectives | Outputs | Activities | Implementation Status | Reason for Deviation |
| --- | --- | --- | --- | --- |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment report prepared | Conduct CNA (data collection, processing and analysis) | CNA completed | NA |
|  |  | Write CNA report | CNA report written | NA |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting | Community awareness meeting conducted | NA |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members | 20 Members identified | NA |
|  |  | Make preparations for training (training materials and logistics) | Training preparations completed successfully | NA |
|  |  | Conduct three days training on the importance of savings, loans, entrepreneurship, record keeping and financial management | Training successfully done, all topics covered | NA |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 | Constitution prepared and registration certificate obtained | Conduct a one day preliminary meeting to agree on articles and election of leaders | Meeting conducted, articles agreed upon and leaders selected | NA |
|  |  | Write, print, bind and sign the constitution | Constitution in place | NA |
|  |  | Submit request to DED for registration | Registration completed and Certificate obtained | NA |
|  | Open Savings Bank Account | Fundraise to open bank account | TZS 50,000 collected for opening bank account | NA |
|  |  | Submit application package to the bank to open Bank account | Bank Account opened | NA |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Purchase pass books, cash box, padlocks, ledgers and stamps | Tools purchased as per requirements | NA |
|  | VICOBA operations started | Obtain office | Office obtained | NA |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution | One meeting has been conducted. Shares were bought and loans issued. However, no repayment was done yet | No repayment was realized because the repayment cycle is six months. |

# 4.3.3.2 Project Implementation Ghannt Chat

This section covers the project implementation report where details on how the activities were carried out and the project implementation Ghantt which indicates time used in project activities implementation.

# Table 4.7: Project Implementation Ghannt Chat

| OBJECTIVES | OUTPUTS | ACTIVITIES | FEB 2020 | MAR 2020 | APR 2020 | MAY 2020 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment report prepared | Conduct CNA (data collection, processing and analysis) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Write CNA report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Make preparations for training (training materials and logistics) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conduct three days training on the importance of savings, loans, entrepreneurship, record keeping and financial management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 | Constitution prepared and registration certificate obtained | Conduct a one day preliminary meeting to agree on articles and election of leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Write, print, bind and sign the constitution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Submit request to DED for registration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Open Savings Bank Account | Fundraise to open bank account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Submit application package to the bank to open Bank account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Fundraise for buying tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Purchase pass books, cash box, padlocks, ledgers and stamps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | VICOBA operations started | Obtain office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Source: researcher, 2020

# CHAPTER FIVE

# PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

## 5.1 Introduction

According to Drucker (2006), participatory monitoring and evaluation is a process of involving all identified stakeholders of the project in all implementation stages including project planning, daily implementation of activities and finally assessment of the project towards achieving the goal. Involving the stakeholders makes them own the project fully and increases the chance of sustainability. This chapter provides discussion on participatory monitoring, evaluation and sustainability. It looks at how the community and various stakeholders used resources to facilitate day to day implementation of project activities towards achieving the desired project objectives. In this chapter we will also look at how the project has succeeded to achieve the expected objectives and analyze durability and continuity of the project.

## 5.2 Participatory Monitoring

Monitoring is the process of regularly collecting information concerning the daily progress of project (Schmidt, 2009). The collected information is normally used to assess the prevailing situation and discover trends and patterns towards achieving the project objectives. The project managers use the collected data to identify challenges and find solutions, keep project activities on schedule and measure progress towards realization of the project objectives. The information can further be used to inform decisions on human, financial and material resources and formulating or revising goals and objectives.  For the case of establishment of Upendo na Amani VICOBA, the community members participated fully from inception of the idea, group formation and registration, opening bank account and daily implementation of activities in order to realize the predetermined objectives. Leaders from host organization, CED student, Community Development Officer and trade officer took part in daily monitoring of activities including awareness creation, capacity building, tools acquisition, writing constitution, formal registration of VICOBA and finally facilitating initial meetings to supervise buying shares, provision of loans and loan repayment.

### 5.2.1 Monitoring Information System

The collected data were analyzed to generate analytical information which is used by stakeholders in making various decisions. Information was collected mainly through observation and meeting discussions with the community during regular field visits. Records were kept by MCED student and the community secretary. The collected data were on whether the activities are implemented as per schedule, inputs are available and if there are gaps and obstacles and the ways to address them.

Some of important information regarding the project included a number of trained community members (members of Upendo na Amani VICOBA), the process of acquiring tools, tools inventory, records on collected funds and how they were spent, stakeholders involved, project activity plan, amount of shares sold, the amount of loans issued and documentation on registration and bank details. Apart from the individual passbooks and ledger to keep financial records, the community has another book kept by the group secretary who is responsible for recording all information on project progress.

# Table 5.1: Monitoring Information System

| SN | Categories of information and activities | Elements to be monitored | Records to be kept | Who is collecting information | Who is the user of information | How to use information | Decision to be made and output to be achieved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Work Plan activities | Implementation of activities as planned, activity schedule and timing, and availability of resources to facilitate implementation of activities | Work plans and their implementation status | CED student and group secretary | Project management team | Identifying the activities to be implemented; identifying the implementation gaps and make decisions | Re-planning, assess resources required and decide on how to access them |
| 2 | Project Cost and expenditure | Financial resources required, how to access them and how income and expenditure records are kept | Income and expenditure ( shares bought by each member, micro insurance, loans issued, repayment of loans and interest) | CED student, group secretary and treasurer | Project management team, CED student and project beneficiaries | Assess adherence to the constitution, project budget and Identifying financial gaps. | Decide on how to adhere to the constitution, budget and how to access more financial resources |
| 3 | Staff and supervision | Number of required staff, qualification and roles | Qualification and performance for each role | Chairperson, Secretary CED student | Project management team, CED student and project beneficiaries | Assess on the performance of roles for each position | Determine the performance gaps and plan how to fix them |
| 4 | Other inputs | Other required inputs which were not planned before | List of required additional inputs | Chairperson Secretary, treasurer and CED student | Project management team and project beneficiaries | Assess the necessity of having emerging inputs and the available alternatives | Plan on how to get the inputs (if they are necessary) use the available inputs effectively |

Source: researcher, 2020

### 5.2.2 Participatory Monitoring Methods

Monitoring allows project implementers and supervisors to record progress of planned activities. In monitoring this project, various methods were used but mostly we used Participatory Rural Appraisal (PRA), Beneficiaries Assessment (BA) and participatory community needs assessment through which the community and other stakeholders shared their knowledge and experience regarding the project management. Regular meetings were conducted for planning and progress monitoring of the project. On call follow-ups were used by Community Development Officer (CDO) and trade officer especially to record progress made during preparation of group constitution that was required for group registration and opening of bank account.

### 5.2.3 Participatory Monitoring Plan

The monitoring plan was prepared in a participatory manner to guide the project monitoring exercise. It guides the stakeholders on the nature of information to collect, the indicators, the tools to use and the source of data in relation to the outputs and project objectives. It further specifies the timeframe within which monitoring will be done and the responsible persons to do the monitoring.

# Table 5.2: Project Monitoring Plan

| Objectives | Outputs | Activities | Indicators | Data Source | Methods/Tools | Responsible | Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment report prepared | Conduct CNA (data collection, processing and analysis) | Community Needs Identified | CNA report | Review CNA report | CED student | February 2020 |
|  |  | Write CNA report | Community Needs Identified | CNA report | Review CNA report | CED student | February 2020 |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting | List of attendants | Community awareness report | Review Community awareness report | CED student, CDO, Trade officer, ROPA | March 2020 |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members | Number of members identified | List of identified members | Review of training report | CED student, CDO, Trade officer, ROPA | March 2020 |
|  |  | Make preparations for training (training materials and logistics) | Training manuals, stationery, venue | list of stationery and training manuals | Observation | CED student, CDO, Trade officer, ROPA | March 2020 |
|  |  | Conduct three days training on the importance of savings, loans, entrepreneurship, record keeping and financial management | Number of attendants Covered topics | List of attendants, | Participant Observation | CED student, CDO, Trade officer, ROPA | March 2020 |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 | Constitution prepared and registration certificate obtained | Conduct a one day preliminary meeting to agree on articles and election of leaders | Number of attendants and agenda | Minutes of the meeting | Participant observation; Review of minutes | CED student, CDO, Trade officer, ROPA | April 2020 |
|  |  | Write, print, bind and sign the constitution | Printed constitution | Observation | Observation | CED student, CDO, Trade officer, ROPA | April 2020 |
|  |  | Submit request to DED for registration | Registration certificate | Observation | Observation | CED student, CDO, Trade officer, ROPA | April 2020 |
|  | Open Savings Bank Account | Fundraise to open bank account | Amount of money contributed | List of contributors | Observation; list of contributors | CED student, CDO, Trade officer, ROPA | April 2020 |
|  |  | Submit application package to the bank to open Bank account | Bank account details | Bank details document | Observation | CED student, CDO, Trade officer, ROPA | April 2020 |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Fundraise for buying tools | Amount of money contributed | List of contributors | Observation; list of contributors | CED student, ROPA | May 2020 |
|  |  | Purchase pass books, cash box, padlocks, ledgers and stamps | Physical verification of tools | List of purchased tools | Observation | CED student, VICOBA leaders | May 2020 |
|  | VICOBA operations started | Obtain office | Physical verification of office | Agreement | Observation, review of agreement | CED student, ROPA | May 2020 |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution | Number of shares sold (savings) Amount of money given as loans Amount of money paid as loan repayment and interest | Passbooks, ledger | Participant observation, review of passbooks and ledger | CED student, VICOBA leaders, CDO | May 2020 |

Source: researcher, 2020

## 5.3 Participatory Evaluation

Participatory Project Evaluation is a systematic process of involving the community and stakeholders in investigating the significance or value of the project and determines whether the predetermined goal and objectives have been achieved. Through evaluation, the stakeholders get to know what was actually achieved; what was not achieved and why; what was learned; and what else can be improved in order to enhance future performance. Evaluation forms part of management process consisting of planning, implementation and evaluation, each following the other in unbroken cycle until completion of the project and starting the other.

Evaluation is normally done with reference to the indicators which measure the achievement or failure of the project. For the case of establishment of VICOBA, the project beneficiaries were involved in conducting participatory community needs assessment and identification of the project. While all objectives have been achieved, final evaluation will be done later after several meetings of buying shares, provision of loans, loan and interest payment to assess the achievement of the project goal.

### 5.3.1 Performance Indicators

Performance indicators for establishing Upendo na Amani VICOBA were categorized into input indicators, output indicators and impact indicators and they are qualitative and quantitative. Input indicators include time, amount of money spent in training, buying tools and opening a bank account. The output indicators include number of community members trained, and the tools purchased, the written constitution, the registration certificate and bank details.  Output indicators also include the amount of money saved and the amount of loans taken by the association members.  Impact indicator for this project is the expansion and diversification of entrepreneurial ventures and improved life standard of the association members as a result of improved income which will be obtained from savings and acquisition of soft loans. The summary of performance indicators is presented in Table 5.3.

# Table 5.3: Project Performance Indicators

| Objectives | Outputs | Activities | Inputs Required | Performance Indicators |
| --- | --- | --- | --- | --- |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment report prepared | Conduct CNA (data collection, processing and analysis) | Transport, stationery, human resources, time, | Community Needs identified CNA report |
|  |  | Write CNA report | Stationery, time, human | CNA report |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting | PA system, awareness materials, human resources | Community awareness report and willingness to join VICOBA |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members | Time, | List of identified members |
|  |  | Make preparations for training (training materials and logistics) | Training preparations completed successfully | Availability of training materials, venue and meals |
|  |  | Conduct three days training on the importance of savings, loans, entrepreneurship, record keeping and financial management | Time, human resources, training materials, venue, meals, | List of attendants, training report, covered topics, participants’ understanding on the covered topics |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 | Constitution prepared and registration certificate obtained | Conduct a one day preliminary meeting to agree on articles and election of leaders | Time, human resource, meals | Meeting minutes |
|  |  | Write, print, bind and sign the constitution | Time, human, meals, stationery | Printed and signed Constitution |
|  |  | Submit request to DED for registration | Transport costs, time, human resources | Registration certificate |
|  | Open Savings Bank Account | Fundraise to open bank account | Time, human | Cash amounting to TZS 50,000 |
|  |  | Submit application package to the bank to open Bank account | Transport costs, time, cash for opening bank account | Bank account details |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Purchase pass books, cash box, padlocks, ledgers and stamps | Cash, time, human | Availability of purchased tools |
|  | VICOBA operations started | Obtain office | Time, cash | Availability of office |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution | Time, human | Records regarding sold shares, loans given, loan paid, interests paid |

Source: researcher, 2020

### 5.3.2 Participatory Evaluation Methods

This project had three objectives; namely, to train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020; to facilitate preparation of constitution, group registration and opening Bank account by April 2020; and to start VICOBA operations by May 2020. All planned project activities for all objectives have been timely completed as per schedule.  As noted earlier on, final evaluation of this project has not been done because the major activities have just started. It is therefore anticipated that the evaluation will be done at a later stage after several rounds of savings and taking loans to assess the progress towards achieving the wider project goal.

It is anticipated that the project evaluation will be done by the beneficiaries in collaboration with other stakeholders by using Beneficiaries Assessment (BA) approach and Participatory Rural Appraisal (PRA). A checklist with predetermined questions will be used to interrogate the direct beneficiaries so that they can give their views on how the project has achieved the outputs, objectives, and goal and sustainability factors.

### 5.3.3 Project Evaluation Summary

The project evaluation summary provides achievement of the project based on the predetermined goal, objectives, outputs, activities performance indicators and expected outcome and finally the project impact. So far, the implementation of all project activities has been completed and almost all objectives have been achieved. Generally, for the completed activities, we have witnessed strong commitment of the project beneficiaries and stakeholders from the project inception up to the stage of activity planning and implementation. All project activities were implemented and finished as per project implementation plan.  The last evaluation which will be done later will provide a clear assessment on the extent to which the goal has been achieved.

# Table 5.4: Project Evaluation Summary

| Objectives | Outputs | Activities | Performance Indicators | Expected Outcome | Actual Outcome | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| To train 20 Upendo na Amani group members on VICOBA establishment and management by the end of March 2020 | Community Needs Assessment report prepared | Conduct CNA (data collection, processing and analysis) | Community Needs identified CNA report | The community Needs Identified | The community needs were identified | Completed |
|  |  | Write CNA report | CNA report | The community Needs recorded | Community Needs were recorded and project identified | Completed |
|  | The Community is aware on the need to establish VICOBA | Conduct community awareness meeting | Community awareness report and willingness to join VICOBA | Community awareness meeting conducted | Community awareness meeting conducted | Completed |
|  | 20 Upendo na Amani Group members trained on VICOBA establishment and management | Identify 20 VICOBA members | List of identified members | 20 VICOBA members identified | 20 VICOBA members identified | Completed |
|  |  | Make preparations for training (training materials and logistics) | Availability of training materials, venue and meals | Training materials, Venue and facilitator obtained | Training materials, Venue and facilitator obtained | Completed |
|  |  | Conduct three days training on the importance of savings, loans, entrepreneurship, record keeping and financial management | List of attendants, training report, covered topics, participants’ understanding on the covered topics | 20 members of Upendo na Amani group aware of savings, loans, entrepreneurship, record keeping and financial management | 20 members of Upendo na Amani group aware of savings, loans, entrepreneurship, record keeping and financial management | Completed |
| To facilitate preparation of constitution, VICOBA registration and opening Bank account by April 2020 | Constitution prepared and registration certificate obtained | Conduct a one day preliminary meeting to agree on articles and election of leaders | Meeting minutes | Meeting conducted | Meeting conducted | Completed |
|  |  | Write, print, bind and sign the constitution | Printed and signed Constitution | Constitution in place | Constitution in place | Completed |
|  |  | Submit request to DED for registration | Registration certificate | VICOBA registered by DED | VICOBA registered by DED and certificate in place | completed |
|  | Open Savings Bank Account | Fundraise to open bank account | Cash amounting to TZS 50,000 | TZS 50,000 collected | TZS 50,000 collected | Completed |
|  |  | Submit application package to the bank to open Bank account | Bank account details | Bank account opened | Bank account opened | Completed |
| To start VICOBA Operation by May 2020 | Tools (cash box, pass books, padlocks, stamps and ledger books purchased | Purchase pass books, cash box, padlocks, ledgers and stamps | Availability of purchased tools | Pass books, cash box, padlocks, ledgers and stamps purchased | Pass books, cash box, padlocks, ledgers and stamps purchased | Completed |
|  | VICOBA operations started | Obtain office | Availability of office | Office available | Office available | completed |
|  |  | Conduct meetings for selling and buying shares, issuance of loans and loan repayment as agreed in the constitution | Records regarding sold shares, loans given, loan paid, interests paid | Meetings for selling and buying shares, issuance of loans and loan repayment started | Meetings for selling and buying shares, issuance of loans and loan repayment started | Continuous |

Source: researcher, 2020

## 5.3.4 Lessons Learned During Project Implementation

Lessons learned include the knowledge and experience gained from the process of implementing the project. Collection of lessons included both positive and negative experience so that we can replicate the positive and avoid repeating the negative ones. During implementation of this project, we learned the following lessons:

- The community, particularly women, know very well their challenges and the available opportunities towards overcoming them. There is a need of having a skilled person who can guide and mobilize them towards taking action to use the available opportunities

and solve the challenges.

- There are a lot of constraints for the rural community to access financial services especially loans from the commercial banks and other Microfinance Institutions. Establishment of self managed community based savings and loans associations would reduce that challenge.

- The government has put in place procedures to form and register CBOs dealing with various income generating activities. The challenge is that these procedures are not well known to the community. There is a need for the government to cascade that knowledge to the community so that they can use that knowledge to access such services and use them in reducing poverty.

- The community need to be provided with entrepreneurship skills in order to improve their business operations and make significant contribution in improving their personal development and contribute in the general economy of the country.

## 5.4 Project Sustainability

Project sustainability is assessed by looking at the factors that will make stakeholders of the project maintain its operations and benefits to beneficiaries even after withdrawal of external funders.  Assessment of project sustainability elements considers the strategies in place and ability of the community to proceed running the project by using internal resources. In order to ensure the project is sustainable, the CED student in collaboration with the host organization and other stakeholders kept on involving the group members in all stages of the project from identification, implementation, monitoring and preliminary evaluation. The use of participatory approach has empowered the community members with all necessary skills and experience such that they can now run the project operations with very minimal dependency from external support. They will need some support during the first payout which requires careful calculation of total shares, loans taken and the amount of repaid loans with interests, and the new share value for each individual.

### 5.4.1 Strategies for Project Sustainability

There are various strategies to ensure sustainability of the established Upendo na Amani VICOBA in Kilimahewa Village. The strategies included involvement of project beneficiaries in all project stages from CNA, resource mobilization, project implementation and monitoring of activities. Another strategy is involvement of community development officer and trade officers who trained the group and is still close to the project to instil the members with management skills. In terms of financial sustainability, the community members make financial savings every month and take loans which are repaid with a 10% interest rate. Furthermore, the use of self- written constitution to guide daily group management, involvement of the village council and the host organization; and formalization of the group into a registered VICOBA with a bank account are very important strategies to ensure the group and the project are sustainable.

### 5.4.2 Project Sustainability Assessment

Sustainability assessment of the project is part of evaluation process which was done after completion of all project activities in May 2020. However, some indicators of sustainability were assessed at the beginning and during the implementation of the project. Preliminary sustainability indicators include commitment of Upendo na Amani community members to work together with other stakeholders to identify the project, follow training instructions provided by facilitators and willingness to implement the project operations. The economic impact of the project will be assessed in April 2021 after the annual pay out of the first cycle.

### 5.4.3 Financial Sustainability

The project was implemented by twenty women entrepreneurs who according to their constitution, are expected to save on monthly basis through buying shares. The savings made a fund from which members were getting loans which are repaid at 10% interest rate after six months. So it is obvious that the individual members and the association will be financially stable from the savings and the interest rates charged from each loan.

### 5.4.4 Institutional Sustainability

It is anticipated that this association will respect all articles of their self -prepared constitution and they will proceed to work under supervision of the host organization and the village council which is a permanent institution in the government structure. Also as indicated during reviewing the policy framework, the organization and the members have a chance to benefit from government support through various policies. So long as the group has been formalized into a registered VICOBA, it is obvious that the members can access any support from the government, NGOs and other financial institutions whose objectives are to support women entrepreneurs. The established VICOBA will be able to access other loans and other capacity building opportunities including trainings on various income generating activities and business.

### 5.4.5 Political Sustainability

The project has been established by involving the government whose current policy is to support the people to participate in economic improvement activities. Also there are a number of government policies which are in support of the project as indicated in the third chapter of this document. The project is being implemented in a politically healthy environment with full political support from ward and village leaders who even contributed a lot towards its establishment. It is anticipated that political leaders will proceed supporting the group and their project; and they will sensitize the rest of the groups to establish similar projects through which the household incomes will be improved.

# CHAPTER SIX

# CONCLUSIONS AND RECOMMENDATIONS

## 6.1 Introduction

This chapter is an overview of the whole process from project identification through Participatory Community Needs Assessment, project implementation, monitoring and project evaluation. It discusses key issues identified in CNA, literature review, the reasons for selecting the project, project implementation report, participatory monitoring, evaluation and sustainability. Further still, the chapter presents the recommendations to the community and host organization who may wish to implement similar projects. The chapter also discusses the impact of unanticipated issues that affected the project. In short, this chapter is a summary of what has been covered in all previous chapters of this document.

## 6.2 Conclusion

The conducted Participatory Community Needs Assessment (CNA) as presented in the first chapter revealed that the leading challenge facing the community of women entrepreneurs in Kilimahewa village is a limited access to affordable credits. As a result, they do not have enough capital to expand or diversify their ventures. The community which implemented the project is made of women entrepreneurs with very limited income earning but yet with relatively high domestic workloads and household responsibilities. These are middle aged women whose households have up to five members on average, most of whom are children who need education, medication and nutrition services.

As a way of dealing with the challenges affecting them, these women came up with the idea to establish a Community Managed Savings and Loan Association through which they started to mobilize their financial savings and access to loans. The choice to establish VICOBA considered various opportunities as revealed through the Community Participatory Assessment. Some of the reasons behind the idea to establish VICOBA included the presence of willing members who can buy shares, take loans and repay the agreed interests.  Also, the decision was influenced by the presence of host organization, trade officer and community development officer who provided technical support.

Through theoretical and empirical literature review, we gathered and documented the available knowledge and experience from more or less similar initiatives of poverty reduction and how they helped members make savings and access loans at reasonable interest rates. The collected information and experience added value in establishing Upendo na Amani VICOBA in Kilimahewa village.  The available policy framework on poverty reduction, women empowerment, community development policy, Microfinance and the Vision 2025 were also reviewed to assess on how we can use the opportunity provided by policies to support the project.

Generally, the available literature depicts that apart from continuous efforts to combat poverty, many Tanzanians especially women are still experiencing low incomes. The Tanzanian policy framework provides opportunity for groups and associations of disadvantaged people especially women and youth to engage in income generating activities depending on their choices and ability. The information obtained in the reviewed literature regarding poverty is quite similar to the results of the CNA as presented in the first chapter of this document and has greatly contributed towards successful implementation of the project.

Implementation of the project involved a total of 20 selected members who own small entrepreneurial activities in Kilimahewa Village. The project was coordinated by ROPA which coordinated all activities in collaboration with CED student, Village leadership and the elected VICOBA leaders. The project aimed at capacity building to the community on how establish and operate the community bank , and finally facilitate the community to write the constitution and register  the organization  and opening a bank account. In order to facilitate implementation of the objectives, the District Council, as a major stakeholder, provided technical support through the community development officer and trade officer who offered all necessary guidance and skills in various aspects regarding the formation, registration and daily operation of the association.

The actual implementation of the project started in February 2020 by conducting the Participatory Community Needs Assessment and all other activities followed the Implementation schedule which was completed in May 2020. The group of beneficiaries was registered into VICOBA namely Upendo na Amani with registration number HWR/MJ/UVK/2020/635 with a bank account number 71110029964 held at NMB Ruangwa Branch.

Daily monitoring of project implementation was done by using participatory methods including the participatory Rural Appraisal (PRA) and Beneficiary Assessment (BA). The community members were fully involved as they participated from the beginning and through daily implementation of project activities in order to realize the predetermined project objectives and goal. The CED student in collaboration with leaders from the host organization, community development officer and trade officer took part in daily monitoring of activities especially trainings, purchase of tools, preparation of constitution, registration, opening a bank account and finally starting buying shares and provision of loans.

Some indicators of project sustainability were evaluated at the starting and during the course of implementation. Some primary indicators that are evident include financial sustainability, institutional sustainability and political sustainability. The community confirmed commitment to work together with other stakeholders to identify their needs, suggest the project, and attend trainings provided by experts and willingness to follow their constitution project operations. The host organization with a lot of experience and political support from the village, ward and district level took a leading role in coordinating all project activities. Institutional sustainability is also evidenced by having a signed group constitution, bank account and a registered association with elected leaders who have been capacitated to hold their positions. Other sustainability indicators have not revealed themselves at this stage and they will be recorded after final evaluation of the project. The economic sustainability of the project will only be measured later to assess the economic contribution towards improvement of beneficiaries’’ life and continuity of the project.

## 6.3 Recommendations

It is hereby recommended that the host organization, community development officer and the trade officer keep close supervision in order to support the group and its operations by providing daily couching and conflict resolution. The group still needs more training on financial management, record keeping, and project management as well as conflict resolution to avoid group disintegration. Performance of this project should be taken as a lesson for other disadvantaged groups of women and youth groups around and outside the village who can be mobilized to follow the same path to save money, form and register groups and come up with any income generating project of their choice through which they will improve their income and reduce household poverty and participate in the national economy.

It is further recommended that future projects should use participatory approaches such as PRA and BA as they have proved to be strong tools of involving the community in working together in all stages namely the project identification, project implementation, monitoring and evaluation of project. The use of such approaches have shown  increased chances of project ownership and sustainability because they allow the community to come up with real needs and appropriate solutions towards them. The experience obtained from implementation this project has indicated that the mobilized community and other stakeholders are ready to work together and contribute both materially and financially provided that things are transparent.

# REFERENCES

Arenius, P.  Z. J. & Minniti, M.  (2004). Global Entrepreneurship Monitor. London: London Business School and Babson College.

Becker .G. S. (1975).  Investment in Human Capital; Effect on Earnings. New York: NBER.

Bogdan, R. C. & Biklen, S. K. (2006). Qualitative Research for Education: An Introduction to Theory and Methods, 5th Ed., Boston: Allyn & Bacon.

Britto, S. F. (2006). Poverty in Focus. Brazil: United Nations development Programme.

Brown, J. (2002). Training need assessment: A must for developing an effective. Public Personnel Management, 31(4), 569–578.

Das-Barwa, S. (2015). Women’s Financial Inclusion Case Study: Using Sex-disaggregated data to promote Women’s financial Inclusion in India. The Commonwealth secretariety.

Eckhart, J. & Shane S. A. (2003). Opportunity and Entrepreneurship. Journal of Management, 17(1): 99–120.

Evans D.K, Hausladen S. (2013). Community Based Cash Transfers in Tanzania: Results from a randomized trial. Washington DC: World Bank.

Fiszbein, S. N. (2009). Conditional Cash Transfer. Washington DC: The World Bank.

Ganayake, S. (2001). Community Empowerment; A Participatory Training Manual Community Project Development. Office of International Training and Consultation. Northern Illinois University Dekalb, Illinois 60115, USA. Human Annual Reports of UNDP Jere,

Georgina, M. G.   (2008):  Do micro Enterprises Promote Equity or Growth? Havers M. (1991):  NGOs Agencies for Small Enterprises Small Enterprises.

Jody, Z, Z.  K. & Ray. C. (2004). Rist Ten Steps to a Result – Based Monitoring and Evaluation System 9.

Kelly, G., Linder, R. & Shaver, G. (: Person, Process, Choices; The psychological of New Venture Creation. Journal of Business Venturing, 13, 275–294.

Kothari, C. R. (2004): Research Methodology, Methods and Techniques, 2nd Edition.

Kuzikwa, J.  A. (2005). The role of Credit for Small Business Success: A study of the national Entrepreneurship Development Fund in Tanzania. Journal of Entrepreneurship, 1-2, 52-73.

Landstrom, H. (1998). The Roots of Entrepreneurship Research, Conference proceedings, Lyon, France.

McClelland. D, (1961):  Achievement Society. History and Theory, 3(3), 371-381.

McKillip, M. (2007). Mechanical harvesting of Sweet Cherries resource. Washington DC: American Society of Agriculture Engineers.

Milinga, A.  (2007): Training program of .Microfinance policies and regulatory system in Tanzania practitioner perspective, presentation to 3rd  African microfinance conference, august 20-23, 2007, Kampala, Uganda.

NBS, (2014). Household Budget Survey 2011/2012 Main Report. Dar es Salaam: URT.

NBS, (2014). Tanzania Conditional Cash Transfer (CCT) Impact Evaluation: Final Report. Dar es Salaam, URT.

Olomi, D. (2004) Unleashing Entrepreneurial Potentials of the Poor in Tanzania: Prospects, Challenges and Way Forward Working Paper for Presentation to the High Level Commission on the Legal Empowerment of the Poor.

Reynolds, P. D. (1991). Sociology and entrepreneurship: Concept and Contributions. Entrepreneurship Theory and practice, 16(2), 47-70.

Roger, C. (2012). Creating Entrepreneurial mind set; failure is an option, Paperback: entus Publishing ApS.

SEDIT, (2008). A Paper presented to National policy dialogue on MKUKUTA, P.E.R. annual consultative meeting on 19th to 21st November 2008.

Susan, J. (1997). microfinance and poverty Reduction) published by ox farm. An International Journal, 2(3), 1-10.

The United Way of America, (2012). World Urbanization prospects the 2001 revision. New York: United Nations.

Todaro, S. C. (2012). Economic Development. Washington DC: Pearson.

UNDP Report, (2004). Committee of Donor Agencies for Small scale Enterprises Development, UNDP.

UNDP, (2011). Human Development Report, London: Oxford University Press.

UNDP, (2016). Poverty in Focus. Brasilia: International Poverty centre, UNDP.

URT (2003). Small and Medium Enterprises Development Policy, URT.

URT (2005). National Strategy for Growth and Reduction of Poverty” Vice President Office, URT.

URT, (1996). Community Development Policy. Dar es Salaam, URT.

URT, (2000). National Microfinance Policy, Ministry of Finance, URT.

URT, (2004). National Economic Empowerment Policy. Dar Es Salaam, URT.

URT, (2005). Poverty and Human Development Report, Research and analysis. Dar es Salaam: Mkukina Nyota Publishers.

URT, (2007). Poverty and Human Development Report, Research and analysis. Dar es Salaam: Ministry of Planning, Economy and Empowerment.

URT, (2011). The five Year Development Plan 2011/ 12- 2015/ 16 Unleashing Tanzanian Latent Growth Potentials ‘President’s Office, planning commission).

URT, (2013). Productive Social Safety Net (PSSN) OPERATION MANUAL. Dar es Salaam: URT.

Wangwe, S. (2004). Innovation in rural finance in Tanzania. URT.

WBGDG, (2003). ‘Gender Equality and the Millennium Development Goals.’

World Bank, (2015). Global Monitoring Report. New York.

World Bank, (2015). Global Monitoring Report. New York: World Bank Group.

World Bank. (2011). Poverty, Growth and Public Transfers. Washington DC: World Bank.

World Bank. (2016). Poverty and Shared Prosperity: Taking on Inequality. Washington DC: World Bank Group.

# APPENDIX

# Appendix: Upendo na Amani Registration Details

# Text boxes

BOARD OF DIRECTORS

CHIEF EXECUTIVE OFFICER

FINANCE OFFICER

GENDER AND COMMUNITY DEVELOMPENT OFFICER

ENVIRONMENTAL OFFICER

SUPPLIES AND LOGISTICS OFFICER