IMPROVING LIVELIHOODS OF HAZINA YOUTH GROUP THROUGH A CAR WASH PROJECT AT RUAHA WARD IN KILOSA DISTRICT

GODWIN ERASTO SELENDA

A DISSERTATION SUBMITTED IN PARTIAL FULFILLMENT OF THE REQUIREMENTS FOR THE DEGREE OF MASTER OF COMMUNITY ECONOMIC DEVELOPMENT (MCED)

DEPARTMENT OF ECONOMICS AND COMMUNITY ECONOMIC DEVELOPMENT

OF THE OPEN UNIVERSITY OF TANZANIA

2022

## CERTIFICATION

The undersigned certifies that he has read and here by recommends this project for acceptance by the Open University of Tanzania a project titled; “Improving Livelihoods of Hazina group through a Car Wash Project at Ruaha ward, in Kilosa District” in partial fulfilment of the requirements for the degree of Master in Community Economic Development (MCED).

……………………………………

Dr. Felician Mutasa

(Supervisor)

…………………..…..……...

Date

# COPYRIGHT

No part of this dissertation may be reproduced, stored in any retrieval system, or submitted in any form or by any means, electronic, mechanical, photocopying, recording or otherwise without prior written permission of the author or Open University of Tanzania.

# DECLARATION

I, Godwin Erasto Selenda, declare that, the work presented in this dissertation is original. It has never been presented to any other University or Institution for the same purpose. Where other people’s works have been used, references have been provided. It is in this regard that I declare this work as originally done by the researcher. It is hereby presented in partial fulfillment of the requirements for the award of Masters Degree in Community Economic Development (MCED).

………………………………………

Signature

………………………………………

Date

# DEDICATION

This work is dedicated to my wife Taswiran Myinga and my child Durkheim for the love and humility they have shown to me throughout the time I have been doing this tough work, surrey, they missed my company and a special farther love during all the period of this dissertation.

# ACKNOWLEDGEMENTS

First and foremost, I thank God who gave me life and strength to do and accomplish this work to this far. In fact, without the grace of God to give me life and good health I could not have time to do this task of writing this project report. In a special way, I thank Dr. Felician Mutasa my supervisor for helping to reach this stage. Real his encouragement and motivation throughout the writing of this project report and he will not be forgotten as you read this thesis. This work would be impossible if not of your sincere and tolerant heart you have shown me, may God bless you abundantly. Also I would like sincerely to appreciate the entire administration of OUT for their fatherly love have shown me, may God bless them so much.

In particularly, I am also thankful to all instructors of the Community Economic Development Program who taught and instructed me in the years 2017 to 2022, on how to study and use the skills of this course Surely, I got the knowledge I expected too. I pray God to bless them all.  I am also indebted to my wife, Taswiran Myinga and children Durkheim and Anna for being patient with me and encouraging me to make my dream reality. They have been and they will always be my source of success and I love them all. Lastly, I cannot ignore some contributions rendered by different friends and relatives of mine may feel happy to receive my heartfelt appreciations.

# ABSTRACT

The study conducted aiming at improving livelihoods of HAZINA youth group through a car wash project conducted at Ruaha ward in Kilosa District. The community members and the researcher studied the necessity of car wash project business in the study area. One of the objectives was to enhance intervention and deliverance. Different ways and processes (steps) made this possible including development of the group strategic plan. The overall objective of the project was to find out the challenges that the community are facing and resources which are available in the community. Implementation was conducted following the assessment which indicated what initiatives need to be undertaken to achieve the intended goals. Through survey the researcher identified three appropriate strategies namely, the establishment of car wash project, capacity building for car wash members on micro-enterprise development and to empower project committee on supervision skills and exercise sustainable development activities. Target group were mobilized to contribute {solicit} money for raising fund of which the response was that 08 youths joined the car wash project named as HAZINA youth group as it is now continuing with its/car wash operations. The project group members were trained on marketing, financial management and then the group were registered at ward level. The implementation of the project was based on community needs assessment which was carried out during the participatory assessment process. The project has been well implemented and left in the hands of the community members and namely HAZINA

Keywords: Livelihoods, Youth, Car Wash, Project.

# TABLE OF CONTENTS

CERTIFICATION	ii

COPYRIGHT	iii

DECLARATION	iv

DEDICATION	v

ACKNOWLEDGEMENTS	vi

ABSTRACT	vii

TABLE OF CONTENTS	viii

LIST OF TABLES	xiv

LIST OF FIGURES	xiv

LIST OF ABBREVIATIONS	xvii

CHAPTER ONE	1

PARTICIPATORY NEEDS ASSESSMENT	1

1.1		Background Information	1

1.2		Community Profile	1

1.2.1		Geographical Location	2

1.2.2		Population	2

1.2.3		Ethnicity	3

1.2.4		Cultural Factors	3

1.2.5		Administrative Structure	3

1.2.6		Economic Activities	4

1.2.6.1		Agriculture	4

1.2.6.2		Livestock Keeping	4

1.2.6.3		Tourism Sector	4

1.2.6.4		Trade	5

1.2.6.5		Social Services	5

1.3		Community Needs Assessment	7

1.3.1		CNA Overall Objective	8

1.3.1.1		Specific Objectives	8

1.3.2		CNA Questions	9

1.3.3		Research Methodology	9

1.3.3.1		Research Design	9

1.3.3.2		Study Population	9

1.3.3.3		Sampling Techniques	10

1.3.3.4		Data Collection Methods	10

1.3.3.5	Data Analysis Methods	12

1.3.3.6	Reliability and Validity	12

1.4		CNA Findings	12

1.4.1		Age of Respondents	13

1.4.2		Level of Education	13

1.4.3		Marital Status	14

1.4.4		Number of Dependents	14

1.4.5		Problems Facing Ruaha Ward Youth	15

1.4.6		Lack of Entrepreneur Skills	16

1.4.7		Suggested Measures	16

1.4.8		Findings from Key Informants	17

1.4.9		Identified Problems	18

1.4.10		Available Resources in the Community	18

1.4.11		Suggested Solutions	19

1.5		Community Needs Priotization	19

1.6		Chapter Summary	20

CHAPTER TWO	21

PROBLEM IDENTIFICATION	21

2.1 	Background to the Research Problem	21

2.2 	Problem Statement	21

2.3 	Project Description	22

2.3.1	Target Community	23

2.3.2 	Stakeholders	23

2.3.3 	Project Goal	23

2.3.3.1 	General Objectives	24

2.3.3.2	 Specific Objectives	24

2.4 	Host organization CBO/Profile	24

2.4.1 	Vision of Ruaha Ward	24

2.4.2	 Mission of Ward Office	24

2.4.3 	Ruaha Ward Organization Structure	25

2.4.4 	Ward SWOT Analysis	25

2.4.5 	Sources of Funds for the Group	26

2.4.6 	The Role of CED Student’s in the Project	26

2.4.7 	Role of Ward as Host organization	26

CHAPTER THREE	27

LITERATURE REVIEW	27

3. 1 	Introduction	27

3.2 	Theoretical Literature	28

3.2.1 	Definition and Concept of Youth	28

3.2.2 	The Theory of Poverty	29

3.2.3 	The Concept of Poverty	29

3.2.4 	The Concept of Youth Unemployment	31

3.3 	Empirical Literature	32

3.3.1 	The Concept of Car Wash	32

3.3.2 	Role of Car Wash Services in Income Generation	32

3.3.3 	Carwashes in MDCS’ and how can reduce Poverty	34

3.3.4 	Contribution of Entrepreneurship on Economic Growth and                    Development	35

3.3.5 	Problems that Hinder Youths Empowerment	36

3.4 	Policy Review	38

CHAPTER FOUR	43

PROJECT IMPLEMENTATION	43

4.1 	Introduction	43

4.2 	Products and Outputs	44

4.2.1 	Project Products	44

4.2.2 	Project Output	44

4.3 	Project Planning	44

4.3.1 	Implementation Plan	45

4.3.2 	Inputs	46

4.3.3 	Project Logical Framework for a Car Wash Services	47

4.3.4 	Staffing Pattern	49

4.3.5 	Project Budget	51

4.4 	Actual Implementation	55

4.4.1 	Project Implementation Gantt Chart	55

4.5 	Chapter Summary	65

CHAPTER FIVE	66

PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY	66

5.1 	Introduction	66

5.2 	Participatory Monitoring	66

5.2.1 	Monitoring Information System	68

5.2.2 	Participatory Monitoring Methods	69

5.2.2.1 	Document Analysis	69

5.2.2.2 	Observation	69

5.2.3 	Participatory Monitoring Plan	70

5.2.4 	Participatory Evaluation	72

5.2.5 	Performance Indicators	73

5.2.6 	Participatory Evaluation Methods	76

5.2.6.1 	Meeting	76

5.2.6.2 	Interview	77

5.2.6.3 	Focused Group Discussion	78

5.2.7	Project Evaluation Summary	78

5.3 	Project Sustainability	79

5.3.1 	Institutional Sustainability	79

5.3.2 	Financial Sustainability	80

5.3.3 	Political Sustainability	81

5.4 	Chapter Summary	82

CHAPTER SIX	83

CONCLUSION AND RECOMMENDATION	83

6.1 	Conclusion	83

6.2 	Recommendations	84

REFERENCES	87

APPENDICES	93

# LIST OF TABLES

Table 1.1: Education Centers in the Ward	5

Table 1.2: Sample Size Composition	10

Table 1.3: Age of Respondent	13

Table 1.4: Level of Education	14

Table 1.5: Marital Status	14

Table 1.6: Number of Dependents	15

Table1.7: Problem Facing Urban Youth	15

Table 1.8: Do You Have any Entrepreneurship Skills	16

Table 1.9: Suggested Measures	17

Table 1.10: The Findings from the Key Informants	17

Table 1.11: Problems Encountered Within the Community	18

Table 1.12: Priotization of Needs through Pair Wise Ranking	19

Table 2.1: Stakeholders Analysis	23

Table 2.2: SWOT Analysis	25

Table 4.1: Project Implementation Plan	45

Table 4.2: Project Inputs	47

Table 4.3: Logical Framework Matrix	48

Table 4.4: Staffing Plan and Training Needs	50

Table 4.5: Project Budget	51

Table 4.6: Project Implementation Gantt Chart	65

Table 5.1: Participatory Monitoring Plan	71

Table 5.2: Performance Indicators	75

Table 5.3: Project Evaluation Summary	79

# LIST OF FIGURES

Figure 1.1: Community Sensitization Meeting with the Chair Person	7

Figure 2.1: Ward Organization Structure	25

Figure 4.1: Church Members Solicit Fund for HAZINA YOUTH GROUP	52

Figure 4.2: HAZINA Members with CED Student during the Formation                             of Group	52

Figure 4.3: Youths during Entrepreneurship Training (Group discussion)	53

Figure 4.4: Easy way Youth used to wash Car	54

Figure 5.1: Facilitators, CED Student and HAZINA GROUP Members                                       Getting Lunch after Entrepreneurship Seminar	70

Figure 5.2: Community Members after Fund Raising	74

Figure 5.3:  Youth Washing Cars	75

# LIST OF ABBREVIATIONS

AIDS	Acquired Immunodeficiency Syndrome

HYG	Hazina Youth Group

CED	Community Economic Development

CNA	Community Needs Assessment

FGD	Focus Group Discussion

FIFO             First in First Out

HIV	Human Immunodeficiency Virus

ICPD	International Conference on Population and Development

IFAD	International fund for Agriculture development

ILO	International Labor Organization

LDCs            Least Developed Countries

MDG	Millennium Development Goals

MIS	Monitoring Information System

M & E 	Monitoring and Evaluation

MDC            Most Developed Countries

MOV	Means of Verification

O & OD	Opportunity and Obstacles to Development

OUT	Open University of Tanzania

OVIs	Objectively Verifiable Indicators

PRA	Participatory Rural Appraisal

SELF	Small Entrepreneurs Loan Facility

SPSS	Statistical Package for Social Scientist

TANESCO   Tanzania Electric Supply Company

UNIFEM	United Nations Development Fund for Women

URT	United Republic of Tanzania

VBA              Village Business Areas

WEO             Ward Executive Officer

VEO	Village Executive Officer

YDF	Youth Development Fund

# CHAPTER ONE

# PARTICIPATORY NEEDS ASSESSMENT

# Background Information

The Participatory need assessment (PNA) is a method for determining from the communities of actual needs aspects. The (PNA) was also supported by Kasaija and Nsabagani (2008) who argue that PNA acknowledges the fact that people know their area more than outsiders and finally ready to identify and discuss the problems in their community.

The aim of conducting participatory needs assessment for the present study was to collect information about the car wash situation in Kilosa district, which would assist in identifying the problems the Community is facing and formulate a possible project to address the main problem based on their ranking. The car wash plays a major role in sustaining the livelihood of the majority of Youth in the community members within the study area; hence, car wash was very important for the current study to have focus on it.

## Community Profile

This section consists in assessing main aspect of the community which is location and the characteristics of the project area. The Kilosa District Council is located within the Morogoro Region. The United Republic of Tanzania plays a pivotal role in trade and development within the Southern African Development Community (SADC). The Kilosa District Council is well positioned to take advantage of the market opportunities within Tanzania and the SADC because it is centrally located within the Southern Agricultural Growth Corridor of Tanzania. Ruaha ward is among the ward which is within the Kilosa district whereby is boarded by Tundwi village to the north by Vianzi Magodani to the south, by Morogoro village to the east.

## Geographical Location

The Kilosa District Council has an average annual rainfall of between 800 mm to 1600 mm depending upon the altitude. The temperature in the District varies with altitude as well. The average annual temperature is 25°C with the coldest month being July and the hottest month being March. The average annual temperature ranges from 19°C to 30°C. The District is divided into three different agro-ecological zones: Mountains, Uplands Plateau and Floodplains. The Mountains run north-south as part of the Eastern Arc System and comprise pre-Cambrian metamorphic rocks covered by coarse soil. The Uplands Plateau is located in the northern part of the District and is characterized by plans, hills and moderately fertile, well-drained soils comprised of clay and loam.

The floodplains are comprised of flat and undulating plains extending to the foothills in the western portion of the District. The central area of the floodplains is comprised of poorly drained, black, ‘cracking’ clays soils with its periphery being comprised of loamy soils. Kilosa district council has 58 rivers that help with providing water for domestic uses, livestock, and irrigation and fishing grounds. These rivers are a significant value to the district and directly contribute to the quality of life of the residents.

## Population

According to the Population and Housing Census of 2012, Kilosa District had a population of 438,175. The 2018 population projections for the District was 511,130, which is a 17% increase in population size over a 6-year period. Within the Kilosa District Council, the largest divisions are Magole and Mikumi, which represent 59% of the entire population size according to the 2018 population projections.  This population size (511,130) combined with its land area (12,394 square km) gives it an average population density of 41 persons per sq. km.

## Ethnicity

The ward as well as the centre comprises Youths of Wakaguru tribe as the majority who account almost over 85%. Other tribe include Wasaga, Wavidunda, Luo and others in minority. For the case of religious, the community of the ward is dominated with Christians, Muslims and few are Pagans (local believes). Youth at Ruaha ward are also included in these ethnicity groups. The majority as named above respectively. Most of youth are Christians followed by Muslims and the rest are Pagans in minimal number.

## Cultural Factors

Ruaha Ward community is dominated by Wakaguru tribe, followed by Wasanga and Wavidunda. The main language of the community is Kiswahili which is mostly used because majority of them are familiar with it. The second languages are the native ones which are mostly used in homes.

## Administrative Structure

# Kilosa District is divided into 9 divisions, 37 wards and 164 villages

## Economic Activities

## Agriculture

According to Ward Agricultural officer (2016) report, individual small-scale farmers cultivate an average of 1.3 - 2.2 hectares of land per year. Food crops grown include rice, cassava, maize, sweet potatoes, sorghum, millet, banana and beans. Rice is the major cash crop as well a steppe food, where sweet potatoes, maize, groundnuts and cassava are also cultivated as cash crops in some areas of the Ruaha Ward. Horticulture crops like onions, carrot, eggplant, tomatoes productions to a large extent is geared toward domestic consumption. In the recent year’s production of both food and cash crop have been increasing due to; high demand and the growing Ruaha ward which is the head quarter of Kilosa district. Also it has few areas useful for irrigation system in the ward. The challenge of the youths is lack of agricultural inputs and implements, small scale farming and insufficient of pests and insecticides and lack of knowledge.

## Livestock Keeping

Within the Kilosa District Council, small scale cattle farming which is approximately .9% of economic activity. Despite this low percentage of economic opportunity, there is significant activity and opportunity within the Livestock Sector. The Kilosa Livestock Office states that there are 629,159 livestock within the District.

## Tourism Sector

The Kilosa District Council has a strong tourism sector due to the Mikumi National Park, the Udzungwa Mountain Range, Ruaha River and Udzungwa Waterfall. These beautiful natural amenities bring thousands of tourists to the Kilosa District on an annual basis. The Mikumi National Park is approximately 3,230 square kilometers, which makes it the fourth-largest park in Tanzania. There are game drives, guided walks, two lodges, three luxury tented camps and three campsites in Mikumi National Park. This national treasure is strategically located within the Kilosa District and is easily accessible for both employees and tourists. The natural amenities combined with its accessibility provides many opportunities for investment in hotels, retail, and tour operators within the Tourism Sector

## Trade

In Ruaha Ward, most of the commercial activities are small and medium shops which are carried out in the center all seasons, and also in various villages commonly known as “Kiosk” which forms the Village Business Areas (VBA). However, a number of shops are located in the surroundings of the VBA and other small shops also found distributed in different village places mostly selling the daily need commodities of the respective residents.

## Social Services

## Education

# Table 1.1: Education Centers in the Ward

|  | Primary Schools | Secondary Schools | Training Centers |
| --- | --- | --- | --- |
| Owned by Government | 04 | 01 | 01 |
| Private | 00 | 00 | ---- |
| Total | 04 | 01 | 01 |

Source: Survey (2016)

Ruaha Ward has primary schools and Secondary schools owned by the Government and one private institution as summarized in Table 1.1 providing education services in the Ward.

## Health

The ward has 1 dispensary owned by the government, 2 laboratories for primary diagnoses and 5 small pharmacies which are private owned.

## Water

There are several water sources which deliver water services to Ruaha ward community. These sources include Pangani river water supply authority (KWASA), 7 bore holes owned by both Government and private and several traditional shallow wells within the ward.

## Infrastructures

According to the Kilosa Council Socio-Economic Profile, the Kilosa district council has a 1,426 km roadway network, of which 20% are trunk roads, 15% are regional roads, 32% are district roads and 32% are feeder roads. About 30% of all districts roads are tarmac, 22% are gravel and 57% earth, which represents an investment need to improve roadway infrastructure in the District. In addition, the growing population of the district increases the need for additional energy capacity, waste management services and mobility options for residents and tourists.

## Communication Services

The Ruaha ward is an urban with more Communication lines/ telephone which is dominated by the presence of, AIRTEL, TIGO, VODACOM, ZANTEL and HALOTEL The centre is also connected with permanent power from the TANESCO Company which is durable. In short, the community is good in networking’s systems for communication with all places in Kilosa from Kidatu and other areas which support socio-economic growth as well as social issues.

## Community Needs Assessment

The CNA was conducted at Ruha ward in order to identify different needs available at the community in order to come up with the best need to solve the community problem where different needs were identified by the community members as follows based from first need to the last need.

# Figure 1.1: Community Sensitization Meeting with the Chair Person

The CAN adopted a participatory approach in which survey method and group discussions were used and identified the different needs as shown above where car wash project was identified with the community members with research in order to reduce an employment among the young person’s at Ruha ward, and identify which group may under take this project where Hazina young group was chosen among the groups.

However, Whang-Ramos, Seekins and Bradford (1987) and Suarez, Balcazar and Keys (1999) contends that Community Needs Assessment can be done simply by the indigenous/residents interacting to pose their opinions about the development off services within the community, how they satisfy with the services, and what particular services are needed. Their opinions and suggestions can be used in building an agenda aims at community change that can build the capacity of community –based organizations that are designed to provide services and development opportunities to residents. Community Needs Assessment was conducted basing on this principle of Participatory approach

## CNA Overall Objective

The overall objective for conducting community needs assessment (CAN) was to collect information about the youth community at Ruaha ward that would assist Youth in identifying the socio economic needs and the main problem the community is facing and suggest ways and formulate a project to address the main problem based on their ranking.

## Specific Objectives

- To identify the problems facing social economic needs of youth within Ruaha ward

- To identified the problems and needs of youth within the community Ruaha ward community.

- To identify the type of assets available within the community and among community members.

## CNA Questions

- What are the problems facing Youth/community members involved within the area?

- What is the most problem of socio- economic status of youth at Ruaha ward?

- What is the type of assets available within the Youths and among community members?

## Research Methodology

## Research Design

According to Oso and Onen (2008), research design is an overall plan or strategy for conducting the research. In this study the cross – sectional design was used, in which simple random sampling and purposive sampling were used to select a representative sample to collect information. The design is considered to save time and resources and is eventually used for determination of relationship between variables (Bailey, 1998). Both quantitative and qualitative data were obtained through this design. The main emphasis was on the discovery of ideas and viewes. The process of conducting CNA involved three methods namely; survey, interview and observation methods.

## Study Population

This study was conducted in Ruaha ward particularly in Kilosa district about 526 youths and 57 key informants /staff ward. Ruaha ward is one of the 37 wards in Kilosa District in Morogoro Region. It has many jobless youths at Ruaha ward. It is therefore, considered appropriate for providing a focal point for the study of improving livelihoods of Hazina youth group through a car wash project at Ruaha ward.

## Sampling Techniques

# A total of 62 house hold respondents were randomly sampled from the Ruha ward which comprises of 79 household and other influential person(politician) and three representatives from Ruaha ward using simple random sampling. The sample size used for quantitative data collection took into consideration of researcher’s resources and the possibility of making meaningful analysis of data collected. Also purposive sampling techniques was used to select potential respondents who were conversant to the topic who. The sampling techniques which were used to get the required sample size included Simple Random Sampling (SRS) and Purposive sampling. The SRS method was used to choose 12 respondents who are Car washers while Purposive sampling was used to obtain 62 youths from Ruaha ward,

# Table 1.2: Sample Size Composition

| Category of Respondents | Number of Respondents |
| --- | --- |
| Street A | 31 |
| Street B | 31 |
| Car washers | 12 |
| Key informants | 10 |
| Total | 84 |

### Source: Surveyed Data, 2021

## Data Collection Methods

Data collection method based only on primary, data collected during the survey process. Primary data were collected from the community through questionnaire, semi-structured interview and observations

## Interview (Key Informants)

An interview is among the techniques of data collection in which information is obtained in a face to face situation. The interview conducted to gather primary data from 10 key informants. This was done for individual respondent separately using a semi structured questions this helps to guide the interview process, to get challenges facing youths ‘and sustainable solutions.

## Observations

The survey engaged at the target group and observes physically what was going on without direct doing or participating on the business. This method helped the researcher to understand the situation and context of the youths are engaging in business operations as far as the problem of socio-economic is concerned like unemployment among young people and laziness’.

## Questionnaires

Self – administered questionnaires (structured) were distributed to 84 respondents. For the illiterate respondents, the researcher assisted them. The questionnaire technique for gathering data is widely used in most of research studies. The questionnaire was used in this to determine opinions and attitudes of the respondents on problems facing youth’s members who involved in socio-economic issues. In this study the open-ended questions were included in the questionnaire to enable the respondent to state her/his case freely and allowed to give reasons as well.

## Data Analysis Methods

##### Both qualitative and quantitative techniques of data analysis were used in the study. The quantitative techniques used were descriptive statistics which were used to define the percentage of respondents while the qualitative data was analyzed using content analysis method. Data was presented using tables, graph and charts to give an easy understanding of the findings

## Reliability and Validity

The reliability and validity in a qualitative research study can be improved by the application of pluralized methodologies for triangulation (Gorman and Clayton 2005), as well as by including authoritative guidelines for coding terminology to avoid coder bias (White and McCain 1998). This study employed several methodologies such as interviews, observation, documents/artifacts data collections, content analysis, and focus group discussions as data collection techniques to enhance the reliability and validity. Due to the heavily qualitative nature of this study, all research procedures were applied consistently, further enhancing the study’s reliability. The descriptive analysis was done to get frequencies and percentages. The analyzed data were presented by using tables and qualitative data were thematically analyzed to make meaningful interpretation.

## CNA Findings

## This section gives findings of the CNA where tables and figures to illustrate the findings. Information’s were presented in tables and figures illustrate the findings. Section 1.4.1 discusses the demographic issues of the respondents so as to get the first hand information of the respondent. Also, the assessment was made on getting to know problems facing urban youth, level of livelihood, economic activities do urban youth engaged, income earning per month, as well as measures undertaken to intervene the problem (section 1.4.2 suggested solutions.)

## Age of Respondents

The findings show that 74 respondents are of the age group of 18 - 29 years’ equivalents to 83.4%, which is an active group for car wash services and business operations. The age group distribution pattern shows the dominance of the active manpower and the potential of the society in economic productivity.The age of respondents involved during the study/data collection. The age group 18 – 30 which is the target of the researcher   covers 83.4%.  This group experience different socio economic activities and faces a lot of challenges in the community. This comes from the fact that, youth under this age are at the position of having many responsibilities and duties in their lives.

# Table 1.3: Age of Respondent

|  | Frequencies | Valid Percentages |
| --- | --- | --- |
| Valid | 18-23 years | 35 | 41.7 |
|  | 24-29 years | 35 | 41.7 |
|  | 30 and above | 14 | 16.7 |
|  | Total | 84 | 100.0 |

Source: Researcher, 2021

## Level of Education

Table 1.4 shows that, among 84 respondents in the study area, 50.0 % proved to access primary education, 25.0% not attain any education level while 17.9% of the respondents have secondary education, and 7.1% attend adult education. Generally, the results show that most of respondents (75.0%) received at least basic education which will facilitate the adoption of entrepreneurial skills and the implementation of new technologies when applied and if they are skilled.

# Table 1.4: Level of Education

|  | Frequencies | Valid Percentages |
| --- | --- | --- |
| Valid | Not attended school | 21 | 25.0 |
|  | Adult education | 6 | 7.1 |
|  | primary education | 42 | 50.0 |
|  | Secondary education | 15 | 17.9 |
|  | Total | 84 | 100.0 |

Source: Researcher, 2021

## Marital Status

Table 1.5 show marital status of respondents within the study area.  The findings show that most of respondents 84.5% were single while 15.5% of the respondents were married. Most of the respondents were single; this indicates that probably they fear to marry because of cost of living. Although there few married, they face even more challenges than single one. This means that urban youth do face the same socio – economic challenges no matter which status they have.

# Table 1.5: Marital Status

|  | Frequency | Valid Percent |
| --- | --- | --- |
| Valid | Single | 71 | 84.5 |
|  | Married | 13 | 15.5 |
|  | Total | 84 | 100.0 |

Source: Researcher, (2021)

## Number of Dependents

The table 1.6 shows the respondent’s number of dependents from the study area. The data shows that 50.0% of respondents do have 2 dependent’s, followed by 39.3% have 1dependent’s, which imply that apart from their personal life, urban youth have to take care of their families despite the fact that they are facing a lot of challenges within the community. They play many roles such as domestic, economic and social roles in order to make sure that they engage fully for their lives, their families and community in general.

# Table 1.6: Number of Dependents

|  | Frequencies | Valid Percentage |
| --- | --- | --- |
| Valid | 1 | 33 | 39.3 |
|  | 2 | 42 | 50.0 |
|  | 3 | 6 | 7.1 |
|  | 4 and above | 3 | 3.6 |
|  | Total | 84 | 100.0 |

Source: Researcher, (2021)

## Problems Facing Ruaha Ward Youth

Table 1.7 shows that, despite many challenges facing urban youth in Ruaha ward, income poverty seems to be the main problem facing the them as it displays 38.1% followed by Lack of capital by 28.6%, Lack of entrepreneurial skills by 15.5%, lack of improved technology by 9.5% and lack of special area for their petty business by 8.3%. Income poverty among youth in urban areas is still the challenging issue e.g. the majority of youth are engaged in small scale business in informal sector but. face problem in their struggle for economic and social make up.

# Table1.7: Problem Facing Urban Youth

|  | Frequencies | Valid Percent | Rank |
| --- | --- | --- | --- |
| Valid | Lack of entrepreneur skills | 13 | 15.5 | 3 |
|  | Lack of special area for their petty business | 7 | 8.3 | 5 |
|  | Lack of capital | 24 | 28.6 | 2 |
|  | Income poverty | 32 | 38.1 | 1 |
|  | Lack of improved technology | 8 | 9.5 | 4 |
|  | Total | 84 | 100.0 |  |

Source: Researcher, 2021

## Lack of Entrepreneur Skills

Table 1.8 shows that 86.9% of all respondents don’t have any entrepreneurship skills and only 13.1% at least are knowledgeable. This reveals that, most youth in Ruaha ward who are engaged in different petty business and other IGAs have no entrepreneurship skills. During the interview and focus group discussion respondents suggested that, youth should be provided with entrepreneurship training for their business including car wash.  Through the entrepreneurial training youth will be able to generate business idea, carry out a market research, and develop a business plan, set up the business and managing & monitoring the business initiated.

# Table 1.8: Do You Have any Entrepreneurship Skills

|  | Frequencies | Valid Percentage |
| --- | --- | --- |
| Valid | Yes | 11 | 13.1 |
|  | No | 73 | 86.9 |
|  | Total | 84 | 100.0 |

Source: Researcher, 2021

## Suggested Measures

Table 1.9 shows that 42.9% of respondents suggested car wash as the most need in improving their livelihood. 22.6% needed vegetable garden, 17.9 soap making project, 11.9% need saloon project and 4.8% need entrepreneurship skills. Through the focus group discussion with urban youth, the researcher used time to ask the respondents to identify the possible opportunities having which can improve the livelihood of urban youths in Ruaha ward. Most of them suggested the establishment of car wash and its’ services as an income generating activity (IGA) according to their domicile. Car wash- services is very marketable for urban youth as it cost less capital to establish but also the availability of many cars all the time in Kilosa district, this proves the presence of market all the time. This exercise and evidence helped the researcher to know what is supposed to be done & emphasized when planning the suggested project.

# Table 1.9: Suggested Measures

|  |  | Frequencies | Valid Percentage | Ranking order |
| --- | --- | --- | --- | --- |
| Valid | Establishment of vegetable garden | 19 | 22.6 | 2 |
|  | Establishment of carwash | 36 | 42.9 | 1 |
|  | Establishment of saloon | 10 | 11.9 | 4 |
|  | Soap making skills | 15 | 17.9 | 3 |
|  | Entrepreneurship skills | 4 | 4.8 | 5 |
|  | Total | 84 | 100.0 |  |

Source: Researcher, 2021

## Findings from Key Informants

Key informants involved were 10, include: WEO; VEO; Local leader, Hamlet leader religious leaders, parents on their interview had identified the problems and challenges facing the community and suggested measures to overcome. Key informants identified the major problem is lack of car wash knowledge and skills of handling it. They said that “urban youth in Ruaha ward do depend much on petty business including selling scrappers though others do engage in collar jobs, begging, as well as vendors/ machinga.

# Table 1.10: The Findings from the Key Informants

| Key informants | Female | Male | Total |
| --- | --- | --- | --- |
| WEO/ VEO | 00 | 02 | 02 |
| Local leader/ Hamlet leader | 01 | 01 | 02 |
| Religious leaders/parents | 03 | 03 | 06 |
| Total | 04 | 06 | 10 |

Source: Researcher, 2021

When asked, what are the suitable measures for improving the livelihood status of urban youth? They proposed that, “youth should be supported with income generating activities (IGAs) like car wash-services simply because the market for it is available all the time within their local area”. With this notion they said that “though youth will be supported with income generating activities that should collaborate with entrepreneurship training.

## Identified Problems

# Table 1.11: Problems Encountered Within the Community

| Problem | Score | % scored | Rank |
| --- | --- | --- | --- |
| Inadequate capital for business operations | 1 | 6.7 | 5.5 |
| Lack of capital/income poverty | 5 | 33.3 | 1 |
| Lack of capacity in establishment of cooperative society | 3 | 20.0 | 2.5 |
| Lack of modern car wash | 3 | 20.0 | 2.5 |
| Lack of entrepreneurship skills | 2 | 13.3 | 4 |
| Lack of book keeping skills to members of the group | 1 | 6.7 | 5.5 |
| TOTAL | 15 | 100 |  |

Source: Survey (2021)

Participatory results on Community Needs Assessment with a particular focus on problems identification (Table 1.11) revealed five common major problems namely; Lack of entrepreneur skills, Lack of special area for their petty business, Lack of capital, Income poverty and Lack of improved technology.

## Available Resources in the Community

Based on the survey results the notable available resources of the community include Land, lake, steams, human resources, township location, bicycles, motor cycles, cars, tracks and water taps These resources can be utilized for economic progress to the study area.

## Suggested Solutions

Following the availability of resources also the participatory approach was involved to local people in identifying their problems and the way in solving them. It was thus important to get their views on the possible remedies of the existing problems as far as the hand car wash and Pressure pump is concerned.

## Community Needs Priotization

According to the results of pair wise ranking, the lack of knowledge and skills of establishment of Car wash, handling and quality control becomes a most priority area of the community need Table 1.12: shows the Pair wise ranking exercise which involved members of the group and the exercise was done successfully because each member participated fully and freely by asking, arguing and making decision according to her/his wishes.

# Table 1.12: Priotization of Needs through Pair Wise Ranking

| Need | Establishment of vegetable garden | Establishment of carwash | Establishment of saloon | Soap making skills | Entrepreneurship skills | Score | Ranking |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Establishment of vegetable garden |  | Establishment of carwash | Establishment of vegetable garden | Establishment of vegetable garden | Entrepreneurship skills | 2 | 3 |
| Establishment of carwash |  |  | Establishment of carwash | Establishment of carwash | Establishment of carwash | 4 | 1 |
| Establishment of saloon |  |  |  | Soap making skills | Entrepreneurship skills | 0 | 5 |
| Soap making skills |  |  |  |  | Entrepreneurship skill | 1 | 4 |
| Entrepreneurship skills |  |  |  |  |  | 3 | 2 |

Source: Research Findings, 2022

Members of the group were supposed to list as many as possible problems which hinders their socio-economic development/income poverty and which business can help them and finally members of the group come up with five main needs. Frequently the exercise was pausing for waiting consensus of the audience on comparative of five areas.

## Chapter Summary

This s chapter on participatory needs assessment has presented the community profile of Ruaha ward where the Community Needs Assessment (CNA) was done. The CNA used a participatory approach in undertaking the study. The sample from the target population was both randomly and purposively selected from among community members and got involved in the identification of the problem as far as the car wash project is concerned. The CNA based on the pair wise ranking indicated that lack of knowledge of establishment of Car wash which is the most pressing need that requires immediate attention. Thus the anticipated project will focus on addressing issues related to car wash handling and quality control as well as car wash day- to-day business in the area.

# CHAPTER TWO

# PROBLEM IDENTIFICATION

# 2.1 Background to the Research Problem

The most identified problem facing the Hazina group CBO was income poverty. However, several problems were included and prioritized to determine the most pressing problem in their business which were inadequate capital for business operations, lack of capacity in establishment of cooperative society, lack of modern car wash, tools and equipments for business operations, inadequate knowledge and skills on car wash handling and quality control and car wash marketing, lack of entrepreneurship and cooperative skills, lack of book keeping skills to members of the group. Based on the participatory findings of the CNA the most need to overcome the income poverty was establishment of car wash, which is the focus of the proposed project towards addressing this problem.

# 2.2 Problem Statement

The core problem of Youths in Tanzania is income poverty caused by unemployment Atkinson & Micklewright, (1991). Most youths are also lacking formal education and lack of entrepreneurship skills. (Chetty, Weber, A. (2008). The government and NGOs are helping youths for moral and material support. Nevertheless, these supports are vanishing with time due to severe household income poverty, effects of globalization, change of technology, socio-economic changes and income poverty among of youths. Moreover, low ability to acquire their basic needs due to low income which is not enough contributes to poverty hence fail to sustain life in town. Also failure to use resources available for producing goods and services is another challenge. However, the proposed project establishment of car wash will be the solution.

Car wash are the highly pressing need to address the problem in modern world especially in urban areas. The business is good for youth since it needs energetic and strong people. The increase of cars, tracks, motorcycles, tractors and bicycles in urban areas foster the project to be in high demanded. It is also the right source of income to income youths who have no formal employment in the urban areas. The project is situated at Ruaha ward which is a populated area and gives hence more cars are found here offering more opportunity for car wash business to have many clients.

Due to above resources and opportunity, the current study came up with the detailed study which unveils the opportunities for viable and reliable economic activity with the focus of contributing in sustainable economic development. In view of this situation the current study came out with Hand and Pressure Washer Car wash project for HAZINA as a way utilizing the available investment fortune. Before implementation of the project it was necessary to impart skills to car wash and handling practices among youths who are involved in car wash operation/group, marketing and controlling within the community.

# 2.3 Project Description

## The title of the project is “Improving livelihoods of HAZINA YOUTH GROUP through establishing a car wash project at Ruaha ward in Kilosa District”. The project was undertaken in Ruaha Ward, in Morogoro Region and the owners of the project are HAZINA YOUTH GROUP.

# 2.3.1Target Community

The targeted community in the project is the urban youths in Ruaha ward who are totally six young groups in the ward (Street A& B) as well as the entire community.

# 2.3.2 Stakeholders

Different stakeholders have contributed in the implementation and success of the project. The main stakeholder is the Kilosa District Council which includes: Trade Officer; WEO & VEO; Youth development officer, the stakeholders of the project everyone was assessed depending on what stakeholder can contribute strengths, weaknesses, threats, experience and stakeholder’s needs. See Table 2.1.

# Table 2.1: Stakeholders Analysis

| S/N | Stakeholder | Role | Expectations |
| --- | --- | --- | --- |
| 1 | Kilosa Council | Financial support through YDF Facilitate group registration Advisor of the project | The fund is released at a reasonable time for the implementation of the project. |
| 2 | Urban youth | Initiate, manage and operate the project. Owners of the project | Ensure sustainability of the project Improve standard of living from car wash services. |
| 3 | Ruaha ward community | Consumers of car wash products | Clients improve live of their cars |
| 4 | Commercial banks | Loan provision to the group | Improves project growth |

### Source: Researcher, (2021)

### 2.3.3 Project Goal

The goal of this project is to improve the livelihood of Hazina Youths Group through income generating projects in Ruaha ward.

### 2.3.3.1 General Objectives

To empower urban youth’s economically in Ruaha ward by provision of knowledge and skills of car wash handling and quality control to car wash operators, by establishment of hand and pressure washer car wash project by June, 2021.

# 2.3.3.2 Specific Objectives

- To conduct training to 12 youths on car wash by January, 2021

- To conduct training on entrepreneurship to 12 youths in Ruaha   by February, 2021.

- To establish car wash project at Ruaha ward by May 2021.

## 2.4 Host organization CBO/Profile

The host organization is Ruaha ward in Kilosa District. The ward is led by the ward Executive Officer. The Hazina youth group( CBO) is working under the leadership of the    WEO offices. However, for management of the project, the group has its own leaders, among of them are; chairperson, Secretary and the treasury selected by all members through voting.

### 2.4.1 Vision of Ruaha Ward

Assume the responsibility of offering the current and future needs of the community with high quality of life and human value.

### 2.4.2 Mission of Ward Office

Ruaha ward offer services, for all people in the society with all respect regardless of their race or gender.

### 2.4.3 Ruaha Ward Organization Structure

# Figure 2.1: Ward Organization Structure

### 2.4.4 Ward SWOT Analysis

# Table 2.2: SWOT Analysis

| Strengths | Weakness |
| --- | --- |
| 1.The organization has good leadership and cooperative Community for progress issues 2.The committed & Volunteered personnel 3. Has experienced and hardworking staff. 4. Positive relationship with other churches as well as local go government leaders | 1.Solely dependency on donors 2, Shortage of working capital 3.Lack of materials/ facilities 4.Parents not allow youths to join groups |
| Opportunities | Threats |
| 1.Positive participation of Youths in advocacy of work 2.The readiness of Government officials helping Youths’ CBOs 3.The group has good relationship with surrounding community, customers, Ward and Kilosa Council’s leaders | 1.. Delay in Financial release from the Donors 2. Youths not soliciting their subscription fees on time. |

### Source: Researcher, 2017

### 2.4.5 Sources of Funds for the Group

### The group has different sources of funds which include:

- ward organization.

### Membership & subscription fee T.shs 100,000/=

- Earning from Car wash business

- Aid or grants from donors/NGO

### The organized funds rising from well- wishers.

### 2.4.6 The Role of CED Student’s in the Project

- To discuss with the CBO leaders to invite expert on Carwash.

- To sensitize Ruaha community members on the importance of Car wash.

- Collaborate with ward office and other stakeholders for monitoring/ evaluation the project.

# 2.4.7 Role of Ward as Host organization

- To create the conducive environment for the project

- To ensure the sustainability of the project

- To provide technical know how to the project

- To assist administrative activities during the project life

- To make sure that progress report is provided wherever is required

# CHAPTER THREE

# LITERATURE REVIEW

## 3. 1 Introduction

This chapter presents theoretical, empirical and policy review literature. According to Ngaiza et al (2003), literature review is a procedure that guides writers to access both published and unpublished source of information in respect to study. Theoretical literature refers to citations of other studies from books, professional journals, reports, etc. which had been made in relation to the research topic. Empirical literature describes how similar projects (in local, national or international) are doing and how others have approached to embark on the similar projects.

Narrative information, which provides empirical literature, were found and cited in books, articles, web sites, reports etc. Policy literature refers regional and national and international policies designed to provide a framework to the entire project. This is the area, which study and review how the current policies provide clear guidelines or promote community economic development initiatives in the area of project intervention. ‘A critical summary and assessment of the range of existing materials dealing with knowledge and understanding in a given field … Its purpose is to locate the research project, to form its context or background, and to provide insights into previous work’ (Blaxter et al., 1996: 110).

Furthermore, Burton, (2000: 137) argued that, the literature review therefore involves a detailed search through a range of resources such as books, journals, the Internet and electronic journals, abstracts and microfiche. Literature review clarifies and focuses the research question. It helps the researcher understand the subject area more fully and identify the different theoretical approaches that have previously been applied. The literature review therefore enables the researcher to conceptualize the research question and point to gaps in existing social research into the chosen area of study. Second, the literature review may improve the researcher’s methodology

## 3.2 Theoretical Literature

## 3.2.1 Definition and Concept of Youth

Various definitions have been given by different scholars about youths. According to Oxford Advanced Learner’s Dictionary (2001), “A Youth is the time of life when a person is young, especially the time before a child becomes an adult” (2001). Shaidi Joyce (2006) argues that a youth in Tanzania is defined as a person between the ages of 15-35 years. The total population of Tanzania is 34 million equal to 33 % of the total population is Youth and 68 % of the active labour force is young people.  The core problem facing youth in Tanzania is unemployment. This problem is characterized by lack of job opportunities in urban areas, and underutilization of the majority of the national labour force in both rural and urban areas.

Unemployment has led to the increase of jobless (vulnerable) youth most in urban areas. The youth aged between 15 and 34 years are more vulnerable to unemployment. As a result the youth engage themselves in bad behaviours like theft’s, robbing (Panya road in Dar- es-Salaam, Teleza in Kigoma and more others), begging, scooping others property, immorality issues (sexual business) and being subject to get HIV/ AIDS. To rescue the situation of a vulnerable youth a co operate effort is needed.

### 3.2.2 The Theory of Poverty

Sometimes poverty can be caused by Corruption of the country as reported by ACG, (2006) which sites that the link between corruption and development is clear. Various studies involving different countries have shown that the more corrupt a government, the more underdeveloped the country becomes. (UNDP 2004). Poverty becomes more rampant, social services are reduced and investments in infrastructure and social services are diminished. Corruption fosters an anti-democratic environment characterized by uncertainty, unpredictability, declining moral values and disrespect for authority. Corruption embodies, not just a governance deficit, but also an amputation of human rights, resulting to poverty and threatening human security. Corruption is a governance issue because it involves society through its political, economic and social. When these formal and informal institutions break down, laws and policies that ensure accountability and transparency of the government become harder to implement.

### 3.2.3 The Concept of Poverty

Poverty has been the global concern for enormous years. Each country in the world is striving to get rid of poverty to her people. Poverty can be defined as a state of deprivation and prohibitive of decent life by failure to meet basic needs (URT, 2003). Poverty can be classified into absolute poverty and relative poverty. Absolute poverty is the inability of a person to attain minimum specified standards of living based on nutrition and other none food basic necessities. Relative poverty refers to the level of wellbeing which is judged to be poor or well-off based on comparing people who are of the same society or community (URT, 2005; URT, 2007).

Poverty which resulted for unemployment has existed for a long time in urban areas, whereby majorities are engaging in small business. However, poverty is classified into two main different forms, these are; income poverty and none income poverty. Income poverty is said to be exacerbating any other categories of poverty (URT, 2006) also this is justified by the (T.H.D.R, 1999/2000). In Tanzania, which in 1999 ranked 156 out of 174 countries in the Human Development Index (HDI), In Tanzania: 51% of the population live on less than $1 a day; About half or 42% of these live in absolute poverty on less than $0.75 cents a day; 81% of the labour force is rural; the majority of the urban workforce is underemployed and minimally skilled, a good number of this group is vulnerable one (THDR, 2000).

To establish car wash was thought as one of the initiatives to address poverty problem. Tanzania has engaged itself into effective Participatory approach in its different planning process to involve youths on fighting against poverty reduction. Youth’s participation in development planning as well as policy making has been the contemporary approach to ensure that youths participate in struggling pulling out from abject poverty as envisaged by the National Development Vision 2025 (URT, 2000). Striving to pool out of poverty has resulted into different strategies. MKUKUTA II has an intention of halving abject poverty by 2015. Tanzania also has adopted the Millennium Goals which aim to reduce absolute poverty by 2015 (URT, 2006).

Therefore, fighting for poverty alleviation is a crucial issue which needs many techniques of curbing it. Poverty for a long time has said to be a major phenomenon whereby majorities of Youth are engaging in hand to mouth economy. For this reason, small business for youth organized groups through diversification is the only possible means to carter the problem. However, Tanzania has engaged herself into different and effective Participatory approach in its planning process to involve local communities on fighting the enemy against poverty alleviation. Community participation in development planning has been the contemporary approach to ensure that the community participate in struggling pulling out from abject poverty by the National Development Vision 2025 (URT, 2000).

### 3.2.4 The Concept of Youth Unemployment

Tanzania, together with many other Sub-Saharan countries (Guar cello et al, 2005), suffers from a severe youth unemployment and inactivity problem in urban areas (Mjema 1997). Despite of sustained growth in the second half of the last decade, during the 1990s labor market outcomes have further deteriorated (Government of Tanzania, 2003). Although unemployment is by no means a problem unique to youths in Sub-Saharan Africa, the problem there is compounded by disappointing education outcomes that make the prospects of youths appear rather dim and by the circumstance that work is often the only asset for a large part of the population while no publicly provided insurance mechanism against the risk of unemployment is in place (Mancorda and Kondylis, 2006).

The number of Youth who complete different levels of education, from primacy, secondary and high learning institutions are entering the labour force annually is about 700,000 but only 40,000 get employment into formal sector, about 660,000. The incidence of unemployment among the youth is relatively high. The youth constitute 60 % of all people who are unemployed. According to labour Force Survey 2001 unemployment rate for the whole country is 12.9%. Almost half of the unemployed live in urban areas. For example, 46.5% of active people in Dar es Salaam are unemployed, unemployment for the other urban areas is 25.5 %, and for rural areas is 8.4%. Unemployment for people aged 18-34 was 8.6% in the rural areas and 41.4% in the urban areas. The youth aged between 15 and 34 years are more vulnerable to unemployment (Shaidi Joyce, 2006)

## 3.3 Empirical Literature

### 3.3.1 The Concept of Car Wash

A car wash (also written as "carwash") or auto wash is a facility used to clean the exterior and, in some cases, the interior of motor vehicles. No matter what happens, it is likely that as long as there are cars, there will always be a need for car washes. Fun Fact The world’s first car wash opened in 1914 in Detroit. It was called “The Automated Laundry.” Stat Fact According to recent data derived from a variety of industry sources; there are approximately 90,000 car washes in the United States. In 2013, there were approximately 113,000 car washes in the United States. As long as there are cars on the road, there will be a need for car wash businesses. Depending on factors, such as location and weather, a car wash can be a lucrative business for a budding entrepreneur. www.eynacarwash.com Accessed on 11/03/2016

### 3.3.2 Role of Car Wash Services in Income Generation

There is a parallel increase, as the number of cars on the road continues to increase the need for car wash businesses should also increase, according to the International Carwash Association website (ICAW). A car wash can also be a good business for someone who enjoys working with his hands and enjoys working with the public. Anyone can make money running a car wash!” you might have thought. Many people think a car wash is a great business opportunity because they see it as a business that doesn’t require a great deal of hands-on work but that still produces a great return on your investment.

# A car wash can be a good business for an entrepreneur with little previous business experience. According to the International Carwash Association, 37% of car wash owners have owned their business for less than five years in USA. According to a survey in Auto Laundry News, profits can range from $55,000 to $100,000 per year for a self-service car wash; also can range $500,000 to $900,000 for a full-service business. The trend in this business is offering extra services. For example, you can sell car spare parts and lubricants alongside other motor vehicle accessories. You can also set up a shop selling snacks and drinks as well as the more usual air fresheners and key chains. This is a business that can be combined along with others. For instance, it works very well with a petrol station, entertainment joints, among others. Also you can offer carpet cleaning services. (International Carwash Association www.eynacarwash.com) accessed on 13/03/2021

Starting a car wash is one of the easiest and low cost types of business. This is a business venture that can be started with just a bucket, soap and washing cloth at the bank of a river. However, if you desire a more professional service in the urban areas, you’ll have to have higher standards. One of the most important aspects of starting this business is location. You need a convenient location that has some space mostly around residential areas. For those with large capital can invest in an automatic car washing machine. This type consisting of a machine that literally “rolls over” a stationary car parked in a washing bay. Waxing: you can also offer waxing services mostly targeting the top of the range vehicles (ibid).

Finally, a nation's development should be people-centred, based on sustainable and shared growth and be free from abject poverty. For Tanzania, this development means that the creation of wealth and its distribution in society must be equitable and free from inequalities and all forms of social and political relations which inhibit empowerment and effective democratic and popular participation of social groups (men and women, boys and girls, the young and old in society by the year 2025, such that economic activities will not be identifiable by gender, race. law, politics, employment, education or culture and will have been reformed. (URT,2010).

# 3.3.3 Carwashes in MDCS’ and how can reduce Poverty

In most developed countries in different areas will demand different types of car washes. While an affluent neighborhood may have a greater market for full-service car washes, a moderate- to low-income area might have greater market demand for in-bay automatic or self-service car washes. In short, you must match your services with the demands of the neighborhood in which you’ll do business. Beyond these basics, there are the factors that determine the success of any business—how successful you are at marketing and selling your services, keeping costs under control, hiring quality employees and so on. Here are some general guidelines for the profit potential of the four types of car washes we’ve mentioned:

- Full-service car wash: $500,000 to $900,000 per year

- Exterior-conveyor car wash: $125,000 to $500,000 per year

- In-bay automatic car wash (a “3 and 1” combination of self-service and in bay automatic wash bays, discussed in Chapter 4): $75,000 to $125,000 per year

- Self-service car wash (assuming a four-bay, self-service facility): $55,000 to $100,000 per year Now that you know the basics of the car wash industry, it’s time to move on to the nitty-gritty of running and building your business.

For those with large capital can invest in an automatic car washing machine. Therefore, this is profitable business to MDCS’. http://www.entrepreneur.com/ downloads/guides/1076_Car_Wash_08_ch1.pdf

### 3.3.4 Contribution of Entrepreneurship on Economic Growth and Development

Reinforcement on promotion of small enterprises including small industries development put in place under the Small Enterprise Policy which intends to prioritize small business in the county plans (Shaidi 2006). The purchase of Pressure washer car wash machine project is planned to be used at Ruaha ward. This will be the modern car wash for income generating activities (IGA) revised Youth Policy of Tanzania of 2007 under the youth development. The project is also in hand to hand with Millennium Development Goals (MDG) 2015, the MKUKUTA II under the section of poverty reduction. MKUKUTA II builds on the predecessor Strategy (MKUKUTA I), it is more oriented towards growth and give better productivity with greater alignment of the interventions towards wealth creation as way out of poverty (URT, 2010:2).

This research tries to run parallel with the Tanzania five years Development plan (2011/12-2015/16) as well as the Nation Development vision 2025, focusing on poverty reduction through SMEs involvement. However, the basic issues in the development Vision focuses on increasing production and market availability for the products. These objectives mainly deal with economic issues and also increase involvement of the people in working for their own development. The thrust of these objectives is to attain a sustainable development of the people with high quality livelihood. Therefore, the car wash project is hereby presented as a driving force towards youth involvement in poverty reduction goals and creates self-employment through those strategies Vision (2025).

### 3.3.5 Problems that Hinder Youths Empowerment

According to URT, (2007) and the Integrated Labor Force Survey (2001), Young people who constitute about 65 per cent of the total labor force, require economic enfranchisement and equitable access to resources that provide a solid economic and material base for their development. One of the key resources is land of which young people have limited access to land ownership. Customary practices discriminate young ones to own and even to inherit land. There is limitation on equity of resource allocation and capital accessibility for youth development, which affect their effective participation in economic activities.

On the other hand, the major challenges facing youth are the same viewed by Simon Amenya, et al., (2009) Young people are provoked to start their own business with small capital, this is due to the chance of finding jobs in the current labour market which is very limited. However, lacking of support on sustainability governed by other factors such as availability of investment capital, risk absorption capacity, and lack of know how in terms of financial management, enterprises development and market accessibility (Juma, 2007). The ineffectiveness of enforcing regulations with respect to registering, monitoring and coordination of labor migration poses a serious challenge for Tanzania to provide employment opportunities for its youths.

According to Ngowi, et al., (2014) Access to finance for youths is very challenging in the context of accessing the available funds for initial capital, particularly in banks. Youths entrepreneurs (aged 15-24) do face more challenges most of the time compared to mature people. Some of the challenges to youths includes requirement to have formal business with license and address, to have good business plan, to have collateral most also fixed asset. They are also required to have business transactions documentations such as sales, sales revenues, profit and loss, to have good referee, required to pay for loan fees, need to get approval of male members of the family (family head) before accessing a loan to financial institutions.

According to Jonathan, (2014) attests that “Despite of the increased role that youths are playing in the growth and development of the nation’s economy it is depicted that development programs totally does not involved the need of this special group”. In Tanzania the government and other stakeholders has taken tremendous efforts to empower youths and other vulnerable groups, but they are still facing major challenges in accessing employment opportunities in many sectors. Other challenges are on how to facilitate access to information and technology to the majority of youths especially those in the urban setting (URT, 2005).

The United Nations, since its inception, has continuously called for the increased participation of youth. Historically, youth participation has been very limited. However, recently it has gained momentum and they are now seen and heard at various levels of the UN. Youth from all parts of the world participate not actively in all relevant levels of decision making processes because this affects their lives today and has implications for their lives today and in futures. Moreover, they should establish mechanisms that permit youth access to information and provide them with the opportunity to present their perspectives on government decisions for their destiny (UN 2002).

The major problem faced by many youths today is lack of enough capital to run their business. The income poverty has said to be the urban phenomenon whereby majority of people are concentrated on small business by using little capital and poor transport. Household’s consumption reports have been mainly used in establishing poverty status by matching it with the established poverty lines in the particular time. Expenditure pattern tend to be more stable than income and commonly used as the best indicators of income poverty. The term income poverty has been used throughout since it is in more common usage than the more technically correct consumption poverty (URT, 2005).

# 3.4 Policy Review

The Ministry of Labor and Youth Development (MoL) is in charge of implementing the National Employment Policy, sanctioned by cabinet in April 1997. This policy revisits the state of wage employment in Government, parastatals and the private sector and self -employment in agriculture and the informal sector. The National Employment Promotion Service Act was passed by Parliament in 03/1999. Special attention was given to the employment implications of micro and small enterprise development. Tanzania Youth Policy, the National Youth Development Policy (2007) defines a youth as 'a boy or girl who is in transition from childhood to adulthood'. The policy adopts the definition of youth as declared by the United Nations, which defines a youth as a person aged between 15 to 24 years. The analysis of youth employment is based on this age group. Some policies of its different kinds have been formulated for dealing with the purposes of addressing youth’s empowerment. Some of them are as follows; -

Youth’s Development Policy (2007) mainly focuses on economic empowerment of youths and eradication of poverty and hunger as one of its four main areas of focus by the government of Tanzania through the National response of Micro-Finance Policy, as regards the MDGs for Action. The policy has enabled mainstreaming of youth concerns in the other Government Policies like the National Health Policy, the Education and Training Policy, the Labor Development Policy and Youth Development Policy included. Contemporarily, every effort took place in Tanzania should focus on the National Development Vision of 2025.

The policy envisages alleviating poverty for all Tanzanian by 2025. Minority of Tanzanian still residing in urban areas (25%) in which its major economic activity is small enterprises. To realize the National Development Vision, deliberate and conscious efforts should focus on Youths development. The envisioned status of Tanzanians is substantially developed one with a high quality livelihood. Under this vision, by 2025 abject poverty will be a thing of the past.

In addition, Tanzania Development Vision 2025, one of the strategies is Poverty Eradication Strategy. MKUKUTA which was accompanied with some policy and national strategies: The National Employment Policy; The Youth Development Policy; The Local Government Reform Agenda; National Population Policy; Small Enterprise Policy and MKURUBITA for Tanzania Zanzibar. The Youth Development policy and the Nationals Employment Policy are currently under review to take into consideration the globalization and National Vision 2025 Poverty Reduction Strategy is in place.

The National Youth Development policy of 2007 focuses on youth development issues which include; economic empowerment, environment, employment promotion, youth participation, H1V and AIDS, gender, arts and culture, sports, adolescent reproductive health and family life issues. Youth Development is a crosscutting issue which requires multi-sectoral approach for effective implementation. The National Youth Development Policy will therefore depend on successful mainstreaming of the youth development issues in Ministries' policies and other stakeholder’s development programs.

However, different policies identify strategies to address the problems of youth unemployment. According to the  Millennium Development Goals (MDGs) which are eight international development goals that were established following the Millennium Summit of the United Nations in 2000, one of them is to eradicate hunger, following the adoption of the United Nations Millennium Declaration. All 189 United Nations member states at the time (there are 193 currently) and at least 23 international organizations committed to help achieve the Millennium Development Goals by 2015, the Youths who are majority in LDCs Tanzania included.

Furthermore, Tanzania as a country has signed various rules that protect and fight youth’s rights, such as the right of education. Right of protection, Avoidance of hard works and more others.  Also other efforts are being made to assist youth to acquire good standards of life from their activities they are doing. They are obliged to access internal and external markets like street vendors complex in Dar-es-salaam. Various credit facilities targeting youths have been initiated. Some of them are the youths’ development fund (YDF), which is supported by the government administered by the local councils. The fund provides credit to youths for total of 114 local councils of mainland Tanzania. There are also other funds, established by different stakeholders, which are geared for vulnerable youths. These include; promotion of urban initiative and development enterprise.

The national micro-finance policy (2000) provides guidelines to achieve gender equity in accessing financial services in order to empower women economically. It directs that special efforts be made to incorporate mechanisms that would make the services accessible to both women and men. The policy also gives flexibility in regulating micro-finance institutions including specialized and non-specialized banks, urban community banks, like bank of Africa (BOA), Exim Bank, Equity Bank, SACCOS, NGO’s and other private owned financial institutions. Those few institutions provide credit to youths provided are in groups also terms and conditions that can be adhered by youths. Although the policy has been able to explain various things it has its complications for implementation.

The national youth development policy (2007) reveals that young people have limited equitable access to resources that provide a solid economic and material base for their development; however, the issue is more critical to young ones they are not allowed to inherit land. The policy directs a promotion of equitable access to land and other resource allocations. Emphasis shall be put on rural youth and gender equity, nevertheless there is limitation on equity of resource allocation and capital accessibility for youth development, which affect their effective participation in economic activities. The policy directs that there shall be an affirmative action by the ministries of concern to allocate funds which will enhance satisfactory direction with a view of having sustainable funds, to support youth with specific focus on their income generating activities. Also there shall be mechanism to promote the establishment of youth friendly credit support services and empower youth on credit.

According to URT, (2007) and the Integrated Labor Force Survey (2001), young people also lack skills on marketing and production of quality products. The policy statement states that “there shall be a promotion of equitable access to land and other resource allocations. Emphasis shall be put on small and medium enterprise policy, but this is not practical to youth in urban areas. This was proved by the leader of youth district commissioner who said ‘there is no land even a small one which has been located by the local council for youth’’ (April, 2021).

# CHAPTER FOUR

# PROJECT IMPLEMENTATION

## 4.1 Introduction

Implementation plan is a plan design that indicates the table of activities, resources required to implement the project and responsible persons who will execute the activities. The implementation plan shows the sequence of activities and time that will be implemented. The purpose of the project is to improve quality of life of Ruaha ward community members especially youths. The overall objective of the project was to provide knowledge and skills of hand and pressure washer machine its operation and maintenance for owners and users/clients by the end of June, (2016). Project implementation was participatory in nature involving target group, stakeholders as well as a researcher.

The implementation of the project begun in January 2021, the project planning involved CNA and situational analysis of the HAZINA YOUTH GROUP to identify capacity building gaps hence prepare an implementation plan to address the gaps which were identified. The chapter documents the project plan through a logical frame work analysis, the actual implementation that took place and the project Gantt chart. Therefore, this chapter represents the actual work done in implementing the project and describes what was supposed to be done according to the plan, what have been done and report what was accomplished. Furthermore, the chapter describes in detail the project, which was to be implemented, it shows planning schedule and activities that had to be implemented. It itemizes expected and actual products and outputs and staffing pattern.

# 4.2 Products and Outputs

During the preparation of the implementation plan a list of output indicators describing project activities were also developed according to specific objectives. List of indicators was very important in the process of measuring the desired success.

# 4.2.1 Project Products

The major product among of many others is livelihood improvement of HAZINA YOUTH GROUP members at Ruaha ward.

# 4.2.2 Project Output

The project was expected to accomplish the following outputs by the end of 2021. These included;

- Primary stakeholders skilled in both hand pressure car washing services.

- Car wash owners skilled in business and handling.

### Primary stakeholder’s self-employed as car washers

### Car wash owners and community equipped with knowledge of the importance of car wash storage and handling.

### Good networking between car washers and consumers of car washing services

## 4.3 Project Planning

Project planning is a discipline for stating how to complete a project within a certain timeframe, usually with defined stages and with designated resources. In this section project implementation plan, inputs needed to accomplish activities, the staffing pattern of the HAZINA and project budget are shown as to how the project will be implemented. Moreover, logical framework and budgeting are also part of planning process. Project planning generally consists of identifying deliverables and creating the work breakdown structure, identifying the activities needed to complete those deliverables and networking issues and the activities in their logical sequence, estimating the resource required, time and cost for activities under taken.

### 4.3.1 Implementation Plan

# Table 4.1: Project Implementation Plan

| Objective | Activities | Resource/ Input | Responsible Persons | Time Frame |
| --- | --- | --- | --- | --- |
| To conduct training 12 car washing project by June 2021 | To conduct training on; Effective car washing Car wash overhead Proper detergents for car washing Car wash chemical management | -Transport -Funds -Stationeries -Training materials - Experts costs | CED Students, Trainers ATAPE NEMC | April - June, 2021 |
| To conduct training on entrepreneur’s skills for 12HAZINA members by May, 2021 | To conduct training on; -Car washing requirements, e.g. Brushes, soaps -Steps in car washing, -Handling of the car washing machines, -Precautions to be taken when washing, -How to operate the machine. | Transport -Funds -Stationeries -Training materials -Experts/NEMC costs | CED Students, Trainers, ATAPE NEMC | May- June, 2021 |
| To establish car wash project by May, 2021 | -electrification of the site -installation of car washing equipment -acquiring a license -procure the necessary consumables -Environmental issues/ (NEMC -Construction of Car wash site -Building /set-up the car wash house -purchasing Pressure washer pump -sewage system -water installation | Transport -Funds -Stationeries -Training materials -Experts/NEMC costs | CED Students, Trainers, ATAPE NEMC | May-June,2021 |
| To establish reliable market of car washing of HZN by June, 2021 | To conduct train on Preparation of marketing tools such as brochures, radio adverts etc Identifying potential customers Distributing brochures and paying for the adverts to reach potential customers -Sensitize them on the benefits of regular car washing | Transport -Funds -Stationeries -Training Materials Trader officer -Experts/NEMC costs | ATAPE, WCD Officer ,SIDO Business officer and VEO | May-June,2021 |

Source: Survey, 2021

The participatory planning of the project was done by the MCED student in collaboration with HAZINA members and different stakeholders in the community to provide their views on how the project was supposed to be implemented. A work plan shows a number of activities to be conducted within the located time, available resources and the person responsible for each project objective. The project work plan was participatory in nature and the approach prepared by involving different stakeholders and others people were consulted to provide their views on how the project was supposed to be implemented.

In short the project implementers were HAZINA GROUP members, NGO members, VEO, WEO and District leaders and others developmental institutions. The CED student was collaborating with all project implementers in planning, implementation, monitoring and giving advice to the right direction on how the project should take off. Table 4.1 testifying the implementations plan.

# 4.3.2 Inputs

The inputs of project implementation involve various things such as materials resources, financial, time and human who employed to meet the expected planned goals. Human resources were experts from KILOSA LGA, Ward officer from Ruaha ward and HAZINA GROUP chairperson from Ruaha. The inputs required for accomplishing the above planed objectives and activities are shown in Table 4.2.

## Table 4.2: Project Inputs

| Inputs | Cost ( Tshs) |
| --- | --- |
| Trainers cost | 70,000 |
| Training costs | 803,000 |
| Training venue | 200,000 |
| Training materials/manual | 110,000 |
| Purchasing &Transport of Pumps for car wash from one place to site | 1,200,000 |
| Car wash construction & materials purchase | 2,230,600 |
| Total input ( costs) | 3,413,600 |

### Source: Survey, 2021

### 4.3.3 Project Logical Framework for a Car Wash Services

Logical framework is a management tool for effective planning and implementation of developmental projects. It provides clear, concise and systematic information about a project through a framework. We know about various components of a project such as goal, objectives, activities, results and indicators concerned. The Logical framework helps in connecting all these components in one framework, presenting the clear relationship between these components and leading to the achievements of the expected results. It is also widely known as Goal Oriented Project Planning/ Objectives Oriented Project Planning. Logical framework for Car wash services project were tools for concisely describing the results of project design process, as it gives a summary in a standard form as follows: -

- What the project is going to perform & achieve

- What activities will be involved in the project

- What are resources or inputs (human, technical, infrastructural) are needed

- What are predictions/ potential problems could affect / hinder the success of the project to take off

- How the progress and success of the project will be measured and verified

The details on activities, inputs (resources) and outputs are described in the project logical framework (Table 4.3).

# Table 4.3: Logical Framework Matrix

| Summary of Objectives and Activities | Objectively Verifiable Indicators (OVI) | Means/Source of Verification (MOV) | Assumptions |
| --- | --- | --- | --- |
| Goal: To train target group proper ways of car wash business, handling and Maintenance. | Car wash handling, Maintenances and quality Services | - CBO reports - Observation | -Successful implementation of the car wash Project business. |
| 1. To conduct training on car wash to 12 youths in Ruaha ward by February, 2021 | (i) 12 members of CBO group trained on Car wash services (ii)Skills on effective car wash handling. (iii) Skills on car wash overheads (iv) Skills on proper detergent use for car washing (v) Skills on car wash chemical management | -Survey/ Observations - CBO reports & trainer’s reports | - Youths are willingly to form group. - Fund available. - Target group attended Training. - Active participation of target group |
| 2. To establish car wash project at Ruaha ward by May 2021 | (i)Most number of participants attended & participated in training (ii) The high income of car wash. (iii)Number of car wash services materials constructed (iv)Number of some car wash material purchased | -Trainers/ CBO report - Observations - Interview | -Target members are willing to attend training -Availability of training materials -HAZINA members are willing to participate |
| 3. To establish a reliable market of Car wash services rendered by HZN members by June 2016. | (i)More services offered and sold at the market by HAZINA -High quality services of car wash |  | -Availability of Customers, - willingness to buy /get the services -Good services offered |
| Expected outputs 1. Effective use of Car wash, handling and quality services. 2.Good and genuine machines. 3.Increased quality of washing. 4.Innovative,initiative attitudes | 1. High income to target group 2. Increased sales turnover 3. Customer care improved. 4. High quality of Car wash services offered to customers. | 1. Interview with group members. 2. Interview with customers. 3. CBO financial report 4. Observation and interview with customers 5. Improved sewage systems and water recycling. | - Training objectives achieved. - Qualified staff employed. - Brushes & soaps facilities Purchased |
| Activities 1. To train the target group on Pressure pumps car wash. 2. To train target group on better handling & running of car wash. 3. To train the target group on methods of improved way of car wash services. 4. To conduct training on entrepreneurship & marketing skills in relation to car wash business. 4. To train target group on the basic principles and practice of entrepreneurship | Inputs 1. Training venue 2.Trainers/facilitators 3.Transport 4. Stationery 5. Food and Refreshment 6. Training materials 7. Accommodations 8. Training manual 9. Funds 10. Facilitators cost | 1. Cash Sale receipts. 2. Receipt voucher. 3. Delivery Note 4. ledger | - Availability of financial resources to pay trainers/ facilitators. - Positive participation in Training of target group. - Availability of resources to Cater training costs. |

Source: Survey, 2021.

### 4.3.4 Staffing Pattern

The project has five voluntary staff being a program coordinator, program accountant officer, Technical officer, M&E officer, and field officer. Kilosa District offered the land as project site. The project implementation was getting high support from community development department, cooperative and Trade and market department and Human resource department.

# Table 4.4: Staffing Plan and Training Needs

| No | Position | Duties /Supervisory Roles | Training needs |
| --- | --- | --- | --- |
| 1 | Chair person | To ensure the Management Committee functions properly To ensure the project/ group is managed effectively To provide supervision to the project To represent the group as public relations To call special meetings of the group where appropriate To review and sign minutes of group meetings/HAZINA To act as Chairperson for meetings of shareholders | Skills of leadership Job descriptions |
| 2 | Vice Chair Person | To assist the chair person To serve as chair person in the absence of the chair person To take the important role in monitoring the implementation of the project strategies | Job descriptions. |
| 3 | Secretary | Ensuring meetings are effectively organized and minute Maintaining effective records and administration Upholding the legal requirements of governing documents Communication and correspondence issues | Responsibility of the secretary. Accountability Recording & Keeping |
| 4 | Vice Secretary | Directly assist the Secretary in all matters pertaining the group issues | Job descriptions. Responsibility |
| 5 | Treasure | To maintain an overview of the project financial status for all transactions and To ensure that proper financial records and procedures are maintained | Financial skills. Accountability Book keeping Business management |

Source: Survey, (2021)

Also the project has more support from the municipal council office of youth’s development department and the office of land department and CED Student for technical knows how. For effective   and smooth running of the organization, no salaries are provided by the group to the leaders, each member of the staff adhered his or her responsibilities and duties as described in Table 4.4.

### 4.3.5 Project Budget

A project budget is the total amount of authorized financial resources allocated for the particular purpose(s) of the project for a specific period of time. It is the primary financial document that constitutes the necessary funds for implementing the project and producing the deliverables. The budget planned for the car wash project was      Tshs 5,178,600 as indicated in table 4.5

# Table 4.5: Project Budget

| Activity | Budget (T.shs) |
| --- | --- |
| Identification of training needs | 35,000 |
| Preparation of training materials/ manual | 130,000 |
| Identification of training resources (Human and financial resources) | 40,000 |
| Identification of training venue/hiring | 100,0000 |
| Acquiring required training resources | 45,000 |
| Meeting with target group leaders to discuss and agree the training schedule | 55,000 |
| Trainers costs | 80,000 |
| Purchasing materials and Construction of Car wash site | 2,795.600 |
| Conducting training on maintenances, Car wash installation & handling. Keeping records & running car wash business. | 325,000 |
| Conducting training on installing system of Car wash business. | 85,000 |
| Purchasing facilities of car wash business. | 1,300,000 |
| Conducting training on the concept of marketing and Entrepreneurship skills. | 120,000 |
| .Designing/ Disseminate of advertisement through posters and local Radio PM & E | 68,000 |
| Total budget | 5,178,600 |

Source: Research Data,(2021)

Ruaha ward council contributed a total of Tshs 2,661,800.00 as photocopying and training venue cost and some building materials while Tshs 1,876,800.00 was contributed by FPCT Church, Tshs 12,000.00 WEO office Tshs 1,000,000.00 solicited from well-wishers and T.shs 520,000/= contributed by HAZINA GROUP. However, the fund obtained were expected to be enough for the completion and implementation of the planned project activities as per work plan as stipulated in Table 4.5.

The Ruaha ward meetings were organized for sensitization of the community members about the project and mobilization of Hazina youth Group to establish the Car wash services project. The program/activity was done by the CED student who was in charge/ researcher for this project. Formation of a group of 12 urban youths was organized and formed a group which will be the key in dealing with the project. CED student was there to assist the urban youths to form entire group. See the members of HAZAINA YOUTH GROUP.

# Figure 4.1: Church Members Solicit Fund for HAZINA YOUTH GROUP

Source: Survey, 2021

# Figure 4.2: HAZINA Members with CED Student during the Formation of Group

Source: survey, 2021

Formalization and selection of leaders, members decided to run it officially by the name HAZINA members and they have opened up the bank account. The CED student assisted the group to reform a group constitution in order to connect them to District Council. Training manuals were prepared for use during training. These manuals were entrepreneurship education training manual and Car wash services training manuals. The CED student monitored the activity which was done by the community development officer and trade district officer. Community development officer prepared entrepreneurship education training manual and trade officer prepared car wash services training manual. In fact, two manuals were prepared for catering the intervention of car wash services in urban areas.

Conduct training, this was a three days training of which the CBO group was trained on entrepreneurship skills and how to run the car wash services. The members were imparted skills on how to run the car wash services project as well to be good entrepreneurs. Some topics and sub-topics of their kind were taught including how to develop a business plan, set up the business and managing it and carrying out a market research. In short all the above intended to make the project sustainable.

# Figure 4.3: Youths during Entrepreneurship Training (Group discussion)

Source: Survey, 2021

The Construction of car wash site, two technicians were hired to construct one site for car wash services. Two pressure washer machines were purchased ready to start the business of car wash services. Various ways were adopted to reach the clients and market the business. Word-of-mouth is the fastest and most effective, although it can also place classified pumps according to the power purchase. Two pumps below are some of among eight types of pressure washer machines. They both use diesel and petrol fuels. Each one cost of Tshs 600,000/= and 400,000/= respectively. This added the business value and Services

Running the car wash services, installing of water systems roller and some connecters were needed and were purchased. The group members guards the site and uses the facilities properly. Youth project members have divided themselves in four groups of which each group consists of three people. The division makes them to rotate two times per week for offering services to clients. Each group works for one day per week. Figure 4.4 shos the details.

# Figure 4.4: Easy way Youth used to wash Car

Source: Survey, (2021)

Designing of advertisement: The adverts were designed and produced in order to disseminate the information to the community. These adverts were in form of posters. Posters were distributed within the community and also those who were outside the community were informed through phones. So the market was found through these means of communication. The checklist for monitoring and evaluation were prepared to monitor the activity. This enabled to see if the project was implemented as planned.

### 4.4 Actual Implementation

The actual implementation is the process whereby “project inputs are turned to project outputs”. Also, this is putting in action the activities of the project, putting into practice what was proposed in the project document. In short is involves transforming the project proposal into the actual project, and administration of the project purposes. Car wash services project applied involvement approach, whereby KUVM are the first beneficiaries’ who implemented the project. However, other stakeholders provided the financial resources, including Kilosa district council, CED student and technical personnel assistance. The actual implementation also it shows whether the activities implemented as scheduled or planned, objective, output, activities, resources, timeframe, actual implementation and remarks are shown in figure 4.5.

### 4.4.1 Project Implementation Gantt Chart

Gantt chart is a technique in which the activities of the project are drawn as a horizontal bar, the   length of which is proportional to the time duration of the activities (Namwata, M.L.2010). During project implementation process Gantt chart method facilitated stakeholders to visualize easier what was taking place showing the primary dependency relationship among activities and the actual time spent from January to June 2021.  It also depicted activity progress which obtained towards the completion of each step of activity as summarized in Table 4.6.

# Table 4.6: Project Implementation Gantt Chart

| Activities | Implementation period | Resource needed | Responsible person |
| --- | --- | --- | --- |
|  | Year 2019 | Year 2021 |  |  |
|  | O | N | D | J | F | M | A | M | J | J |  |  |
| Identification of the Community |  |  |  |  |  |  |  |  |  |  | Stationery | CED student |
| Writing a letter requesting to conduct CNA |  |  |  |  |  |  |  |  |  |  | Stationery | CED student |
| Conducting CAN |  |  |  |  |  |  |  |  |  |  | Funds Stationery Fuel | CED student Community Member |
| Identification of problem |  |  |  |  |  |  |  |  |  |  | Funds Stationery | CED student Community Member |
| Project formulation |  |  |  |  |  |  |  |  |  |  | Stationery | CED student Community Members |
| Writing CNA report |  |  |  |  |  |  |  |  |  |  | Stationery, Funds | CED student |
| Identification of training needs |  |  |  |  |  |  |  |  |  |  | Funds Stationery | CED student and target group |
| Identification of training resources |  |  |  |  |  |  |  |  |  |  | Funds, Stationery | Facilitator CBO leaders |
| Mobilization of financial resource |  |  |  |  |  |  |  |  |  |  | Funds Stationer | -CED student |
| Preparation of training materials/ manual |  |  |  |  |  |  |  |  |  |  | Funds, Stationery | CED student Trainers |
| Identification of training venue |  |  |  |  |  |  |  |  |  |  | Stationery, Funds | CED student |
| Acquiring required training resources |  |  |  |  |  |  |  |  |  |  | Funds | CED student |
| Meeting with CBO leaders to compromise and confirm training schedule |  |  |  |  |  |  |  |  |  |  | Funds, Stationery | CED student Trainers CBO leaders |
| Conducting training on Car wash project |  |  |  |  |  |  |  |  |  |  | Funds, Training materials | CED student Trainers |
| Conducting training on better ways of car wash operation & maintenances |  |  |  |  |  |  |  |  |  |  | Funds, Training materials | CED student Trainers |
| Conducting training on methods of improved way of running car wash |  |  |  |  |  |  |  |  |  |  | Funds, Training materials | Trainers CED student |
| Conducting training on the concept of marketing and entrepreneurship. |  |  |  |  |  |  |  |  |  |  | Funds, Training materials | Trainers CED student |
| Conducting training on simple Book keeping |  |  |  |  |  |  |  |  |  |  | Funds, Training materials | Trainers CED student |
| Conducting Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  | Funds, Training materials | CBO leaders |
| Writing project report |  |  |  |  |  |  |  |  |  |  | Funds, Training materials | CED student |

Source: Survey, 2021

### 4.5 Chapter Summary

Based on the findings from project, it was evident that the group strongly believes in the participation of the HAZINA YOUTH GROUP themselves in all decision-making processes that ultimately influence and have an impact youth unemployment. For this reason, project sustainability became a very crucial matter for group to consider during the project’s implementation. The financial sustainability was a core aspect of the project since one of its objectives was to ensure the organization improved its resource mobilization and fundraising approaches. The project enabled to acquire funding from Kilosa district council. Furthermore, the project made other concrete follow-up recommendations that will enhance the sustainable income generating activity to alleviate poverty.

# CHAPTER FIVE

# PROJECT PARTICIPATORY MONITORING, EVALUATION AND SUSTAINABILITY

## 5.1 Introduction

Any successful project benefits to the end recipients are entirely built on participatory monitoring, evaluation and sustainability. The chapter explains more about the project participatory monitoring, evaluation and sustainability. Participatory monitoring and evaluation is crucial in any project. To determine whether the project is operating within the stipulated limits and within the resources available, monitoring of the activities is required. At the same time to determine whether the activities will lead to the expected objectives, a periodical, midterm evaluation is required and at the end of the project evaluation is required to determine whether the expected objectives and outcomes are compiled/ achieved.

PM&E can, therefore, provide more comprehensive information on efficiency, relevance, sustainability, impact, clearness and effectiveness of work in progress/ project. However, the chapter is divided into the following parts: monitoring information system; participatory monitoring methods, participatory monitoring plan, participatory evaluation plan, performance indicator, participatory evaluation methods, project evaluation summary and project sustainability.

# 5.2 Participatory Monitoring

This refers to systematic recording and periodic analysis of information which has been chosen and recorded by both insiders with the help of outsiders. Therefore, participatory monitoring is a system that involves the community to monitor the programmer activities. The objectives of participatory monitoring was to analyze current situation, identify problems and find solutions, discover trends and patterns, ensure project activities on timeframe, measure progress towards objectives and formulate the future goals and objectives and make decisions about human, material resources and financial.

The aims of Participatory Monitoring was to supervise the implementation of planned activities such as sensitization/awareness, meeting to Ruaha ward community members, training on entrepreneurship skill, financial management, governance and leadership, establishing of Car wash services, empowering and advocacy meeting. However, various technique and methods were employed to collect information, process and analysis to verify the progress of the planned activities. Participatory monitoring also used various participatory methods and includes various stakeholders such as municipal leaders, ward leaders, local government leaders, and NGOS members themselves. Participatory monitoring was the continuous assessment of the progress of the project towards achieving the desired goal and objectives.

Monitoring basically included the project activities implementation, project output and project outcome or impact. Monitoring as per project implementation plan involved the whole process of routine data gathering and giving feedback about the progress of the project to stakeholders.  Another aim of Participatory Monitoring was to build a spirit of ownership of the project to the target group and to bring the attention of the project implementers to any relevant changes to project implementation. It was conducted to measure the progress and evaluate the project success and get a clear picture of project activities such as sensitization meeting to HAZIANA members and Ruaha community members, training on entrepreneurship skills, financial management, managerial skills, record management, HIV/AIDS and leadership to HAZIANA members. It was planned to be undertaken throughout of the entire period of the project implementation, to ensure effectiveness of the project activities, to establish indicators and to maintain the standards of the aimed project. It also intends to get information for future evaluation process.

### 5.2.1 Monitoring Information System

Monitoring information system is a monitoring tool designed to collect and analyse  the project information regarding the planned activities which assists the implementers of that project to assess their performance during the implementation process. For creation employment for the youth project the monitoring information system designed to create data sheet which can record the related information against planned activities within the timeframe. The necessary information include number of training and sensitization meeting required and actual implementation, records of participants who attended that project activities, information on project materials received from different stakeholders.

Monitoring also include the amount of loan taken by the target group, loan repayment and type of business ventures established by youth group.  The process of recording will be done weekly bases because the youth group met twice per monthly and the youth management are the responsible of writing monthly report and present it to general meeting and CED student will help the group. For improving life standards through business in improving livelihoods of HAZINA youth’s members through a car wash project at Ruaha ward in Kilosa.

### 5.2.2 Participatory Monitoring Methods

The participatory monitoring methods used to engage community in the monitoring of the project. The project employed participatory methods and techniques to ensure that all internal implementers were fully involved in project activities. The PRA and techniques employed to collect information like observation and documentation analysis for secondary data, these methods are explained below.

### 5.2.2.1. Document Analysis

This method was used to collect data from some documents sources at the Centre and municipal level. The documents used were training report, sensitization and advocacy meeting conducted. Minutes for weekly and monthly meetings from the target group who meet in every week to discuss their achievements, challenges and agreements on how to overcome challenges and the way forward were also used. Other information’s documented were loan and loan repayment forms. Furthermore, CED students hand book were used as a guiding tool towards this exercise / task.

### 5.2.2.2 Observation

Through observation, internal implementers observed the progressive of activities if it had implemented as planned. These activities included type of training, business ventures and meeting carried out, number of participants attended such training and meeting, number of HAZINA group members who joined the groups, and the loan taken from the Bank if deemed so, and amount of profit raised by the targeted group (HAZINA).

### 5.2.3 Participatory Monitoring Plan

Jain & Polman (2003) asserts that “Participatory community monitoring and evaluation are extremely important for learning about the achievement/ deviation from the original concerns and problems faced by local development projects/ programs being implemented, so that corrective measures can be taken in time”. The main purpose of monitoring is to provide information during the life of the project, so that adjustments and/ or modifications can be made if necessary. Monitoring is the process of routine gathering of information on all aspects of the projects.

# Figure 5.1: Facilitators, CED Student and HAZINA GROUP Members Getting Lunch after Entrepreneurship Seminar

Source: Survey, 2021

The project has participatory monitoring plan that includes monitoring methods, activities to be monitored, indicators of progress, responsible person and time frame. All these helped stakeholders to collect information needed to analyze the current situation, identify the problem and find solution, keep the project activities on schedule hence smooth achieving of intended objectives.

# Table 5.1: Participatory Monitoring Plan

| Work plan Activities | Monitoring Objective | Objective verifiable indicators | Importance of monitoring | How gathering monitoring information | Responsible person | Time frame |
| --- | --- | --- | --- | --- | --- | --- |
| Identification of training needs | - To know training needs of the target group | -Conducted trainings -Target groups attended trainings | -Know the gap and train what is real needed by the target group | -Training needs assessment report | CED student CBO members | Jan 2021 |
| Identification of resources ( Human and financial resources) | - To know and get right trainers and funds for training | - Acquired resources -Conduct training Opening account. | - To have valuable resources for implementation of the project. | -Human and finance resource report | - CED student, -CBO members - CBO leaders | Jan,2021 |
| Preparation of training materials/ Training Manual | - To get training manual for guide training. | - Developed training manual | - Having a tool of training | Training report and Manual | - CED student | Jan-Feb.2021 |
| Identification of training venue | - To have venue for training | - Acquire venue for training | - To avoid inconveniences | -Visiting training venue | - CED student - CBO members – Leaders | March-April, 2021 |
| Acquiring required training resources | - To acquire training materials | - Acquired training materials | To be well organized before starting trainings | -Training resources report | - CED student | April, 2021 |
| Meeting with target group leaders to compromise and confirm training schedule | - Acquitting group leaders and members the intention of trainings | - Conducting group leaders meeting | To make training move smoothly and as planned | -Visiting the CBO leaders -CBO leaders meeting | CED student –Trainers | April, 2021 |
| Conducting training on Car wash project | - To provide knowledge and skills to the target group | -Number of participants attended trainings | Target group acquire knowledge and skills | Training report -Relevance of training materials | -CED student -Trainers | April, 2021 |
| Conducting training on better ways of car wash operation & maintenances | - To provide knowledge and skills to the target group | - Number of participants attended trainings | Target group acquire knowledge and skills | -Training report -Relevance of training materials | -CED student –Trainers | April, 2021 |
| Conducting training on methods of improved way of car wash handling and quality control | - To provide knowledge and skills to the target group | - Number of participants attended trainings | Target group acquire knowledge and skills | -Training report - Relevance of training materials | -CED student –Trainers | April-May. 2021 |
| Conducting training on the concept of marketing and entrepreneurship | - To provide knowledge and skills to the target group | - Number of participants attended trainings | Target group acquire knowledge and skills | -Training report - Relevance of training materials | -CED student –Trainers | May, 2021 |
| Training on simple Book keeping | - To provide knowledge and skills to the target group | - Number of participants attended trainings | Target group acquire knowledge and skills | - Training report - Relevance of training materials | -CED student –Trainers | June, 2021 |

Source: Survey, 2021

# 5.2.4 Participatory Evaluation

According to Zikoski A. & Luluquisen M. (Aoril, 2002) “Participatory evaluation is a partnership approach to evaluation in which stakeholders actively engage in developing the evaluation and all phases of its implementations”. Also TACAIDS, (2004) define participatory evaluation as a process that advocates for involvement and participation of community members and other stakeholders in designing and execution of the evaluation process.

Participatory Evaluation uses data and records during the process of monitoring and other information such as focus group discussion and user survey to review performance and identify ways to make improvement better. Therefore, monitoring and evaluation are complementary project management functions which ensure that the project is running on the right way/ direction.

## This aimed at enhancing the best practices of the project. Evaluation was carried out as a continuous activity with the participation of all project stakeholders and most important beneficiaries. Negotiation leads to agreement on how progress would be measured and the findings acted upon, they decided to undertaken the midterm evaluation after six months and one year after ending of the project. The evaluation was carried out by project management committee from village representing the targeted group and some officials from the District and NGO themselves.

Participatory evaluation involves the assessment of change through processes that involve many people, each of which is affected by the impacts being assessed. Negotiation leads to agreement on how progress should be measured and the findings acted upon. Before the implementation of creation employment for youth project the all implementers discussed and agreed on how to implement the project by setting the project objectives, goals and activities. They decided to undertake the mid-term evaluation after six months and one year after ending of the project.

### 5.2.5 Performance Indicators

From the Wikipedia, the free encyclopedia, (accessed on 24th May, 2021); “A performance indicator or key performance indicator (KIP) is an industry jargon for a type of performance measurement. KIPs are commonly used by an organization to evaluate its success or the success of a particular activity in which it is engaged”. Indicators are signs or variables that show the extent of change that resulted from projects. Indicators help to measure what actually happened in terms of quantity, quality and timelines against what was planned. They measure progress in achieving outputs and outcomes.

# Figure 5.2: Community Members after Fund Raising

Source: Survey, 2021

The process of identification and indicators was participatory approach, all stakeholders and project management were involved and agreed on quantitative and qualitative as an indicator for creation employment for youth project, these measures based on project objective and overall goal. The input indicators described the means by which the projects are implemented, such as the number of hours of training and the amount of money spent. In turn the output measure the extent to which the project is delivering what it is intended to be delivered. However, the impact indicators measure the actual change to HAZINA GROUP members. In general, the youth in Ruaha are expected to employee themselves by establishing income generating activities (IGA)/ business venture hence create self-employment and reduced unemployment as well as poverty and achieve their basic needs.

# Figure 5.3:  Youth Washing Cars

Source: Survey, (2021)

The project goal and project objectives performance indicators were summarized in Table 5.2.

# Table 5.2: Performance Indicators

| Objective | Output | Activity | Resources Needed | Performance Indicator |
| --- | --- | --- | --- | --- |
| To conduct training on car wash and entrepreneurship to the group of 12 youth in Ruaha by February 2021 | 12 youth at Ruaha ward trained on car wash and entrepreneurship skills | Preparation of training manual Conduct training | Printing and photocopying Stationeries Facilitators Transport (fuel) Refreshment Communication | Number of training manual developed Number of days for training Number of participants trained |
| To establish car wash project at Ruaha by May 2021 | One car wash services project established | Construction of car wash site/ house To purchase of pressure pumps Car wash in operation | Construction Materials Technicians Transport (fuel) 2pumps Purchase water pipes Water storage/ systems | Number of pumps purchased Number of pipes purchased Number of taps in place |
| To establish a reliable market for car wash services produced by the HAZINA by June 2021 | Stable market for car wash established by the youth group | Designing of advertisement Disseminate advertisement Conduct midterm M & E of project implementation | Stationeries Posters Air time | Number of advertisement designed Number of posters and airtime made Number of days for monitoring and evaluation |

Source: Survey, 2021

### 5.2.6 Participatory Evaluation Methods

The methods which are used to undertake Participatory Evaluation are almost the same as those used in Participatory Monitoring, Briefly, participatory evaluation can be explained as a partnership approach which stakeholders, “actively engaged in developing the evaluation of all phases of its implementation. Those who have the most at stake in the program – partners, program beneficiaries, funders and key decision markers- play active roles” (Ibid Zioski) Participation occurs throughout the evaluation process including: identification of relevant questions; planning the evaluation design; selecting appropriate measures and data collection methods; gathering and undertaking data analysis.

The participatory evaluation employed and assesses the progress in work plan, implementation of planned activities, achievement of objectives, effectiveness of project and impact of project. It also evaluates the project sustainability. For the case of creation employment for the youth the key informants used for youth management, LGA officials (WEO and VEO), project officers while focus group discussion used for youth group (target beneficiaries to collect data and information at the same time as observation used to verify collected data and information related to project to see if the intended objectives and activities are collaborated. In the participatory evaluation side, the following results were detected.

### 5.2.6.1 Meeting

During the advocacy meeting, when discussing about  ‘‘Role  of entrepreneurship  in Tanzania economy’’ participants discuss and shows evidence, some people in Ruaha ward community who engaged in small generating activities especially Youths, such as selling of second hand iron (scrappers), street vendors  and hawkers (Machinga) among of many others of this type, normally can afford or not to meet their basic needs such as getting food, shelter and some time can support their family compared to those who do not engaged in any kind of generating activities finally become frustrated and even commits suicide themselves or  run away his/her family premises.

From that discussion it observed that entrepreneurship as a crucial element for the informal sectors. Capacity building to Hazina group members has a clear mind to project intervention; it gives the implementer skills and knowledge in running out their project profitable oriented.

### 5.2.6.2 Interview

Evaluation team interviewed some of community members to learn more about the implementation and project success. This took place immediately after ending the evaluation meeting and it aimed to collect some information during the meeting. About 87.2% of the interviewees concurred that the project has brought some changes among community members. This was proved by the community itself when it involves more in caring and supporting Hazina group members. The purpose of establishment of car wash project was to enable them to increase their household income. The project has undergone a participatory evaluation. The internal and external stakeholders gave their own views concerning the project performance.

### 5.2.6.3 Focused Group Discussion

The Focus group discussion (FGD) was used for target group (target beneficiaries) to collect data and relevant information through observation method which was used to verify the collected data and information related to project to prove whether the intended objectives and activities are achieved. For example, objective 4 which intended to establish the feasible market for Car wash services to serve and support to 5 local government community leaders and 12 HAZINA committee members on improvement livelihood through car wash projects have shown the positive outcome. The Municipal council will include youths in its budget from own source to support HAZINA for the financial year 2021/2022.

### Project Evaluation Summary

Table shows the project evaluation summary based on the project goal, objectives, performance indicators, expected outcomes and actual outcome. Based on the project goal, objectives and activities planned have been met with exception of terminal and annual evaluation that will be done after six months of project implementation. Generally, the evaluation shows that there are strong commitments of various stakeholders from the planning stage to the implementation stage/ activities. This proves that the project is very important to both beneficiaries and community based. This is also in the Table 5.3.

# Table 5.3: Project Evaluation Summary

| Objective | Output | Activity | Performance Indicator | Expected outcome | Actual Outcome |
| --- | --- | --- | --- | --- | --- |
| To conduct training on car wash and entrepreneurship to the group of 12 youth in Ruaha by February 2021 | 12 youth at HAZINA trained on car wash and entrepreneurship skills | Preparation of training manual Conduct training | Number of training manual developed Number of days for training Number of participants trained | 12 group members acquired skills on car wash services and entrepreneurship | HAZINA trained on car wash services and entrepreneurship skills. |
| To establish car wash project at Ruaha ward by May 2021 | One car wash project established | Construction of car wash house To purchase pressure pumps Storage of water systems | Pumps purchased And stored at the site | Viable economic activity established | Car wash project established |
| To establish a reliable market for car wash services produced by the youth group by June 2021 | Stable market for car wash services established by the youth group | Designing of advertisement Disseminate advertisement Conduct midterm M & E of project implementation | Number of advertisement designed Number of posters and airtime made Number of days for monitoring and evaluation | Availability of market/ clients | Reliable market established/ many cars |

## Source: Survey, (2021)

## 5. 3 Project Sustainability

The project sustainability refers to the capacity of a project to maintain or keep on functioning, supported by its own resources (human, material, and financial), even external sources of funding have ended. The implementers (HAZINA GROUP members) are responsible for planning to make the project sustainable on institutional, financial as well as political.

### 5.3.1 Institutional Sustainability

The capacity building was given to youth through entrepreneurship training which helps in strengthening the implementation of their income generating activities established by managing properly their business/ income generating activity. This will result to create self-employment for the Ruaha ward youth by applying knowledge and establish business centers. In fact, every member of youth will understand and resume his/ her responsibilities patterning to leadership and good governance, training provided to them during the implementation stage of the project, this knowledge/ experience will be a good contribution to work hard and produce more.

### 5.3.2 Financial Sustainability

The improving livelihoods of HAZINA group youths group through a car wash project at Ruaha ward will sustain even after the phase out of project, firstly the car wash services for the youth has started and registered, this will be easy for them to access loans from bank like CRDB, and other credit financial systems to maintain financial stability for car wash. Secondly, every beneficiary contributed TZS 50,000/= as entry fees and involves in supervision in rotation bases/ weekly, this gives the assurance to know the money issues, thirdly, each member is able to borrow the money after two months as a loan and repay in four months (allowed to loan up to TZS 100,000/=) Because one of the aim of the project allow youth to access loan at reasonable interest rate and establish small income generating activities (selling snacks, oil, aerated drinks). Fourthly, the pressure pump car wash is used to first and washes more cars in a short time. This also will attract many clients, hence generate more income and sustain the project.

The idea of establishing the project catches the attention of youth ministry and agreed the national call of self-employment. This   income generating activities managed by them (HAZINA) members will be sustainable because, the site of Car wash project for the youth in Ruaha ward is surrounded by many cars, motor cycles and bicycles, this will help the project beneficiaries to establish good system of market and serve more clients within and outside the Ruaha ward Headquarter) this will increase the capital. Also the members putting on written the mechanism of ensuring there is no any defaulters by constructing a constitution which is leading the institution. For those who will pay a loan repayment late will be required to pay loan plus interest as well as penalty of five percentage of the total loan taken. Also within the constitution each group the member is subject to leadership jus after every two years.

# 5.3.3 Political Sustainability

The establishment of a car wash project at Ruaha ward for improving livelihoods of HAZINA youths group, is significance to the Tanzania economic because the project is relay with National Strategy for Growth and Reduction of Poverty II, Millennium Development Goal, National Youth Development Policy 2007, due to these, the leaders from grass root to district council/ municipal council level are in support of the project. The political leaders have shown their interest in this project; especially youths project. Also the project has been supported by different stakeholders (NGOs) who created a bridge to local government, community members and youths in general.

In 2009, a total of 3,755 NGOs were registered compared to 2,893 NGOs in 2008. Similarly, during the period under review, 816 NGOs were registered and received certificates of approval, equivalent to an increase of 22 percent. All of these NGOs are there to support Projects including youth’s projects (HAZINA). Therefore, these make the project to be politically sustainable (URT, 2009).

# 5.4 Chapter Summary

# The community needs assessment that was conducted in a participatory manner paved the way to understanding the community needs such as lack of reliable income generating activities. The stakeholders of the project included group members, and the local government authority (staff from ward office). HAZINA Group identified their problems which were believed to limit their economic development, including operating individually without putting their resources together for a greater good.

# Regardless of the challenges faced, the project took off successfully and was able to be implemented and per the project implementation plan. The implementation process included the beneficiaries of the project making it a participatory process. Apart from the efforts that were made by the project stakeholders to see the project reach its objectives, it was noted that participation of the beneficiaries in all stages along the project life cycle had a significant role in making this project a success.

# CHAPTER SIX

# CONCLUSION AND RECOMMENDATION

# 6.1 Conclusion

Income poverty among of many youths is the most critical problem which led to the setup of this project. This project focused on addressing issues related to establishment of car wash, quality control and car wash marketing. The lack of car washes not only led to income poverty of the Youths, but also attributed to high rate of poverty.  Project intervention was mainly required to fight against income poverty situation of the CBO. So the project had four specific objectives, which were to conduct training to 12 youths on car wash by January, 2021, to conduct training on entrepreneurship to 12 youths in Ruaha ward by February, 2021, to establish car wash project at Ruaha ward by May 2021, to establish a reliable market of Car wash services rendered by HAZINA members by June 2021.

The project expected to achieve and accomplish the objectives by the following outputs by the end of 2021. This includes;

- Primary stakeholders skilled in both hand pressure car washing services.

- Car wash owners skilled in business and handling.

- Primary stakeholder’s self-employed as car washers

- Car wash owners and community equipped with knowledge of the importance of car wash storage and handling.

- Good networking between car washers and consumers of car washing services

- Training of12 youths of Car wash handling, Maintenances and quality Services

- High income to target group

- Increased sales turnover

- Customer care improved.

- High quality of Car wash services offered to customers.

It is very important to note that project objectives has been achieved. To a large extent the activities planned have been accomplished in the right time as scheduled. Significant income is yet to be realized since they have not served many cars /clients as the product of the project initiated as also the time is too short to realize the maximum profit.

It is also important to note that, the services like lubricants, aerated drinks, shoe polish and snacks are adding value to business.  These available resources, which may help the HAZINA group members in developing their skills and creating sustainable income with less inputs and get more output. The project is growing well this will be an answer for economic empowerment to urban youth (HAZINA) in Ruaha, in turn improve livelihood of their lives. The researcher had only 6 months to work with the CBO and the established project was limited to time due to the fact that the period set by the University for Project Implementation was not enough. Also the project had fund constraints where 80% of Funds to implement the project were mobilized from, ATAPE, different Donors of the CBO and well-wishers.

## 6.2 Recommendations

Considered on experience from the implementation of creation of employment for the urban youth was proved, that the participatory community needs assessment (PCNA) is very crucial in planning of any development project. Therefore, it creates carries with the feelings of ownership, and builds a strong accountability for the intervention in the community; also forms trustiness among youth’s and ensures that the intervention will have more credibility in all sector of the community. I would rather suggest and recommended, to use participatory rural appraisal when someone is interested to ascertain creation employment for the youth project because it gives a room for the local people and other stakeholders to plan together (participatory approach) on proper ways.

From existing literature review challenges and suggestion on creating youth employment the government should work hard together with other stakeholders including NGOs and other well-wishers to improve the living standard life of youth in urban areas. Furthermore, HAZINA members and their families in Ruaha are disturbed by a social problem, in order to minimize this, the following are recommended. HAZINA Group members problems should be tackled collectively by home and community itself, churches, private sectors and some stakeholders, NGOs, the existing community structure should be firmly enough to meet HAZINA members’ basic needs.

The establishment of HAZINA car wash services (Pressure washer car wash) to support HAZINA (Unemployed youth) at every center in urban/ town setting should be encouraged and supported as one of important stage for the employment problem facing youth by either providing them land/ special areas for their business or giving them soft loans for their small generating income activities, and make sure that no youth is left out without being supported. Lastly but not least, the findings obtained in this study should be the initial stage and act as base for policy/ decision makers to put emphasis on the community participation at all levels in fighting income poverty against HAZINA members as well as youth unemployment problems.

Despite the fact that different policies such as the Social Security Policy of 2003 by developing and implementing a national strategy for social security and Protection for Vulnerable groups (VPO, 2005), Youth Development Policy 2007 and Vulnerable Youth National Data Management System that has been undertaken by the government of Tanzania to address the issue of Vulnerable Youth, some policies are on paper and if practiced are for few. This implies that there is a need to have other significant policies that provide guideline and education to stakeholders on criteria that influence proper identification of vulnerable children; create a sense of accountability and ownership to support HAZINA. Since the study  have proved its significance toward solving HAZINA  problem in the society, one may decide to carry out an investigation on the role of HAZINA  members registration as CBOs towards addressing HAZINA  problem as purposive sensitization to group members is highly needed.Self - serviceTouch free systemsSoft touch rolloversDrive Through Fleet Wash

Conveyor tunnel

Truck & Bus wash

Accessories

Chemical products

Water treatment

# REFERENCES

Africa: Monitoring progress towards the UN Declaration of Commitment on    HIV/AIDS (2005), UK: World Vision.

# Amin, E. (2005). Social Science Research Concept, Methodology and Analysis, Uganda: Makerere University Printer.

Carol, T. F. (1990). Performance indicator, BERA Dialogues (2). October 13–15, Somerset West, South Africa.

CEDPA, (1994). Project Design for Program Managers. Washington DC. URL retrieved 2004 November from the World Wide Web: (Free) http://www.cedpa.org/publications/pdf/projdesign.html.

Cole, A. H. (1959). Business enterprise in its social setting, Cambridge: Harvard University Press.

Freeman, A. M. (2002), What Might We Do About It?', Journal of Economic Perspectives,10(1), 1-8.

Freeman, R. B. and Lindauer, D. (1999). 'Why not Africa?', NBER working papers, w6942, February 1999.

Helgesson, L. (2006). Getting Ready for Life: Life Strategies of Town Youth in Mozambique and Ibadan, Department of Economics, Ibadan, Nigeria.

Heymann, J. Sherr, L. and Kidman, R., (2004). Protecting child hood in the AIDS Pandemic: finding solution that work. United state of America: Oxford University of 	press.

Jain, S. P. & Palman, W. (2003). The Panchayati Raj model in India: A handbook for Trainers on Participatory Local Development: Training module on participatory community monitoring and evaluation, Bangkok: FAO.

Juma, A. (2007). Promoting Livelihood Opportunities, for Rural Youth: Some Lessons.

Jupp, V. (2006). Sage Dictionary of Social Research Methods, New Delhi: SAGE Publications.

Kasaija, J. & Nsabagani, X. (2008). Community HIV counseling and testing a Handbook, retrieved on 30th March, 2017 from; Retrieved from:http://www.worlded.org/docs/Publications/.

Kiria, J. (2006). youth development in Tanzania. retrieved on 30th March, 2017 from;  www.infoyouth.or.tz.

Leibbrandt, M., and C. Mlatsheni. (2004). “Youth in Sub-Saharan Labor Markets.” Paper presented at African development and poverty reduction: The macro-micro linkage forum, October 13-15, Somerset West, South Africa.

Mancorda and Kondylis, (2006). Youth in the labuor Makert and the Transtion From School    to Work in Tanzania, retrieved on 20th March, 2017 from; https://books.google.co.tz/books?isbn=0857240005.

Mwanza City Profile, (2008). Retrieved on 26th October, 2017 from; mwacity@thenet.co.tz or mwacity-dir@thenet.co.tz.

Mwanza’s per capita income (2013). The Citizen Daily, Dar es Salaam, Tanzania. Retrieved on 21st April, 2017 from; http://mwanzanewsblog.blogspot.com /2013/01/mwanzas-per-capita-income-up.html.

NBS, (2003). 2002 Population and Housing Census, Volume II. Age and Sex Distribution, Dar es Salaam, Tanzania.

NBS, (2007). Analytical Report for Integrated Labour force Survey (ILFS) 2006, Analytical Report. Dar es Salaam: National Bureau of Statistics. Dar es Salaam, Tanzania.

Ngaiza, M. K., Lyimo, F. and Mniachi, A. (2003). A test manual for research methodology training,University of Dar es Salaam, Tanzania.

O’Higgins, N. (2003), 'Trends in the Youth Labour Market in Developing and Transition Countries', World bank, Social Protection Discussion Paper Series, n. 321, October 2003.

Oso and Onen (2008). A general Guide To Writing Research Proposal and Research Report, Makerere: Makerere University Press.

Project Design for program managers, (1994). Conducting a workshop on planning Community-Based Projects: the CEDPA training manual series, II. U.S.A: Washington D. C. (PP 46-64).

RAWG, URT, (2008). Views of the People 2007, Tanzanians give Their Opinions on: Growth and Reduction of Income Poverty, Their Quality of Life and Social Well-being, and Governance and Accountability. Dar es Salaam, Tanzania.

Research on Poverty Alleviation, (2007). Children and Vulnerability in Tanzania: a brief synthesis'. Special Paper 07.25, Tanzania: Dar es Salaam press.

Saunders, M. (2009). Research Methods for Business Students, 5th ed, England: Pearson Education Limited.

Simon, G. (2011). The Effects of Unemployment among Youth in the Society of South Africans, Pictorial, South Africa.Britain:Oxford University Press.

United Nation, (2005). Youth and violent conflict: society and development in crisis? A strategic review with a special focus on West Africa. New York: UNDP Bureau for Crisis Prevention   and Recovery.

United Nations, (2007). World Development Report: WHO. Retrieved on 15th March, 2017 from; http://www.unodc.org/pdf/research/Cr_and_Vio_Car_ E.pdf.

United Nations, (2007). A Joint Report by the United Nations Office, retrieved on 27th February, 2017 from; http://www.unodc.org/pdf/research/Cr_and_Vio_ Car_E.pdf.

United Nations, (2008). The Millennium Development Goals Report,, New York, USA.

URT, (1999). “Tanzania small and medium scale enterprise policy proposals” Prepared by: Calcopietro, C. M., Washington, DC, and Massawe D., Dar es Salaam, Tanzania.

URT, (2000). “Tanzania Development Vision, Planning Commision”, Dar es Salaam: Government Printers.

URT, (2002). Tanzania put in place a Small and Medium Enterprise Development. Policy, Dar es Salaam: UNIDO.

URT, (2005). Country report on implementation of the Beijing platform for action and the outcome document of the twenty-third special session of the general assembly- Beijing +10, Tanzania. Dar es Salaam, Tanzania.

URT, (2005). National Strategies for Growth and Reduction of Poverty: ministry of Finance and Economic affairs. Tanzania, Dar es Salaam: Dar es Salaam University press.

URT, (2005). Poverty and Human Development Report, Research and analysis, Dar es Salaam: Mkuki na Nyota Publishers.

URT, (2005). Summary of the National Strategy for Growth and Reduction of Poverty, Vice Presidents office 11Pp, Dar es Salaam, Tanzania.

URT, (2006). “Millennium Development Goals Progress Report”, Ministry of Planning, Dar es Salaam, Tanzania.

URT, (2007). National Youth Development Policy, Ministry of Labour, Employment and Youth Development United Nation, Dar es Salaam, Tanzania.

URT, (2007). “National quality standards of care for service provision to most vulnerable Children”. Tanzania: Dar es Salaam press.

URT, (2007). “National Youth Development policy December”, Dar es Salaam, Tanzania.

URT, (2007). “Poverty and Human Development Report, Research and analysis”, Dar es Salaam, Tanzania.

URT, (2008). “Millennium Development Goal Report”, Midi-way Evaluation 2000-2008 PP44, Dar es Salaam, Tanzania.

URT, (2008). The national coasted plan of action for Most Vulnerable Children: Ministry of Health and Social Welfare, Dar es Salaam: University of Dar-es-salaam press.

URT, (2009). “Poverty and Human Development Report, Research and Analysis working group”, MKUKUTA Monitoring System. Ministry of Finance and Economic affairs. pp13, Dar es Salaam, Tanzania.

URT, (2009).The Economic Survey, Produced by: The Ministry of Finance and Economic Affairs, Dar es Salaam, Tanzania.

URT, (2009). “National Guideline for Quality Improvement for the Most Vulnerable Children: ministry of Health and Social Welfare”. Dar es Salaam: Dar es Salaam press.

URT, (2010). Millennium Development Goals, ministry of Ministry of Finance and Economic. Dar es Salaam, Tanzania.

URT, (2010). National Strategy for Growth and Reduction of Poverty II, Ministry of Finance and Economic Affairs, Dar es Salaam, Tanzania.

URT, (2011). “Tanzania Country Report on the Millennium Development Goals 2010”. Dar es Salaam, Tanzania.

URT, (2011). Tanzania Five Years Development Plan, President’s Offices Planning Commission, Unleashing Tanzania’s latent growth potentials, Dar es Salaam Pp 1-11. Dar es Salaam, Tanzania.

URT, (2013). “Mwanza’s per capita income up from the Citizen Daily”, Dar es Salaam. Retrieved on 20th March, 2020 from; http://mwanzanewsblog. blogspot.com/2013/01/mwanzas-per-capita-income-up.html.

VETA, (2014). Addressing Youth Unemployment through TVET: Policy Perspective in Tanzania; retrieved on 21st March, 2017 from; http://www.veta.go.tz/assets/uploads/b7cd9-Final-Paper-on--Addressing-youth-unemployment-through-TVET--Policy-perspective-in-Tanzania-(2)-1.pdf.

Wilson, C. (1993): Economics the Science of Cost. Benefits and Choice Working Papers, w3875, October 199. Economics Working Paper No. 85.

World Vision, (2005). More than words? Action for Orphans and Vulnerable, retrieved on 20th March, June, 2017 from; www.eynacarwash.com.

Zioski, A. & Luluquisen, M. (2002). Participatory evaluation: Community based public health- Policy Practice for Participatory Evaluation, retrieved on 23rd May, 2017 from; http/depts. Washingtong.edu/pdf files/Evaluation.pdf.

# APPENDICES

Appendix 1: Structured questionnaire for vulnerable youth in urban areas.

Topic:  Improving livelihood of youth’s in Ruaha ward.

Instructions

Dear Respondent,

I salute you in the name of God.

My name is Mr. Godwin Erasto Selenda. I’m from Open University of Tanzania I would like to invite you to this good exercise of answering some questions about y urban youths. The information you give in this questionnaire will be useful for developing a tool that will help you to address the needs of your community. Your participation in this survey is completely voluntary and your answers will be 
kept confidential

General information: Tick (√) the correct answers where applicable

1. What is your age?

- 18-23yrs

- 24-29yrs

(c)     30 and above

2. The level of education

- Not attended school

- Adult education

- Primary education

- Secondary education

3. Marital status

- Single

- Married

4. The number of dependants

- 1

- 2

- 3

- 4 and above

5. What are the main problems facing Urban Youths?

- Lack of entrepreneur skills

- Lack of special area for their petty business

- Lack of capital

- Income poverty

- Lack of improved technology

6. Do you have any entrepreneurship skills?

- Yes...........

- No............

7. What should be done to improve the livelihood of the urban Youths in Ruaha ward?

- .........................................................................................

- .........................................................................................

- ..........................................................................................

Thank You For Good Cooperation And God Bless You

APPENDIX 2: QUESTIONS USED IN INTERVIEW

Key informants to identify the socio-economic status of youth

1. What are the sources of your household income?

2. What is the level of livelihood of urban youth?

- What are the existing income generating activities (IGAs)?

- What are the main Problems facing urban youth?

5. How many jobless youths in your street?

6. How do Youths have their daily needs?

7. Did you have any plan for youth to help them economically? YES / NO.

8 How many families are solely dependents on youth?

9. What is the economic status of youths is it increasing/ decreasing and why?

Thank You for Your Co-Operation